|  | Monday June 21 | Tuesday June 22 | Wednesday June 23 |
| --- | --- | --- | --- |
| owl | PREx ends 0700 Turn off beam to hall B | complete steering at 5.6 GeV correct pathlength ORFP take injector multiharp data | float |
| day | 0700 survey hall B for restricted access 0700 download magnets, lem at new energy (1100 MeV/pass). A2/B5/C1 0700 survey SL for restricted access, leave in controlled 0730 begin JT valve flow test SL02 0800 beg. thermal equil. test hall B, 24h 0800 RadCon survey Hall A 0830-1500 swap Pockels Cell (PC) or driver to reduce ringing Change helicity flip rate to 1 kHz Other maintenance RF recovery NL | Additional work on laser table and beam characterization with Pockels cell. Set Wien filter for Qweak poolarization maximum. Reverse target polarization in hall B Other maintenance RF recovery both linacs | production beam to hall B |
| swing | 1500-1800 complete JT test in SL02 1500 to perhaps 2200 - Pockels cell studies ~2200 beam to FC2 ~2200 start spinning up beam at 5.6 GeV | ~1700 end Pockels cell work. Restore beam ~1730 multiharp data 2C04 ~1800 Steer 5 pass beam to hall B tagger beam quality checks hall B revert helicity flip rate to 240 Hz if hall B DAQ can't accept 1 kHz |  |

Spin dance to hall B for Qweak information?

APEX beam commissioning begins in hall A, second pass, Thursday swing 6/24 per Bogdan's schedule.

Tuesday June 29: SL21 JT valve test and hall B target polarization

Tuesday July 6 owl: APEX ends

Tuesday July 6: SL14 JT test, hall B polarization, Exp. Staging Bldg 480V tie-in with East Arc down, Qweak target cooldown