## JLAB Accelerator Division
## 6GeV Accelerator Model
Scientific/Technical Project Charter

Field	Forms
Project Name and number	6GeV Accelerator Model
Project Abstract	Convert the existing 6GeV Optim/Art++ accelerator model to one based on elegant toolset. This project will complete the transition to elegant modeling toolset and in the process improve the model to more closely resembled the 6GeV accelerator. Elegant being unix based will be easier to integrate into the CEBAF control system and will leverage the effort at APS and other labs to continuously improve elegant.
Project Sponsor	Arne Freyberger, Michele Joyce (AHLA team)
Funding Sources	RTM-AHLA
Project Management Team	Arne Freyberger, Michele Joyce
Lead Organizations	AHLA
Supporting Organizations	CASA
Scientific/Technical / Background	An accurate accelerator model is critical for accelerator operations. The model is used for real-time calculations and well as for offline modeling of proposed and past accelerator configurations. A common tool-set for both real-time and offline work will result in seamless migration between offline and real-time use of the model.
Project Scope	Convert existing Optim decks into elegant decks. Convert Art++ real-time tools to elegant based tools. Develop elegant based API for tool development. Improve the deck representation of the existing machine in include element (monitors and correctors) lengths and accurate element orientation (entrance and exit angles). Scope does not include developing new optics, but does include accommodating changes to the optics due to errors found and subsequently fixed in the Optim decks and Optim itself.
Objectives	Unix based accelerator model of the 6GeV CEBAF. API for real-time and offline modeling efforts. Ability to model previous, present and future accelerator configurations.
Deliverables	Elegant decks that represent the 6GeV machine. API based on elegant toolset for real-time and offline accelerator modeling. Revision control infrastructure for tracking old, present and future configurations and changes between revisions. Conversion of existing real-time tools to the new elegant API and infrastructure(see https://devweb.acc.jlab.org/twiki/bin/view/AHLA/ConvertToElegant)
Constraints	Must be completed by the end of 6GeV accelerator operations. Use of elegant as the toolset has been pre-selected; conversion to other accelerator optics programs (MAD, MAD-X...) are not within this projects scopes.
Assumptions	The elegant tool-set is continuously improved by the APS team (with help from the worldwide accelerator community) and remains compatible with Linux/Unix hardware used by Operations.
Special JLab Commitments	None
Budget	This is predominately a labor effort. / FY11: 1/5 FTE AHLA staff, 1/10 FTE CASA staff / FY12: 1/4 FTE AHLA staff, 1/10 FTE CASA staff / FY13: none / If the project determines specialized computer hardware is required from some real-time or offline modeling, the Budget will need to be modified.
Schedule	Project must be complete by the end of the 6GeV operations: May 2012. / Oct. 2010: Project details (Major/minor milestones) developed and communicated to staff. / May 2011: Rematch elegant decks and download the quad values to the machine. / Nov. 2011: Correctors with proper length in decks. (Monitors are a “like”). / Feb. 2012: All real-time tools (https://devweb.acc.jlab.org/twiki/bin/view/AHLA/ConvertToElegant) converted to use elegant decks. / May 2012: 6GeV decks archived. 12GeV decks imported
Controls/Reporting	Project management granularity will be at the one-month increment level. Project managers will up date project status monthly and report the status to the Operations leader at the weekly Operations leaders meeting.