## Sheet1
Test Plan | Description | Owner | Run Period | CP | BTP | Comment
Beam to PCUP | Initial beam transport from cathode to Polarized Source Faraday Cup. | Marcy Stutzman | 1 |  |  | Already covered by Commissioning Plan. Not needed?
Setup 5D Spectrometer | Commission the 5D beamline as a spectrometer. | Joe Grames | 1 |  |  | New beamline to replace 2D spectrometer. Move to BTP?
Setup 3D Mott | Initial beam commissioning of the Mott Polarimeter. | Riad Suleiman | 1 |  |  | Not part of Commissioning Plan. Should it be added?
Test Beam Modes and Diagnostics | Checkout of macropulse structure for different beam modes using Pup as a diagnostic. | Matt Poelker | 1 |  |  | Already in Commissioning Plan.
QE Measurement and Analyzer | Checkout of Cathode Quantum Efficiency measurement software. | Marcy Stutzman | 1 |  |  | Already in Commissioning Plan.
Injector Steering (spot move, spin change) | Checkout of the Injector Steering application in response to laser spot moves and Wien changes. | Joe Grames | 1 |  |  | Already in Commissioning Plan.
HVPS vs. PCUP Current Calibration | Cross Calibrate the Gun High Voltage and the Polarized Source Faraday Cup. | Matt Poelker | 1 |  |  | Not part of Commissioning Plan. Should it be added?
IBC0L02 vs. FC2 Current Calibration | Calibrate the cavity current monitor at 0L02 vs. the Faraday Cup at 0L03. | Riad Suleiman | 1 |  |  | Already in Commissioning Plan.
Measure 130 keV Emittance | Measure the emittance of the beam at 130 keV using IHA1I06. | Joe Grames | 1 |  |  | Can also get a first look at the qsUtility.
INJTWF Phase Sensitivity Improvement and Emittance Degradation | Characterize the emittance evolution for different configurations of the Injector Two-Wien Flipper. | Joe Grames | 1 and 2
60Hz and Helicity Pickup Measurements | Measure the 60 Hz noise of the beam. Checkout | Riad Suleiman | 1
Brock Cavity Measurements | Beam tests of the Brock RF cavity Bunchlength monitor on the 1D beamline. | Matt Poelker | 1 and 2
Beam Energy Characterization for Bubble Chamber Experiment | Setup of 5-8 MeV beam to the 5D spectrometer in preparation for the Bubble Chamber experiment. | Riad Suleiman | 1 |  |  | Radcon to shadow the test to look for neutron production thresholds. Is this a separate test plan?
Mott Upgrade and Re-Commissioning | Commission the upgraded Mott Polarimeter on 3D beamline (1% polarimeter). | Riad Suleiman | 1 and 2
Prototype Pulse Picker for 4-Hall Operations | Test system to provide sub-harmonics of 500 MHz micropulse structure. | John Hansknecht | 1 |  |  | Needed for ultimate 4-Hall Operations
BLM High Voltage Checkout | Beam-based determination of the default Beam Loss Monitor high voltage settings. | Kelly Mahoney | 1 and 2 |  |  | Test needs to be done for all CW Machine Protection System BLMs.
Linac Energy Management (LEM) Software Tests | Tests to study advanced optimization algorithms for setting the energy profile in the linac. | Geoff Krafft | 1
FOpt Tests | Beam-based checkout of the FOpt application. | Vasiliy Morozov | 1 and 2
qtSnyder Application | Beam-based checkout of the qtSnyder application. | Yves Roblin | 1 and 2
Beam Energy Monitor | Beam-based calibration of the Beam Energy Monitor application. | Fanglei Lin | 1 and 2 |  |  | Test needs to be done for the Injector chicane, Arcs 1 through 10 and the Hall A and Hall C beamlines.
AutoSteer | Development of an elegant-based algorithm for steering beamline segments. | Yves Roblin | 1 and 2
AutoQuad | Development of an elegant-based algorithm for finding the magnetic center of quads relative to an adjacent BPM. | Todd Satogata | 1 and 2
elegant Download Tool (eDT) | Checkout of the tool for downloading settings from the CED model. | Dennis Turner | 1 and 2
123 MeV Spectrometer Magnet and Dump Diagnostics Commissioning | Commission the 123 MeV Spectrometer | Reza Kazimi | 1 and 2
Cross Calibrate 123 MeV Spectrometer with 0R01/0R02 Chicane Dipoles | Beam-based calibration of first two chicane dipoles relative to spectrometer to provide a reliable and calibrated online energy monitor. | Reza Kazimi | 1 and 2
Emittance Measurements (qsUtility) | Measure the Emittance of the beam in the Injector matching region, at the entrance of each Arc and in front of Hall Dumplets.B34 | Rui Li | 1 and 2
Characterize the cross-talk between chicane and West Arc dipoles | Measure the influence of the west Arc dipole power supplies on the low energy injector beam. | Reza Kazimi | 2 |  |  | Will have to wait until power supplies arrive.
SEE BPM calibration validation tests | Repeat earlier measurements to validate performance of the SEE BPM system and to validate the bench calibrations that were done during the down. | Michael Tiefenback | 1
0R02 Synchrotron Light Monitor Commissioning | Commission the upgraded Synchrotron Light Monitor. | Michael Tiefenback | 1
0R04 Bunch Length Monitor | Commission and develop the Radia Beams diagnostic for Bunch Length. Cross calibrate with the 1L02 Yao cavity. | Ali Ahmad | 2 |  |  | Mike Wilson is working on a 6 GHz amplifier for the 1L02 Yao cavity.
Chicane M56 Studies | Characterize the bunch compression of the Injector chicane from M56 = 0 cm through M56 = -24 cm. | Alex Bogacz | 1 |  |  | Emittance measurements in parallel using IHA0L07, IHA0L08, IHA0L09, IHA0L10.
0L/1L/2L RF Gradient Calibration | Calibrate the gradients of all SRF cavities to better than 5%. | Jay Benesch | 1
1A Synchrotron Light Monitor Recommissioning | Commission the Synchrotron Light Monitor. | Michael Tiefenback | 1
2A Synchrotron Light Monitor Recommissioning | Commission the Synchrotron Light Monitor. | Michael Tiefenback | 1
NL/SL M56 Cavity Commissioning | Commission the upgraded electronics for the linac M56. | Geoffrey Krafft | 2 |  |  | Electronics won't be ready for Run 1.
Dogleg Focusing Studies |  | Byung Yunn | 1 and 2
Dogleg Physical Location | Move each of the Center Dogleg magnets to its ideal position. | Byung Yunn | 1, 2 and 3. |  |  | Need to adjust the positions hen the Dogleg system is upgraded.
Linac Focusing Studies | Characterize the effect of the Linac Energy profile on upper pass beam transport optics. | Todd Satogata | 2
LOCO measurements of Arc Body Gradients | Measure the body gradients of all Arc dipoles. | Yves Roblin | 1 and 2