## Sheet1
RICH Task List- Updated 5/19/2016
# | Item | Responsible Group | Status | Date Updated | Comments
1 | FPGA programming | Fast Electronics | Unknown
2 | Test mirrors | Italians | Not started |  | Mirrors will be tested on arrival.
3 | Gas system hardware procurement | DSG/Italians | Not started |  | Will start when system is approved.
4 | Cooling system hardware procurement | DSG/Italians | Not started |  | Will start when system is approved.
5 | Interlock system hardware procurement | DSG/Italians | Not started |  | Will start when system is finalized.
6 | Aerogel charactarization | Italians | Not started | 2016-05-18 | Weighing to determine moisture absorbed; Would DSG help be needed in process?
7 | Detector assembly | DSG/Italians | Not started |  | Assemble in EEL 124 when DCs move to Hall.
8 | Arrange EEL 124 for assembly | DSG | Not started |  | Will start when DCs move to hall.
9 | Develop interlock system LabVIEW code | DSG | Not started |  | Will start when hardware is bought.
10 | Move components from storage to assembly area | Hall B Engineering | Not started |  | Will start when assembly is to begin.
11 | Rack for mirror testing | DSG/Italians | Waiting for shipment | 2016-05-18 | If mirrors are shipped in sturdy box, will just use shipping box for storage.
12 | Electronics delivery | Italians | Expected June 2016 | 2016-05-19 | Information in installation document emailed by Marco Mirazita on 3/10/2016.
13 | External frame and support structure delivery | Italians | Expected May 2016 | 2016-05-19 | Information in installation document emailed by Marco Mirazita on 3/10/2016.
14 | Mirror shipments | Italians | Starting June 2016 | 2016-05-12 | First mirrors delivered around 6/13/2016, see Marco Contalbrigo's email from 5/12/2016.
15 | Install Debian OS onto PCs | DSG | Contacted Computer Center | 2016-05-18 | Contacted JLAB Computer Center on 5/18/2016 about having Debian OS PCs on JLAB network.
16 | Scale for aerogel measurements | DSG | Researching scales and vendors | 2016-05-18 | Started procurement process for a ~300 g scale with 0.01 g precision.
17 | Gloves and masks for aerogel testing | DSG | Need to order masks | 2016-05-18 | Gloves in cleanroom, masks can be ordered.
18 | Cooling system hardware list | DSG | Waiting for info from INFN Group | 2016-05-13 | Tyler's email on 5/13/2016
19 | Interlock system hardware list | DSG | Preliminary list compiled | 2016-05-18 | In DSG weekly meeing talk from 5/18/2016.
20 | Approve location for cooling system compressors | Hall B Engineering | Information for use of space sent | 2016-04-27 | Emailed Bob Miller, Doug Tilles, Eugene Pasyuk on 4/27/2016 about using Pie Tower Level 3.
21 | Gas system hardware list | DSG | Started | 2016-05-19 | George is compiling list.
22 | Assembly structure anchoring approval | Hall B Engineering | Started | 2016-05-05 | Bolt size needs approval, sent engineering drawing to Saptarshi.
23 | Interlock system design | DSG | Started | 2016-05-18 | cRIO-based system, DSG researching cRIO modules needed for interlocks.
24 | ASME valve approval | Hall B Engineering | Started | 2016-05-19 | George sent cooling system diagram on 5/12/2016, more info and parts list emailed on 5/19/2016
25 | Aerogel shipments | Italians | Started October 2015 | 10/2015 | Aerogel stored in dryboxes in cleanrooms.
26 | PCs for mirror testing | DSG | Completed | 2016-05-18 | Will use RHEL PCs SVTSystem2 and PCAMPERO, both meet requested specs.
27 | LV supply (5 V, minimum 2 A, two channels) | DSG | Completed | 2016-05-18 | Required LV supply available for use.
28 | Oscilloscope | DSG | Completed | 2016-05-18 | Required oscilloscope available for use.
29 | Mulitmeter | DSG | Completed | 2016-05-18 | Required multimeter availble for use, in EEL 121b cleanroom.
30 | Gas system design | DSG | Completed | 2016-03-01 | George made preliminary drawing.
31 | Cooling system design | DSG | Completed | 2016-05-05 | George made preliminary drawing, see George's email (5/5/2016).
32 | CAEN HV interlocks | DSG | Completed | 2016-05-17 | Confirmed CAEN HV supply has internal interlocks.
33 | Darken EEL 121b cleanroom | DSG | Completed | 2016-03-08 | Tyler's email on 3/8/2016
34 | Remove excess equipment from EEL 121b cleanroom | DSG | Completed | 2016-05-10 | Completed week of 5/10/2016.
35 | PMT shipments | Italians | Completed | 1/2016 | half of total PMTs in cabinet in TED, remaining in Valery's and Andrey's offices.
36 | Move optical tables to EEL 121b cleanroom | Hall B Engineering | Completed | 2016-04-15 | Tyler's email on 4/15/2016