## Sheet1
RICH Task List- Updated 5/27/2016
# | Category | Item | Responsible Group | Status | Comments
1 | Electronics | FPGA programming | Fast Electronics | On Hold | On hold until Q1 2017 calendar year; FPGA boards are produced already, at Jlab, and tested (see Ben's emails 5/23 & 5/26/2016)
2 |  | Electronics delivery | INFN | Expected June 2016 | Information in installation document emailed by Marco Mirazita on 3/10/2016.
3 |  | Test electronics boards | DSG/INFN | Not started | Ideally start in August, see Marco Contalbrigo's email on 5/25/2016
4 | Mirrors | Test mirrors | INFN | Not started | Mirrors will be tested on arrival.
5 |  | Rack for mirror testing | DSG/INFN | Waiting for more info | Mirrors shipped in cardboard box, will need to discuss storage options.
6 |  | Spherical mirror shipments | INFN | First shipment received | First 4 spherical mirror segments received on 5/23/2016, stored in EEL 121b
7 |  | CMM for Mirror charactarization | DSG | Contacted Survey group | Survey Group can assist, arranging measurements for 6/14-6/17, roughness measurement of samples will be taken (Chris Gould's email 5/26/2016)
8 |  | Planar mirror shipments | INFN | Not started | Delivered to JLAB after summer, see Marco Contalbrigo's email on 5/25/2016
9 |  | Install Debian OS onto PCs | DSG | Waiting for info from INFN | Computer Center's (CC) protocol that nonsupported OS goes on guest network; Is guest network okay? Is network access needed for tests?
10 |  | Validate mirrors shipped | INFN/DSG | Not started | Occur week of 6/13/2016, validation includes visual inspection, point-like source spot imaging
11 | Aerogel | Scale for aerogel measurements | DSG | PR submitted | PR submitted on 5/25/2016 (PR # 363877P), estimated delivery date on or before 6/15/2016
12 |  | Gloves and masks for aerogel testing | DSG | Completed | Gloves and masks in brown cabinet in EEL 121b gowning room
13 |  | Aerogel shipments | INFN | Started October 2015 | Aerogel stored in dryboxes in cleanrooms, received shipment of 10 tiles on 5/19/2016
14 |  | Aerogel weighing | INFN | Not started | Weighing to determine moisture absorbed and density; Would DSG help be needed in process?
15 |  | Visually inspect aerogel on delivery | DSG | On-going | Shipment from 5/19/2016 inspected
16 |  | Measure aerogel transmission | INFN | Not started | Measure in Washington, DSG assistance requested
17 |  | Study optical effects of aerogel | INFN | Planning phase | Not definite task, INFN checking JLAB laser safety protocol
18 |  | Check dimensions of aerogel with mold | INFN | Planning phase | Not definite task, shape of mold to be determined
19 | Cooling | Cooling system hardware list | DSG | List compiled, rack layout created | Updated for higher capacity flow, rack layout for valves created (See George's email from 5/24/2016 and 5/26/2016, respectively)
20 |  | Approve location for cooling system compressors | Hall B Engineering | Completed | Top level of forward carriage reserved, See Bob's email on 5/24/2016, DSG will visit and relay pictures to INFN
21 |  | Cooling system hardware procurement | DSG/INFN | Not started | Will start when system is approved.
22 |  | ASME valve approval | Hall B Engineering | Info received, approval in process | See Saptarshi's email from 5/24/2016
23 |  | Cooling system hardware installation in hall | DSG/Hall B Engineering | Not started | Will start as detector is assembled
24 | N2 Purge | N2 purge system hardware list | DSG | List compiled | Updated for higher capacity flow, See George's email from 5/24/2016
25 |  | N2 purge system hardware procurement | DSG/INFN | Not started | Will start when hardware is approved
26 |  | N2 purge system hardware installation in hall | DSG/Hall B Engineering | Not started | Will start as detector is assembled
27 | Interlocks | Interlock system hardware list | DSG | Preliminary list compiled | In DSG weekly meeing talk from 5/18/2016.
28 |  | Interlock system design | DSG | Started | cRIO-based system, DSG researching cRIO modules needed for interlocks.
29 |  | Interlock system hardware procurement | DSG/INFN | Not started | Will start when system is finalized.
30 |  | Develop interlock system LabVIEW code | DSG | Not started | Will start when hardware is bought.
31 |  | Interlock hardware installation in hall | DSG/Hall B Engineering |  | Will start as detector is assembled and after development
32 | Assembly | Minimize leaks in detector body | INFN | Not Started | Will occur during and after detector assembly.
33 |  | Arrange EEL 124 for assembly | DSG | Not started | Will start when DCs move to hall.
34 |  | Move components from storage to assembly area | Hall B Engineering | Not started | Will start when assembly is to begin.
35 |  | External frame and support structure delivery | INFN | Expected May 2016 | Information in installation document emailed by Marco Mirazita on 3/10/2016.
36 |  | Assembly structure anchoring approval | Hall B Engineering/INFN | Started | Sandro will evaluate bolt size and lifting points, not critical task for review, see Sandro's email on 5/23/2016
37 |  | Detector assembly | DSG/INFN | Not started | Assemble in EEL 124 when DCs move to Hall.
38 | Testing | Internal Pulse Generator | DSG/INFN | Not started | Will be developed after electronics production; mentioned during INFN-DSG phone meeting on 5/23/2016; who would develop this?
39 | Safety | THA for cooling and N2 purge systems | DSG | In process | Valery requested help with THA for cooling and N2 purge system on 5/26/2016, see Tyler's email on 5/26/2016
40 | Complete | PCs for mirror testing | DSG | Completed | Will use RHEL PCs SVTSystem2 and PCAMPERO, both meet requested specs.
41 |  | LV supply (5 V, minimum 2 A, two channels) | DSG | Completed | Required LV supply available for use.
42 |  | Oscilloscope | DSG | Completed | Required oscilloscope available for use.
43 |  | Mulitmeter | DSG | Completed | Required multimeter availble for use, in EEL 121b cleanroom.
44 |  | N2 purge system design | DSG | Completed | George updated diagram for higher capacity flow, see George's email from 5/24/2016
45 |  | Cooling system design | DSG | Completed | Updated for higher capacity flow, See George's email from 5/24/2016
46 |  | CAEN HV interlocks | DSG | Completed | Confirmed CAEN HV supply has internal interlocks.
47 |  | Darken EEL 121b cleanroom | DSG | Completed | Tyler's email on 3/8/2016
48 |  | Remove excess equipment from EEL 121b cleanroom | DSG | Completed | Completed week of 5/10/2016.
49 |  | PMT shipments | INFN | Completed | half of total PMTs in cabinet in TED, remaining in Valery's and Andrey's offices.
50 |  | Move optical tables to EEL 121b cleanroom | Hall B Engineering | Completed | Tyler's email on 4/15/2016