## Slide 1
NIM draft articles for the CLAS12 system Status – 03/14/19
Components | Lead | available in binder description/performance | Completion Status (%) | Reviewer
Silicon Vertex Tracker | Y. Gotra/L. Elouadrhiri | YES | 100 | Carman
Micro Megas Tracker | F. Bossu/M. Defurne |  |  | 
Central Time-of-Flight Detector | D. Carman | YES | 100 | Gothe ?
Central Neutron Detector | S. Niccolai |  |  | 
High Threshold Cherenkov Counter | Y. Sharabian | YES | 25 | 
Drift chambers | M. Mestayer |  |  | 
Low Threshold Cherenkov Counters | M. Ungaro | YES | 100 | Carman
Ring Image Cherenkov Detector | P. Rossi/M Contalbrigo | soon |  | 
Forward Time-of-Flight | D. Carman/R. Gothe | YES | 100 | Gothe, Mestayer
Electromagnetic Calorimeter | S. Stepanyan/C. Smith | YES | 25 | 
Forward Tagger | M. Battaglieri/R. De Vita | soon |  | 
Beamline | S. Stepanyan/ B. Raue | soon | 75 | 
Data Acquisition/Trigger | S. Boiarinov/V. Koubarovski | YES/YES | 75/75 | 
Simulations | M. Ungaro | YES | 100 | 
Offline event reconstruction | V. Ziegler/R. De Vita |  |  | 
Torus & Solenoid magnets | R. Fair, D. Kashy | YES | 100 | Burkert
Slow Control | N. Baltzell |  |  | 
Overview paper | V .Burkert , L. Elouadrhiri | YES | 75 | 
OVERALL ` |  |  | 45% | 

## Slide 2: Proposed Time Line (updated)
Date | Milestone | Updated
8/2/2018 | Kickoff meeting | 
9/6/2018 | Detailed outline of each article | 
10/4/2018 | Detailed outline of the complete Document on github- list of drawings needed | 
12/6/2018 | First draft | 4/4/2019
4/4/2019 | Second draft (preliminary data) | 6/27/2019
6/27/2019 | Final draft (submitted for internal review) | 8/29/2019
9/27/2019 | Final document submitted to NIM | 11/07/2019
Regular progress meetings – 1st Thursday of months
Agenda will be send out two weeks before the meeting.
Leads need to organize themselves within their groups
Repository: https://github.com/JeffersonLab/clas12Nim

## Slide 3: Generic Outline (15-30 pages)
Overview of system
Requirements/specs (include table from portfolio: https://www.jlab.org/Hall-B/clas12-web/)
Design
Hardware components & construction
Electronics
Signal readout
Calibration
Event reconstruction
Simulation
Performance & specs in table form
Conclusions