## Physics
WO# | WBS | Title | Description | Type Of Space | Sq Ft Needed | Requirements | Assigned Location | Start Date | End Date | Comments | Contact | Status
12014 | Physics | Physics - HALLB & HALLD | 3,000 - 5,000 SF of contingency space for light tech assembly and clean (conditioned) storage. Near term usage would be for Hall B or Hall D overflow. | Technical Workspace | 5000 | Light tech assembly space (same as Blue Crab usage for CEBAF: RF & DC Power). Floor Loading ???, |  | TBD | TBD |  | Claus Rode/Dianne Napier
13045 | Physics Hall B | Physics - Hall B CTOF Physics - Hall B HTCC | CTOF prototype assembly & testing HTCC: mirror fabrication, construction, testing, staging | CTOF: Semi-clean, temperature controlled HTCC: Cl 100000 cleanroom | CTOF: 260 HTCC: 600 | CTOF: 1T movable crane, 17’ high HTCC: 5T crane, 24’ high, truck access additional requirments for mezzanine area: Access gate to the ground floor area with opening of 10ft x 10ft; access gate (3m wide) to the mezzanine floor level for a "forklift" on top of (1); fence at the mezzanine 2.7-3 m height to secure the work at ~1m height; ceiling height minimum 11.5ft; standard compressed air line; additional equipment power and data requirements; fire extinguisher; vertical cable trays (2) along the bulk wall. | EEL Stockroom Mezzanine (CTOF: upperdeck of mezzanine; HTCC: under mezzanine) | 2010-01-01 | 2014-09-30 | 7/13/10: Mezzanine is awarded. Received shop drawings 12 july 2010. Planning for August build and ready for Sept. 6/17/10: Bids are in and more than the estimate. Plan to award in a few days per FML. 6/16/10: New WO# 13045 assigned to track status of EEL Mezzanine space that will be used for both CTOF (formerly #12022) & HTCC (formerly 12043). 6/4/10: Rusty will follow up on clearing out of the stock room space as it is needed for storage, but then this equipment being stored will need to be moved out for construction of the mezzanine (cannot build mezzanine around the equipment to be stored in this space) 6/4/10: Site visit held, rusty will follow up on bids. After shop drawings are received by contrator/vendor, then discussion for electrical can start (clean power, etc). 5/13/10: Rusty will update drawings and send to Latifa for review. Rusty put in the PR last week and was signed off on 5/12/10. Award period (low bid) ~1 month. Rusty will push award. Time frame for delivery after award is 12 weeks. 5/13/10: Stockroom area to be partly moved out into transportainers and then a mezzanine area to be constructed, with space on upper deck for CTOF. Removal of stock room items starts this week. | L. Elouadrhiri | WORKING
12054 | Physics Hall B | Physics - Hall B Pcal | PCal module storage | Humidity controlled | 800 | Note: two stacks of three high, 400 sq. ft each | Staging Building | 2010-10-01 | 2014-09-30 | 7/13/10: August BOD for Experimental Staging Bldg. Latifa states start date has some wiggle room, will re-evaluate date as we get closer. | L. Elouadrhiri
12056 | Physics Hall B | Physics - Hall B SVT Sensor |  | Cl 10000 cleanroom | 1000 | need all of EEL 121. 90 percent is cleanroom space | EEL 121 | 2011-01-01 | 2014-09-30 | 7/13/10: Revised layout sent to Glenn and Latifa. FML needs feedback. Req not in the system yet. Glenn working on final decision week of 13 july. 6/17/10: FML states the start date of 1/1/2011 won't be met due to cleanroom time. Need impact information from Latifa. Glenn stated the layout was been send to Rusty. FML states estimates are in and needs an account code. Rusty will try a no-fund req in the meantime. 6/4/10: Rusty still needs layout for EEL 121 SVT clean room - Glenn will follow up on this. 5/13/10: Clean room is 10-12 weeks for manufacturing and then need to add procurement time. Award June 2010 would be the goal. Rusty needs priority with procurement to meet this goal. 5/13/10: Timeline: January 2011 for the clean room up and running with power and utilities. 5/13/10: Rusty needs a final floor plan from Hall B (Latifa). 5/13/10: EEL 121 is to be cleared and have perhaps 80% of the floor space enclosed in a class 10,000 clean room erected inside the current room for the SVT. Rusty has had conference calls and more calls today with clean room companies to understand the requirements. The air handling will need work since they cannot have outside air coming in as direct make-up air with e.g. smoke from distant fires as has happened in the past. They also need better temperature and humidity control than now. The offices in EEL 121 will have to be moved to the cubicle area on the mezzanine above EEL 126. This means the cubicle area needs some re-arrangement and addition of doors to secure the electronics test gear now in EEL 121. | L. Elouadrhiri | FEEDBACK
13041 | Physics Hall B | Physics - Hall B EEL Offices | EEL Offices moved from EEL 121 to mezzanine 126 |  |  |  |  | *Dependent on 12056* |  | 7/13/10: D. Fazenbaker will set up meeting week of 19 July. 7/13/10: Cleanroom in 121 and then move people end of the month. Offices in EEL121 will have to be moved to the cubicle area on the mezzanine above EEL126. This means the cubicle area needs some rearrangement and addition of doors to secure the electronics test gear now in EEL 121. | L. Elouadrhiri | WORKING
12044 | Physics Hall B | Physics - Hall B HTCC | HTCC: containment vessel assembly and finished detector storage | humidity controlled | 300 | 15'x20' 5T crane | Staging Building | 2011-06-01 | 2014-04-30 |  | L. Elouadrhiri
13040 | Physics Hall B | Physics - Hall B CTOF | CTOF Assembly and Storage | temperature controlled | 260 | 120vac; 1T movable crane, 17ft high |  | 2011-10-01 | 2014-09-01 |  | L. Elouadrhiri
12057 | Physics Hall B | Physics - Hall B Torus | Torus storage | Storage | 240 | 20’ x 12’ 5T crane, 18’ high, truck access | Hall B | 2012-01-01 | 2012-10-31 | Will go to Hall B as long as CLAS is out by the time it shows up | L. Elouadrhiri
12039 | Physics Hall B | Physics - Hall B FTOF Panel | FTOF Panel 1a test/repair/store | Semi-clean, temperature controlled | 600 | 20'x30' 2T mobile crane and cart access, 16’ high |  | 2012-05-01 | 2014-09-30 |  | L. Elouadrhiri
12040 | Physics Hall B | Physics - Hall B FTOF Panel | FTOF Panel 2 repair/assemble/test/store | Semi-clean, temperature controlled | 1575 | (35’x45’) 2T mobile crane and cart access, 10’ high |  | 2012-05-01 | 2014-09-30 |  | L. Elouadrhiri
12046 | Physics Hall B | Physics - Hall B LTCC | LTCC: remove and reinstall needed interior components | Cl 100000 cleanroom | 572 | (22’x26’) 2T mobile crane, 24’ high, truck access |  | 2012-05-01 | 2013-06-30 |  | L. Elouadrhiri
12047 | Physics Hall B | Physics - Hall B LTCC | LTCC: modify walls | Work space | 400 | 2T mobile crane, 18’ high, truck access |  | 2012-05-01 | 2013-06-30 |  | L. Elouadrhiri
12048 | Physics Hall B | Physics - Hall B LTCC | LTCC: remove 6 sectors and store | Storage | 1000 | Humidity controlled, 20'x50' 2T mobile crane | Staging Building | 2012-05-01 | 2014-03-31 | detectors refurbished for 12 GeV | L. Elouadrhiri
12055 | Physics Hall B | Physics - Hall B Solenoid/Detector Fitup | Solenoid testing, Central detector fitup | Temperature, humidity controlled | 320 | 16’x20’ 20 metric ton crane, 24’ high |  | 2012-10-01 | 2014-09-30 |  | L. Elouadrhiri
12041 | Physics Hall B | Physics - Hall B FTOF Panel | FTOF Panel 1b mount/test/store | Semi-clean, temperature controlled | 600 | 2T mobile crane and cart access |  | 2012-11-01 | 2014-09-30 |  | L. Elouadrhiri
12033 | Physics Hall B | Physics - Hall B Drift Chambers | Drift chambers: assembled chamber storage | temperature/ humidity controlled | 1950 | 3T crane, 20’ high, 12’ x 12’ door access | Staging Building | 2013-02-01 | 2014-05-31 | 5/13/10: Plan is to put these in the Experimental Staging Building per Rusty 5/13/10: Need a place to put finished modules starting Aug/Sept 2010. First one can stay in the clean room (EEL 124), but then follow on finished modules need storage 5/13/10: Module storage (Aug-Sept, 400 sqft, growing to 2,000 sqft by Feb 2013) | L. Elouadrhiri | WORKING
12024 | Physics Hall B | Physics - Hall B Drift Chambers | Drift chambers: assembly & stringing (drift chamber parts storage staging and assembly; drift chambers stringing first chamber R2; drift chambers string two chambers in parallel) | Temperature controlled, Semi-clean | 1000 | 3T gantry crane, 20’ high, under cover, 20’ door access | EEL 124 | 2009-10-01 | 2014-05-31 |  | L. Elouadrhiri | RESOLVED
12045 | Physics Hall B | Physics - Hall B LTCC | LTCC: work area | Humidity controlled | 525 | Presently in EEL, room 125 (Could be combined w. HTCC containment vessel assembly) | Corner of EEL 125 | 2010-01-01 | 2014-04-30 |  | L. Elouadrhiri | RESOLVED
12050 | Physics Hall B | Physics - Hall B Pcal | PCal assembly & test | Humidity controlled, semi-clean | 400 | 120VAC; 200lbs suction crane and truck access | EEL 125 | 2010-01-01 | 2012-01-31 | 6/4/10: replacing curtains, but room is essentially done. 5/13/10: As of last week, has been cleaned out. Mechanical vent removed, painting walls. Next week: flooring and painting. Will be ready 24 May 2010 for Hall B. 5/13/10: We will have meeting Monday May 3 at 8:15 in the cafeteria with Hall B group (Latifa, Doug, Stepan, Youri and Vitaly), If Tom can join us that will be great if not Doug will be in contact with him. We will need a cost and time estimates for the painting and fixing EEL 125 from Bob. So the goal is to hand the room to Rusty's group by end of next week. DC 5/13/10: We identified also temporary space for CTOF (in target area now) to be able to continue the PMT testing 5/13/10: EEL 125 is being cleaned out and is to be refurbished starting this week by Rusty's people - floor, walls, general sprucing up, then the PCAL construction goes there. 5/13/10: We did identify the spaces where we have temporary storage for HTCC and PCAL when we move them from EEL125. The work on these two detectors will have stop until the room is cleaned and painted. So keeping this process on schedule is critical. | L. Elouadrhiri | RESOLVED
12059 | Physics Hall C | Physics - Hall C | Cryo Cans: receive, test, inspect, store, repack, ship 5 cryo cans | Work floor | 200 | Large fork lift or 5T crane, space to perform He mass spec leak tests, pressure and electrical tests. Two cryogenic valve boxes requirements Storage for 2 cryo valve boxes arriving in July 2010 and April 2010); 4ft x 4ft x 10ft high - there are two; storage needed for 6 months; must be readily accessible so they can be shipped out upon notice. Three Cryogenic Valve Boxes Requirements Storage for 3 cryo valve boxes arriving in 5/1/2011; 4ft x 4ft x 10ft high - there are three; storage needed for 6 months; must be readily accessible so they can be shipped out upon notice. |  | 2010-04-01 | 2012-12-31 | 7/13/10: start date changed from 10/1/2010 to April 2010 7/13/10: 1st delivery of cryogenic valve box here week of 19 july, but will go to the test lab to support Hall D solenoid. Next box planned for April 2010 for storage needed. | P. Brindza
13042 | Physics Hall C | Physics - Hall C | Magnet Current Leads | Storage | 8ft x 4 ft x 3 ft box | Storage needed for 1 year | GPB Bldg 36; then relocated to Experimental Staging Bldg in Aug 2010 | 2010-05-13 | 2011-05-13 | 5/18/10: J. Campbell found space in the GPB building until the experimental staging bldg is completed in Aug 2010 and can then be relocated to the ESB. 5/13/10: Rusty to follow up with Brindza on information/solution. | P. Brindza | WORKING
12061 | Physics Hall C | Physics - Hall C | Power supplies | Work floor (G0/Qweak target cage?) | 200 | Space to receive, test, inspect and store (5) power supplies. 4 RR racks (24 x 36) each. Large fork lift or 5 T crane. |  | 2011-01-01 | 2012-12-31 | 7/13/10: will be installed in hall C as early as May 2012. | P. Brindza
12069 | Physics Hall C | Physics - Hall C SMHS | SHMS spectrometer | Outdoor storage | 43560 | Space to receive, inspect, and store SHMS support structure components. Minimum 1 acre (to include access area surrounding - need min 1/2 acre for dipole), sleepers on grass, heavy 18 wheel truck access and access for 50T road crane. Weight ~ 500 tons. | CMSA or new laydown area behind RadCon trailers | 2011-01-01 | 2012-12-31 | 7/13/10: will look at new laydown area behind Radcon Trailers | P. Brindza
12058 | Physics Hall C | Physics - Hall C | SC cable: sort, pack and ship cable. Also copper extrusion, soldered magnet conductor | Work floor (G0/Qweak target cage or Test Lab Qweak space) | 200 | Superconducting Cable Requirements: RESOLVED Staging Area; Secure Storage for cable reels 20 in number; some are on 4ft x 4ft pallets and some are on wood reels 36in diameter; Need storage for 4 months immediately; fork truck access; high theft potential Copper Extrusion Requirements Secure storage for 30,000 pounds of copper extrusion for 3 months; due in sept 2010; 44 steel reels 48 inch diameter; value $240k easy to steel and must be secure; high theft potential; Soldered Magnet Conductor Requirements Secure storage; due in Jan 2011; 44 reels 6 feet diameter; duration 6 months; fork truck access; high theft potential Crane – done? |  | Copper Extrustion: Sept 2010 Soldered Magnet Conductor: Jan 2011 | 2009-12-31 | 7/13/10: Superconduction cable is here and stored in a transportainer. FML states they can re-key if needed, just to give them the key number. 7/13/10: Copper Extrustion will be here Sept 2010. 7/13/10: Soldered magnet conductor: due in Jan 2011. three to six month temp storage until shipped to another facility. 6/4/10: Glenn to follow up with P. Brindza & Metzker on this requirement. For the SC cables. Copper extrusion and soldered magnet conductor planned for storage in experimental staging building per Rusty. 5/13/10: Rusty asked if this is something more than what they currently have now. | P. Brindza
12067 | Physics Hall C | Physics - Hall C SMHS | SHMS rotation parts | Work floor (physics storage area?) | 400 | Space to store SOS parts for reuse for SHMS: bogey assemblies, bearing, motors, drive reducers. 20T crane, indoor. One large heavy bearing requirements Box size is 6ft x 6ft x 3 ft; arrives 12/2010; storage needed for 2 years; cannot go outside. |  | 2011-05-01 | 2012-09-01 | 7/13/10: Start date changed from 10/1/2010 to 5/1/2011. End date changed from 12/31/2012 to 9/1/2012 5/13/10: Rusty to follow up with Brindza on more details of requirements | P. Brindza
12063 | Physics Hall C | Physics - Hall C | HB, Q1 | Work floor (G0/Qweak target cage?, can move to Hall C ~July 2012) | 500 | Space to receive, test, inspect and store HB + Q1 magnets. Leak and pressure tests. Acceptance test + magnetic mapping of Q1. 20T crane and high load floor. |  | 2012-01-01 | 2013-12-31 |  | P. Brindza
12064 | Physics Hall C | Physics - Hall C | Cryo transfer lines | Work floor (physics storage area or cryo building?) | 1000 | Space to receive, test, inspect and store cryo transfer lines, U tubes, vacuum equipment for spectrometer and beam line. |  | 2012-01-01 | 2013-12-31 |  | P. Brindza
12062 | Physics Hall C | Physics - Hall C | Yoke steel | Work floor (High Bay) | 500 | Space to receive, test, inspect, measure and assemble. 20T crane. 250 ton floor load. |  | 2013-01-01 | 2012-12-31 | 7/13/10: start date changed from 1/1/2011 to 1/1/2013. | P. Brindza
12065 | Physics Hall C | Physics - Hall C | Q2/3,D | Work floor (Hall C?) | 600 | Space to receive, test, inspect and store Q2/3 and D magnets. Leak and pressure tests. 20T crane and high load floor. |  | 2013-01-01 | 2013-12-31 |  | P. Brindza
12060 | Physics Hall C | Physics - Hall C SMHS | SMHS Controls: assembly, test, store | Semi-clean (G0/Qweak target cage?, ARC office?) | 200 | Space for magnet controls assembly, 17 RR racks (24 x 36) with space to work. Large fork lift access. | ARC 500-25 | 2010-01-01 | 2013-12-31 | Crates will be delivered to the ARC loading dock where the contents will be unpacked and then moved to ARC 500-25 | P. Brindza | RESOLVED
12066 | Physics Hall C | Physics - Hall C SMHS | SHMS calorimeter | Semi-clean, temperature controlled (EEL-126) | 200 | 10’x20’ | EEL 126 | 2010-01-01 | 2013-09-30 |  | P. Brindza | RESOLVED
12068 | Physics Hall C | Physics - Hall C SMHS | SHMS Detector stack | Semi-clean (EEL-126) | 600 | Need changed with detectors mostly at universities. Use EEL 126 for Hall D FDC. | EEL 126 | 2011-01-01 | 2013-09-30 | 7/13/10: Shower blocks can stay in EEL 126. Resolved | P. Brindza | RESOLVED
12072 | Physics Hall D | Physics - Hall D FDC | FDC Construction (component fab/assembly, testing, component storage) | Technical Workspace | 3000 | 2,000 sq ft of cl 10,000 clean room | Blue Crab | 2010-09-01 | 2013-12-31 | 8/3/10: PR 292575 for clean room. R. Bartek is the POC. Bids due last week of July but delayed 2 weeks due to vendor issues. Specification modified. Bids now due 13 August 2010. 1 week for award and 12 weeks for delivery after award. Planned for delivery end of Oct 2010 and installation complete before Thanksgiving. NOTE: 2 weeks for installation and one week for startup/commissioning/certification. 7/13/10: Claus signed the req. All signatures on the spec sheet. Out for bid. No long term lease for space and meeting week of 16 July 2010 to discuss utilities needed, but moving ahead with cleanroom. 6/17/10: Estimate is ~$400K for clean room. FML needs clean requirements for number of people planned to work in this area as this has impacts on A/C requirements and will cost more as the number of people increases. 6/16/10: T. Whitlatch added the 2,000 sq ft of cl 10,000 requirement. 6/4/10: PR will be written by Rusty on Monday June 7th. NEED Account Code. Rusty will provide estimated costs to include the air conditioning as well. Rusty needs push with procurement personnel to help get this a priority. 5/13/10: long-term lease arrangement still being worked by FML. 5/13/10: R. Bartek is the FML POC for the clean room layout at blue crab. 5/13/10: Rusty had conference calls with clean room vendors, looking at hard wall (as it has lower operating costs). ~7 week delivery after approval of shop drawings. Turn key by vendor (1 week to setup on site). Rusty is working on the requirements for the procurement package to be out week of 4 June 2010. 5/13/10: T. Whitlatch is the POC for Hall D for this space need. Space must be ready by Sept 2010. Planned for blue crab with 2000sq ft of class 10,000 clean room space (hard-wall purchased clean room). | T. Whitlatch | WORKING
12015 | Physics Hall D | Physics - Hall D | Hall D Transportainer (solenoid parts) | Outdoor storage space | 40 ft transportainer (plus items on a hard stand: see other requirements) | On site. Needs to be accessible to get parts for soleniod (being worked on in thetest lab) We (Hall D) own everything including the transportainer (pr196175). These are all for the Hall D solenoid. The materials being shipped are: Inside transportainer; 1. Nitrogen pump, 2. Magnet power supply - 3. feet for upstream and downstream yokes 4. mounting pads and rails 5. jack screws assemblies for inclusion in the piers In addition, we need to store on a hard stand: 1. the old Cryo Box (Puffing billy) 5 ft X 15 footprint 2. the coil cradle 4 ft x 6 ft footprint 3. the coil; handling frame 4 x 12 footprint | Behind Hall B | 2010-03-01 | 2011-12-31 | 7/13/10: Currently stored behind Hall B. Space Resolved. Tim to send FML the trailer number 6/16/10: Per T. Whitlatch: Cryobox is not coming here anymore. End date of 2011 not valid. We will be needing the transportainer throught the project and beyond. | T. Whitlatch | FEEDBACK
13012 | Physics Hall D | Physics - HALLD | BCAL Wedge Inspection, Testing, & Storage | Storage | 550 | **Need space to work on the wedges if stored in staging bldg** 550sq footage requirement includes area to work around them 1200 lbs a piece. Air Conditioned? | Staging Building | 2010-03-31 | 2012-03-31 | 7/13/10: Next batch of wedges arrive as early as week of 26 July. Can be stored in Warwick. FML will review space at warwick. 6/16/10: T. Whitlatch changed start date from 11/1/2009 to 3/31/2010. 6/4/10: Warwick Warehouse for 4 modules coming in June 2010 will work fine for Hall D (per Whitlatch). Next 4 are coming in August 2010 (stored in ESB if it is completed in August). 5/13/10: Rusty to check warwick storage to see if these 4 modules coming in June 2010 can go there. 5/13/10: Current 4 modules in Warwick storage. Next 4 modules coming in June 2010. 5/13/10: 550 sq ft air conditioned space in plan. Hall D requested storage in New Experimental Staging Bldg. Rusty noted that the new experimental staging bldg won’t be ready until July 2010. | T. Whitlatch | WORKING
12017 | Physics Hall D | Physics - HALLD | Hall D Office Trailer for Hall D Staff | Mixed Use | 1440 | House 8-12 people. Double wide with a ramp. Lockable. Needs phones, ethernet (phones and ethernet quoted by computer center - see T. Whitlatch for details). Needs A/C (cooling and heating) and general power receptacles. Power for trailer needs to be coordinated with R. Yasky to not interfere with any utility construction plans for Hall D. Location to be coordinated with R. Yasky as this will be on the construction site. Close to Hall D Truck Ramp. Yasky has provided a sketch for location to FLM. Need to include a port-a-potty. Also need a 40 x 60 Laydown area for staging equipment for installation into Hall D. Crush & run (ie, does not have to be a hard surface like concrete). | Proposed location is on the east side of the Hall D truck ramp. | 2010-10-01 | 2014-12-31 | 7/26/10: Meeting held, minutes issued. Computer center revising estimate for interim communications (Hall D Ops funded for FY10). Need trailer and comm setup by Jan 2011 (comm in Hall D and for trailer). FML (D. Fazenbaker) to provide estimates for trailer, infrastructure, and port-a-potty as this needs funding allocated (NOT hall d Ops funds). 7/13/10: D. Napier to get all parties together to discuss all requirements and time frame for trailer and associated utilties (power, comm, etc). Mtg scheduled 26 July 2010 6/16/10: Per T. Whitlatch, start date changed from 8/1/2010 to 10/1/2010. 6/4/10: R. Yasky will cover laydown area in her 12GeV Civil construction scope. Rusty to check with Rebecca about "permanent" laydown yard. FML understanding was that this would only be temporary. 6/4/10: Requirements updated: Went from 8-12 people to ~14 people. Trailer is now needed until 2014. Also, was requested that Hall D techs stay in trailer 34G until solenoid completion in summer of 2011. 5/13/10: Hall D RFE is November 2010. Trailer and laydown yard need to be in place 1-2 months before. Procurement in June 2010 to meet the deadline. 5/13/10: Tom Carstens (Hall D people) are currently in Trailer 34G. Plan is for them to move to the new Hall D Trailer once it is ready. | T. Whitlatch | WORKING
13011 | Physics Hall D | Physics - HALLD | Cryogenic equip. storage | Indoor Dry | 400 | inside storage 10000 lb lifting capability |  | 2010-12-01 | 2011-09-30 | 7/13/10: Type of space changed from "air conditioned space" to "Indoor dry" by T. Whitlatch. 5/13/10: Rusty will find space once more details are known about this. | T. Whitlatch | FEEDBACK
13014 | Physics Hall D | Physics - HALLD | Component pre-assy/ staging area | Air conditioned | 500 |  |  | 2011-02-01 | 2013-07-31 | space to bring in tracking chambers and calorimeters | T. Whitlatch
13010 | Physics Hall D | Physics - HALLD | Permanent /Sweep magnet Test/Fab area | Air conditioned | 400 | High bay accessible, 2 ton weight capacity **Related to 13044** |  | 2011-03-01 | 2011-02-28 | 7/13/10: Magnets currently stored in physics storage bldg. Need some room around the magnets to work on 2 of the 3 magnets. T. Whitlatch to check on the RMA for the magnets and provide feedback to FML for additional space in the physics storage bldg. 7/13/10: Start date changed from 9/1/2010 to 3/1/2011 6/16/10: T. Whitlatch changed start date from 6/1/2009 to 9/1/2010 and end date from 2/28/2010 to 2/28/2011 | T. Whitlatch | FEEDBACK
xxxxx | Physics Hall D | Physics - Hall D Fcal | Hall D storage space for FCAL lead glass block assemblies | Storage | 200 | There are approximately 13 crates at 2,000lbs each. Will be assembled at indiana university and shipped here in crates. Fork lift friendly. |  | 2011-02-01 | 2012-08-01 | 6/29/10: new request from Hall D entered into system | Tim Whitlatch
13032 | Physics Hall D | PHALLD New Position Hire | We are going to hire another staff scientist starting in April. We need another cubicle on the 3rd floor of F Wing | Office Space | 90 |  |  | 2010-04-30 |  | 7/13/10: FML stated Rachel Harris is working on user space for reconfiguration of 3rd floor F wing. Sept 2010 one more person from hall d will be here that needs a space. Current personnel are being accomodated until the reconfiguration occurs, but additional person in Sept needs a space if the reconfiguration doesn't occur prior to his/her arrival 6/17/10: Reconfiguration using cubicles being worked. Planned for end of summer for configuration. | Eugene Chudakov | WORKING
xxxxx | Physics Hall D | Physics - Hall D Eng/des staff | Need room for current 11 people getting kicked off 4th floor of ARC | Office Space | 1000 |  | ? | 2010-07-15 |  | 7/13/10: 13 spots on the 4th floor have been created. 4 spots on the 5th floor have been created. FML needs to know what else is needed (awaiting feedback from M. Wiseman). Arc 238 lease still in progress 6/17/10: Planned for July 6, 7, and 8 for 4th and 5th floors. Will fix ~80% of the problem, and leasing ARC 238 will fix the remaining 20%. 5th floor or 2nd floor ARC? | Eugene Chudakov | WORKING
13015 | Physics Hall D | Physics - HALLD | Target assy/testing | Assembly space (EEL-127?) | 400 | Liquid He |  | 2011-11-01 | 2013-01-31 |  | T. Whitlatch
12071 | Physics Hall D | Physics - Hall D BCAL | BCAL SiPM & fiber tests | Semi-clean (CC-F117) | 455 | CC-F117 o.k. | CEBAF F117 | 2008-05-01 | 2014-12-31 |  | T. Whitlatch | RESOLVED
12076 | Physics Hall D | Physics - Hall D GlueX | GlueX electronics & testing | Semi-clean (CC-F117) | 100 | ------ | CEBAF F117 | 2008-05-01 | 2014-12-31 | 7/13/10: Work planned to start 15 july 2010 after hours. FML provided plastic wrap to hall d for their equipment as well as plastic to keep construction dust contained when cutting wall open. 6/4/10: Wall must be opened for rack to move out of this room by July 16th. 6/4/10:Work order in the system #23317 (4/30/10). Currently K. Boyes assigned from FML | T. Whitlatch | RESOLVED
13008 | Physics Hall D | Physics - Hall D | Electronics Test Stand | semi-clean | 100 | 120VAC | CEBAF F117 | 2008-05-01 | 2014-12-31 | 6/16/10: T. Whitlatch said this is for an item that Fernando Barbosa is working on for Hall D. Plan is to have this work take place in CEBAF F117. | T. Whitlatch | RESOLVED
12077 | Physics Hall D | Physics - Hall D Solenoid | Solenoid coil 1 repair | Semi-clean | 800 | 28,000 lb crane capability, conditioned space | Test Lab High Bay | 2008-12-01 | 6/31/2010 | 6/16/10: T. Whitlatch changed end date from 10/31/2011 to 6/31/2010 C. Rode/G. Young need to provide updated dates for the solenoid work in the test lab as recent changes in schedule have been done. | T. Whitlatch | RESOLVED
13009 | Physics Hall D | Physics - HALLD | Radiation shielding storage | outdoors | 600 |  |  | 2009-06-01 | 2012-03-31 | 7/13/10: small number of blocks need space out on the grass. Tim working on updated SEG/Lead block requirements for Rolf. Space issue considered RESOLVED since space needs are so small. SEG blocks out on the grass | T. Whitlatch | RESOLVED
12078 | Physics Hall D | Physics - Hall D Solenoid | Solenoid testing | High Bay, 300,000 lb floor load (600 sq ft allocated + using 150 sq ft SRF space for power supply) | 750 | 100,000 lb Crane (2ea 25 ton), Liq. He, Liq. nitrogen, LCW, Warm he supply, large magnetic fringe field | Test Lab High Bay | 2009-11-01 | 2011-10-31 | C. Rode/G. Young need to provide updated dates for the solenoid work in the test lab as recent changes in schedule have been done. | T. Whitlatch | RESOLVED
12080 | Physics Hall D | Physics - Hall D Solenoid | Solenoid coil 2 repair | Semi-clean | 800 | 28,000 lb crane capability, conditioned space, good local lighting. Used Qweak target cage (Test Lab Hi Bay “C”) | Test Lab High Bay | 2009-11-01 | 2011-10-31 | C. Rode/G. Young need to provide updated dates for the solenoid work in the test lab as recent changes in schedule have been done. | T. Whitlatch | RESOLVED
13044 | Physics Hall D | Physics - HALLD | Permanent Sweep magnet storage | Storage | 80 | 3 magnets total Air Conditioned? | Physics Storage | 2009-11-01 | 2012-03-31 | 7/13/10: magnets are stored in the physics storage bldg. 6/16/10: Per T. Whitlatch, yes it is. | T. Whitlatch | RESOLVED
12075 | Physics Hall D | Physics - Hall D FDC | FDC Chamber Testing & Storage | Cl 10000 cleanroom & semi-clean area for testing, air conditioned (EEL-126?) | 1450 | Crane or gantry/ support granite table. 500 sqft is for FDC component storage | EEL 126 | 2010-02-01 | 2013-12-31 | 6/4/10: Hall D is currently sharing EEL 126 with Hall C. This has been resolved for Hall D to remain in this space. 5/13/10: Rolf needs information on their space in EEL 126. Glenn will follow up. 5/13/10: Hall D needs to retain their space in EEL 126 for the next 3 years for the test stand for the FDC. | T. Whitlatch | RESOLVED
12079 | Physics Hall D | Physics - Hall D Solenoid | Solenoid coil 1 storage | High Bay, 100,000 lb floor loading | 150 | 28,000 lb Crane access, conditioned storage | Injector Cave | 2010-06-15 | 2011-10-31 | 7/13/10: currently stored in inj cave area for now. Space resolved 6/16/10: T. Whitlatch changed start date from 11/1/2009 to 6/15/2010 6/4/10: Need addition 100sq ft for approximately 2 months to store coil number one until ready for test. Need end of week 4 june 2010. T. Carstens is the POC. Coild is ~28,000 lbs. Suresh looking at the structural suppport requirements. 5/13/10: Existing space is sufficient | T. Whitlatch | RESOLVED
13013 | Physics Hall D | Physics - HALLD | BNL Pair Spectrometer Magnet Testing/storage | High bay, 150,000 lb total floor load | 200 | 35 ton capacity Crane access/LCW large magnetic fringe field two halves at 30tons each | Hall D | 2010-11-01 | 2012-03-31 | 7/13/10: Hall D decided to put this in Hall D 6/4/10: can be stored in ESB once work has been completed and then installed in hall d at a later date. 6/4/10: Can this go into the hall and worked on in the hall? Hall D prefers not to as it will be in the way of installation work. 6/3/10: Solenoid and collimator cave components and shielding are planned to be installed before pair spectrometer. 5/13/10: Note: to be installed in hall D before the solenoid – info in installation schedule needs to be added 5/13/10: Experimental Staging Building is being looked at by Rusty – but can it be put in the hall once RFE is issued in Nov 2010? – Glenn to follow up on installation schedule and is it in sections/components (talk with Tim). 5/13/10: Need by November 2010. Weighs 65 tons. Will come in halves. Needs 400 sqft of air-conditioned space. Needs to be on site since we need to modify the magnet. | T. Whitlatch | RESOLVED