## schedule
| Dark Light Installation |  | 2016-04-04 | 2016-07-06
Item | Task Name | Group | Start | Finish | % Complete | Comment
Vault Prep
1 | Remove blocks | Installation | 2016-05-16 | 2016-05-17 | 100 | Scheduled
2 | Vent 4F vacuum and remove components/ instrumentation/ beamline | Install, EESIC, EESDC | 2016-04-14 | 2016-05-13 | 100 | Completed
3 | Remove 3F Skew Quads from beamline | Install | 2016-04-14 | 2016-05-13 | 100 | Completed
4 | Remove UV Quads and skew quads, quads/ wiggler, THz chicane from beamline | Install | 2016-04-14 | 2016-05-20 | 100 | Completed
5 | Fabricate skew quad stands | ME, Machine Shop | 2016-04-04 | 2016-05-27 | 50 | spacing blocks, plate submitted to machine shop
6 | Complete Box Supply Shuffle | DCPower/ Electricians | 2016-04-14 | 2016-05-16 | 75 | Complete interlocks, com, power ,LCW
7 | Reconnect 3F region quad LCW | Install | 2016-04-14 | 2016-05-13 | 50
| 4F Beamline Layout |  | 2016-04-04
1 | 4F - Beamline mechanical layout, | Mech. Engineering | 2016-04-04 | 2016-05-16 | 60 | Need vacuum Layout Completed
2 | Identify survey points | Mech. Engineering | 2016-04-14 | 2016-05-06 | 100
3 | Vault Point Layout | Survey | 2016-05-19 | 2016-05-19 | 95 | All but solenoid plate done
4 | Element/ Instrumentation List | Mech. Engineering | 2016-04-04 | 2016-05-16 | 75 | Need final mechanical/ instumentation locations
5 | Design Moller dump shielding | Radcon, ME | 2016-05-16 | 2016-05-27 | 10 | Waiting for source term information from MIT
6 | Install Skew quads/ new girders into 4F line/ reconnect LCW, DC power leads | Install/ DCP | 2016-05-23 | 2016-06-10
7 | Fabricate beam tubes/ spool pieces | Install | 2016-04-18 | 2016-06-03 |  | Need Layout Completed
8 | 4F Beamline- Detector/ Blower | Facilties/ /Install/ DCPower/ Electricians | 2016-07-01 | 730/2016 | 50 | Requirements received: identify/ complete installation/test
Solenoid Box Supply
1 | Delivery (PS) | MIT/ Install | 2016-06-16 | 2016-06-17 |  | 2016-06-15
1a | Set into final position |  |  | 2016-06-17 |  | 2016-06-17
2 | 500A Breaker Install | Facilities | 2016-05-09 | 2016-06-16 | 25 | ordered 05/20/2016
3 | Installallation AC/ LCW/ DC Leads | Facilties/ /Install/ DCPower/ Electricians | 2016-06-16 | 2016-06-21 |  | Identify cable runs/ Order wire/ MCM Cable
4 | Box Supply Checkout | DCPower/ MIT/ Physics |  |  |  | Assembly has began
Solenoid/ Stand
1 | Delivery | MIT/ Install | 2016-05-30 |  |  | 2016-05-30
2 | Install solenoid stand | MIT/ Install | 2016-06-01 | 2016-06-03 |  | Stand will come with magnet might be late
4 | Install solenoid | MIT/ Install | 2016-06-06 | 2016-06-09 |  | 8 tons, material handling in planning stage
5 | Align solenoid | Survey | 2016-06-10 | 2016-06-14 | 10 | Survey has a plan
6 | Connect Solenoid magnet LCW/ DC Leads and covers | MIT/ Physics/ DCPower ? | 2016-06-15 | 2016-06-17
7 | PS/Solenoid Commissioning | MIT/ Physics/ DCPower ? | 2016-06-20 | 2016-06-24
Post Installation Tasks
1 | Re-Install skew quads into 4F region | Install | 2016-05-02 | 2016-05-27 |  | Have points
2 | Install final vacuum chambers/ restore vacuum | Install | 2016-06-20 | 2016-06-24
3 | Re-install 4F10-4F12 | Install | 2016-06-20 | 2016-06-22
4 | Install Moller dump and shielding | install | 2016-06-27 | 2016-07-02
5 | Final Alignment | Survey | 2016-06-20 | 2016-06-24 |  | need to schedule
6 | Install/ connect 4F diagnostics/ instrumentation/ magnets | EESIC, DC, | 2016-04-25 | 2016-06-13
7 | Reinstall blocks | Install | 2016-07-01 | 2016-07-05 |  | Can be done anytime after magnet delivery
8 | Re-Certify Box supply Arc 2 | PSS |  |  |  | Need to Schedule
9 | Hot Check out prep and punch list | EES | 2016-04-04 | 2016-07-01 |  | Ongoing
10 | Final Hot check out | EES | 2016-07-05 | 2016-07-14
11 | Dark Light Run | Ops/ Physics | 2016-07-14 | 2016-08-02

## 05_09
Activity Last Week:
Bolt patterns for the solenoid stand have been completed. Floor layout scheduled for 5/19
Block removal is scheduled for 5/16
Continued with 4F beamline removal at the 4F03 thru the 4F04 girders
Completed upgrade and installation for HystArea (trim cycling tool)
Brandi working with Gary to update the Box Supply Cycling tool.
dlsupport mailing list is active
Tasks for this week:
Get the 3F quad water cooling reconnected.
Derive a list of changes to the 4F including physical and control changes. 5/16/2016
What are the pressure and flow (and perhaps pressure vs. flow if there is strong dependence) of the nitrogen line.
Get AC power specifications for power supply so that breaker can be ordered
Continue with box supply shuffle (connect AC, LCW, controls)

## 05_17
Activity Last Week:
B. Zihlmann has been named the Physics liason
Songsheet and element list for the 4F region nearly complete, meeting with DiPette, Curtis, Lassiter to review before release
Received the power and water requirements requirements for the detector pumps
Quote for PS breaker received (will order today)
The P&ID (Process and Instumentation diagram) for the detector has been received, forwarded to the EESIC group.
Meeting scheduled witth EESIC to identify interlocks
A path forward from EESIC has been proposed for the additional BPM's and vacuum valves
Modeling status:
Chris Tennant to deliver elegant decks for 3F and 4F regions to Michele
Dave Douglas to deliver properties and values needed for his master spreadsheet.
All BPM screens and tools have been submitted for certification and release.
Tasks for this week:
Get the 3F quad water cooling reconnected.
What are the pressure and flow (and perhaps pressure vs. flow if there is strong dependence) of the nitrogen line.
Remove Wiggler, ThZ chicane from beamline
Begin point layout
Begin installation of 4F skew quads
Begin cable installation for 4F skew quads

## 05_24
Activity Last Week:
Shielding blocks removed
Completed 4F beamline removal (wiggler, THz chicane, 4F03 and 4F09 stands)
4F Skew quad floor points laid out
Arc 2 box supply relocated to new postion/ ThZ supply and string decommissioned/ removed
Solenoid breaker ordered, 3-5 day (turn around) delivery ~ 5/25
Cable delivered for Arc 2 AC power
Skew spacers/ plate ordered from machine shop ( 7 day turn around)
Had a meeting with MIT, Survey, Install to identify issues with solenoid installation, target alignmnet
Agreed on vacuum interlock strategy
P&ID update released
Nomenclature document updated
Tasks for this week:
Complete Arc2 power supply com/ power/ LCW connections (requires power outage)
Start modification of 3 quads into skew quads
Begin installation of 4F skew quads
Begin cable installation for 4F skew quads
Complete final 4F songsheets
Measure N2 flow with higher limit
Get E-BPM computer running
Arrange for Solenoid delivery (lay out floor plate)
Chris Tennant to deliver elegant decks for 3F and 4F regions to Michele

## nomenclatureRevB
X | Y | Z | Nomenclature |  | Description | Old Nomenclature | Comments | New MPS input
14.6 | 0 | 64.25 | MDB4F00AH | 1 | Hor. Corr. | MDB4F00AH
14.6 | 0 | 64.25 | MDH4F00AV | 2 | Vert. corr. | MDH4F00AV
14.6 | 0 | 64.25 | IPM4F00A | 3 | BPM (SEE) | IPM4F00A
14.6 | 0 | 64.49 | ITV4F00A | 4 | Viewer | ITV4F00A
14.6 | 0 | 64.49 | VIP4F00C | 5 | Ion pump | VIP4F00C
14.6 | 0 | 64.8 | ILM4F00A | 6 | BLM head | ILM4F00A
14.6 | 0 | 65.1896 | MQX4F01 | 7 | Normal quad | MQX4F01
14.6 | 0 | 65.9896 | MQX4F02 | 8 | Normal quad | MQX4F02
14.6 | 0 | 66.7896 | MQX4F03 | 9 | Normal quad | MQX4F03
14.6 | 0 | 67.4896 | MQX4F03AS | 10 | Skew quad | MQX3F03S | Moved from 3F line
14.6 | 0 | 67.8 | ILM4F03A | 11 | BLM HEAD | ILM4F03
14.6 | 0 | 69 | IEO4F03A | 12 | Electro-optic cell | new | Use ring resonator support stand. Align horiz to <3 mm precision | Y, Mode 2 when off outer limit
14.6 | 0 | 68 | MDB4F03AH | 13 | Hor. Corr. | MDB8F11H | Fed from UV rack?
14.6 | 0 | 68 | MDH4F03AV | 14 | Vert. Corr. | MDH8F11V | Fed from UV rack?
14.6 | 0 | 68 | IPM4F03A | 15 | BPM (new) | IPM8F11 | Have to verify that it fits
14.6 | 0 | 68.4896 | MQX4F03BS | 16 | Skew quad | MQX3F04S | Moved from 3F line
14.6 | 0 | 69.4896 | MQX4F03CS | 17 | Skew quad | MQX4F05 | Modified to rotate quad. Mounted on 4F05 girder along with Happek viewer assembly
14.6 | 0 | 67.82 | ITV4F03C | 18 | Viewer | ITV4F03 | Happek viewer moved from 4F03 girder to 4F05 girder
14.6 | 0 | 67.82 | VIP4F03C | 19 | Ion pump | VIP4F03 | moved with Happek viewer
14.6 | 0 | 67.82 | VPG4F03C | 20 | Pirani gauge | VPG4F03 | Interlocked to valve VBV4F03D | Y, now interlocked to valve
14.6 | 0 | 68.18 | MDB4F03CH | 21 | Hor. Corr. | MDB4F03H | Moved from 4F03 girder
14.6 | 0 | 68.18 | MDH4F03CV | 22 | Vert. corr. | MDH4F03V | same
14.6 | 0 | 68.18 | IPM4F03C | 23 | BPM (4chan) | IPM4F03 | same
14.6 | 0 | 70.4896 | MQX4F03DS | 24 | Skew quad | MQX3F05S | Moved from 3F line
14.6 | 0 | 71 | ICM4F03D | 25 | Current monitor | ICM4F03 | Use beamline support stands from ring resonator
14.6 | 0 | 71.2 | VBV4F03D | 26 | Vacuum valve | new | Need to identify valve flanges. | Y
14.6 | 0 | 71.4896 | MQX4F03ES | 27 | Skew quad | MQX3F06S | Moved from 3F line
14.6 | 0 | 71.83 | MDB4F03EH | 28 | Hor. Corr. | MDB8F12H | Moved from 8F line
14.6 | 0 | 71.83 | MDH4F03EV | 29 | Verti. Corr. | MDH8F12V | same
14.6 | 0 | 71.83 | IPM4F03E | 30 | BPM (new) | IPM8F12 | same
14.6 | 0 | 72.1896 | MQX4F04 | 31 | Normal quad | MQX4F04
14.6 | 0 | 72.52 | VPG4F04 | 32 | Pirani gauge | new | Use old VPG4F05. Mounted on MIT Turbo chamber. Interlocked to VBV4F03D
14.6 | 0 | 72.52 | VRV4F04 | 33 | Roughing valve | VRV4F06 |  | Change label in MPS
14.6 | 0 | 72.9896 | MQX4F05 | 34 | Normal quad | MQX8F12 | girder and quad moved from 8F
14.6 | 0 | 73.54 | ILM4F04 | 35 | Beam loss monitor | ILM4F05 | relabel?
14.6 | 0 | 73.7896 | MQX4F06 | 36 | Normal quad | MQX4F06
14.6 | 0 | 74.4 | ITV4F06 | 37 | Viewer | new | HDR viewer | Y (moved from ITV4F06) new input for Harp
14.6 | 0 | 74.7 | MDB4F06H | 38 | Hor. Corr. | new
14.6 | 0 | 74.7 | MDH4F06V | 39 | Vert. corr. | new
14.6 | 0 | 74.7 | IPM4F06 | 40 | BPM (SEE) | new | Take buttons from Arc 2
14.6 | 0 | 75.8646 | MFF4F06 | 41 | Detector solenoid | new | MIT detector solenoid | Y for both magnet and target OK.
14.6 | 0 | 76.5 | ITV4F06A | 42 | Viewer | new |  | Y(moved from ITV4F06A)
14.6 | 0 | 76.5 | ILM4F06A | 43 | Beam loss monitor | ILM4F06A
14.6 | 0 | 76.5 | MDB4F06AH | 44 | Hor. Corr. | new | use trim channel for old MDB4F06AH
14.6 | 0 | 76.5 | MDH4F06AV | 45 | Vert. corr. | new | use trim channel for old MDH4F06AV
14.6 | 0 | 76.4 | IPM4F06A | 46 | BPM (SEE) | new | Take buttons from Arc 2
14.6 | 0 | 78.5546 | MQX4F07 | 47 | Normal quad | MQX4F07
14.6 | 0 | 79.19 | MDB4F07H | 48 | Hor. Corr. | MDB4F07H | Need to see if it fits
14.6 | 0 | 79.19 | MDH4F07V | 49 | Vert. corr. | MDH4F07V | Need to see if it fits
14.6 | 0 | 79.19 | IPM4F07 | 50 | BPM(new) | IPM4F07 | Need to see if it fits
14.6 | 0 | 79.4 | ILM4F07 | 51 | Beam loss monitor | ILM4F07
14.6 | 0 | 79.5546 | MQX4F08 | 52 | Normal quad | MQX4F08
14.6 | 0 | 79.88 | ITV4F08 | 53 | Viewer (with hole) | ITV4F07 | Change label?
14.6 | 0 | 79.88 | VIP4F08 | 54 | ion pump | VIP4F08 | Not interlocked to valve
14.6 | 0 | 72.52 | VPG4F08 | 55 | Pirani gauge | VPG8F13 | Interlocked to valve VBV4F09B
14.6 | 0 | 72.52 | VRV4F08 | 56 | Roughing valve | VRV8F13 |  | Change label in MPS
14.6 | 0 | 80.5546 | MQX4F09 | 57 | Normal quad | MQX4F09
14.6 | 0 | 81.2596 | MQX4F09AS | 58 | Skew quad | new | Use 8F12 stand, 8F13 quad, and new T-plate
14.6 | 0 | 81.94 | MDB4F09AH | 59 | Hor. Corr. | MDB8F13H | Use beamline support stands from ring resonator
14.6 | 0 | 81.94 | MDH4F09AV | 60 | Vert. corr. | MDH8F13V | same
14.6 | 0 | 81.94 | IPM4F09A | 61 | BPM (new) | IPM8F13 | same
14.6 | 0 | 82.2596 | MQX4F09BS | 62 | Skew quad | MQX3F07S | Moved from 3F line
14.6 | 0 | 82.76 | VBV4F09B | 63 | Vacuum valve | VBV4F09 | supported as before | Now interlocked to convectron gauges.
14.6 | 0 | 83.2596 | MQX4F09CS | 64 | Skew quad | MQX3F08S | Moved from 3F line
14.6 | 0 | 83.93 | ITV4F09C | 65 | Viewer | ITV4F09 | Use 8F10 girder, have to rotate the stand 180 degrees.
14.6 | 0 | 83.93 | VIP4F09C | 66 | ion pump | VIP4F09 | Use 8F10 girder
14.6 | 0 | 84.2596 | MQX4F09DS | 67 | Skew quad | MQX8F10 | Use 8F10 girder. Remount modified quad with spacer plate.
14.6 | 0 | 84.62 | MDB4F09DH | 68 | Hor. Corr. | MDB4F09H | Can either use 8F10 corrector or 4F09 corrector
14.6 | 0 | 84.62 | MDH4F09DV | 69 | Vert. corr. | MDH4F09V | same
14.6 | 0 | 84.62 | IPM4F09D | 70 | BPM(new) | IPM8F10
14.6 | 0 | 86.7 | ILM4F09D | 71 | Beam loss monitor | ILM4F10
14.6 | 0 | 85.2596 | MQX4F09ES | 72 | Skew quad | MQX3F09S | Moved from 3F line
14.6 | 0 | 85.9646 | MQX4F10 | 73 | Normal quad | MQX4F10
14.6 | 0 | 86.9646 | MQX4F11 | 74 | Normal quad | MQX4F11
14.6 | 0 | 87.32 | VIP4F11 | 75 | ion pump | VIP4F11
14.6 | 0 | 87.32 | VPG4F11 | 76 | Pirani gauge | VPG4F11 | Interlocked to valve VBV4F09B
14.6 | 0 | 87.32 | VRV4F11 | 77 | Roughing valve | VRV4F11
14.6 | 0 | 87.9646 | MQX4F12 | 78 | Normal quad | MQX4F12
14.6 | 0 | 89 | MDB4F12H | 79 | Hor. Corr. | MDB4F12H
14.6 | 0 | 89 | MDH4F12V | 80 | Vert. corr. | MDH4F12V
14.6 | 0 | 89 | IPM4F12 | 81 | BPM (4chan) | IPM4F12
14.6 | 0 | 89 | ITV4F12 | 82 | Viewer | ITV4F12
14.6 | 0 | 89 | VIP4F12 | 83 | ion pump | VIP4F12
14.6 | 0 | 89.5 | ILM4F12 | 84 | Beam loss monitor | ILM4F12
14.6 | 0 | 90 | VBV4F12 | 85 | Beamline valve | VBV4F12
14.6 | 0 | 89 | ITV4F12 | 86 | Viewer | ITV4F12
14.6 | 0 | 89 | VIP4F12 | 87 | ion pump | VIP4F12
14.6 | 0 | 89.5 | ILM4F12 | 88 | Beam loss monitor | ILM4F12
14.6 | 0 | 90 | VBV4F12 | 89 | Beamline valve | VBV4F12