## schedule
| Dark Light Installation |  | 2016-04-04 | 2016-07-06
Item | Task Name | Group | Start | Finish | % Complete | Comment
Vault Prep
1 | Remove blocks | Installation | 2016-05-16 | 2016-05-17 | 100 | Completed
2 | Vent 4F vacuum and remove components/ instrumentation/ beamline | Install, EESIC, EESDC | 2016-04-14 | 2016-05-13 | 100 | Completed
3 | Remove 3F Skew Quads from beamline | Install | 2016-04-14 | 2016-05-13 | 100 | Completed
4 | Remove UV Quads and skew quads, quads/ wiggler, THz chicane from beamline | Install | 2016-04-14 | 2016-05-20 | 100 | Completed
5 | Fabricate skew quad stands | ME, Machine Shop | 2016-04-04 | 2016-05-27 | 75 | spacing blocks, plate submitted to machine shop
6 | Complete Box Supply Shuffle | DCPower/ Electricians | 2016-04-14 | 2016-05-16 | 100 | Completed
7 | Reconnect 3F region quad LCW | Install | 2016-04-14 | 2016-05-13 | 75
| 4F Beamline Layout |  | 2016-04-04
1 | 4F - Beamline mechanical layout, | Mech. Engineering | 2016-04-04 | 2016-05-16 | 90 | Need Layout Completed/ upstream beamline layout is completed/ including BPM's /correctors/ quads/ interlocks/ vacuum. Downstream needs bellow/ all else in place. Update due from R. Lassiter 06/07/2016
2 | Identify survey points | Mech. Engineering | 2016-04-14 | 2016-05-06 | 100 | is finaized / nomenclature Rev B
3 | Vault Point Layout | Survey | 2016-05-19 | 2016-05-19 | 100 | need solenoid base plate/ EO/ Happek stand
4 | Element/ Instrumentation List | Mech. Engineering | 2016-04-04 | 2016-05-16 | 90 | need longitudinal positions for diagnostic elements
5 | Design Moller dump shielding | Radcon, ME | 2016-05-16 | 2016-05-27 | 30 | in progress
6 | Install Skew quads/ new girders into 4F line/ reconnect LCW, DC power leads | Install/ DCP | 2016-05-23 | 2016-06-10 | 50 | 8 stands in and aligned.
7 | Fabricate beam tubes/ spool pieces | Install | 2016-04-18 | 2016-06-13 | 80 | Awaiting sign off
8 | 4F Beamline- Detector/ Blower | Facilties/ /Install/ DCPower/ Electricians | 2016-07-01 | 2016-07-30 | 50 | Requirements received: identify/ complete installation/test/ working to have it delivered earlier
Solenoid Box Supply
1 | Delivery (PS) | MIT/ Install | 2016-06-16 | 2016-06-17 |  | shipping 06/24/2016?
1a | Set into final position |  |  | 2016-06-17 |  | see line 26
2 | 500A Breaker Install | Facilities | 2016-05-09 | 2016-06-16 | 50 | delivered/ installation is at first opportunity
3 | Installallation AC/ LCW/ DC Leads | Facilties/ /Install/ DCPower/ Electricians | 2016-06-16 | 2016-06-21 | 25 | locate water cooled leads
4 | Box Supply Checkout | DCPower/ MIT/ Physics |  |  | 25 | vendor/ MIT/ DC Power has discussed initial factory testing
Solenoid/ Stand
1 | Delivery | MIT/ Install | 2016-06-06 |  | 100 | 2016-06-14
2 | Install solenoid plate | MIT/ Install | 2016-06-06 | 2016-06-07 | 90 | delivered
4 | Install solenoid | MIT/ Install | 2016-06-07 | 2016-06-09 |  | delivered 06/14/2016
5 | Align solenoid | Survey | 2016-06-10 | 2016-06-14 | 10 | Survey has a plan
6 | Connect Solenoid magnet LCW/ DC Leads and covers | MIT/ Physics/ DCPower ? | 2016-06-15 | 2016-06-17 |  | behind schedule
7 | PS/Solenoid Commissioning | MIT/ Physics/ DCPower ? | 2016-06-20 | 2016-06-24 |  | might have to commission both PS and Magnet at same time
Post Installation Tasks
1 | Re-Install skew quads into 4F region | Install | 2016-05-02 | 2016-05-27 | 75 | Have points
2 | Install final vacuum chambers/ restore vacuum | Install | 2016-06-20 | 2016-06-24 |  | awaituing spool pieces/ update on vacuum electronincs
3 | Re-install 4F10-4F12 | Install | 2016-06-20 | 2016-06-22 |  | under discussion due to blower delivery
4 | Install Moller dump and shielding | install | 2016-06-27 | 2016-07-02 | 10
5 | Final Alignment | Survey | 2016-06-20 | 2016-06-24 |  | need to schedule
6 | Install/ connect 4F diagnostics/ instrumentation/ magnets | EESIC, DC, | 2016-04-25 | 2016-06-13
7 | Reinstall blocks | Install | 2016-07-01 | 2016-07-05 |  | Can be done anytime after magnet delivery
8 | Re-Certify Box supply Arc 2 | PSS |  |  |  | Need to Schedule Arc 2 is complete
9 | Hot Check out prep and punch list | EES | 2016-04-04 | 2016-07-01 |  | Ongoing
10 | Final Hot check out | EES | 2016-07-05 | 2016-07-14
11 | Dark Light Run | Ops/ Physics | 2016-07-14 | 2016-08-02

## 05_09
Activity Last Week:
Bolt patterns for the solenoid stand have been completed. Floor layout scheduled for 5/19
Block removal is scheduled for 5/16
Continued with 4F beamline removal at the 4F03 thru the 4F04 girders
Completed upgrade and installation for HystArea (trim cycling tool)
Brandi working with Gary to update the Box Supply Cycling tool.
dlsupport mailing list is active
Tasks for this week:
Get the 3F quad water cooling reconnected.
Derive a list of changes to the 4F including physical and control changes. 5/16/2016
What are the pressure and flow (and perhaps pressure vs. flow if there is strong dependence) of the nitrogen line.
Get AC power specifications for power supply so that breaker can be ordered
Continue with box supply shuffle (connect AC, LCW, controls)

## 05_17
Activity Last Week:
B. Zihlmann has been named the Physics liason
Songsheet and element list for the 4F region nearly complete, meeting with DiPette, Curtis, Lassiter to review before release
Received the power and water requirements requirements for the detector pumps
Quote for PS breaker received (will order today)
The P&ID (Process and Instumentation diagram) for the detector has been received, forwarded to the EESIC group.
Meeting scheduled witth EESIC to identify interlocks
A path forward from EESIC has been proposed for the additional BPM's and vacuum valves
Modeling status:
Chris Tennant to deliver elegant decks for 3F and 4F regions to Michele
Dave Douglas to deliver properties and values needed for his master spreadsheet.
All BPM screens and tools have been submitted for certification and release.
Tasks for this week:
Get the 3F quad water cooling reconnected.
What are the pressure and flow (and perhaps pressure vs. flow if there is strong dependence) of the nitrogen line.
Remove Wiggler, ThZ chicane from beamline
Begin point layout
Begin installation of 4F skew quads
Begin cable installation for 4F skew quads

## 05_24
Activity Last Week:
Completed 4F beamline removal except 4F09
4F Skew quad points layed down
Arc 2 box supply relocated to new postion/ ThZ supply and string decommissioned/ removed
Solenoid breaker ordered, 3-5 day (turn around) delivery ~ 5/25
Cable delivered for Arc 2 AC power
Skew spacers/ plate ordered from machine shop ( 7 day turn around)
Had a meeting with MIT, Survey, Install to identify issues with solenoid installation, target alignmnet
Chris Tennant to deliver elegant decks for 3F and 4F regions to Michele (status?)
Dave Douglas to deliver properties and values needed for his master spreadsheet. (status?)
Tasks for this week:
Complete Arc2 com/ power/ LCW connections
Begin installation of 4F skew quads
Begin cable installation for 4F skew quads
Release final 4F songsheets
Wait for Solenoid delivery

## 05_31
Activity Last Week:
Complete Arc2 com/ power/ LCW connections
Began installation of 4F skew quads
Laid out vacuum elements in the 4F
Complete Arc2 com/ power/ LCW connections
Remove girders and quads for modifications
Tasks for this week:
Prepare for magnet arrival
Complete LED information
Complete vacuum element layout, specify drift tubes
Complete diagnostic requirements
Modify quads into skew quads
Assemble 4F03C and 4F09D girders

## 06_07
Activity Last Week:
Prepare for magnet arrival/ plate will be delivered before magnet/ installation plan confirmed with MIT
elegant file for the 4F region was delivered, loading of the Optics began
DC Power is verifying LED elements/ beginning HCO of the box supplies
Complete vacuum element layout, specify drift tubes..complete/ drawings need check and sign off
M:\me-group\Ron_Lassiter\LERF\Dark_Light\LRF0000440-0001-rev A
Complete diagnostic requirements / pretty much complete per S. Benson
Modify quads into skew quads/ in progress. Plate and spacers delivered to magnet test/ quads being split
Assemble 4F03C and 4F09D girders/ work continues
nomenclature document is awaiting final check off
Tasks for this week:
complete assembly 4F03C and 4F09D girders
Complete modification of quads into skew quads
Install reamining girders
calculate the derating value of the penetration / order MCM cable and lugs
design the moving lense assembly for Happek (shiny bald guy)
begin DC Power cable install for the 4F magnet components
release final element layout

## 6_14
Activity Last Week:
Sub region 2 and 4 are complete and waiting sign off :
M:\DarkLight_Team\Drawings LRF0000550-01, LRF0000550-182
Magnet plate was delivered, installation almost complete
Solenoid magnet en route
HCO complete for power suppies Arc 1, Arc 2
Cable installation for 4F quads continuing
Conventional cabling cost to high for magnet, attempting to locate 200' of water cooled leads from Physics
BPM effort ongoing, now is a 2 prong attack
Systems integration meetings are at 10:00 Thursdays in the MCC conference room
Received completion date for PS testing 6/24
Please begin all LERF Atlis' with the ^ charactater
Received completion date for PS testing 6/24
Tasks for this week:
Complete modification of quads into skew quads and install
Continue with BPM system
Begin installation of the Solenoid magnet
Begin power distribution for the root blowers
Continue with the Beamline installation

## Punch List
| Punch List Items (not a complete list) | POC | % Complete | Comments
CIS
| Replace Drive Laser Mechanical shutters | Zhang | 75 | shutters ordered and received, need update
| Repair or replace Radiation Monitor RADMONxCH6 | Garcia/Bullard |  | Need Update
EESDCP
| Verify and repair GC magnet EPICS controls | Coleman | 10 | May be able to find working screen and use it
| HCO of new Magnet IOC | DCP | 50 | Part of HCO tasks
EESRFS
Nelson/Cooper
1 | Crowbar ready fix for Zone FL03
2 | Load in proper RF drive-high values |  |  | Drury should have starting values.
3 | RF power is high on cavity 4-2
4 | Find out why the 12V power supplies fail in zone 3 and 4?
EESSAF
T. Michaelides/ R. Araiza
1 | BM3 and BM6 keys are backwards; you should be able to remove the key after switching system into those modes to lock them in |  | 10
2 | Change mode 6 truth table so that BLMs trip the beam but can be masked.
3 | Update ODH heads. |  | 100
4 | Recertify PSS (done) |  | 100
RadCon
1 | Fix W55 rad monitor | M. Washington |  | re-configure for Dark Light
| Rapid Access System |  |  | HCO , move heads if needed
EESICS
O. Garza
1 | Install additional valve and channel in 4F | Kortze | 20 | Interlock new valves to convectrons and inficons
2 | Get E-style BPMs working or replace with other technology | Francis/ Allison | 20 | Use E-style BPMs. Borrow electronics from UV line and get new computer up.
4 | SEE BPMs triggering must come from time delay cards. | Francis
5 | FELScope Ext triggers were missing | Cole
6 | Regain remote control of oscilloscope | Cole |  | Need strategy for O'scope controls
7 | Current monitor readbacks in EPICS | Cole |  | Need details on signal inteffaces
8 | Viewers in 3F align, focus, and set gains | Dela Cruze/ Norris
9 | Replace damaged cameras as needed | Dela Cruze/ Norris
10 | Put 5F alignment laser in a more permanent fixture and align to 1F line |  |  | Have to remove viewer when using.
11 | Move IR Happek to IR controls (now partially on UV controls) |  |  | Use UV controls and relabel if possible
MSNST
1 | Fix noisy ion pumps (especially in the 5F region) | Kortze
OPSADM
1 | Console FEL05 requires a reboot to wake up after it goes to sleep
2 | Replace magnet IOC | G. Croke
3 | Update IOC controls
OPSSFT
2 | ADL monitor logs not working |  |  | Possibly due to hardware being off?
3 | Update turn-on procedure to include check of BLM HV |  |  | This may be just a procedural change. Need to see if the software has to be modified.
4 | Archive signals for many of the BPMs | Slominski/ Francis |  | This is done through Archive request channels.
5 | "All-valve" controls | S. Weatherspoon/ Kortze |  | Have to get hardware fixed first.
OPS
M. Joyce/ M. McCaughan
1 | Develop magnet screens |  |  | Derived mostly from LED
2 | Develop BPM screens |  |  | Derived from LED
3 | Develop BLM screens
4 | Update viewer screens |  |  | Update using McCaughan's ideas
5 | FSD screen |  |  | Derived from LED?
6 | Vacuum screens
7 | Get 5F08 beam stop working from viewer pages |  |  | Mike wants have a separate screen for this.
8 | Other ease of operation updates |  |  | Need to meet with Frierson, McCaughan, Freeman and Larrieu to determine task list.
9 | Bluecherry for video signals | B. Freeman
OPSHLA
M. Joyce/ B. Cade
1 | LED development and implementation |  | 75 | This is the highest priority.
2 | –Update phasing script to check for out-of-bounds magnet supply requests |  |  | need update
3 | shutdown scripts crash because of missing / unresponsive elements |  |  | need update
Hot Check Out
1 | CIS – Heat clean and condition cathode | M. Poelker/ C. Hernandez
2 | EESICS - Check zone 1 wiring for AMS
3 | EESRFS - Condition the zone 1 couplers
4 | EESRFS - Noisy RF control loops (have to reset the loop gains)
5 | EESICS - Check all timing signals (need documentation)
LERF Ops Procedures
S. Frierson/ Benson/ MIT
1 | SOP's
2 | TSOP's

## nomenclature
X | Y | Z | Nomenclature |  | Description | Old Nomenclature | Comments | New MPS input
14.6 | 0 | 64.25 | MDB4F00AH | 1 | Hor. Corr. | MDB4F00AH
14.6 | 0 | 64.25 | MDH4F00AV | 2 | Vert. corr. | MDH4F00AV
14.6 | 0 | 64.25 | IPM4F00A | 3 | BPM (SEE) | IPM4F00A
14.6 | 0 | 64.49 | ITV4F00A | 4 | Viewer | ITV4F00A
14.6 | 0 | 64.49 | VIP4F00C | 5 | Ion pump | VIP4F00C
14.6 | 0 | 64.8 | ILM4F00A | 6 | BLM head | ILM4F00A | BLMs in LED?
14.6 | 0 | 65.1896 | MQX4F01 | 7 | Normal quad | MQX4F01
14.6 | 0 | 65.9896 | MQX4F02 | 8 | Normal quad | MQX4F02
14.6 | 0 | 66.7896 | MQX4F03 | 9 | Normal quad | MQX4F03
14.6 | 0 | 67.4896 | MQX4F03AS | 10 | Skew quad | MQX3F03S
14.6 | 0 | 67.8 | ILM4F03A | 11 | BLM HEAD | ILM4F03
14.6 | 0 | 69 | IEO4F03A | 16 | Electro-optic cell | new | Use ring resonator support stand | Y
14.6 | 0 | 68 | MDB4F03AH | 12 | Hor. Corr. | MDB8F11H | Fed from UV rack
14.6 | 0 | 68 | MDH4F03AV | 13 | Vert. Corr. | MDH8F11V | Fed from UV rack
14.6 | 0 | 68 | IPM4F03A | 14 | BPM (new) | IPM8F11
14.6 | 0 | 68.4896 | MQX4F03BS | 15 | Skew quad | MQX3F04S
14.6 | 0 | 69.4896 | MQX4F03CS | 17 | Skew quad | MQX4F05 | Modified to rotate quad. Uses Happek viewer assembly.
14.6 | 0 | 67.82 | ITV4F03C | 18 | Viewer | ITV4F03 | Happek viewer
14.6 | 0 | 67.82 | VIP4F03C | 19 | Ion pump | VIP4F03
14.6 | 0 | 67.82 | VPG4F03C | 20 | Pirani gauge | VPG4F03
14.6 | 0 | 68.18 | MDB4F03CH | 21 | Hor. Corr. | MDB4F03H
14.6 | 0 | 68.18 | MDH4F03CV | 22 | Vert. corr. | MDH4F03V
14.6 | 0 | 68.18 | IPM4F03C | 23 | BPM (4chan) | IPM4F03
14.6 | 0 | 70.4896 | MQX4F03DS | 24 | Skew quad | MQX3F05S
14.6 | 0 | 71 | ICM4F03D | 25 | Current monitor | ICM4F03
14.6 | 0 | 71.2 | VBV4F03D | 26 | Vacuum valve | new |  | Y
14.6 | 0 | 71.4896 | MQX4F03ES | 27 | Skew quad | MQX3F06S
14.6 | 0 | 71.83 | MDB4F03EH | 28 | Hor. Corr. | MDB8F12H
14.6 | 0 | 71.83 | MDH4F03EV | 29 | Verti. Corr. | MDH8F12V
14.6 | 0 | 71.83 | IPM4F03E | 30 | BPM (new) | IPM8F12
14.6 | 0 | 72.1896 | MQX4F04 | 31 | Normal quad | MQX4F04
14.6 | 0 | 72.52 | VIP4F04 | 32 | Ion pump | VIP4F05
14.6 | 0 | 72.52 | VPG4F04 | 33 | Pirani gauge | new
14.6 | 0 | 72.52 | VRV4F04 | 34 | Roughing valve | VRV4F06 |  | Change label in MPS
14.6 | 0 | 72.9896 | MQX4F05 | 35 | Normal quad | MQX8F12 | moved from 8F
14.6 | 0 | 73.54 | ILM4F04 | 36 | Beam loss monitor | ILM4F05 | relabel?
14.6 | 0 | 73.7896 | MQX4F06 | 37 | Normal quad | MQX4F06
14.6 | 0 | 74.4 | ITV4F06 | 38 | Viewer | new | HDR viewer | Y(moved from ITV4F06) new input for wire
14.6 | 0 | 74.4 | VIP4F06 | 39 | Viewer | new | Use old VIP4F06 channel, off during target operation. Mounted opposite last upstream turbo?
14.6 | 0 | 74.7 | MDB4F06H | 40 | Hor. Corr. | new
14.6 | 0 | 74.7 | MDH4F06V | 41 | Vert. corr. | new
14.6 | 0 | 74.7 | IPM4F06 | 42 | BPM (SEE) | new | Take buttons from Arc 2
14.6 | 0 | 75.8646 | MSS4F06 | 43 | Detector solenoid | new | MIT detector solenoid | Y
14.6 | 0 | 76.5 | ITV4F06A | 44 | Viewer | new |  | Y(moved from ITV4F06A)
14.6 | 0 | 76.5 | ILM4F06A | 45 | Beam loss monitor | ILM4F06A
14.6 | 0 | 76.5 | MDB4F06AH | 46 | Hor. Corr. | new | use trim for old MDB4F06AH
14.6 | 0 | 76.5 | MDH4F06AV | 47 | Vert. corr. | new | use trim for old MDH4F06AV
14.6 | 0 | 76.4 | IPM4F06A | 48 | BPM (SEE) | new | Take buttons from Arc 2
14.6 | 0 | 76.4 | VIP4F06A | 49 | ion pump | VIP4F06A | Shut off during target operation. Mounted on tee on ITV4F06A?
14.6 | 0 | 78.5546 | MQX4F07 | 50 | Normal quad | MQX4F07
14.6 | 0 | 79.19 | MDB4F07H | 51 | Hor. Corr. | MDB4F07H
14.6 | 0 | 79.19 | MDH4F07V | 52 | Vert. corr. | MDH4F07V
14.6 | 0 | 79.19 | IPM4F07 | 53 | BPM(new) | IPM4F07
14.6 | 0 | 79.4 | ILM4F07 | 54 | beam | ILM4F07
14.6 | 0 | 79.5546 | MQX4F08 | 55 | Normal quad | MQX4F08
14.6 | 0 | 79.88 | ITV4F08 | 56 | Viewer (with hole) | ITV4F07
14.6 | 0 | 79.88 | VIP4F08 | 57 | ion pump | VIP4F08
14.6 | 0 | 72.52 | VPG4F08 | 58 | Pirani gauge | VPG8F13
14.6 | 0 | 72.52 | VRV4F08 | 59 | Roughing valve | VRV8F13 |  | Change label in MPS
14.6 | 0 | 80.5546 | MQX4F09 | 60 | Normal quad | MQX4F09
14.6 | 0 | 80.9 | VIP4F09 | 61 | ion pump | VIP8F13 | Use old VIP4F08A channel
14.6 | 0 | 81.2596 | MQX4F09AS | 62 | Skew quad | MQX8F13 | Use 8F13 girder with quad rotation?
14.6 | 0 | 81.94 | MDB4F09AH | 63 | Hor. Corr. | MDB8F13H
14.6 | 0 | 81.94 | MDH4F09AV | 64 | Vert. corr. | MDH8F13V
14.6 | 0 | 81.94 | IPM4F09A | 65 | BPM (new) | IPM8F13 | supported by MQX4F09AS girder
14.6 | 0 | 82.2596 | MQX4F09BS | 66 | Skew quad | MQX3F07S
14.6 | 0 | 82.76 | VBV4F09B | 67 | Vacuum valve | VBV4F09
14.6 | 0 | 83.2596 | MQX4F09CS | 68 | Skew quad | MQX3F08S
14.6 | 0 | 83.93 | ITV4F09C | 69 | Viewer | ITV4F09 | Use 8F10 girder, have to flip the stand.
14.6 | 0 | 83.93 | VIP4F09C | 70 | ion pump | VIP4F09 | Use 8F10 girder
14.6 | 0 | 84.2596 | MQX4F09DS | 71 | Skew quad | MQX8F10 | Use 8F10 girder
14.6 | 0 | 84.62 | MDB4F09DH | 72 | Hor. Corr. | MDB4F07H
14.6 | 0 | 84.62 | MDH4F09DV | 73 | Vert. corr. | MDH4F07V
14.6 | 0 | 84.62 | IPM4F09D | 74 | BPM(new) | IPM8F10
14.6 | 0 | 86.7 | ILM4F09D | 75 | Beam loss monitor | ILM4F10
14.6 | 0 | 85.2596 | MQX4F09ES | 76 | Skew quad | MQX3F09S
14.6 | 0 | 85.9646 | MQX4F10 | 77 | Normal quad | MQX4F10
14.6 | 0 | 86.9646 | MQX4F11 | 78 | Normal quad | MQX4F11
14.6 | 0 | 87.32 | VIP4F11 | 79 | ion pump | VIP4F11
14.6 | 0 | 87.32 | VPG4F11 | 80 | Pirani gauge | VPG4F11
14.6 | 0 | 87.32 | VRV4F11 | 81 | Roughing valve | VRV4F11
14.6 | 0 | 87.9646 | MQX4F12 | 82 | Normal quad | MQX4F12
14.6 | 0 | 89 | MDB4F12H | 83 | Hor. Corr. | MDB4F12H
14.6 | 0 | 89 | MDH4F12V | 84 | Vert. corr. | MDH4F12V
14.6 | 0 | 89 | IPM4F12 | 85 | BPM (4chan) | IPM4F12
14.6 | 0 | 89 | ITV4F12 | 86 | Viewer | ITV4F12
14.6 | 0 | 89 | VIP4F12 | 87 | ion pump | VIP4F12
14.6 | 0 | 89.5 | ILM4F12 | 88 | Beam loss monitor | ILM4F12
14.6 | 0 | 90 | VBV4F12 | 89 | Beamline valve | VBV4F12

## nomenclatureRevA
X | Y | Z | Nomenclature |  | Description | Old Nomenclature | Comments | New MPS input
14.6 | 0 | 64.25 | MDB4F00AH | 1 | Hor. Corr. | MDB4F00AH
14.6 | 0 | 64.25 | MDH4F00AV | 2 | Vert. corr. | MDH4F00AV
14.6 | 0 | 64.25 | IPM4F00A | 3 | BPM (SEE) | IPM4F00A
14.6 | 0 | 64.49 | ITV4F00A | 4 | Viewer | ITV4F00A
14.6 | 0 | 64.49 | VIP4F00C | 5 | Ion pump | VIP4F00C
14.6 | 0 | 64.8 | ILM4F00A | 6 | BLM head | ILM4F00A | BLMs in LED?
14.6 | 0 | 65.1896 | MQX4F01 | 7 | Normal quad | MQX4F01
14.6 | 0 | 65.9896 | MQX4F02 | 8 | Normal quad | MQX4F02
14.6 | 0 | 66.7896 | MQX4F03 | 9 | Normal quad | MQX4F03
14.6 | 0 | 67.4896 | MQX4F03AS | 10 | Skew quad | MQX3F03S | Moved from 3F line
14.6 | 0 | 67.8 | ILM4F03A | 11 | BLM HEAD | ILM4F03
14.6 | 0 | 69 | IEO4F03A | 16 | Electro-optic cell | new | Use ring resonator support stand. Align horiz to <3 mm precision | Y, Mode 2 when off outer limit
14.6 | 0 | 68 | MDB4F03AH | 12 | Hor. Corr. | MDB8F11H | Fed from UV rack?
14.6 | 0 | 68 | MDH4F03AV | 13 | Vert. Corr. | MDH8F11V | Fed from UV rack?
14.6 | 0 | 68 | IPM4F03A | 14 | BPM (new) | IPM8F11 | Have to verify that it fits
14.6 | 0 | 68.4896 | MQX4F03BS | 15 | Skew quad | MQX3F04S | Moved from 3F line
14.6 | 0 | 69.4896 | MQX4F03CS | 17 | Skew quad | MQX4F05 | Modified to rotate quad. Uses Happek viewer assembly.
14.6 | 0 | 67.82 | ITV4F03C | 18 | Viewer | ITV4F03 | Happek viewer moved from 4F03 girder to 4F05 girder
14.6 | 0 | 67.82 | VIP4F03C | 19 | Ion pump | VIP4F03 | moved with Happek viewer
14.6 | 0 | 67.82 | VPG4F03C | 20 | Pirani gauge | VPG4F03 | same | Y, now interlocked to valve
14.6 | 0 | 68.18 | MDB4F03CH | 21 | Hor. Corr. | MDB4F03H | same
14.6 | 0 | 68.18 | MDH4F03CV | 22 | Vert. corr. | MDH4F03V | same
14.6 | 0 | 68.18 | IPM4F03C | 23 | BPM (4chan) | IPM4F03
14.6 | 0 | 70.4896 | MQX4F03DS | 24 | Skew quad | MQX3F05S | Moved from 3F line
14.6 | 0 | 71 | ICM4F03D | 25 | Current monitor | ICM4F03 | Use beamline support stands from ring resonator
14.6 | 0 | 71.2 | VBV4F03D | 26 | Vacuum valve | new |  | Y
14.6 | 0 | 71.4896 | MQX4F03ES | 27 | Skew quad | MQX3F06S | Moved from 3F line
14.6 | 0 | 71.83 | MDB4F03EH | 28 | Hor. Corr. | MDB8F12H
14.6 | 0 | 71.83 | MDH4F03EV | 29 | Verti. Corr. | MDH8F12V
14.6 | 0 | 71.83 | IPM4F03E | 30 | BPM (new) | IPM8F12
14.6 | 0 | 72.1896 | MQX4F04 | 31 | Normal quad | MQX4F04
14.6 | 0 | 72.52 | VIP4F04 | 32 | Ion pump | VIP4F05 | Mounted on Turbopump chamber
14.6 | 0 | 72.52 | VPG4F04 | 33 | Pirani gauge | new |  | Y, interlocked to VBV4F03D
14.6 | 0 | 72.52 | VRV4F04 | 34 | Roughing valve | VRV4F06
14.6 | 0 | 72.9896 | MQX4F05 | 35 | Normal quad | MQX8F12 | girder and quad moved from 8F
14.6 | 0 | 73.54 | ILM4F04 | 36 | Beam loss monitor | ILM4F05 | relabel?
14.6 | 0 | 73.7896 | MQX4F06 | 37 | Normal quad | MQX4F06 |  | Y (moved from ITV4F06) new input for Harp
14.6 | 0 | 74.4 | ITV4F06 | 38 | Viewer | new | HDR viewer
14.6 | 0 | 74.4 | VIP4F06 | 39 | Viewer | new | Use old VIP4F06 channel, off during target operation. Mounted opposite last upstream turbo?
14.6 | 0 | 74.7 | MDB4F06H | 40 | Hor. Corr. | new
14.6 | 0 | 74.7 | MDH4F06V | 41 | Vert. corr. | new
14.6 | 0 | 74.7 | IPM4F06 | 42 | BPM (SEE) | new | Take buttons from Arc 2
14.6 | 0 | 75.8646 | MSS4F06 | 43 | Detector solenoid | new | MIT detector solenoid | Y for both magnet and target OK.
14.6 | 0 | 76.5 | ITV4F06A | 44 | Viewer | new |  | Y(moved from ITV4F06A)
14.6 | 0 | 76.5 | ILM4F06A | 45 | Beam loss monitor | ILM4F06A
14.6 | 0 | 76.5 | MDB4F06AH | 46 | Hor. Corr. | new | use trim channel for old MDB4F06AH
14.6 | 0 | 76.5 | MDH4F06AV | 47 | Vert. corr. | new | use trim channel for old MDH4F06AV
14.6 | 0 | 76.4 | IPM4F06A | 48 | BPM (SEE) | new | Take buttons from Arc 2
14.6 | 0 | 76.4 | VIP4F06A | 49 | ion pump | VIP4F06A | Shut off during target operation. Mounted on tee on ITV4F06A?
14.6 | 0 | 78.5546 | MQX4F07 | 50 | Normal quad | MQX4F07
14.6 | 0 | 79.19 | MDB4F07H | 51 | Hor. Corr. | MDB4F07H | Need to see if it fits
14.6 | 0 | 79.19 | MDH4F07V | 52 | Vert. corr. | MDH4F07V | Need to see if it fits
14.6 | 0 | 79.19 | IPM4F07 | 53 | BPM(new) | IPM4F07 | Need to see if it fits
14.6 | 0 | 79.4 | ILM4F07 | 54 | Beam loss monitor | ILM4F07
14.6 | 0 | 79.5546 | MQX4F08 | 55 | Normal quad | MQX4F08
14.6 | 0 | 79.88 | ITV4F08 | 56 | Viewer (with hole) | ITV4F07 | Change label? | Change label in MPS
14.6 | 0 | 79.88 | VIP4F08 | 57 | ion pump | VIP4F08
14.6 | 0 | 72.52 | VPG4F08 | 58 | Pirani gauge | VPG8F13
14.6 | 0 | 72.52 | VRV4F08 | 59 | Roughing valve | VRV8F13
14.6 | 0 | 80.5546 | MQX4F09 | 60 | Normal quad | MQX4F09
14.6 | 0 | 80.9 | VIP4F09 | 61 | ion pump | VIP8F13 | Use old VIP4F08A channel
14.6 | 0 | 81.2596 | MQX4F09AS | 62 | Skew quad | new | Use 8F12 stand, 8F13 quad, and new T-plate
14.6 | 0 | 81.94 | MDB4F09AH | 63 | Hor. Corr. | MDB8F13H | Use beamline support stands from ring resonator
14.6 | 0 | 81.94 | MDH4F09AV | 64 | Vert. corr. | MDH8F13V | same
14.6 | 0 | 81.94 | IPM4F09A | 65 | BPM (new) | IPM8F13 | same
14.6 | 0 | 82.2596 | MQX4F09BS | 66 | Skew quad | MQX3F07S | Moved from 3F line
14.6 | 0 | 82.76 | VBV4F09B | 67 | Vacuum valve | VBV4F09 |  | Now interlocked to convectron gauges.
14.6 | 0 | 83.2596 | MQX4F09CS | 68 | Skew quad | MQX3F08S | Moved from 3F line
14.6 | 0 | 83.93 | ITV4F09C | 69 | Viewer | ITV4F09 | Use 8F10 girder, have to flip the stand.
14.6 | 0 | 83.93 | VIP4F09C | 70 | ion pump | VIP4F09 | Use 8F10 girder
14.6 | 0 | 84.2596 | MQX4F09DS | 71 | Skew quad | MQX8F10 | Use 8F10 girder
14.6 | 0 | 84.62 | MDB4F09DH | 72 | Hor. Corr. | MDB4F09H | Can either use 8F10 corrector or 4F09 corrector
14.6 | 0 | 84.62 | MDH4F09DV | 73 | Vert. corr. | MDH4F09V | same
14.6 | 0 | 84.62 | IPM4F09D | 74 | BPM(new) | IPM8F10
14.6 | 0 | 86.7 | ILM4F09D | 75 | Beam loss monitor | ILM4F10
14.6 | 0 | 85.2596 | MQX4F09ES | 76 | Skew quad | MQX3F09S | Moved from 3F line
14.6 | 0 | 85.9646 | MQX4F10 | 77 | Normal quad | MQX4F10
14.6 | 0 | 86.9646 | MQX4F11 | 78 | Normal quad | MQX4F11
14.6 | 0 | 87.32 | VIP4F11 | 79 | ion pump | VIP4F11
14.6 | 0 | 87.32 | VPG4F11 | 80 | Pirani gauge | VPG4F11
14.6 | 0 | 87.32 | VRV4F11 | 81 | Roughing valve | VRV4F11
14.6 | 0 | 87.9646 | MQX4F12 | 82 | Normal quad | MQX4F12
14.6 | 0 | 89 | MDB4F12H | 83 | Hor. Corr. | MDB4F12H
14.6 | 0 | 89 | MDH4F12V | 84 | Vert. corr. | MDH4F12V
14.6 | 0 | 89 | IPM4F12 | 85 | BPM (4chan) | IPM4F12
14.6 | 0 | 89 | ITV4F12 | 86 | Viewer | ITV4F12
14.6 | 0 | 89 | VIP4F12 | 87 | ion pump | VIP4F12
14.6 | 0 | 89.5 | ILM4F12 | 88 | Beam loss monitor | ILM4F12
14.6 | 0 | 90 | VBV4F12 | 89 | Beamline valve | VBV4F12

## nomenclatureRevB
X | Y | Z | Nomenclature |  | Description | Old Nomenclature | Comments | New MPS input
14.6 | 0 | 64.25 | MDB4F00AH | 1 | Hor. Corr. | MDB4F00AH
14.6 | 0 | 64.25 | MDH4F00AV | 2 | Vert. corr. | MDH4F00AV
14.6 | 0 | 64.25 | IPM4F00A | 3 | BPM (SEE) | IPM4F00A
14.6 | 0 | 64.49 | ITV4F00A | 4 | Viewer | ITV4F00A
14.6 | 0 | 64.49 | VIP4F00C | 5 | Ion pump | VIP4F00C
14.6 | 0 | 64.8 | ILM4F00A | 6 | BLM head | ILM4F00A
14.6 | 0 | 65.1896 | MQX4F01 | 7 | Normal quad | MQX4F01
14.6 | 0 | 65.9896 | MQX4F02 | 8 | Normal quad | MQX4F02
14.6 | 0 | 66.7896 | MQX4F03 | 9 | Normal quad | MQX4F03
14.6 | 0 | 67.4896 | MQX4F03AS | 10 | Skew quad | MQX3F03S | Moved from 3F line
14.6 | 0 | 67.8 | ILM4F03A | 11 | BLM HEAD | ILM4F03
14.6 | 0 | 68 | MDB4F03AH | 12 | Hor. Corr. | MDB8F11H | Fed from UV rack?
14.6 | 0 | 68 | MDH4F03AV | 13 | Vert. Corr. | MDH8F11V | Fed from UV rack?
14.6 | 0 | 68 | IPM4F03A | 14 | BPM (new) | IPM8F11 | Support using ring resonator floor stands
14.6 | 0 | 68.4896 | MQX4F03BS | 15 | Skew quad | MQX3F04S | Moved from 3F line
14.6 | 0 | 69 | IEO4F03B | 16 | Electro-optic cell | new | Use ring resonator support stand. Align horiz to <3 mm precision | Y, Mode 2 when off outer limit
14.6 | 0 | 69.4896 | MQX4F03CS | 17 | Skew quad | MQX4F05 | Modified to rotate quad. Mounted on 4F05 girder along with Happek viewer assembly
14.6 | 0 | 67.82 | ITV4F03C | 18 | Viewer | ITV4F03 | Happek viewer moved from 4F03 girder to 4F05 girder
14.6 | 0 | 67.82 | VIP4F03C | 19 | Ion pump | VIP4F03 | moved with Happek viewer
14.6 | 0 | 67.82 | VPG4F03C | 20 | Pirani gauge | VPG4F03 | Interlocked to valve VBV4F03D | Y, now interlocked to valve
14.6 | 0 | 68.18 | MDB4F03CH | 21 | Hor. Corr. | MDB4F03H | Moved from 4F03 girder
14.6 | 0 | 68.18 | MDH4F03CV | 22 | Vert. corr. | MDH4F03V | same
14.6 | 0 | 68.18 | IPM4F03C | 23 | BPM (4chan) | IPM4F03 | same
14.6 | 0 | 70.4896 | MQX4F03DS | 24 | Skew quad | MQX3F05S | Moved from 3F line
14.6 | 0 | 71 | ICM4F03D | 25 | Current monitor | ICM4F03 | Use beamline support stands from ring resonator
14.6 | 0 | 71.2 | VBV4F03D | 26 | Vacuum valve | new | Need to identify valve flanges. | Y
14.6 | 0 | 71.4896 | MQX4F03ES | 27 | Skew quad | MQX3F06S | Moved from 3F line
14.6 | 0 | 71.83 | MDB4F03EH | 28 | Hor. Corr. | MDB8F12H | Moved from 8F line
14.6 | 0 | 71.83 | MDH4F03EV | 29 | Verti. Corr. | MDH8F12V | same
14.6 | 0 | 71.83 | IPM4F03E | 30 | BPM (new) | IPM8F12 | same
14.6 | 0 | 72.1896 | MQX4F04 | 31 | Normal quad | MQX4F04
14.6 | 0 | 72.52 | VPG4F04 | 32 | Pirani gauge | new | This is an inficon gauge with inficon controller mounted below the first turbopump | Y, interlocked to VBV4F03D
14.6 | 0 | 72.52 | VRV4F04 | 33 | Roughing valve | VRV4F06
14.6 | 0 | 72.9896 | MQX4F05 | 34 | Normal quad | MQX8F12 | girder and quad moved from 8F
14.6 | 0 | 73.54 | ILM4F04 | 35 | Beam loss monitor | ILM4F05 | relabel?
14.6 | 0 | 73.7896 | MQX4F06 | 36 | Normal quad | MQX4F06
14.6 | 0 | 74.4 | ITV4F06 | 37 | Viewer | new | HDR viewer | Y (moved from ITV4F06) new input for Harp
14.6 | 0 | 74.7 | MDB4F06H | 38 | Hor. Corr. | new
14.6 | 0 | 74.7 | MDH4F06V | 39 | Vert. corr. | new
14.6 | 0 | 74.7 | IPM4F06 | 40 | BPM (SEE) | new | Mount on short spool piece. Take buttons from Arc 2
14.6 | 0 | 75.8646 | MFF4F06 | 41 | Detector solenoid | new | MIT detector solenoid | Y for both magnet and target OK.
14.6 | 0 | 76.5 | ITV4F06A | 42 | Viewer | new | Must come up with design. | Y(moved from ITV4F06A)
14.6 | 0 | 76.5 | ILM4F06A | 43 | Beam loss monitor | ILM4F06A
14.6 | 0 | 76.5 | MDB4F06AH | 44 | Hor. Corr. | new | use trim channel for old MDB4F06AH
14.6 | 0 | 76.5 | MDH4F06AV | 45 | Vert. corr. | new | use trim channel for old MDH4F06AV
14.6 | 0 | 76.4 | IPM4F06A | 46 | BPM (SEE) | new | Take buttons from Arc 2
14.6 | 0 | 78.5546 | MQX4F07 | 47 | Normal quad | MQX4F07
14.6 | 0 | 79.19 | MDB4F07H | 48 | Hor. Corr. | MDB4F07H | Need to see if it fits
14.6 | 0 | 79.19 | MDH4F07V | 49 | Vert. corr. | MDH4F07V | Need to see if it fits
14.6 | 0 | 79.19 | IPM4F07 | 50 | BPM(new) | IPM4F07 | Need to see if it fits
14.6 | 0 | 79.4 | ILM4F07 | 51 | Beam loss monitor | ILM4F07
14.6 | 0 | 79.5546 | MQX4F08 | 52 | Normal quad | MQX4F08
14.6 | 0 | 79.88 | ITV4F08 | 53 | Viewer (with hole) | ITV4F07 | Change label? | Change label in MPS
14.6 | 0 | 79.88 | VIP4F08 | 54 | ion pump | VIP4F08 | Not interlocked to valve
14.6 | 0 | 72.52 | VPG4F08 | 55 | Pirani gauge | VPG8F13 | Use inficon gauge on turbo?
14.6 | 0 | 72.52 | VRV4F08 | 56 | Roughing valve | VRV8F13
14.6 | 0 | 80.5546 | MQX4F09 | 57 | Normal quad | MQX4F09
14.6 | 0 | 81.2596 | MQX4F09AS | 58 | Skew quad | new | Use 8F12 stand, 8F13 quad, and new T-plate
14.6 | 0 | 81.94 | MDB4F09AH | 59 | Hor. Corr. | MDB8F13H | Use beamline support stands from ring resonator
14.6 | 0 | 81.94 | MDH4F09AV | 60 | Vert. corr. | MDH8F13V | same
14.6 | 0 | 81.94 | IPM4F09A | 61 | BPM (new) | IPM8F13 | same
14.6 | 0 | 82.2596 | MQX4F09BS | 62 | Skew quad | MQX3F07S | Moved from 3F line
14.6 | 0 | 82.76 | VBV4F09B | 63 | Vacuum valve | VBV4F09 | supported as before | Now interlocked to convectron gauges.
14.6 | 0 | 83.2596 | MQX4F09CS | 64 | Skew quad | MQX3F08S | Moved from 3F line
14.6 | 0 | 83.93 | ITV4F09C | 65 | Viewer | ITV8F10 | Use 8F10 girder, have to rotate the stand 180 degrees.
14.6 | 0 | 83.93 | VIP4F09C | 66 | ion pump | VIP8F10 | Use 8F10 girder
14.6 | 0 | 84.2596 | MQX4F09DS | 67 | Skew quad | MQX8F10 | Use 8F10 girder. Remount modified quad with spacer plate.
14.6 | 0 | 84.62 | MDB4F09DH | 68 | Hor. Corr. | MDB4F09H | Can either use 8F10 corrector or 4F09 corrector
14.6 | 0 | 84.62 | MDH4F09DV | 69 | Vert. corr. | MDH4F09V | same
14.6 | 0 | 84.62 | IPM4F09D | 70 | BPM(new) | IPM8F10
14.6 | 0 | 86.7 | ILM4F09D | 71 | Beam loss monitor | ILM4F10
14.6 | 0 | 85.2596 | MQX4F09ES | 72 | Skew quad | MQX3F09S | Moved from 3F line
14.6 | 0 | 85.9646 | MQX4F10 | 73 | Normal quad | MQX4F10
14.6 | 0 | 86.9646 | MQX4F11 | 74 | Normal quad | MQX4F11
14.6 | 0 | 87.32 | VIP4F11 | 75 | ion pump | VIP4F11
14.6 | 0 | 87.32 | VPG4F11 | 76 | Pirani gauge | VPG4F11 | Interlocked to valve VBV4F09B
14.6 | 0 | 87.32 | VRV4F11 | 77 | Roughing valve | VRV4F11
14.6 | 0 | 87.9646 | MQX4F12 | 78 | Normal quad | MQX4F12
14.6 | 0 | 89 | MDB4F12H | 79 | Hor. Corr. | MDB4F12H
14.6 | 0 | 89 | MDH4F12V | 80 | Vert. corr. | MDH4F12V
14.6 | 0 | 89 | IPM4F12 | 81 | BPM (4chan) | IPM4F12
14.6 | 0 | 89 | ITV4F12 | 82 | Viewer | ITV4F12
14.6 | 0 | 89 | VIP4F12 | 83 | ion pump | VIP4F12
14.6 | 0 | 89.5 | ILM4F12 | 84 | Beam loss monitor | ILM4F12
14.6 | 0 | 90 | VBV4F12 | 85 | Beamline valve | VBV4F12