## schedule
| Dark Light Installation |  | 2016-04-04 | 2016-07-06
Item | Task Name | Group | Start | Finish | % Complete | Comment
Vault Prep
1 | Remove blocks | Installation | 2016-05-16 | 2016-05-17 | 100 | Completed
2 | Vent 4F vacuum and remove components/ instrumentation/ beamline | Install, EESIC, EESDC | 2016-04-14 | 2016-05-13 | 100 | Completed
3 | Remove 3F Skew Quads from beamline | Install | 2016-04-14 | 2016-05-13 | 100 | Completed
4 | Remove UV Quads and skew quads, quads/ wiggler, THz chicane from beamline | Install | 2016-04-14 | 2016-05-20 | 100 | Completed
5 | Fabricate skew quad stands | ME, Machine Shop | 2016-04-04 | 2016-05-27 | 100 | spacing blocks, plate submitted to machine shop
6 | Complete Box Supply Shuffle | DCPower/ Electricians | 2016-04-14 | 2016-05-16 | 100 | Completed
7 | Reconnect 3F region quad LCW | Install | 2016-04-14 | 2016-05-13 | 100
4F Beamline Layout
1 | 4F - Beamline mechanical layout, for engineering run 07/15 | Mech. Engineering | 2016-04-04 | 2016-05-16 | 95 | Need sub region 3 complete. Sub region 2 and 4 songsheets completed but not signed off.
2 | Identify survey points | Mech. Engineering | 2016-04-14 | 2016-05-06 | 100 | is finaized / nomenclature Rev D
3 | Vault Point Layout | Survey | 2016-05-19 | 2016-05-19 | 100 | Completed
4 | Element/ Instrumentation List | Mech. Engineering | 2016-04-04 | 2016-05-16 | 95 | Need sub region 3 instrumentation and beamline songsheets complete.
6 | Install Skew quads/ new girders into 4F line/ reconnect LCW, DC power leads | Install/ DCP | 2016-05-23 | 2016-06-10 | 100 | All quads installed and wired
| Install, connect and test corrector sets in 4F region | DCP |  | 2016-06-10 | 0
7 | Fabricate beam tubes/ spool pieces | Install | 2016-04-18 | 2016-06-13 | 90 | sub regions 2 and 4 being worked on.
| Install Target spool piece, Moeller stand and dump, and align | Install |  | 2016-06-13 | 0 | Arriving 07/05/2016
8 | 4F Beamline- Detector/ Blower/ not needed for engineering run | Facilties/ /Install/ DCPower/ Electricians | 2016-07-01 | 2016-07-30 | 50 | Requirements received: identify/ complete installation/test/ working to have it delivered earlier
5 | Design Moller dump shielding/ not needed for engineering run | Radcon, ME | 2016-05-16 | 2016-05-27 | 80 | not needed for July run
Solenoid Box Supply
1 | Delivery (PS) | MIT/ Install | 2016-06-16 | 2016-06-17 | 0 | delivery now set for 07/18
1a | Set into final position |  |  | 2016-06-17 | 0
2 | 500A Breaker Install | Facilities | 2016-05-09 | 2016-06-16 | 100 | done
3 | Installallation AC/ LCW/ DC Leads | Facilties/ /Install/ DCPower/ Electricians | 2016-06-16 | 2016-06-21 | 50 | one lead failed presseure test/ find and test the other
4 | Box Supply Checkout | DCPower/ MIT/ Physics |  |  | 0 | need requirements from MIT for controls/ delivery set for 07/18
Solenoid/ Stand
1 | Delivery | MIT/ Install | 2016-06-06 |  | 100 | 2016-06-14
2 | Install solenoid plate | MIT/ Install | 2016-06-06 | 2016-06-07 | 100 | delivered
4 | Install solenoid | MIT/ Install | 2016-06-07 | 2016-06-09 | 100 | delivered 06/14/2016
5 | Align solenoid | Survey | 2016-06-10 | 2016-06-14 | 90 | Need to pull top half of plate
6 | Connect Solenoid magnet LCW/ DC Leads and covers | MIT/ Physics/ DCPower ? | 2016-06-15 | 2016-06-17 | 50 | behind schedule
7 | PS/Solenoid Commissioning | MIT/ Physics/ DCPower ? | 2016-06-20 | 07/18//2016 | 0 | might have to commission both PS and Magnet at same time
Post Installation Tasks
1 | Re-Install skew quads into 4F region | Install | 2016-05-02 | 2016-05-27 | 100 | need last 3 skew quads installed
2 | Install final vacuum chambers/ restore vacuum | Install | 2016-06-20 | 2016-06-24 | 75 | awaituing spool pieces/ update on vacuum electronincs
3 | Re-install 4F10-4F12 girders | Install | 2016-06-20 | 2016-06-22 | 100 | needs completion
4 | Install Moller dump and shielding | install | 2016-06-27 | 2016-07-02 | 10 | find out when dump is arriving. Have a plan B Need drop dead on delivery
5 | Final Alignment | Survey | 2016-06-20 | 2016-06-24 |  | need to schedule
6 | Install/ connect 4F diagnostics/ instrumentation/ magnets | EESIC, DC, | 2016-04-25 | 2016-06-13 | 25 | beamline not complete
7 | Reinstall blocks | Install | 2016-07-01 | 2016-07-05 |  | Can be done anytime after magnet delivery
8 | Re-Certify Box supply Arc 2 | PSS |  |  |  | Need to Schedule/ Arc 2 install is complete
9 | Hot Check out prep and punch list | EES | 2016-04-04 | 2016-07-01 |  | Ongoing
10 | Final Hot check out | EES | 2016-07-05 | 2016-07-14
11 | Dark Light Run | Ops/ Physics | 2016-07-14 | 2016-08-02
racks downstairs
sheilding downstairs

## 05_09
Activity Last Week:
Bolt patterns for the solenoid stand have been completed. Floor layout scheduled for 5/19
Block removal is scheduled for 5/16
Continued with 4F beamline removal at the 4F03 thru the 4F04 girders
Completed upgrade and installation for HystArea (trim cycling tool)
Brandi working with Gary to update the Box Supply Cycling tool.
dlsupport mailing list is active
Tasks for this week:
Get the 3F quad water cooling reconnected.
Derive a list of changes to the 4F including physical and control changes. 5/16/2016
What are the pressure and flow (and perhaps pressure vs. flow if there is strong dependence) of the nitrogen line.
Get AC power specifications for power supply so that breaker can be ordered
Continue with box supply shuffle (connect AC, LCW, controls)

## 05_17
Activity Last Week:
B. Zihlmann has been named the Physics liason
Songsheet and element list for the 4F region nearly complete, meeting with DiPette, Curtis, Lassiter to review before release
Received the power and water requirements requirements for the detector pumps
Quote for PS breaker received (will order today)
The P&ID (Process and Instumentation diagram) for the detector has been received, forwarded to the EESIC group.
Meeting scheduled witth EESIC to identify interlocks
A path forward from EESIC has been proposed for the additional BPM's and vacuum valves
Modeling status:
Chris Tennant to deliver elegant decks for 3F and 4F regions to Michele
Dave Douglas to deliver properties and values needed for his master spreadsheet.
All BPM screens and tools have been submitted for certification and release.
Tasks for this week:
Get the 3F quad water cooling reconnected.
What are the pressure and flow (and perhaps pressure vs. flow if there is strong dependence) of the nitrogen line.
Remove Wiggler, ThZ chicane from beamline
Begin point layout
Begin installation of 4F skew quads
Begin cable installation for 4F skew quads

## 05_24
Activity Last Week:
Completed 4F beamline removal except 4F09
4F Skew quad points layed down
Arc 2 box supply relocated to new postion/ ThZ supply and string decommissioned/ removed
Solenoid breaker ordered, 3-5 day (turn around) delivery ~ 5/25
Cable delivered for Arc 2 AC power
Skew spacers/ plate ordered from machine shop ( 7 day turn around)
Had a meeting with MIT, Survey, Install to identify issues with solenoid installation, target alignmnet
Chris Tennant to deliver elegant decks for 3F and 4F regions to Michele (status?)
Dave Douglas to deliver properties and values needed for his master spreadsheet. (status?)
Tasks for this week:
Complete Arc2 com/ power/ LCW connections
Begin installation of 4F skew quads
Begin cable installation for 4F skew quads
Release final 4F songsheets
Wait for Solenoid delivery

## 05_31
Activity Last Week:
Complete Arc2 com/ power/ LCW connections
Began installation of 4F skew quads
Laid out vacuum elements in the 4F
Complete Arc2 com/ power/ LCW connections
Remove girders and quads for modifications
Tasks for this week:
Prepare for magnet arrival
Complete LED information
Complete vacuum element layout, specify drift tubes
Complete diagnostic requirements
Modify quads into skew quads
Assemble 4F03C and 4F09D girders

## 06_07
Activity Last Week:
Prepare for magnet arrival/ plate will be delivered before magnet/ installation plan confirmed with MIT
elegant file for the 4F region was delivered, loading of the Optics began
DC Power is verifying LED elements/ beginning HCO of the box supplies
Complete vacuum element layout, specify drift tubes..complete/ drawings need check and sign off
M:\me-group\Ron_Lassiter\LERF\Dark_Light\LRF0000440-0001-rev A
Complete diagnostic requirements / pretty much complete per S. Benson
Modify quads into skew quads/ in progress. Plate and spacers delivered to magnet test/ quads being split
Assemble 4F03C and 4F09D girders/ work continues
nomenclature document is awaiting final check off
Tasks for this week:
complete assembly 4F03C and 4F09D girders
Complete modification of quads into skew quads
Install reamining girders
calculate the derating value of the penetration / order MCM cable and lugs
design the moving lense assembly for Happek (shiny bald guy)
begin DC Power cable install for the 4F magnet components
release final element layout

## 06-21
http://www.dailypress.com/news/science/dp-nws-darklight-jeff-lab-20160617-story.html
Activity Last Week:
Solenoid was delivered/ both magnet and plate installed
Sub region 3 songsheet is almost complete, waiting on MIT for delivery dates for solenoid / target spool piece
Desire to be under vacuum as soon as possible
Fiducialization of the solenoid magnet has begun
Labview scheme for the BPM effort is functional
Spool piece fabrication for sub region 2 and 4 has begun
Cable installation for 4F quads complete
Shunts have been merged into the LED
The magnet LED for the 3F region has been updated
Systems integration meetings are at 10:00 Thursdays in the MCC conference room
Tasks for this week:
Complete modification of last 3 skew quads and install (due 06/21)
Install 4F10-4F12 girders
Measure N2 flow for detector (outstanding item )
Complete fiducialization of solenoid
Begin power up of trim racks for the 0F-3F regions for HCO
Begin installation for the root blowers power distrubution (continuing )
Continue with the beamline spool piece installation and other vacuum hardware. Need update on vacuum electronics for 4F region.
Can the linac valves be opened to begin viewer alignmnent in the 0F thru 2F region?
Find a solution for the DC power leads
Power Supply controls specifications from MIT
Moeller Dump section preliminarily will be on time for installation
Continue with any BPM screen issues.
Software will begin on the Alarm Handler configuration

## 06-28
http://www.dailypress.com/news/science/dp-nws-darklight-jeff-lab-20160617-story.html
Activity Last Week:
Modifications and installation of the 3 skew quads were completed
4F10-4F12 girders were installed
N2 flow measurement has been assigned to Cryo, no problem expected, we need 3 SCFM and can expect 5
Final fidulization has been put on hold due to measurement of inner bore
Power up of trim racks complete except the new 4F components
Continue with the beamline spool piece installation and other vacuum hardware. Need update ?
Able to achieve valve permit in the linac.
Located some water cooled leads on site, pressure testing will begin 06-28 thanks to Physics division
New water leads have been ordered, lead time 3 weeks, will install whats available, replace leads during August break
Power Supply controls specifications from MIT due this week
Nomenclature Rev B has been released
Points for the EO cell and Happek were marked
Tasks for this week:
Complete flow measurement
Install floor bolts for EO cell and Happek
Get survey point s for the Large Dynamic Range (LDR) viewer
Pressure, electrical testing then installation of power leads
Continue installation for the root blowers power distrubution , not all hardware received
Continue AC installation for Power Supply
Sub region 3 step file needs to completed for the test setup ( for verification of the model, MIT)
Continue with the beamline spool piece installation and other vacuum hardware as schedule allows
Continue DC Power terminations of the 4F quads
Gun Cathode was made successfully, need to schedule HV processing
Continue pressuring MIT for the Power Supply controls specifications
Unexpected Installation Tasks:
Need ceiling hooks for the end plates of the solenoid installed or other lifting solution
Remove end plate for target spool piece installation
Installation Date Shuffle:
Delivery date for the target spool piece and Moeller stand and chamber is July 1 ?
Delivery date for PS is now July 5-ish
Schedule shielding block installation
solid concrete blocks moved in before shielding blocks installed (60 blocks) needed 08/15
What about the steel? Needed 08/15

## 07-05
Activity Last Week:
Pressure tested power leads. One passed one failed. Looking for spare cable
Breaker and AC wiring for solenoid power supply installed
Received step file from MIT to complete Sub region 3
Continued with the beamline spool piece fabrication and other vacuum hardware as schedule allows
Completed DC Power terminations of the 4F quads
Continued pressuring MIT for the Power Supply controls specifications
Some parts sent down from MIT
Power supply delivery slipped again. Now week of 07/18/2016
Tasks for this week:
System owners should power up and look over their respective systems after Friday's power outage
Complete flow measurement
Install lifting solution for end plates
Install floor bolts for EO cell and Happek
Come up with design for Shiny bald guy lens
Get survey points for the Large Dynamic Range (LDR) viewer
find new power lead and install leads
Begin DC Power HCO of existing hardware
Continue installation for the root blowers power distrubution , not all hardware received
Sing off on all 4F song sheets
Continue with the beamline spool piece installation and other vacuum hardware as schedule allows
Start installation and termination of corrector coils
Schedule HV processing (resubmit TOSP)
Continue pressuring MIT for the Power Supply controls specifications and delivery date
Start installation of MIT hardware
Remove end plate for spool piece installation and fiducialization
Install concrete blocks for rack shielding
Begin vault clean out
Installation Date Shuffle:
Delivery date for the target spool piece and Moeller stand and chamber is July 5 ?
Delivery date for PS is now July 13-ish
Schedule shielding block installation
What about the steel? Needed 08/15

## Punch List
| Punch List Items (not a complete list) | POC | % Complete | Comments
CIS
| Replace Drive Laser Mechanical shutters | Zhang | 100 | Done
| Repair or replace Radiation Monitor RADMONxCH6 | Garcia/Bullard |  | Need Update
EESDCP
| Verify and repair GC magnet EPICS controls | Coleman | 50 | same screens as before
| HCO of new Magnet IOC | DCP | 50 | Part of HCO tasks
EESRFS
Nelson/Cooper
1 | Crowbar ready fix for Zone FL03
2 | Load in proper RF drive-high values |  |  | Drury should have starting values.
3 | RF power is high on cavity 4-2
4 | Find out why the 12V power supplies fail in zone 3 and 4?
EESSAF
T. Michaelides/ R. Araiza
1 | BM3 and BM6 keys are backwards; you should be able to remove the key after switching system into those modes to lock them in |  | 90 | in progress
2 | Change mode 6 truth table so that BLMs trip the beam but can be masked. |  | 50 | Firmware update in pregress
3 | Update ODH heads. |  | 100
4 | Recertify PSS (done) |  | 100 | Recertify Arc 2/ has been scheduled
RadCon
1 | Fix W55 rad monitor | M. Washington |  | re-configure for Dark Light
| Rapid Access System |  |  | HCO , move heads if needed
EESICS
O. Garza
1 | Install additional valve and channel in 4F | Kortze | 20 | Interlock new valves to convectrons and inficons
2 | Get E-style BPMs working or replace with other technology | Francis/ Allison | 75 | Use E-style BPMs. Borrow electronics from UV line and get new computer up.
4 | SEE BPMs triggering must come from time delay cards. | Francis | 75
5 | FELScope Ext triggers were missing | Cole
6 | Regain remote control of oscilloscope | Cole |  | Need strategy for O'scope controls
7 | Current monitor readbacks in EPICS | Cole |  | Need details on signal inteffaces
8 | Viewers in 3F align, focus, and set gains | Dela Cruze/ Norris
9 | Replace damaged cameras as needed | Dela Cruze/ Norris
10 | Put 5F alignment laser in a more permanent fixture and align to 1F line |  |  | Have to remove viewer when using.
11 | Move IR Happek to IR controls (now partially on UV controls) |  | 25 | Use UV controls and relabel if possible
12 | Install new shiny bals guy | K. Jordan
MSNST
1 | Fix noisy ion pumps (especially in the 5F region) | Kortze
OPSADM
1 | Console FEL05 requires a reboot to wake up after it goes to sleep
2 | Replace magnet IOC | G. Croke | 100
3 | Update IOC controls
OPSSFT
2 | ADL monitor logs not working |  |  | Possibly due to hardware being off?
3 | Update turn-on procedure to include check of BLM HV |  |  | This may be just a procedural change. Need to see if the software has to be modified.
4 | Archive signals for many of the BPMs | Slominski/ Francis | 25 | This is done through Archive request channels.
5 | "All-valve" controls | S. Weatherspoon/ Kortze |  | Have to get hardware fixed first.
OPS
M. Joyce/ M. McCaughan
1 | Develop magnet screens |  | 75 | Derived mostly from LED
2 | Develop BPM screens |  | 100 | Derived from LED
| software updates |  | 50 | 4 channel left to due
3 | Develop BLM screens OTF |  | 75
4 | Update viewer screens |  | ? | Update using McCaughan's ideas
5 | FSD screen |  | 25 | Derived from LED?
6 | Vacuum screens |  |  | need hardware to software tag
7 | Get 5F08 beam stop working from viewer pages |  |  | Mike wants have a separate screen for this.
8 | Other ease of operation updates |  |  | Need to meet with Frierson, McCaughan, Freeman and Larrieu to determine task list.
9 | Bluecherry for video signals | B. Freeman |  | deferred
OPSHLA
M. Joyce/ B. Cade
1 | LED development and implementation |  | 60 | still needs system owner input/ OTF screens?
2 | –Update phasing script to check for out-of-bounds magnet supply requests |  |  | need update
3 | shutdown scripts crash because of missing / unresponsive elements |  |  | need update
Hot Check Out
1 | CIS – Heat clean and condition cathode | M. Poelker/ C. Hernandez |  | scheduled for 06/27
2 | EESICS - Check zone 1 wiring for AMS
3 | EESRFS - Condition the zone 1 couplers
4 | EESRFS - Noisy RF control loops (have to reset the loop gains)
5 | EESICS - Check all timing signals (need documentation)
LERF Ops Procedures
S. Frierson/ Benson/ MIT
1 | SOP's
2 | TSOP's

## nomenclature
X | Y | Z | Nomenclature |  | Description | Old Nomenclature | Comments | New MPS input
14.6 | 0 | 64.25 | MDB4F00AH | 1 | Hor. Corr. | MDB4F00AH
14.6 | 0 | 64.25 | MDH4F00AV | 2 | Vert. corr. | MDH4F00AV
14.6 | 0 | 64.25 | IPM4F00A | 3 | BPM (SEE) | IPM4F00A
14.6 | 0 | 64.49 | ITV4F00A | 4 | Viewer | ITV4F00A
14.6 | 0 | 64.49 | VIP4F00C | 5 | Ion pump | VIP4F00C
14.6 | 0 | 64.8 | ILM4F00A | 6 | BLM head | ILM4F00A | BLMs in LED?
14.6 | 0 | 65.1896 | MQX4F01 | 7 | Normal quad | MQX4F01
14.6 | 0 | 65.9896 | MQX4F02 | 8 | Normal quad | MQX4F02
14.6 | 0 | 66.7896 | MQX4F03 | 9 | Normal quad | MQX4F03
14.6 | 0 | 67.4896 | MQX4F03AS | 10 | Skew quad | MQX3F03S
14.6 | 0 | 67.8 | ILM4F03A | 11 | BLM HEAD | ILM4F03
14.6 | 0 | 69 | IEO4F03A | 16 | Electro-optic cell | new | Use ring resonator support stand | Y
14.6 | 0 | 68 | MDB4F03AH | 12 | Hor. Corr. | MDB8F11H | Fed from UV rack
14.6 | 0 | 68 | MDH4F03AV | 13 | Vert. Corr. | MDH8F11V | Fed from UV rack
14.6 | 0 | 68 | IPM4F03A | 14 | BPM (new) | IPM8F11
14.6 | 0 | 68.4896 | MQX4F03BS | 15 | Skew quad | MQX3F04S
14.6 | 0 | 69.4896 | MQX4F03CS | 17 | Skew quad | MQX4F05 | Modified to rotate quad. Uses Happek viewer assembly.
14.6 | 0 | 67.82 | ITV4F03C | 18 | Viewer | ITV4F03 | Happek viewer
14.6 | 0 | 67.82 | VIP4F03C | 19 | Ion pump | VIP4F03
14.6 | 0 | 67.82 | VPG4F03C | 20 | Pirani gauge | VPG4F03
14.6 | 0 | 68.18 | MDB4F03CH | 21 | Hor. Corr. | MDB4F03H
14.6 | 0 | 68.18 | MDH4F03CV | 22 | Vert. corr. | MDH4F03V
14.6 | 0 | 68.18 | IPM4F03C | 23 | BPM (4chan) | IPM4F03
14.6 | 0 | 70.4896 | MQX4F03DS | 24 | Skew quad | MQX3F05S
14.6 | 0 | 71 | ICM4F03D | 25 | Current monitor | ICM4F03
14.6 | 0 | 71.2 | VBV4F03D | 26 | Vacuum valve | new |  | Y
14.6 | 0 | 71.4896 | MQX4F03ES | 27 | Skew quad | MQX3F06S
14.6 | 0 | 71.83 | MDB4F03EH | 28 | Hor. Corr. | MDB8F12H
14.6 | 0 | 71.83 | MDH4F03EV | 29 | Verti. Corr. | MDH8F12V
14.6 | 0 | 71.83 | IPM4F03E | 30 | BPM (new) | IPM8F12
14.6 | 0 | 72.1896 | MQX4F04 | 31 | Normal quad | MQX4F04
14.6 | 0 | 72.52 | VIP4F04 | 32 | Ion pump | VIP4F05
14.6 | 0 | 72.52 | VPG4F04 | 33 | Pirani gauge | new
14.6 | 0 | 72.52 | VRV4F04 | 34 | Roughing valve | VRV4F06 |  | Change label in MPS
14.6 | 0 | 72.9896 | MQX4F05 | 35 | Normal quad | MQX8F12 | moved from 8F
14.6 | 0 | 73.54 | ILM4F04 | 36 | Beam loss monitor | ILM4F05 | relabel?
14.6 | 0 | 73.7896 | MQX4F06 | 37 | Normal quad | MQX4F06
14.6 | 0 | 74.4 | ITV4F06 | 38 | Viewer | new | HDR viewer | Y(moved from ITV4F06) new input for wire
14.6 | 0 | 74.4 | VIP4F06 | 39 | Viewer | new | Use old VIP4F06 channel, off during target operation. Mounted opposite last upstream turbo?
14.6 | 0 | 74.7 | MDB4F06H | 40 | Hor. Corr. | new
14.6 | 0 | 74.7 | MDH4F06V | 41 | Vert. corr. | new
14.6 | 0 | 74.7 | IPM4F06 | 42 | BPM (SEE) | new | Take buttons from Arc 2
14.6 | 0 | 75.8646 | MSS4F06 | 43 | Detector solenoid | new | MIT detector solenoid | Y
14.6 | 0 | 76.5 | ITV4F06A | 44 | Viewer | new |  | Y(moved from ITV4F06A)
14.6 | 0 | 76.5 | ILM4F06A | 45 | Beam loss monitor | ILM4F06A
14.6 | 0 | 76.5 | MDB4F06AH | 46 | Hor. Corr. | new | use trim for old MDB4F06AH
14.6 | 0 | 76.5 | MDH4F06AV | 47 | Vert. corr. | new | use trim for old MDH4F06AV
14.6 | 0 | 76.4 | IPM4F06A | 48 | BPM (SEE) | new | Take buttons from Arc 2
14.6 | 0 | 76.4 | VIP4F06A | 49 | ion pump | VIP4F06A | Shut off during target operation. Mounted on tee on ITV4F06A?
14.6 | 0 | 78.5546 | MQX4F07 | 50 | Normal quad | MQX4F07
14.6 | 0 | 79.19 | MDB4F07H | 51 | Hor. Corr. | MDB4F07H
14.6 | 0 | 79.19 | MDH4F07V | 52 | Vert. corr. | MDH4F07V
14.6 | 0 | 79.19 | IPM4F07 | 53 | BPM(new) | IPM4F07
14.6 | 0 | 79.4 | ILM4F07 | 54 | beam | ILM4F07
14.6 | 0 | 79.5546 | MQX4F08 | 55 | Normal quad | MQX4F08
14.6 | 0 | 79.88 | ITV4F08 | 56 | Viewer (with hole) | ITV4F07
14.6 | 0 | 79.88 | VIP4F08 | 57 | ion pump | VIP4F08
14.6 | 0 | 72.52 | VPG4F08 | 58 | Pirani gauge | VPG8F13
14.6 | 0 | 72.52 | VRV4F08 | 59 | Roughing valve | VRV8F13 |  | Change label in MPS
14.6 | 0 | 80.5546 | MQX4F09 | 60 | Normal quad | MQX4F09
14.6 | 0 | 80.9 | VIP4F09 | 61 | ion pump | VIP8F13 | Use old VIP4F08A channel
14.6 | 0 | 81.2596 | MQX4F09AS | 62 | Skew quad | MQX8F13 | Use 8F13 girder with quad rotation?
14.6 | 0 | 81.94 | MDB4F09AH | 63 | Hor. Corr. | MDB8F13H
14.6 | 0 | 81.94 | MDH4F09AV | 64 | Vert. corr. | MDH8F13V
14.6 | 0 | 81.94 | IPM4F09A | 65 | BPM (new) | IPM8F13 | supported by MQX4F09AS girder
14.6 | 0 | 82.2596 | MQX4F09BS | 66 | Skew quad | MQX3F07S
14.6 | 0 | 82.76 | VBV4F09B | 67 | Vacuum valve | VBV4F09
14.6 | 0 | 83.2596 | MQX4F09CS | 68 | Skew quad | MQX3F08S
14.6 | 0 | 83.93 | ITV4F09C | 69 | Viewer | ITV4F09 | Use 8F10 girder, have to flip the stand.
14.6 | 0 | 83.93 | VIP4F09C | 70 | ion pump | VIP4F09 | Use 8F10 girder
14.6 | 0 | 84.2596 | MQX4F09DS | 71 | Skew quad | MQX8F10 | Use 8F10 girder
14.6 | 0 | 84.62 | MDB4F09DH | 72 | Hor. Corr. | MDB4F07H
14.6 | 0 | 84.62 | MDH4F09DV | 73 | Vert. corr. | MDH4F07V
14.6 | 0 | 84.62 | IPM4F09D | 74 | BPM(new) | IPM8F10
14.6 | 0 | 86.7 | ILM4F09D | 75 | Beam loss monitor | ILM4F10
14.6 | 0 | 85.2596 | MQX4F09ES | 76 | Skew quad | MQX3F09S
14.6 | 0 | 85.9646 | MQX4F10 | 77 | Normal quad | MQX4F10
14.6 | 0 | 86.9646 | MQX4F11 | 78 | Normal quad | MQX4F11
14.6 | 0 | 87.32 | VIP4F11 | 79 | ion pump | VIP4F11
14.6 | 0 | 87.32 | VPG4F11 | 80 | Pirani gauge | VPG4F11
14.6 | 0 | 87.32 | VRV4F11 | 81 | Roughing valve | VRV4F11
14.6 | 0 | 87.9646 | MQX4F12 | 82 | Normal quad | MQX4F12
14.6 | 0 | 89 | MDB4F12H | 83 | Hor. Corr. | MDB4F12H
14.6 | 0 | 89 | MDH4F12V | 84 | Vert. corr. | MDH4F12V
14.6 | 0 | 89 | IPM4F12 | 85 | BPM (4chan) | IPM4F12
14.6 | 0 | 89 | ITV4F12 | 86 | Viewer | ITV4F12
14.6 | 0 | 89 | VIP4F12 | 87 | ion pump | VIP4F12
14.6 | 0 | 89.5 | ILM4F12 | 88 | Beam loss monitor | ILM4F12
14.6 | 0 | 90 | VBV4F12 | 89 | Beamline valve | VBV4F12

## nomenclatureRevA
X | Y | Z | Nomenclature |  | Description | Old Nomenclature | Comments | New MPS input
14.6 | 0 | 64.25 | MDB4F00AH | 1 | Hor. Corr. | MDB4F00AH
14.6 | 0 | 64.25 | MDH4F00AV | 2 | Vert. corr. | MDH4F00AV
14.6 | 0 | 64.25 | IPM4F00A | 3 | BPM (SEE) | IPM4F00A
14.6 | 0 | 64.49 | ITV4F00A | 4 | Viewer | ITV4F00A
14.6 | 0 | 64.49 | VIP4F00C | 5 | Ion pump | VIP4F00C
14.6 | 0 | 64.8 | ILM4F00A | 6 | BLM head | ILM4F00A | BLMs in LED?
14.6 | 0 | 65.1896 | MQX4F01 | 7 | Normal quad | MQX4F01
14.6 | 0 | 65.9896 | MQX4F02 | 8 | Normal quad | MQX4F02
14.6 | 0 | 66.7896 | MQX4F03 | 9 | Normal quad | MQX4F03
14.6 | 0 | 67.4896 | MQX4F03AS | 10 | Skew quad | MQX3F03S | Moved from 3F line
14.6 | 0 | 67.8 | ILM4F03A | 11 | BLM HEAD | ILM4F03
14.6 | 0 | 69 | IEO4F03A | 16 | Electro-optic cell | new | Use ring resonator support stand. Align horiz to <3 mm precision | Y, Mode 2 when off outer limit
14.6 | 0 | 68 | MDB4F03AH | 12 | Hor. Corr. | MDB8F11H | Fed from UV rack?
14.6 | 0 | 68 | MDH4F03AV | 13 | Vert. Corr. | MDH8F11V | Fed from UV rack?
14.6 | 0 | 68 | IPM4F03A | 14 | BPM (new) | IPM8F11 | Have to verify that it fits
14.6 | 0 | 68.4896 | MQX4F03BS | 15 | Skew quad | MQX3F04S | Moved from 3F line
14.6 | 0 | 69.4896 | MQX4F03CS | 17 | Skew quad | MQX4F05 | Modified to rotate quad. Uses Happek viewer assembly.
14.6 | 0 | 67.82 | ITV4F03C | 18 | Viewer | ITV4F03 | Happek viewer moved from 4F03 girder to 4F05 girder
14.6 | 0 | 67.82 | VIP4F03C | 19 | Ion pump | VIP4F03 | moved with Happek viewer
14.6 | 0 | 67.82 | VPG4F03C | 20 | Pirani gauge | VPG4F03 | same | Y, now interlocked to valve
14.6 | 0 | 68.18 | MDB4F03CH | 21 | Hor. Corr. | MDB4F03H | same
14.6 | 0 | 68.18 | MDH4F03CV | 22 | Vert. corr. | MDH4F03V | same
14.6 | 0 | 68.18 | IPM4F03C | 23 | BPM (4chan) | IPM4F03
14.6 | 0 | 70.4896 | MQX4F03DS | 24 | Skew quad | MQX3F05S | Moved from 3F line
14.6 | 0 | 71 | ICM4F03D | 25 | Current monitor | ICM4F03 | Use beamline support stands from ring resonator
14.6 | 0 | 71.2 | VBV4F03D | 26 | Vacuum valve | new |  | Y
14.6 | 0 | 71.4896 | MQX4F03ES | 27 | Skew quad | MQX3F06S | Moved from 3F line
14.6 | 0 | 71.83 | MDB4F03EH | 28 | Hor. Corr. | MDB8F12H
14.6 | 0 | 71.83 | MDH4F03EV | 29 | Verti. Corr. | MDH8F12V
14.6 | 0 | 71.83 | IPM4F03E | 30 | BPM (new) | IPM8F12
14.6 | 0 | 72.1896 | MQX4F04 | 31 | Normal quad | MQX4F04
14.6 | 0 | 72.52 | VIP4F04 | 32 | Ion pump | VIP4F05 | Mounted on Turbopump chamber
14.6 | 0 | 72.52 | VPG4F04 | 33 | Pirani gauge | new |  | Y, interlocked to VBV4F03D
14.6 | 0 | 72.52 | VRV4F04 | 34 | Roughing valve | VRV4F06
14.6 | 0 | 72.9896 | MQX4F05 | 35 | Normal quad | MQX8F12 | girder and quad moved from 8F
14.6 | 0 | 73.54 | ILM4F04 | 36 | Beam loss monitor | ILM4F05 | relabel?
14.6 | 0 | 73.7896 | MQX4F06 | 37 | Normal quad | MQX4F06 |  | Y (moved from ITV4F06) new input for Harp
14.6 | 0 | 74.4 | ITV4F06 | 38 | Viewer | new | HDR viewer
14.6 | 0 | 74.4 | VIP4F06 | 39 | Viewer | new | Use old VIP4F06 channel, off during target operation. Mounted opposite last upstream turbo?
14.6 | 0 | 74.7 | MDB4F06H | 40 | Hor. Corr. | new
14.6 | 0 | 74.7 | MDH4F06V | 41 | Vert. corr. | new
14.6 | 0 | 74.7 | IPM4F06 | 42 | BPM (SEE) | new | Take buttons from Arc 2
14.6 | 0 | 75.8646 | MSS4F06 | 43 | Detector solenoid | new | MIT detector solenoid | Y for both magnet and target OK.
14.6 | 0 | 76.5 | ITV4F06A | 44 | Viewer | new |  | Y(moved from ITV4F06A)
14.6 | 0 | 76.5 | ILM4F06A | 45 | Beam loss monitor | ILM4F06A
14.6 | 0 | 76.5 | MDB4F06AH | 46 | Hor. Corr. | new | use trim channel for old MDB4F06AH
14.6 | 0 | 76.5 | MDH4F06AV | 47 | Vert. corr. | new | use trim channel for old MDH4F06AV
14.6 | 0 | 76.4 | IPM4F06A | 48 | BPM (SEE) | new | Take buttons from Arc 2
14.6 | 0 | 76.4 | VIP4F06A | 49 | ion pump | VIP4F06A | Shut off during target operation. Mounted on tee on ITV4F06A?
14.6 | 0 | 78.5546 | MQX4F07 | 50 | Normal quad | MQX4F07
14.6 | 0 | 79.19 | MDB4F07H | 51 | Hor. Corr. | MDB4F07H | Need to see if it fits
14.6 | 0 | 79.19 | MDH4F07V | 52 | Vert. corr. | MDH4F07V | Need to see if it fits
14.6 | 0 | 79.19 | IPM4F07 | 53 | BPM(new) | IPM4F07 | Need to see if it fits
14.6 | 0 | 79.4 | ILM4F07 | 54 | Beam loss monitor | ILM4F07
14.6 | 0 | 79.5546 | MQX4F08 | 55 | Normal quad | MQX4F08
14.6 | 0 | 79.88 | ITV4F08 | 56 | Viewer (with hole) | ITV4F07 | Change label? | Change label in MPS
14.6 | 0 | 79.88 | VIP4F08 | 57 | ion pump | VIP4F08
14.6 | 0 | 72.52 | VPG4F08 | 58 | Pirani gauge | VPG8F13
14.6 | 0 | 72.52 | VRV4F08 | 59 | Roughing valve | VRV8F13
14.6 | 0 | 80.5546 | MQX4F09 | 60 | Normal quad | MQX4F09
14.6 | 0 | 80.9 | VIP4F09 | 61 | ion pump | VIP8F13 | Use old VIP4F08A channel
14.6 | 0 | 81.2596 | MQX4F09AS | 62 | Skew quad | new | Use 8F12 stand, 8F13 quad, and new T-plate
14.6 | 0 | 81.94 | MDB4F09AH | 63 | Hor. Corr. | MDB8F13H | Use beamline support stands from ring resonator
14.6 | 0 | 81.94 | MDH4F09AV | 64 | Vert. corr. | MDH8F13V | same
14.6 | 0 | 81.94 | IPM4F09A | 65 | BPM (new) | IPM8F13 | same
14.6 | 0 | 82.2596 | MQX4F09BS | 66 | Skew quad | MQX3F07S | Moved from 3F line
14.6 | 0 | 82.76 | VBV4F09B | 67 | Vacuum valve | VBV4F09 |  | Now interlocked to convectron gauges.
14.6 | 0 | 83.2596 | MQX4F09CS | 68 | Skew quad | MQX3F08S | Moved from 3F line
14.6 | 0 | 83.93 | ITV4F09C | 69 | Viewer | ITV4F09 | Use 8F10 girder, have to flip the stand.
14.6 | 0 | 83.93 | VIP4F09C | 70 | ion pump | VIP4F09 | Use 8F10 girder
14.6 | 0 | 84.2596 | MQX4F09DS | 71 | Skew quad | MQX8F10 | Use 8F10 girder
14.6 | 0 | 84.62 | MDB4F09DH | 72 | Hor. Corr. | MDB4F09H | Can either use 8F10 corrector or 4F09 corrector
14.6 | 0 | 84.62 | MDH4F09DV | 73 | Vert. corr. | MDH4F09V | same
14.6 | 0 | 84.62 | IPM4F09D | 74 | BPM(new) | IPM8F10
14.6 | 0 | 86.7 | ILM4F09D | 75 | Beam loss monitor | ILM4F10
14.6 | 0 | 85.2596 | MQX4F09ES | 76 | Skew quad | MQX3F09S | Moved from 3F line
14.6 | 0 | 85.9646 | MQX4F10 | 77 | Normal quad | MQX4F10
14.6 | 0 | 86.9646 | MQX4F11 | 78 | Normal quad | MQX4F11
14.6 | 0 | 87.32 | VIP4F11 | 79 | ion pump | VIP4F11
14.6 | 0 | 87.32 | VPG4F11 | 80 | Pirani gauge | VPG4F11
14.6 | 0 | 87.32 | VRV4F11 | 81 | Roughing valve | VRV4F11
14.6 | 0 | 87.9646 | MQX4F12 | 82 | Normal quad | MQX4F12
14.6 | 0 | 89 | MDB4F12H | 83 | Hor. Corr. | MDB4F12H
14.6 | 0 | 89 | MDH4F12V | 84 | Vert. corr. | MDH4F12V
14.6 | 0 | 89 | IPM4F12 | 85 | BPM (4chan) | IPM4F12
14.6 | 0 | 89 | ITV4F12 | 86 | Viewer | ITV4F12
14.6 | 0 | 89 | VIP4F12 | 87 | ion pump | VIP4F12
14.6 | 0 | 89.5 | ILM4F12 | 88 | Beam loss monitor | ILM4F12
14.6 | 0 | 90 | VBV4F12 | 89 | Beamline valve | VBV4F12

## nomenclatureRevD
X | Y | Z | Nomenclature |  | Description | Old Nomenclature | Comments | New MPS input | Item exists
14.6 | 0 | 64.25 | MDB4F00AH | 1 | Hor. Corr. | MDB4F00AH |  |  | Y
14.6 | 0 | 64.25 | MDH4F00AV | 2 | Vert. corr. | MDH4F00AV |  |  | Y
14.6 | 0 | 64.25 | IPM4F00A | 3 | BPM (SEE) | IPM4F00A |  |  | Y
14.6 | 0 | 64.49 | ITV4F00A | 4 | Viewer | ITV4F00A |  |  | Y
14.6 | 0 | 64.49 | VIP4F00C | 5 | Ion pump | VIP4F00C |  |  | Y
14.6 | 0 | 64.8 | ILM4F00A | 6 | BLM head | ILM4F00A |  |  | Y
14.6 | 0 | 65.1896 | MQX4F01 | 7 | Normal quad | MQX4F01 |  |  | Y
14.6 | 0 | 65.9896 | MQX4F02 | 8 | Normal quad | MQX4F02 |  |  | Y
14.6 | 0 | 66.7896 | MQX4F03 | 9 | Normal quad | MQX4F03 |  |  | Y
14.6 | 0 | 67.4896 | MQX4F03AS | 10 | Skew quad | MQX3F03S | Moved from 3F line |  | Y
14.6 | 0 | 67.8 | ILM4F03A | 11 | BLM HEAD | ILM4F03 |  |  | Y
14.6 | 0 | 68 | MDB4F03AH | 12 | Hor. Corr. | MDB8F11H |  |  | Y
14.6 | 0 | 68 | MDH4F03AV | 13 | Vert. Corr. | MDH8F11V |  |  | Y
14.6 | 0 | 68 | IPM4F03A | 14 | BPM (new) | IPM8F11 | Support using ring resonator floor stands upstream of BPM |  | Y
14.6 | 0 | 68.4896 | MQX4F03BS | 15 | Skew quad | MQX3F04S | Moved from 3F line |  | Y
14.6 | 0 | 69 | IEO4F03B | 16 | Electro-optic cell | new | Use ring resonator support stand. Align horiz to <3 mm precision | Y, Mode 2 when off outer limit | Y
14.6 | 0 | 69.4896 | MQX4F03CS | 17 | Skew quad | MQX4F05 | Modified to rotate quad. Mounted on 4F05 girder along with Happek viewer assembly |  | Y
14.6 | 0 | 69.82 | ITV4F03C | 18 | Viewer | ITV4F03 | Happek viewer moved from 4F03 girder to 4F05 girder |  | Y
14.6 | 0 | 69.82 | VIP4F03C | 19 | Ion pump | VIP4F03 | moved with Happek viewer |  | Y
14.6 | 0 | 69.82 | VPG4F03C | 20 | Pirani gauge | VPG4F03 | Interlocked to valve VBV4F03D | Y, now interlocked to valve | Y
14.6 | 0 | 70.08 | MDB4F03CH | 21 | Hor. Corr. | MDB4F03H | Moved from 4F03 girder |  | ?
14.6 | 0 | 70.08 | MDH4F03CV | 22 | Vert. corr. | MDH4F03V | same |  | ?
14.6 | 0 | 70.08 | IPM4F03C | 23 | BPM (4chan) | IPM4F03 | same |  | ?
14.6 | 0 | 70.4896 | MQX4F03DS | 24 | Skew quad | MQX3F05S | Moved from 3F line |  | Y
14.6 | 0 | 70.95 | ICM4F03D | 25 | Current monitor | ICM4F03 | Use beamline support stands from ring resonator |  | Y
14.6 | 0 | 71.1 | VBV4F03D | 26 | Vacuum valve | new | complete valve rebuild | Y | Y
14.6 | 0 | 71.4896 | MQX4F03ES | 27 | Skew quad | MQX3F06S | Moved from 3F line |  | Y
14.6 | 0 | 71.82 | MDB4F03EH | 28 | Hor. Corr. | MDB8F12H | Moved from 8F line |  | Y
14.6 | 0 | 71.82 | MDH4F03EV | 29 | Verti. Corr. | MDH8F12V | same |  | Y
14.6 | 0 | 71.82 | IPM4F03E | 30 | BPM (new) | IPM8F12 | same |  | Y
14.6 | 0 | 72.1896 | MQX4F04 | 31 | Normal quad | MQX4F04 |  |  | Y
14.6 | 0 | 72.57 | VBP4F04 | 32 | Pirani gauge | new | This is an inficon gauge with inficon controller mounted below the first turbopump. Will be near solenoid in July run. | Y, interlocked to VBV4F03D | ?
14.6 | 0 | 72.57 | VRV4F04 | 33 | Roughing valve | VRV4F06 |  |  | ?
14.6 | 0 | 72.9896 | MQX4F05 | 34 | Normal quad | MQX8F12 | girder and quad moved from 8F |  | Y
14.6 | 0 | 73.54 | ILM4F05 | 35 | Beam loss monitor | ILM4F05 |  |  | Y
14.6 | 0 | 73.7896 | MQX4F06 | 36 | Normal quad | MQX4F06 |  |  | Y
14.6 | 0 | 74.195 | ITV4F06 | 37 | Viewer | new | LDR viewer | Y (moved from ITV4F06) new input for Harp? | Need camera hardware
14.6 | 0 | 74.5 | MDB4F06H | 38 | Hor. Corr. | MDB4F06H |  |  | Y
14.6 | 0 | 74.5 | MDH4F06V | 39 | Vert. corr. | MDH4F06V |  |  | Y
14.6 | 0 | 74.5 | IPM4F06 | 40 | BPM (SEE) | IPM8F13 | Use 9 inch stripline BPM can. |  | Y
14.6 | 0 | 75.8646 | MFF4F06 | 41 | Detector solenoid | new | MIT detector solenoid | Y for both magnet and target OK. | Y but no power supply
14.6 | 0 | 76.5 | ILM4F06A | 42 | Beam loss monitor | ILM4F06A |  |  | Y
14.6 | 0 | 76.62 | MDB4F06AH | 43 | Hor. Corr. | new | use trim channel for old MDB4F06AH. Wrapped around 6 inch pipe just downstream of solenoid |  | Have to see if Haimson style corrector coil fits
14.6 | 0 | 76.62 | MDH4F06AV | 44 | Vert. corr. | new | use trim channel for old MDH4F06AV
14.6 | 0 | 76.92 | ITV4F06A | 45 | Viewer | new | Must come up with design for viewer | Y(moved from ITV4F06A) | N
14.6 | 0 | 77.96 | IPM4F06A | 46 | BPM (SEE) | new | Use wire BPM |  | Y have to check funciontality
14.6 | 0 | 78.5546 | MQX4F07 | 47 | Normal quad | MQX4F07 |  |  | Y
14.6 | 0 | 78.96 | VBP4F07 | 48 | Pirani gauge | new | Use inficon gauge mounted below turbo. Will initially be mounted on Moller chamber for July run. |  | ?
14.6 | 0 | 79.19 | MDB4F07H | 49 | Hor. Corr. | MDB4F07H |  |  | Y
14.6 | 0 | 79.19 | MDH4F07V | 50 | Vert. corr. | MDH4F07V |  |  | Y
14.6 | 0 | 79.19 | IPM4F07 | 51 | BPM(new) | IPM4F07 |  |  | Y
14.6 | 0 | 79.4 | ILM4F07 | 52 | Beam loss monitor | ILM4F07 |  |  | Y
14.6 | 0 | 79.5546 | MQX4F08 | 53 | Normal quad | MQX4F08 |  |  | Y
14.6 | 0 | 79.88 | ITV4F08 | 54 | Viewer (with hole) | ITV4F07 | Change label | Change label in MPS | Y
14.6 | 0 | 79.88 | VIP4F08 | 55 | ion pump | VIP4F08 | Not interlocked to valve |  | Y
14.6 | 0 | 80.5546 | MQX4F09 | 56 | Normal quad | MQX4F09 |  |  | Y
14.6 | 0 | 81.2596 | MQX4F09AS | 57 | Skew quad | new | Use 8F12 stand, 8F13 quad, and new T-plate |  | Y
14.6 | 0 | 81.78 | MDB4F09AH | 58 | Hor. Corr. | MDB4F09H | Use beamline support stands from ring resonator |  | Y
14.6 | 0 | 81.78 | MDH4F09AV | 59 | Vert. corr. | MDH4F09V | same |  | Y
14.6 | 0 | 81.78 | IPM4F09A | 60 | BPM (new) | IPM4F09 | same |  | Y
14.6 | 0 | 82.2596 | MQX4F09BS | 61 | Skew quad | MQX3F07S | Moved from 3F line |  | Y
14.6 | 0 | 82.76 | VBV4F09B | 62 | Vacuum valve | VBV4F09 | supported as before | Now interlocked to convectron gauges. | Y
14.6 | 0 | 83.2596 | MQX4F09CS | 63 | Skew quad | MQX3F08S | Moved from 3F line |  | Y
14.6 | 0 | 83.93 | ITV4F09C | 64 | Viewer | ITV8F10 | Use 8F10 girder, have to rotate the stand 180 degrees. |  | Y
14.6 | 0 | 83.93 | VIP4F09C | 65 | ion pump | VIP8F10 | Use 8F10 girder |  | Y
14.6 | 0 | 84.2596 | MQX4F09DS | 66 | Skew quad | MQX8F10 | Use 8F10 girder. Remount modified quad with spacer plate. |  | Y
14.6 | 0 | 84.59 | MDB4F09DH | 67 | Hor. Corr. | MDB4F09H | Can either use 8F10 corrector or 4F09 corrector |  | Y
14.6 | 0 | 84.59 | MDH4F09DV | 68 | Vert. corr. | MDH4F09V | same |  | Y
14.6 | 0 | 84.59 | IPM4F09D | 69 | BPM(new) | IPM8F10 |  |  | Y
14.6 | 0 | 85.2596 | MQX4F09ES | 70 | Skew quad | MQX3F09S | Moved from 3F line |  | Y
14.6 | 0 | 85.9646 | MQX4F10 | 71 | Normal quad | MQX4F10 |  |  | Y
14.6 | 0 | 86.7 | ILM4F09D | 72 | Beam loss monitor | ILM4F10 |  |  | Y
14.6 | 0 | 86.9646 | MQX4F11 | 73 | Normal quad | MQX4F11 |  |  | Y
14.6 | 0 | 87.3 | VIP4F11 | 74 | ion pump | VIP4F11 |  |  | Y
14.6 | 0 | 87.3 | VPG4F11 | 75 | Pirani gauge | VPG4F11 | Interlocked to valve VBV4F09B |  | Y
14.6 | 0 | 87.3 | VRV4F11 | 76 | Roughing valve | VRV4F11 |  |  | Y
14.6 | 0 | 87.9646 | MQX4F12 | 77 | Normal quad | MQX4F12 |  |  | Y
14.6 | 0 | 89 | MDB4F12H | 78 | Hor. Corr. | MDB4F12H |  |  | Y
14.6 | 0 | 89 | MDH4F12V | 79 | Vert. corr. | MDH4F12V |  |  | Y
14.6 | 0 | 89 | IPM4F12 | 80 | BPM (4chan) | IPM4F12 |  |  | Y
14.6 | 0 | 89 | ITV4F12 | 81 | Viewer | ITV4F12 |  |  | Y
14.6 | 0 | 89 | VIP4F12 | 82 | ion pump | VIP4F12 |  |  | Y
14.6 | 0 | 89.5 | ILM4F12 | 83 | Beam loss monitor | ILM4F12 |  |  | Y
14.6 | 0 | 90 | VBV4F12 | 84 | Beamline valve | VBV4F12 |  |  | Y