## Sheet1
Task Name | Beam Test Plan URL | Procedure to be amended and Annotated | Duration |  | LSOS | CASA | Day
FEL Startup Proc | http://opsweb.acc.jlab.org/CSUEApps/atlis/task/ | FEL Startup Plan | 0.5 | shift | Benson |  | Saturday
Thread beam to 0F06, set charge per bunch | http://opsweb.acc.jlab.org/CSUEApps/atlis/task/ | Set bunch charge using BCM | 1 | shift | Benson |  | Saturday
Center beam in solenoids | http://opsweb.acc.jlab.org/CSUEApps/atlis/task/ | Injector Setup Procedure | 0.5 | shift | Tennant |  | Saturday
Center in buncher and set zero crossing | http://opsweb.acc.jlab.org/CSUEApps/atlis/task/ | Injector Setup Procedure | 0.5 | shift | Carlos |  | Sunday
Contingency | Contingency |  | 1 | shift |  |  | Sunday
Rough Phase linacs | http://opsweb.acc.jlab.org/CSUEApps/atlis/task/ | RF Cavity Transient Phasing Procedure | 0.5 | shift | Powers |  | Sunday
Thread beam to Arc 1 | In Progress | In Progress | 1 | shift | Douglas |  | Monday
Run Injector Phasing Script Procedure | http://opsweb.acc.jlab.org/CSUEApps/atlis/task/ | Injector Phasing script | 1 | shift | Benson |  | Monday
Set linac gradients and Phase | http://opsweb.acc.jlab.org/CSUEApps/atlis/task/ | Acc School | 0.5 | shift | Douglas |  | Tuesday
Set 0F & 1F quads | http://opsweb.acc.jlab.org/CSUEApps/atlis/task/ | Match through linac | 0.5 | shift | Douglas |  | Tuesday
Center in 2F quads | http://opsweb.acc.jlab.org/CSUEApps/atlis/task/ | BPM Quad centering Procedure | 0.5 | shift | Tennant |  | Tuesday
MiniPhase | http://opsweb.acc.jlab.org/CSUEApps/atlis/task/ | Miniphase | 0.5 | shift | Tennant |  | Tuesday
Transport to 5F08 check diags & quads | http://opsweb.acc.jlab.org/CSUEApps/atlis/task/ | BPM Quad centering Procedure | 0.5 | shift |  |  | Wednesdy
Thread through Arc 2 | In Progress | Arc 2 steering | 0 | shift |  |  | Sunday
Set MPATH for energy recovery | http://opsweb.acc.jlab.org/CSUEApps/atlis/task/ | TBD | 0.25 | shift |  |  | Sunday
Thread to 1 G dump | http://opsweb.acc.jlab.org/CSUEApps/atlis/task/ | TBD | 0.5 | shift |  |  | Sunday
Diagnostic check out | http://opsweb.acc.jlab.org/CSUEApps/atlis/task/ | Diag checkout | 1 | shift |  |  | Monday
MiniPhase | http://opsweb.acc.jlab.org/CSUEApps/atlis/task/ | Miniphase | 0.25 | shift |  |  | Tuesday
Check out BLM voltages | http://opsweb.acc.jlab.org/CSUEApps/atlis/task/ | BLM Calibration | 1 | shift |  |  | Tuesday
MiniPhase | http://opsweb.acc.jlab.org/CSUEApps/atlis/task/ | Miniphase | 0.25 | shift |  |  | Wednesday
Check out BLMs, map dump BLM to control room | http://opsweb.acc.jlab.org/CSUEApps/atlis/task/ | MPS Checkout | 0.25 | shift |  |  | Wednesday
Clean up orbit and check optics | In Progress | Steer/focus away from any loss/ check diff orbits | 1 | shift |  |  | Wednesday
Miniphase | http://opsweb.acc.jlab.org/CSUEApps/atlis/task/ | Miniphase | 0.25 | shift |  |  | Thursday
Try CW | http://opsweb.acc.jlab.org/CSUEApps/atlis/task/ | Go CW from Pulsed beam | 1 | shift |  |  | Thursday
Contingency | Contingency |  | 0.5 | shift |  |  | Thursday
| Contingency |  | 1.5 | shift |  |  | Friday
|  | TOTAL | 16.25 | Shifts