## Nomenclature with comments
X | Y | Z | Nomenclature |  | Description | Old Nomenclature | Comments | New MPS input | Item exists | Changed from last version
14.6 | 0 | 64.25 | MDB4F00AH | 1 | Hor. Corr. | MDB4F00AH |  |  | Y
14.6 | 0 | 64.25 | MDJ4F00AV | 2 | Vert. corr. | MDH4F00AV |  |  | Y | Changed from DH to DJ
14.6 | 0 | 64.25 | IPM4F00A | 3 | BPM (SEE) | IPM4F00A |  |  | Y
14.6 | 0 | 64.49 | ITV4F00A | 4 | Viewer | ITV4F00A |  |  | Y
14.6 | 0 | 64.49 | VIP4F00C | 5 | Ion pump | VIP4F00C |  |  | Y
14.6 | 0 | 64.8 | ILM4F00A | 6 | BLM head | ILM4F00A |  |  | Y
14.6 | 0 | 65.1896 | MQX4F01 | 7 | Normal quad | MQX4F01 |  |  | Y
14.6 | 0 | 65.9896 | MQX4F02 | 8 | Normal quad | MQX4F02 |  |  | Y
14.6 | 0 | 66.7896 | MQX4F03 | 9 | Normal quad | MQX4F03 |  |  | Y
14.6 | 0 | 67.4896 | MQX4F03AS | 10 | Skew quad | MQX3F03S | Moved from 3F line |  | Y
14.6 | 0 | 67.8 | ILM4F03A | 11 | BLM HEAD | ILM4F03 |  |  | Y
14.6 | 0 | 68 | MDB4F03AH | 12 | Hor. Corr. | MDB8F11H |  |  | Y
14.6 | 0 | 68 | MDJ4F03AV | 13 | Vert. Corr. | MDH8F11V |  |  | Y | Changed from DH to DJ
14.6 | 0 | 68 | IPM4F03A | 14 | BPM (new) | IPM8F11 | Support using ring resonator floor stands upstream of BPM |  | Y
14.6 | 0 | 68.4896 | MQX4F03BS | 15 | Skew quad | MQX3F04S | Moved from 3F line |  | Y
14.6 | 0 | 69 | IEO4F03B | 16 | Electro-optic cell | new | Use ring resonator support stand. Align horiz to <3 mm precision | Y, Mode 2 when off outer limit. Beam shield in series with motor. | Y | Added beam shield to MPS needs
14.6 | 0 | 69.4896 | MQX4F03CS | 17 | Skew quad | MQX4F05 | Modified to rotate quad. Mounted on 4F05 girder along with Happek viewer assembly |  | Y
14.6 | 0 | 69.82 | ITV4F03C | 18 | Viewer | ITV4F03 | Happek viewer moved from 4F03 girder to 4F05 girder |  | Y
14.6 | 0 | 69.82 | VIP4F03C | 19 | Ion pump | VIP4F03 | relabeled |  | Y | change comment
14.6 | 0 | 69.82 | VPG4F03C | 20 | Pirani gauge | VPG4F03 | Interlocked to valve VBV4F03D | Y, now interlocked to valve | Y
14.6 | 0 | 70.08 | MDB4F03CH | 21 | Hor. Corr. | MDB4F03H | Moved from 4F03 girder |  | ?
14.6 | 0 | 70.08 | MDJ4F03CV | 22 | Vert. corr. | MDH4F03V | same |  | ? | Changed from DH to DJ
14.6 | 0 | 70.08 | IPM4F03C | 23 | BPM (4chan) | IPM4F03 | same |  | ?
14.6 | 0 | 70.4896 | MQX4F03DS | 24 | Skew quad | MQX3F05S | Moved from 3F line |  | Y
14.6 | 0 | 70.95 | ICM4F03D | 25 | Current monitor | ICM4F03 | Use beamline support stands from ring resonator |  | Y
14.6 | 0 | 71.1 | VBV4F03D | 26 | Vacuum valve | new | complete valve rebuild | Y | Y
14.6 | 0 | 71.4896 | MQX4F03ES | 27 | Skew quad | MQX3F06S | Moved from 3F line |  | Y
14.6 | 0 | 71.82 | MDB4F03EH | 28 | Hor. Corr. | MDB8F12H | Moved from 8F line |  | Y
14.6 | 0 | 71.82 | MDJ4F03EV | 29 | Verti. Corr. | MDH8F12V | same |  | Y | Changed from DH to DJ
14.6 | 0 | 71.82 | IPM4F03E | 30 | BPM (new) | IPM8F12 | same |  | Y
14.6 | 0 | 72.1896 | MQX4F04 | 31 | Normal quad | MQX4F04 |  |  | Y
End of Sub 2 region
14.6 | 0 | 72.57 | VBP4F04 | 32 | Pirani gauge | new | This is an inficon gauge with inficon controller mounted below the first turbopump. Will be near solenoid in July run. | Y, interlocked to VBV4F03D | at MIT
14.6 | 0 | 72.57 | VRV4F04 | 33 | Roughing valve | VRV4F06
14.6 | 0 | 72.9896 | MQX4F05 | 34 | Normal quad | MQX8F12 | girder and quad moved from 8F |  | Y
14.6 | 0 | 73.54 | ILM4F05 | 35 | Beam loss monitor | ILM4F05 |  |  | Y
14.6 | 0 | 73.7896 | MQX4F06 | 36 | Normal quad | MQX4F06 |  |  | Y
14.6 | 0 | 74.195 | ITV4F06 | 37 | Viewer | new | LDR viewer. Uses two viewer channels to get three positions | Y (moved from ITV4F06) new input for Harp | Need camera hardware
14.6 | 0 | 74.5 | MAT4F06H | 38 | Hor. Corr. | MDB4F06H | changed coils to VTs from DB and DH |  |  | changed coils and nomenclature
14.6 | 0 | 74.5 | MAT4F06V | 39 | Vert. corr. | MDH4F06V | same |  |  | same
14.6 | 0 | 74.5 | IPM4F06 | 40 | BPM (SEE) | IPM8F13 | Use 9 inch stripline BPM can.
14.6 | 0 | 75.8646 | MFF4F06 | 41 | Detector solenoid | new | MIT detector solenoid | Y for both magnet and target OK.
14.6 | 0 | 76.5 | ILM4F06A | 42 | Beam loss monitor | ILM4F06A
14.6 | 0 | 76.62 | MMB4F06AH | 43 | Hor. Corr. | new | use trim channel for old MDB4F06AH. Used SQ coils on 6" pipe downstream of the solenoid |  |  | Use new nomenclature.
14.6 | 0 | 76.62 | MMB4F06AV | 44 | Vert. corr. | new | use trim channel for old MDH4F06AV |  |  | same
14.6 | 0 | 76.92 | ITV4F06A | 45 | Viewer | new | Must come up with design for viewer | Y(moved from ITV4F06A)
14.6 | 0 | 77.96 | xxx | 46 | BPM (SEE) |  | Deleted |  |  | IPM4F06A Merged with IPM4F07
14.6 | 0 | 78.5546 | MQX4F07 | 47 | Normal quad | MQX4F07
14.6 | 0 | 78.85 | MDB4F07H | 48 | Hor. Corr. | MDB4F07H
14.6 | 0 | 78.85 | MDJ4F07V | 49 | Vert. corr. | MDH4F07V |  |  |  | Changed from DH to DJ
14.6 | 0 | 78.85 | IPM4F07 | 50 | BPM(new) | IPM4F07
14.6 | 0 | 79.4 | ILM4F07 | 51 | Beam loss monitor | ILM4F07
14.6 | 0 | 78.96 | VBP4F07 | 52 | Pirani gauge | new | Use inficon gauge mounted below turbo. Will initially be mounted on Moller chamber for July run.
End of Sub 3 region
14.6 | 0 | 79.5546 | MQX4F08 | 53 | Normal quad | MQX4F08
14.6 | 0 | 79.88 | ITV4F08 | 54 | Viewer (with hole) | ITV4F07 | Change label | Change label in MPS
14.6 | 0 | 79.88 | VIP4F08 | 55 | ion pump | VIP4F08 | Not interlocked to valve
14.6 | 0 | 80.5546 | MQX4F09 | 56 | Normal quad | MQX4F09
14.6 | 0 | 81.2596 | MQX4F09AS | 57 | Skew quad | new | Use 8F12 stand, 8F13 quad, and new T-plate
14.6 | 0 | 81.78 | MDB4F09AH | 58 | Hor. Corr. | MDB4F09H | Use beamline support stands from ring resonator
14.6 | 0 | 81.78 | MDJ4F09AV | 59 | Vert. corr. | MDH4F09V | same |  |  | Changed from DH to DJ
14.6 | 0 | 81.78 | IPM4F09A | 60 | BPM (new) | IPM4F09 | same
14.6 | 0 | 82.2596 | MQX4F09BS | 61 | Skew quad | MQX3F07S | Moved from 3F line
14.6 | 0 | 82.76 | VBV4F09B | 62 | Vacuum valve | VBV4F09 | supported as before | Now interlocked to convectron gauges.
14.6 | 0 | 83.2596 | MQX4F09CS | 63 | Skew quad | MQX3F08S | Moved from 3F line
14.6 | 0 | 83.93 | ITV4F09C | 64 | Viewer | ITV8F10 | Use 8F10 girder, have to rotate the stand 180 degrees.
14.6 | 0 | 83.93 | VIP4F09C | 65 | ion pump | VIP8F10 | Use 8F10 girder
14.6 | 0 | 84.2596 | MQX4F09DS | 66 | Skew quad | MQX8F10 | Use 8F10 girder. Remount modified quad with spacer plate.
14.6 | 0 | 84.59 | MDB4F09DH | 67 | Hor. Corr. | MDB4F09H | Can either use 8F10 corrector or 4F09 corrector
14.6 | 0 | 84.59 | MDJ4F09DV | 68 | Vert. corr. | MDH4F09V | same |  |  | Changed from DH to DJ
14.6 | 0 | 84.59 | IPM4F09D | 69 | BPM(new) | IPM8F10
14.6 | 0 | 85.2596 | MQX4F09ES | 70 | Skew quad | MQX3F09S | Moved from 3F line
14.6 | 0 | 85.9646 | MQX4F10 | 71 | Normal quad | MQX4F10 |  |  | Y
14.6 | 0 | 86.7 | ILM4F09D | 72 | Beam loss monitor | ILM4F10 |  |  | Y
14.6 | 0 | 86.9646 | MQX4F11 | 73 | Normal quad | MQX4F11 |  |  | Y
14.6 | 0 | 87.3 | VIP4F11 | 74 | ion pump | VIP4F11 |  |  | Y
14.6 | 0 | 87.3 | VPG4F11 | 75 | Pirani gauge | VPG4F11 | Interlocked to valve VBV4F09B |  | Y
14.6 | 0 | 87.3 | VRV4F11 | 76 | Roughing valve | VRV4F11 |  |  | Y
14.6 | 0 | 87.9646 | MQX4F12 | 77 | Normal quad | MQX4F12 |  |  | Y
14.6 | 0 | 89 | MDB4F12H | 78 | Hor. Corr. | MDB4F12H |  |  | Y
14.6 | 0 | 89 | MDJ4F12V | 79 | Vert. corr. | MDH4F12V |  |  | Y | Changed from DH to DJ
14.6 | 0 | 89 | IPM4F12 | 80 | BPM (4chan) | IPM4F12 |  |  | Y
14.6 | 0 | 89 | ITV4F12 | 81 | Viewer | ITV4F12 |  |  | Y
14.6 | 0 | 89 | VIP4F12 | 82 | ion pump | VIP4F12 |  |  | Y
14.6 | 0 | 89.5 | ILM4F12 | 83 | Beam loss monitor | ILM4F12 |  |  | Y
14.6 | 0 | 90 | VBV4F12 | 84 | Beamline valve | VBV4F12 |  |  | Y

## Punch list
| Punch List Items (not a complete list) | POC | % Complete | Comments
CIS
| Replace Drive Laser Mechanical shutters | Zhang
| Repair or replace Radiation Monitor RADMONxCH6 | Garcia/Bullard
EESDCP
| Verify and repair GC magnet EPICS controls | Coleman |  | May be able to find working screen and use it
| HCO of new Magnet IOC | DCP |  | Part of HCO tasks
EESRFS
Nelson/Cooper
1 | Crowbar ready fix for Zone FL03
2 | Load in proper RF drive-high values |  |  | Drury should have starting values.
3 | RF power is high on cavity 4-2
4 | Find out why the 12V power supplies fail in zone 3 and 4?
EESSAF
T. Michaelides/ R. Araiza
1 | BM3 and BM6 keys are backwards; you should be able to remove the key after switching system into those modes to lock them in
2 | Change mode 6 truth table so that BLMs trip the beam but can be masked.
3 | Update ODH heads.
4 | Recertify PSS (done)
RadCon
1 | Fix W55 rad monitor | M. Washington
EESICS
O. Garza
1 | Install additional valve and channel in 4F | Kortze |  | Determine how many valves drops are necessary
2 | Get E-style BPMs working or replace with other technology | Francis/ Allison |  | We need to know where we are going with this.
4 | SEE BPMs triggering must come from time delay cards. | Francis
5 | FELScope Ext triggers were missing | Cole
6 | Regain remote control of oscilloscope | Cole |  | Need strategy for O'scope controls
7 | Current monitor readbacks in EPICS | Cole |  | Need details on signal inteffaces
8 | Viewers in 3F align, focus, and set gains | Dela Cruze/ Norris
9 | Replace damaged cameras as needed | Dela Cruze/ Norris
10 | Put 5F alignment laser in a more permanent fixture and align to 1F line |  |  | Have to remove viewer when using.
11 | Move IR Happek to IR controls (now partially on UV controls) |  |  | Use UV controls and relabel if possible
MSNST
1 | Fix noisy ion pumps (especially in the 5F region) | Kortze
OPSADM
1 | Console FEL05 requires a reboot to wake up after it goes to sleep
2 | Replace magnet IOC | G. Croke
3 | Update IOC controls
OPSSFT
2 | ADL monitor logs not working |  |  | Possibly due to hardware being off?
3 | Update turn-on procedure to include check of BLM HV |  |  | This may be just a procedural change. Need to see if the software has to be modified.
4 | Archive signals for many of the BPMs | Slominski/ Francis |  | This is done through Archive request channels.
5 | "All-valve" controls | S. Weatherspoon/ Kortze |  | Have to get hardware fixed first.
OPS
M. Joyce/ M. McCaughan
1 | Develop magnet screens |  |  | Derived mostly from LED
2 | Develop BPM screens |  |  | Derived from LED
3 | Develop BLM screens
4 | Update viewer screens |  |  | Update using McCaughan's ideas
5 | FSD screen |  |  | Derived from LED?
6 | Vacuum screens
7 | Get 5F08 beam stop working from viewer pages |  |  | Mike wants have a separate screen for this.
8 | Other ease of operation updates |  |  | Need to meet with Frierson, McCaughan, Freeman and Larrieu to determine task list.
9 | Bluecherry for video signals | B. Freeman
OPSHLA
M. Joyce/ B. Cade
1 | LED development and implementation |  |  | This is the highest priority.
2 | –Update phasing script to check for out-of-bounds magnet supply requests
3 | shutdown scripts crash because of missing / unresponsive elements
Hot Check Out
1 | CIS – Heat clean and condition cathode | M. Poelker/ C. Hernandez
2 | EESICS - Check zone 1 wiring for AMS
3 | EESRFS - Condition the zone 1 couplers
4 | EESRFS - Noisy RF control loops (have to reset the loop gains)
5 | EESICS - Check all timing signals (need documentation)
LERF Ops Procedures
S. Frierson/ Benson/ MIT
1 | SOP's
2 | TSOP's

## Simple nomenclature
Old Nomenclature | New Nomenclature
MDB4F00AH | same
MDH4F00AV | same
IPM4F00A | same
ITV4F00A | same
VIP4F00C | same
ILM4F00A | same
MQX4F01 | same
MQX4F02 | same
MQX4F03 | same
MQX3F03S | MQX4F03AS
ILM4F03 | same
MDB8F11H | MDB4F03AH
MDH8F11V | MDH4F03AV
IPM8F11 | IPM4F03A
MQX3F04S | MQX4F03BS
new | IEO4F03B | Mount 6 way 6" cross on ring resonator stand.
MQX4F05 | MQX4F03CS | Modified to rotate quad. Mounted on 4F05 girder along with Happek viewer assembly
ITV4F03 | ITV4F03C
VIP4F03 | VIP4F03C
VPG4F03 | VPG4F03C
MDB4F03H | MDB4F03CH
MDH4F03V | MDH4F03CV
IPM4F03 | IPM4F03C
MQX3F05S | MQX4F03DS
ICM4F03 | ICM4F03D
new | VBV4F03D
MQX3F06S | MQX4F03ES
MDB8F12H | MDB4F03EH
MDH8F12V | MDH4F03EV
IPM8F12 | IPM4F03E
MQX4F04 | same
new | VPG4F04 | This is an inficon gauge with inficon controller mounted below the first turbopump
VRV4F06 | VRV4F04
MQX8F12 | MQX4F05
ILM4F05 | ILM4F04
MQX4F06 | same
new | ITV4F06 | HDR viewer
new | MDB4F06H
new | MDH4F06V
new | IPM4F06
new | MFF4F06
new | MDB4F06AH
new | MDH4F06AV
new | ITV4F06A | Must come up with design.
ILM4F06A | ILM4F06A
new | IPM4F06A
MQX4F07 | same
MDB4F07H | same
MDH4F07V | same
IPM4F07 | same
ILM4F07 | same
new | VPG4F07
MQX4F08 | same
ITV4F07 | ITV4F08
VIP4F08 | VIP4F08
MQX4F09 | same
new | MQX4F09AS | Use 8F12 stand, 8F13 quad, and new T-plate
MDB8F13H | MDB4F09AH
MDH8F13V | MDH4F09AV
IPM8F13 | IPM4F09A
MQX3F07S | MQX4F09BS
VBV4F09 | VBV4F09B
MQX3F08S | MQX4F09CS
ITV8F10 | ITV4F09C
VIP8F10 | VIP4F09C
MQX8F10 | MQX4F09DS
MDB4F09H | MDB4F09DH
MDH4F09V | MDH4F09DV
IPM8F10 | IPM4F09D
ILM4F10 | ILM4F09D
MQX3F09S | MQX4F09ES
MQX4F10 | same
MQX4F11 | same
VIP4F11 | same
VPG4F11 | same
VRV4F11 | same
MQX4F12 | same
MDB4F12H | same
MDH4F12V | same
IPM4F12 | same
ITV4F12 | same
VIP4F12 | same
ILM4F12 | same
VBV4F12 | same