## assignments
system | type | Screens/Apps | responsible party | status | comments
Magnet | screen | trimscreen | Michele | complete
| screen | boxdetails | OTF | complete
| screen | box supply summary | OTF | complete
| screen | magnet loop screen | Michele | complete
| screen | trimrack screen | Chris S. | complete
| screen | trimrack status | cjs | low priority
| screen | Shunt control | OTF/Croke | in progress
| screen | Shunt summary | OTF | in progress
| app | box supply cycling script | Brandi | complete
| app | HystArea | Michele | complete
BPM | screen | BPM Live Display | Michele | complete
| screen | BPM Offset Screen | Michele | complete
| screen | BPM spikes | Michele | complete
| screen | see bpm global vars | Michele | complete
| app | BPM History | Dennis | low priority
| app | bpmsupercal | Dennis | not needed | per Pete Francis
| app | zero pos | Michele | on hold | Ops has agreed to use the script on the BPM Global diagnostics screen
BLM | screen | BLM Master | Michele | complete
| screen | BLM FSD | chris | complete
| screen | BLM Overview (racetrack) | OPS | on hold | Due to time constraints. Previous run screen checked for completeness. Edited as necessary.
| screen | BLM CW Checklist | OPS
| screen | BLM HV | OPS
| app | BLM limit check script | Theo | on hold | need info from SSG
FSD | screen | FSD Screen | higgins | need status | modify current screen: /usr/feluser/mccops/edm/felmps/MPS.edl
IOC/Controls | screen | All various flavors | Michele | on hold | existing screens can be used and manually updated.
| app | CA_Helper | Ops
| app | SaveIOCS | Ops
Vacuum | screen | vacuum spikes | Ops | on hold | existing screens can be used and manually updated.
| screen | Vacuum Combo | Ops
| screen | valve commander (racetrack) | Ops
| app | vacuum hotcheckout | Michele
Viewer | screen | viewer commander (racetrack) | Ops | on hold | existing screens can be used and manually updated.
| screen | viewer crates | Ops
| app | Jwalk | Michele | low priority
Dumps/insertables | screen | controlling screen | Mike McC | complete
| app | AllCavity Status | HLA | complete
RF | app | FaultCounter suite | HLA | in progress
| app | module editor | HLA | complete
| app | Trim up/trim down | Dennis Turner | not needed
| screen | standard screens | Clyde/Terry |  | need status
| app | RF walk up | Chris | on hold | time constraints/priority
| app | cavity history | Dennis | on hold
| app | Maxjuice |  | on hold | need information
General | app | Saver | HLA | on hold | use previous version.
| app | Shut down script | OPS/HLA | complete
| screen | Tools Screen | OPS | need status | update existing
| screen | HVPS screen | OPS | need status
| app | Gun on/off script | OPS | need status
| app | ALH | Michele | complete
| app | OrbitSnaps | Michele | low priority
| app | GenericKnobs | Michele | complete
| app | ViewText | Michele | complete
| app | Signal Calculator | Michele | complete
| app | Ditherer | Michele | complete
| app | StepNGraph | Michele | complete