## LERFMT
System | Labor | Labor | Procurements | Comment
| FTEs | (p-weeks) | (k$) | Labor tasks | Procurments
EESSAF | 0.13636 | 6 | 6 | PSS certifications, PSS/ODH support | ODH heads
EESDCP | 0.045455 | 2 | 1 | Upgrade solenoid power supply and fix sextupole supplies | spare parts
EEICS | 0.090909 | 4 | 2 | Vacuum maintenance
EESSUP | 0.045455 | 2 | 5
MSINST | 0.090909 | 4 | 4 | Maintenance of vacuum, instrument air and LCW systems
MSSURV | 0.090909 | 4 |  | Annual alignment and spot checks
MSCRYO | 0.090909 | 4 |  | maintain cryo systems and perform system checks
management (eng) | 0.045455 | 2 |  | Geographic Integrator (Coleman)
Engineering total | 0.63636 |  | 18
OPSADM | 0.068182 | 3 | 14 | Network, software license, server maintenance (new alarm computer, recycle CEBAF cast-aways) | Software licences
CIS | 0.068182 | 3 | 8 | Maintain Drive laser and gun | SF6, optics
Management(ops) | 0.022727 | 1 |  | Operations Planning (Benson)
Acc total | 0.15909 |  | 22
Grand Total | 0.79545 | 35 | 40

## LERFOP
System | Labor | Labor | Procurements | Comment
| FTEs | (p-weeks) | (k$) | Labor tasks | Procurements
MSNST | 0.045455 | 2 |  | Leak checking, HCO | Vacuum hardware or ion pumps
EESSUP | 0.045455 | 2 |  | Repairs to equipment, electrical safety improvements | Electrical hardware
EESDCP | 0.13636 | 6 | 9 | HCO. | Replacement trim cards.
EESRFS | 0.18182 | 8 | 6 | HCO. | Repl. Parts and RFCMs
EESICS | 0.5 | 22 | 10 | BPM updates Commission BlueCherry system. Complete modifications to fast valve logic and complete hot checkout. HCO. | BPM electronics, cameras, vacuum controls, video server
Management(eng) | 0.13636 | 6 |  | Geographic Integrator (Coleman)
Egineering total | 1.0455 |  | 25
SRFOPS | 0.11364 | 5 |  | HCO SRF commissioning, cryo bump for injector
OPSADM | 0.11364 | 5 | 6 | Update control software | Alarm server
OPSSFT | 0.13636 | 6 |  | Complete punch list items. Complete LED and rebuild operating screens.
OPSAHL | 0.13636 | 6 |  | Adapt CEBAF high level apps to LERF ERL. Repair bugs in existing software.
CIS | 0.20455 | 9 | 10 | Drive laser HCO and upkeep | Amplifier module,s optics
OPSMCC | 0.72727 | 32 |  | Operate the machine for six weeks two shifts/day. Plus support during 2 wk HCO
ACCASA | 0.18182 | 8 |  | Develop machine model. Provide APLE services.
ACCMGT | 0.15909 | 7 |  | Operations Planning (Benson)
Acc total | 1.7727 |  | 16
Grand Total | 2.8182 | 124 | 41