## Sheet1
# | Task | Staff | Estimated Duration (with no time contingency) | 2023
|  |  |  | June |  |  |  |  | July | [30 empty] | August | [30 empty] | September
|  |  |  | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
1 | Laser interlock circuit PCB review | DSG | 5 days | bar: June 26 to June 30
2 | DAQ circuit PCB design | Marc, Tyler | 15 days | bar: June 26 to June 30; July 3 to July 7; July 10 to July 14
3 | Laser interlock circuit PCB fabrication | N/A (external company) | 15 days | bar: July 3 to July 7; July 10 to July 14; July 17 to July 21
4 | DAQ/stage control program development | Tyler | 20 days | bar: July 3 to July 7; July 10 to July 14; July 17 to July 21; July 24 to July 28
5 | EEL 108 cleaning area set up | Hall C Techs | 15 days | bar: July 3 to July 7; July 10 to July 14; July 17 to July 21
6 | DAQ circuit PCB review | DSG | 5 days | bar: July 10 to July 14
7 | DAQ circuit PCB fabrication | N/A (external company) | 15 days | bar: July 17 to July 21; July 24 to July 28; July 31 to August 4
8 | Laser interlock circuit PCB assembly | Mindy | 5 days | bar: July 24 to July 28
9 | EEL 108 storage set up | George, Tyler, Mindy | 5 days | bar: July 24 to July 28
10 | Initial laser interlock circuit PCB testing after assembly | Tyler | 2 days | bar: July 31 to August 1
11 | Laser interlock circuit installation in EEL 108 | George, Mindy | 5 days | bar: August 2 to August 4
12 | DAQ circuit PCB assembly | Mindy | 5 days | bar: August 7 to August 11
13 | Post installation laser interlock circuit testing | George, Tyler, Mindy | 2 days | bar: August 9 to August 10
14 | Laser test area set up and alignment | Greg, Tyler, George | 15 days | bar: August 14 to August 18; August 21 to August 25; August 28 to September 1
15 | Initial DAQ circuit PCB testing after assembly | Tyler | 2 days | bar: August 14 to August 15
16 | DAQ circuit PCB set up in EEL 108 | George, Tyler | 5 days | bar: August 16 to August 18; August 21 to August 22
17 | DAQ/stage control testing in EEL 108 | George, Tyler | 3 days | bar: August 23 to August 25
18 | Laser test area characterization with reference bars | Greg, George, Tyler | 10 days | bar: August 28 to September 1; September 5 to September 8
19 | Detector components delivery and inventory | George, Mindy | 2 day | bar: September 25 to September 26
20 | Detector components disassembly | George, Mindy | 80 days (4 mo.) | bar: September 27 to September 29
21 | Quartz bar cleaning and storage | George, Mindy | 80 days (4 mo.) | bar: September 27 to September 29