## WorkPlan
Tentative WorkPlan – INFN GEM installation in BB and PR
Version 03/Aug/2020
* Onsite presence of INFN Techs and Researchers cannot be realistically scheduled !
| Month: | September/20 | October/20 |  |  |  | November/20 |  |  |  | December/20 |  |  |  | Jan/21 | Feb/21 | Mar/21
| Week: |  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Finalize GEM module production in Italy
Assemble last module in Catania
Ship module to Rome | bar: October/20 1
Test available modules in Rome | bar: October/20 1 to October/20 3
Ship test-passed modules to JLab together with other spare material | bar: October/20 3 to November/20 2
BB Chambers: Work in INFN Clean Room (Test Lab)
| Replace plastic Cable Trays in GEM chambers | [16 empty] | need metallic trays from JLab | bar: October/20 1 to October/20 2
Fix DAQ timeout | bar: October/20 1 to October/20 2
Do latest HV/cosmic test on BB GEMs before moving to TED | bar: October/20 2 to October/20 4
Finalize BB GEM frame | [17 empty] | jlab with GEM group support | bar: October/20 1 to November/20 1
Preliminary work in TED
Free space in TED for GEM installation | bar: October/20 3 to October/20 4
| Setup the gas system in the TED building | [16 empty] | jlab with GEM group support | bar: October/20 4 to November/20 3
Procure/adapt tools for installation/removal of chamber from BB frame | bar: October/20 4 to November/20 2
| Test Installation/Removal procedure on dummy chamber | [16 empty] | need finalized BB GEM frame | bar: November/20 1 to November/20 3
BB Chambers: Install GEM chambers into BigBite GEM frame
| Move each single GEM chamber to TED and load in BB GEM frame | [16 empty] | need finalized BB GEM frame and gas system in TED | bar: November/20 3 to December/20 2
PR chambers: Work in INFN Clean Room (Test Lab)
Test remaining modules (up to 4) with 90Sr rad source | bar: November/20 2 to December/20 1
Select best 3 modules and integrate last chamber | bar: November/20 4 to December/20 2
| Cosmic test of the 2 GEMs for PR | [16 empty] | need at least 2 GEM chambers to be moved to TED to get space in the cosmic tower | bar: December/20 1 to December/20 4
Move the DAQ system from the Clean Room to TED BigBite area | bar: December/20 3 to December/20 4
BB Chambers: Cabling and Test Chamber + DAQ
Cabling the chambers | bar: November/20 4 to December/20 2
Preliminary GEM-DAQ test outside BB
Install the loaded BB GEM frame into BigBite Spectrometer
BB Integration and test
Chamber integration in PR
| Move the 2 chambers in the PR area (assume TED) | [16 empty] | need gas system in RP area
Install GEMs in the RP (should be simpler than BB integration)
Cabling and testing