## WorkPlan
Tentative WorkPlan – UVa GEM installation in BB and Gen-RP
Version 08/Aug/2020
| Month: | September/20 |  |  |  | October/20 |  |  |  | November/20 |  |  |  | December/20 |  |  |  | January/21 |  |  |  | February/21 |  |  |  | March/21
| Week: | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 3
UVa U-V Strips GEMs: Production at UVa
Assembly & Test of 1st U-V strips layer #1 | bar: September/20 1 to October/20 1
Assembly & Test of 2nd U-V strips layer #2 | bar: September/20 4 to October/20 4
Assembly & Test of 3rd U-V strips layer #3 | bar: October/20 4 to November/20 4
Production of 4-slots backplanes & APV25 FE cards | bar: September/20 1 to November/20 4
Shipment of the first two U-V strips layers to Jlab | bar: November/20 1 to November/20 4
Assembly & Test of 4rd U-V strips layer #4 | bar: December/20 1 to January/21 2
UVa X-Y strips GEMs: Work in EEL124 Clean Room
Modification of HV divider (Huong's team from UVa) | bar: September/20 1 to September/20 4
Investigate APV25 noises and grounding issues | bar: September/20 1 to September/20 4
| 5 layers on cosmic stand and 1 on assembly table | September/20 1: continued activities on cosmic test stand until he installation of the last UVa GEM layers in the Gen-RP spectrometer
Cosmic tests and HV scan for 5 layers on cosmic stand
Preliminary work in TED (here I just follow Evaristo plans)
| Free space in TED for GEM installation | October/20 3: Coordinate with Evaristo and JLab folks
Setup the gas system in the TED building | bar: October/20 3 to November/20 4
BB Chambers: Installation of UVa U-V GEM chambers into BigBite GEM frame
| 2 UVa U-V strips GEMs expected to be available | November/20 3: Installation in BB frame; January/21 2: Check with Evaristo & Bogdan
BB Chambers: Installation of UVa X-Y strips GEM layer into BB Spectrometer
| Installation of UVa X-Y strips GEM layer (behind GRINCH) | November/20 1: Installation in BB frame; January/21 2: Confirm schedule with JLab folks
Move the DAQ & HV PS from UVa to TED for UVa GEMs in BB |  | December/20 1: DAQ & HV from UVa; January/21 2: Confirm with Nilanga
BB Chambers: Cabling and Test Chamber + DAQ
| Cabling the chambers HV, Readout Electronics | February/21 2: Coordination with Evaristo& INFN GEM layers installations
Preliminary GEM-DAQ test outside BB | bar: December/20 3 to January/21 4
Install the loaded BB GEM frame into BigBite Spectrometer | bar: December/20 3 to January/21 4
BB Full Integration: Final tests | bar: January/21 2 to January/21 4
GEn-RP chambers: Move layers to GEn-RP frame
| Installation of 2 UVa X-Y strips GEM layers - ChEx Veto | December/20 1: Installation in ChEx Veto; March/21 3: Confirm schedule & Plans with Brad, JLab folks
| Installation of 4 UVa X-Y strips GEM layers - ChEx Trackers | December/20 3: Installation in ChEx Trackers
| Installation of 2 × 2 UVa X-Y strips GEM layers - PR trackers | February/21 1: Installation in Gen-RP
Move the DAQ & HV PS from UVa to TED for UVa GEMs in BB |  | March/21 1: DAQ & HV from EEL CL
Gen-RP Chambers: Cabling and Test Chamber + DAQ
Cabling the chambers HV, Readout Electronics | bar: January/21 4 to March/21 3
Test of the Gen-RP GEMs DAQ | bar: January/21 4 to March/21 3