## Re-ordered
Modified By: |  | Pablo Campero
Date: |  | 2020-05-04
Comments |  | For group 18, added drawing for ADC PLC module in remote chassis 2
Hall A - SoLID Magnet Instrumentation & Controls Drawings
Group # | Group Name | DWG # | DWG Name | # of Sheets | Description / Comments | Status | Comments
1 | Index | A00000-16-03-0000 | Hall A SoLID Magnet Controls Sheet Index | 1 | Lists numbers and description for all drawings | In progress | Define final DWG numbers
2 | Overview Interconnections | A00000-16-03-0050 | SoLID Magnet Interconnect System Diagram | 1 | Shows main cable connections between magnet and control racks | In progress | misc. sensors not added
3 | Instrumentation Rack Layout | A00000-16-03-0100 | Instrumentation Control Panel Front Layout | 3 | Layout of rack and details for each section of the rack -Front view | in progress
|  | A00000-16-03-0101 | Instrumentation Control Panel Rear Layout | 1 | Layout of rack and details for each section of the rack - Rear view | in progress
|  | A00000-16-03-0102 | Instrumentation Control Panel Frame Layout | 3 | Riel-DIN mounting locations and dimensions
|  | A00000-16-03-0103 | Instrumentation Control Panel -Terminal Strip Layout | 1 | Detail of terminal strips labels and quantity
4 | Parts List | A00000-16-03-0104 | Instrumentation and PLC racks Panel Parts List | 1 | List of instrumentation and control devices
5 | Energy Dump System | A00000-16-03-0200 | Energy Dump System Wire Diagram | 1 | Dump circuit from magnet coils to MPS and control board discharge
6 | Temperatures | A00000-16-03-0210 | Magnet Temperature Sensor Wire Diagram | 12 | Temperature sensors wiring 4 wire sensors -Magnet and Service Tower | in progress | AST4 incomplete
|  | A00000-16-03-0211 | Current Source Module Wire Diagram | 4 | CCS board used to source excitation current for RH/Fe temp sensors | In progress
|  | A00000-16-03-0212 | CCR Temperature Sensor Wire Diagram | 1 | Temperature sensors wiring - 2 wire sensors - Magnet
7 | CCR Instrumentation | A00000-16-03-0220 | Vacuum, Pressure, Mass Flow Wire Diagram | 2 | Vacuum, Lhe and LN2 pressure and MFC s | In progress
|  | A00000-16-03-0221 | Mass Flow, Current, B Field Wire Diagram | 1 | RCL and LCL flows, I_coarse, and Magnetic Field signals
|  | A00000-16-03-0223 | LN2 Liquid Level Meter Wire Diagram | 1 | LN2 probes wiring inside CCR
|  | A00000-16-03-0224 | LHe Liquid Level Meter Wire Diagram | 1 | Lhe probes wiring
|  |  | Vessel Lhe Level Monitor wire Diagram | 1
8 | Magnetic Field Sensor Connections |  | Gauss Meter Wire Diagram? | 1 | Are we going to use same gauss meter ? No
9 | Strain Sensors Connections | A00000-16-03-0240 | Radial Strain Gauge Measurement Wire Diagram | 2 | 16 radial strain gauge sensors
|  | A00000-16-03-0241 | Axial Load Cells Measurement Wire Diagram | 1 | 4 axial load cell sensors
10 | Voltage Taps Connections | A00000-16-03-0250 | Voltage Tap Measurement Wire Diagram | 2 | Connection from voltage taps to signal conditioner output
|  | A00000-16-03-0251 | Potential Voltage Taps Non - Monitored | 1 | Do we have Non monitored voltage taps for the SoLID solenoid ? No
|  | A00000-16-03-0252 | Quench Detector Wire Diagram | 1
11 | JT Valves Connections | A00000-16-03-0260 | Linear Voltage Differential Transducers | 2 | LVDT and macro sensors LVC used for Electric Valves
|  | A00000-16-03-0261 | LVDT Voltage Readout | 1 | Wiring connection in connector to power
|  | A00000-16-03-0262 | Electric Linear Actuator Drive Motors | 2 | Wiring for electric motor drivers for JT Valves
12 | Magnet Power Supply | A00000-16-03-0280 | Power Supply Control Crate Connections | 1
|  | A00000-16-03-0281 | Power Supply M-panel Connections | 1
|  | A00000-16-03-0282 | Power Supply Control Crate Modifications | 1 | Do we need the same modifications for SoLID power supply? Probally Not PSU has not been ID yet
|  | A00000-16-03-0283 | Power Supply Control Crate Panel | 1 | Layout for PSU control crate - hole locations and dimensions
13 | PLC Rack Layout | A00000-16-03-1010 | PLC I/O Control Rack Front Side Layout | 1
14 | PLC Communications and Heartbeat Connections - Local PLC Chassis | A00000-16-03-1011 | Local PLC controller and Communication Modules | 1 | Includes redundant PLC chassis with communication connections
|  | A00000-16-03-1012 | ASCII Communication System Diagram | 1 | FLEX I/O module connections to the PSU
|  | A00000-16-03-1013 | Keep Alive Timing Relay Wire Diagram | 1 | PLC Hardware Watchdog connections
15 | PLC I/O module Connections Remote Chassis 1 | A00000-16-03-0300 | Remote 1 - PLC chassis Layout | 1 | Overview of remote 1 PLC chassis
|  | A00000-16-03-0301 | Remote 1- PLC I/O Slot 1 Terminal Connections | 1
|  | A00000-16-03-0303 | Remote 1- PLC I/O Slot 2 Terminal Connections | 1
|  | A00000-16-03-0303 | Remote 1 - PLC I/O Slot 3 Terminal Connections | 1
|  | A00000-16-03-0304 | Remote 1 - PLC I/O Slot 4 Terminal Connections | 1
|  | A00000-16-03-0305 | Remote 1 - PLC I/O Slot 5 Terminal Connections | 1
|  | A00000-16-03-0306 | Remote 1 - PLC I/O Slot 6 Terminal Connections | 1
|  | A00000-16-03-0307 | Remote 1 - PLC I/O Slot 7 Terminal Connections | 1
|  | A00000-16-03-0308 | Remote 1 - PLC I/O Slot 8 Terminal Connections | 1
|  | A00000-16-03-0309 | Remote 1 - PLC I/O Slot 9 Terminal Connections | 1
16 | 24 VDC and 5VDC Distribution | A00000-16-03-0350 | Power Supply Terminal Strips | 1 | Termination detail for 24 VDC/5VDC power source
|  | A00000-16-03-0351 | Power Distribution Terminal Strips | 1 | Power Distribution to JT valves and VTs
17 | Cable Diagrams | A00000-16-03-0400 | Cable Diagram for Temperature Sensors | 1 | Details of connections from sensor connector to terminal strip for temperature sensors | completed
|  | A00000-16-03-0401 | Cable Diagram for Voltage Taps | 1 | Details of connections from sensor connector to terminal strip for Voltage taps | In progress
|  | A00000-16-03-0402 | Cable Diagram for JT Valves | 1 | Details of connections from sensor connector to terminal strip for JT Valves
|  | A00000-16-03-0403 | Cable Diagram for Radial Strain Gauges | 2 | Details of connections from sensor connector to terminal strip for radial strain gauge sensors | in progress | wire color
|  | A00000-16-03-0404 | Cable Diagram for Axial Load Cells | 1 | Details of connections from sensor connector to terminal strip for axial load cell sensors | In progress | wire color
|  | A00000-16-03-0405 | Cable Diagram for Instrumentation - Miscellaneous | 1 | Details for connector and cable for Vacuum, He and N2 pressure, and Leads' Mass Flow | In progress
18 | PLC I/O module Connections Remote Chassis 2 | A00000-16-03-03010 | Remote 2 - PLC chassis Layout | 1 | Overview of remote 2 PLC chassis
|  | A00000-16-03-03011 | Remote 2- PLC I/O Slot 1 Terminal Connections | 1
|  | A00000-16-03-03012 | Remote 2- PLC I/O Slot 2 Terminal Connections | 1
|  | A00000-16-03-03013 | Remote 2 - PLC I/O Slot 3 Terminal Connections | 1
|  | A00000-16-03-03014 | Remote 2 - PLC I/O Slot 4 Terminal Connections | 1
|  | A00000-16-03-03015 | Remote 2 - PLC I/O Slot 5 Terminal Connections | 1
|  | A00000-16-03-03016 | Remote 2 - PLC I/O Slot 6 Terminal Connections
|  | A00000-16-03-03017 | Remote 2 - PLC I/O Slot 7 Terminal Connections
|  | A00000-16-03-03018 | Remote 2 - PLC I/O Slot 8 Terminal Connections
|  | A00000-16-03-03019 | Remote 2 - PLC I/O Slot 9 Terminal Connections
19 | Heat Exchanger Instrumentation | A00000-16-03-0500 | Transfer Line HX Interconnect System Diagram | 1 | Details of cables from transfer line to Control Panel
|  | A00000-16-03-0501 | HX Temperature Diode Sensor Wire Diagram | 1
|  | A00000-16-03-0502 | Transfer Line HX Vacuum Wire Diagram | 1
|  | A00000-16-03-0503 | Beamline Vacuum/spare Terminal Wire Diagram | 1
|  | A00000-16-03-0504 | Linear Voltage Differential Transducers | 1
|  | A00000-16-03-0505 | LVDT Voltage Readout | 1
|  | A00000-16-03-0506 | Electric Linear Actuator Drive Motors | 1
|  | A00000-16-03-0507 | Current Source Module Wire Diagram | 1
|  | A00000-16-03-0508 | 24V dc Power Supply Terminal Strips | 1 | The power required will be supplied from the SoLID power +24VDC power supply, for Signal conditioners inside the rack
|  | A00000-16-03-0509 | 24V dc Power Distribution Terminal Strips | 1 | The power required will be supplied from the SoLID power +24VDC power supply, for Signal conditioners inside the rack
|  | A00000-16-03-0510 | Cable Diagram | 1
|  | A00000-16-03-0511 | Cable Diagram | 1
93

## Sheet1
Modified By: |  | Pablo Campero
Date: |  | 2020-05-04
Comments |  | For group 18, added drawing for ADC PLC module in remote chassis 2
Hall A - SoLID Magnet Instrumentation & Controls Drawings
Group # | Group Name | DWG # | DWG Name | # of Sheets | Description / Comments | Status | Comments
1 | Index | A00000-16-03-0000 | Hall A SoLID Magnet Controls Sheet Index | 1 | Lists numbers and description for all drawings | In progress | Define final DWG numbers
2 | Overview Interconnections | A00000-16-03-0050 | SoLID Magnet Interconnect System Diagram | 1 | Shows main cable connections between magnet and control racks | In progress | misc. sensors not added
3 | Instrumentation Rack Layout | A00000-16-03-0150 | Instrumentation Control Panel Front Layout | 3 | Layout of rack and details for each section of the rack -Front view | in progress
|  | A00000-16-03-0200 | Instrumentation Control Panel Rear Layout | 1 | Layout of rack and details for each section of the rack - Rear view | in progress
|  | A00000-16-03-0250 | Instrumentation Control Panel Frame Layout | 3 | Riel-DIN mounting locations and dimensions
|  | A00000-16-03-0300 | Instrumentation Control Panel -Terminal Strip Layout | 1 | Detail of terminal strips labels and quantity
4 | Parts List | A00000-16-03-0350 | Instrumentation and PLC racks Panel Parts List | 1 | List of instrumentation and control devices
5 | Energy Dump System | A00000-16-03-0400 | Energy Dump System Wire Diagram | 1 | Dump circuit from magnet coils to MPS and control board discharge
6 | Temperatures | A00000-16-03-0450 | Magnet Temperature Sensor Wire Diagram | 12 | Temperature sensors wiring 4 wire sensors -Magnet and Service Tower | in progress | AST4 incomplete
|  | A00000-16-03-0500 | Current Source Module Wire Diagram | 4 | CCS board used to source excitation current for RH/Fe temp sensors | In progress
|  | A00000-16-03-0550 | CCR Temperature Sensor Wire Diagram | 1 | Temperature sensors wiring - 2 wire sensors - Magnet
7 | CCR Instrumentation | A00000-16-03-0600 | Vacuum, Pressure, Mass Flow Wire Diagram | 2 | Vacuum, Lhe and LN2 pressure and MFC s | In progress
|  | A00000-16-03-0650 | Mass Flow, Current, B Field Wire Diagram | 1 | RCL and LCL flows, I_coarse, and Magnetic Field signals
|  | A00000-16-03-0700 | LN2 Liquid Level Meter Wire Diagram | 1 | LN2 probes wiring inside CCR
|  | A00000-16-03-0750 | LHe Liquid Level Meter Wire Diagram | 1 | Lhe probes wiring
|  | A00000-16-03-0800 | Vessel Lhe Level Monitor wire Diagram | 1
8 | Magnetic Field Sensor Connections | A00000-16-03-0850 | Gauss Meter Wire Diagram? | 1 | Are we going to use same gauss meter ? No
9 | Strain Sensors Connections | A00000-16-03-0900 | Radial Strain Gauge Measurement Wire Diagram | 2 | 16 radial strain gauge sensors
|  | A00000-16-03-0950 | Axial Load Cells Measurement Wire Diagram | 1 | 4 axial load cell sensors
10 | Voltage Taps Connections | A00000-16-03-1000 | Voltage Tap Measurement Wire Diagram | 2 | Connection from voltage taps to signal conditioner output
|  | A00000-16-03-1050 | Potential Voltage Taps Non - Monitored | 1 | Do we have Non monitored voltage taps for the SoLID solenoid ? No
|  | A00000-16-03-1100 | Quench Detector Wire Diagram | 1
11 | JT Valves Connections | A00000-16-03-1150 | Linear Voltage Differential Transducers | 2 | LVDT and macro sensors LVC used for Electric Valves
|  | A00000-16-03-1200 | LVDT Voltage Readout | 1 | Wiring connection in connector to power
|  | A00000-16-03-1250 | Electric Linear Actuator Drive Motors | 2 | Wiring for electric motor drivers for JT Valves
12 | Magnet Power Supply | A00000-16-03-1300 | Power Supply Control Crate Connections | 1
|  | A00000-16-03-1350 | Power Supply M-panel Connections | 1
|  | A00000-16-03-1400 | Power Supply Control Crate Modifications | 1 | Do we need the same modifications for SoLID power supply? Probally Not PSU has not been ID yet
|  | A00000-16-03-1450 | Power Supply Control Crate Panel | 1 | Layout for PSU control crate - hole locations and dimensions
13 | PLC Rack Layout | A00000-16-03-1500 | PLC I/O Control Rack Front Side Layout | 1
14 | PLC Communications and Heartbeat Connections - Local PLC Chassis | A00000-16-03-1550 | Local PLC controller and Communication Modules | 1 | Includes redundant PLC chassis with communication connections
|  | A00000-16-03-1600 | ASCII Communication System Diagram | 1 | FLEX I/O module connections to the PSU
|  | A00000-16-03-1650 | Keep Alive Timing Relay Wire Diagram | 1 | PLC Hardware Watchdog connections
15 | PLC I/O module Connections Remote Chassis 1 | A00000-16-03-1700 | Remote 1 - PLC chassis Layout | 1 | Overview of remote 1 PLC chassis
|  | A00000-16-03-1750 | Remote 1- PLC I/O Slot 1 Terminal Connections | 1
|  | A00000-16-03-1800 | Remote 1- PLC I/O Slot 2 Terminal Connections | 1
|  | A00000-16-03-1850 | Remote 1 - PLC I/O Slot 3 Terminal Connections | 1
|  | A00000-16-03-1900 | Remote 1 - PLC I/O Slot 4 Terminal Connections | 1
|  | A00000-16-03-1950 | Remote 1 - PLC I/O Slot 5 Terminal Connections | 1
|  | A00000-16-03-2000 | Remote 1 - PLC I/O Slot 6 Terminal Connections | 1
|  | A00000-16-03-2050 | Remote 1 - PLC I/O Slot 7 Terminal Connections | 1
|  | A00000-16-03-2150 | Remote 1 - PLC I/O Slot 8 Terminal Connections | 1
|  | A00000-16-03-2200 | Remote 1 - PLC I/O Slot 9 Terminal Connections | 1
16 | 24 VDC and 5VDC Distribution | A00000-16-03-2250 | Power Supply Terminal Strips | 1 | Termination detail for 24 VDC/5VDC power source
|  | A00000-16-03-2300 | Power Distribution Terminal Strips | 1 | Power Distribution to JT valves and VTs
17 | Cable Diagrams | A00000-16-03-2350 | Cable Diagram for Temperature Sensors | 1 | Details of connections from sensor connector to terminal strip for temperature sensors | completed
|  | A00000-16-03-2400 | Cable Diagram for Voltage Taps | 1 | Details of connections from sensor connector to terminal strip for Voltage taps | In progress
|  | A00000-16-03-2450 | Cable Diagram for JT Valves | 1 | Details of connections from sensor connector to terminal strip for JT Valves
|  | A00000-16-03-2500 | Cable Diagram for Radial Strain Gauges | 2 | Details of connections from sensor connector to terminal strip for radial strain gauge sensors | in progress | wire color
|  | A00000-16-03-2550 | Cable Diagram for Axial Load Cells | 1 | Details of connections from sensor connector to terminal strip for axial load cell sensors | In progress | wire color
|  | A00000-16-03-2600 | Cable Diagram for Instrumentation - Miscellaneous | 1 | Details for connector and cable for Vacuum, He and N2 pressure, and Leads' Mass Flow | In progress
18 | PLC I/O module Connections Remote Chassis 2 | A00000-16-03-2650 | Remote 2 - PLC chassis Layout | 1 | Overview of remote 2 PLC chassis
|  | A00000-16-03-2700 | Remote 2- PLC I/O Slot 1 Terminal Connections | 1
|  | A00000-16-03-2750 | Remote 2- PLC I/O Slot 2 Terminal Connections | 1
|  | A00000-16-03-2800 | Remote 2 - PLC I/O Slot 3 Terminal Connections | 1
|  | A00000-16-03-2850 | Remote 2 - PLC I/O Slot 4 Terminal Connections | 1
19 | Heat Exchanger Instrumentation | A00000-16-03-2900 | Transfer Line HX Interconnect System Diagram | 1 | Details of cables from transfer line to Control Panel
|  | A00000-16-03-2950 | HX Temperature Diode Sensor Wire Diagram | 1
|  | A00000-16-03-3000 | Transfer Line HX Vacuum Wire Diagram | 1
|  | A00000-16-03-3050 | Beamline Vacuum/spare Terminal Wire Diagram | 1
|  | A00000-16-03-3100 | Linear Voltage Differential Transducers | 1
|  | A00000-16-03-3150 | LVDT Voltage Readout | 1
|  | A00000-16-03-3200 | Electric Linear Actuator Drive Motors | 1
|  | A00000-16-03-3250 | Current Source Module Wire Diagram | 1
|  | A00000-16-03-3300 | 24V dc Power Supply Terminal Strips | 1 | The power required will be supplied from the SoLID power +24VDC power supply, for Signal conditioners inside the rack
|  | A00000-16-03-3350 | 24V dc Power Distribution Terminal Strips | 1 | The power required will be supplied from the SoLID power +24VDC power supply, for Signal conditioners inside the rack
|  | A00000-16-03-3400 | Cable Diagram | 1
|  | A00000-16-03-3450 | Cable Diagram | 1
92