## Activites
WBS Name | Activity ID | EVMS Code | Activity Name | BL Project Start Date | Calc Start Date | Actual Start Date | Expect to Start Date | BL Project Finish date | Calc Finish Date | Actual Finish Date | Expect To Finish Date | Prev Status % Comp | New Status % Comp | Total Float In Days | EVMS Code | Activity ID
1.4.2.7.7.1 TORUS INSTUMENTATION AND CONTROL | 2427101075 | H | System FMEA (Magnet + Cryogenics) | 2015-06-04 | 2015-06-04 | 2015-09-03 |  | 2015-06-16 | 2015-06-16 | 2016-06-25 | 2016-06-25 | 0 | 100% | 316 | H | 2427101075
1.4.2.7.7.1 TORUS INSTUMENTATION AND CONTROL | 2427101080 | H | Magnet Instrumentation Review | 2015-08-18 | 2015-08-18 | 2015-10-19 |  | 2015-08-27 | 2015-08-27 | 2015-11-13 | 2015-11-13 | 0 | 100% | 366 | H | 2427101080
1.4.2.7.7.1 TORUS INSTUMENTATION AND CONTROL | 2427101085 | S | Instrumentation List (Cryogenics) | 2015-04-13 | 2015-04-13 | 2015-04-13 |  | 2015-06-30 | 2015-06-30 | 2015-09-16 |  | 0 | 100% | 363 | S | 2427101085
1.4.2.7.7.1 TORUS INSTUMENTATION AND CONTROL | 2427101090 | H | Cryogenics Instrument Review | 2015-08-28 | 2015-08-28 |  |  | 2015-09-03 | 2015-09-03 | 2015-11-13 | 2015-11-13 | 0 | 100% | 363 | H | 2427101090
1.4.2.7.7.1 TORUS INSTUMENTATION AND CONTROL | 2427101095 | H | MPS, SOE, PLC Design | 2015-04-13 | 2015-04-13 | 2015-04-13 |  | 2015-07-31 | 2015-07-31 |  | 2015-08-30 | 0 | 100% | 334 | H | 2427101095
1.4.2.7.7.1 TORUS INSTUMENTATION AND CONTROL | 2427101100 | H | MPS, SOE and PLC Hardware Selection | 2015-04-13 | 2015-04-13 | 2015-04-13 |  | 2015-08-03 | 2015-08-03 |  | 2015-08-30 | 0 | 100% | 316 | H | 2427101100
1.4.2.7.7.1 TORUS INSTUMENTATION AND CONTROL | 2427101105 | H | Racking Design | 2015-09-04 | 2015-09-04 |  |  | 2015-09-17 | 2015-09-17 |  |  | 0 | 100% | 316 | H | 2427101105
1.4.2.7.7.1 TORUS INSTUMENTATION AND CONTROL | 2427101110 | H | Racking Hardware Selection | 2015-09-18 | 2015-09-18 |  |  | 2015-09-18 | 2015-09-18 |  |  | 0 | 100% | 316 | H | 2427101110
1.4.2.7.7.1 TORUS INSTUMENTATION AND CONTROL | 2427101120 | S | Quench Protection Design | 2015-08-18 | 2015-08-18 |  |  | 2015-09-14 | 2015-09-14 | 2016-04-15 | 2016-04-28 | 0 | 100% | 316 | S | 2427101120
1.4.2.7.7.1 TORUS INSTUMENTATION AND CONTROL | 2427101125 | H | Quench Protection Review | 2015-09-15 | 2015-09-15 |  |  | 2015-09-15 | 2015-09-15 | 2015-11-25 | 2015-11-30 | 0 | 100% | 316 | H | 2427101125
1.4.2.7.7.1 TORUS INSTUMENTATION AND CONTROL | 2427101130 | S | Voltage, Temp, Strain, Load, Flow, etc. requirement | 2015-06-17 | 2015-06-17 |  |  | 2015-06-29 | 2015-06-29 |  |  | 0 | 100% | 316 | S | 2427101130
1.4.2.7.7.1 TORUS INSTUMENTATION AND CONTROL | 2427101135 | S | Wiring Maps | 2015-09-04 | 2015-09-04 |  |  | 2015-09-25 | 2015-09-25 | 2016-04-10 | 2016-04-28 | 0 | 99.9% | 396 | S | 2427101135
1.4.2.7.7.1 TORUS INSTUMENTATION AND CONTROL | 2427101140 | S | Wiring Diagrams | 2015-09-28 | 2015-09-28 |  |  | 2015-10-09 | 2015-10-09 | 2016-04-16 | 2016-04-28 | 0 | 100% | 396 | S | 2427101140
1.4.2.7.7.1 TORUS INSTUMENTATION AND CONTROL | 2427101145 | H | Rack Maps | 2015-09-04 | 2015-09-04 |  |  | 2015-09-18 | 2015-09-18 | 2016-04-15 | 2016-04-15 | 0 | 100% | 364 | H | 2427101145
1.4.2.7.7.1 TORUS INSTUMENTATION AND CONTROL | 2427101150 | S | Cable Harnesses Design and Materials | 2015-10-19 | 2015-10-19 |  |  | 2015-10-29 | 2015-10-29 | 2016-04-20 | 2016-04-28 | 0 | 100% | 333 | S | 2427101150
1.4.2.7.7.1 TORUS INSTUMENTATION AND CONTROL | 2427101155 | S | Hall Cable Layouts | 2015-09-28 | 2015-09-28 |  |  | 2015-10-16 | 2015-10-16 | 2016-02-26 |  | 0 | 100% | 242 | S | 2427101155
1.4.2.7.7.1 TORUS INSTUMENTATION AND CONTROL | 2427101160 | H | Drawing review and approvals | 2015-10-30 | 2015-10-30 |  |  | 2015-11-05 | 2015-11-05 |  | 2016-11-30 | 0 | 0% | 285 | H | 2427101160
1.4.2.7.7.1 TORUS INSTUMENTATION AND CONTROL | 2427101165 | H | Racking Procurement Prep | 2015-09-21 | 2015-09-21 |  |  | 2015-09-25 | 2015-09-25 | 2015-10-15 |  | 0 | 100% | 285 | H | 2427101165
1.4.2.7.7.1 TORUS INSTUMENTATION AND CONTROL | 2427101170 | H | Racking Procurement | 2015-09-28 | 2015-09-28 |  |  | 2015-10-16 | 2015-10-16 | 2015-10-30 |  | 0 | 100% | 285 | H | 2427101170
1.4.2.7.7.1 TORUS INSTUMENTATION AND CONTROL | 2427101175 | H | MPS, PLC and SOE Procurement Prep | 2015-10-13 | 2015-10-13 | 2015-07-24 |  | 2015-10-19 | 2015-10-19 | 2015-11-10 |  | 0 | 100% | 250 | H | 2427101175
1.4.2.7.7.1 TORUS INSTUMENTATION AND CONTROL | 2427101180 | S | MPS, SOE, and PLC delivery to Jlab | 2015-10-20 | 2015-10-20 | 2015-07-24 |  | 2015-11-09 | 2015-11-09 | 2016-03-20 | 2016-04-15 | 0 | 100% | 250 | S | 2427101180
1.4.2.7.7.1 TORUS INSTUMENTATION AND CONTROL | 2427101190 | D | Purchase/Fabricate Copper lugs for connections | 2016-01-07 | 2016-01-07 |  |  | 2016-01-21 | 2016-01-21 | 2016-02-05 |  | 0 | 100% | 311 | D | 2427101190
1.4.2.7.7.1 TORUS INSTUMENTATION AND CONTROL | 2427101195 | H | LCW Lines | 2015-12-15 | 2015-12-15 |  |  | 2016-01-06 | 2016-01-06 | 2016-02-05 |  | 0 | 100% | 250 | H | 2427101195
1.4.2.7.7.1 TORUS INSTUMENTATION AND CONTROL | 2427101200 | S | PLC Programming | 2015-09-30 | 2015-09-30 |  |  | 2016-02-04 | 2016-02-04 |  | 2016-11-30 | 0 | 74.75% | 250 | S | 2427101200
1.4.2.7.7.1 TORUS INSTUMENTATION AND CONTROL | 2427101210 | H | EPICS Specification | 2016-01-12 | 2016-01-12 |  |  | 2016-01-26 | 2016-01-26 | 2016-03-28 | 2016-03-28 | 0 | 100% | 250 | H | 2427101210
1.4.2.7.7.1 TORUS INSTUMENTATION AND CONTROL | 2427101215 | S | PLC Logic Documentation | 2016-02-05 | 2016-02-05 |  |  | 2016-04-14 | 2016-04-14 |  | 2016-11-30 | 0 | 0% | 250 | S | 2427101215
1.4.2.7.7.1 TORUS INSTUMENTATION AND CONTROL | 2427101220 | S | EPICS Programming | 2016-01-27 | 2016-01-27 |  |  | 2016-02-16 | 2016-02-16 |  | 2016-12-30 | 0 | 5% | 250 | S | 2427101220
1.4.2.7.7.1 TORUS INSTUMENTATION AND CONTROL | 2427101225 | S | Fast DAQ Programming | 2016-02-17 | 2016-02-17 |  |  | 2016-03-04 | 2016-03-04 |  | 2016-10-31 | 0 | 72.5% | 250 | S | 2427101225
1.4.2.7.7.1 TORUS INSTUMENTATION AND CONTROL | 2427101230 | S | Populate Racks and Wire Back Panels | 2015-11-10 | 2015-11-10 |  |  | 2016-01-04 | 2016-01-04 |  | 2016-10-15 | 0 | 99% | 250 | S | 2427101230
1.4.2.7.7.1 TORUS INSTUMENTATION AND CONTROL | 2427101235 | S | Sequence of Events Monitor Build | 2016-01-05 | 2016-01-05 |  |  | 2016-02-08 | 2016-02-08 | 2016-01-28 |  | 0 | 100% | 321 | S | 2427101235
1.4.2.7.7.1 TORUS INSTUMENTATION AND CONTROL | 2427101240 | S | Harness Builds | 2015-11-06 | 2015-11-06 |  |  | 2016-01-08 | 2016-01-08 | 2016-07-20 | 2016-07-05 | 0 | 100% | 377 | S | 2427101240
1.4.2.7.7.1 TORUS INSTUMENTATION AND CONTROL | 2427101245 | S | Interface with Cryo | 2016-02-17 | 2016-02-17 |  |  | 2016-02-26 | 2016-02-26 | 2016-05-15 | 2016-06-15 | 0 | 100% | 222 | S | 2427101245
1.4.2.7.7.1 TORUS INSTUMENTATION AND CONTROL | 2427101250 | H | Test Box Design | 2015-09-16 | 2015-09-16 |  |  | 2015-10-06 | 2015-10-06 | 2016-02-24 |  | 0 | 100% | 219 | H | 2427101250
1.4.2.7.7.1 TORUS INSTUMENTATION AND CONTROL | 2427101255 | S | Test Box Build | 2015-10-07 | 2015-10-07 |  |  | 2015-11-03 | 2015-11-03 | 07.22.2016 | 2016-07-15 | 0 | 100% | 219 | S | 2427101255
1.4.2.7.7.1 TORUS INSTUMENTATION AND CONTROL | 2427101260 | S | Fast DAQ Wiring | 2016-02-09 | 2016-02-09 |  |  | 2016-02-22 | 2016-02-22 |  | 2016-10-30 | 0 | 65% | 219 | S | 2427101260
1.4.2.7.7.1 TORUS INSTUMENTATION AND CONTROL | 2427101265 | S | Cabing in Hall | 2016-01-11 | 2016-01-11 |  |  | 2016-02-01 | 2016-02-01 |  | 2017-03-15 | 0 | 95% | 482 | S | 2427101265
| 2427101270 | S | Power Supply Integration/Installation | 2016-02-23 | 2016-02-23 |  |  | 2016-03-08 | 2016-03-08 |  | 2016-03-20 |  | 100% |  | S | 2427101270
| 2427101275 | S | Cryo Service Box Installation (Electrical/Controls) | 2016-02-29 | 2016-02-29 |  |  | 2016-04-07 | 2016-04-07 |  | 2017-02-15 |  | 10% |  | S | 2427101275
| 2427101280 | S | Current Leads Power & Voltage Tap | 2016-04-08 | 2016-04-08 |  |  | 2016-06-23 | 2016-06-23 |  | 2016-09-16 |  | 100% |  | S | 2427101280
| 2427101285 | S | Final Verification Point-to-Point | 2016-06-24 | 2016-06-24 |  |  | 2016-07-07 | 2016-07-07 |  | 2017-04-14 |  | 0% |  | S | 2427101285
| 2427101290 | H | Fast DAQ Hardware/Software Integration debugging | 2016-07-08 | 2016-07-08 |  |  | 2016-08-04 | 2016-08-04 |  | 2017-04-14 |  | 0% |  | H | 2427101290
| 2427101295 | S | Solenoid - I and C Commissioning (Pump) | 2016-08-05 | 2016-08-05 |  |  | 2016-09-01 | 2016-09-01 |  | 2017-05-04 |  | 20.1% |  | S | 2427101295
| 24271013 |  | Solenoid - I and C Commissioning (Cool) | [7 empty] | 2017-05-05 |  | 0% |  |  | 24271013
| 2427101305 |  | Solenoid - I and C Commissioning (Energize) | [7 empty] | 2017-05-19 |  | 0% |  |  | 2427101305

## W_Steps
Notes:
1.For S-code activities - Expand the groups below activites to see the steps | [6 empty] | NEW PROGRESS (Oct 2016)
| 1a. Steps have a weight in percent under the Percent column | [5 empty] | Activity Complete
| 1b. Mark completed steps with a 1 in the 'Complete' column | [5 empty] | NEW STEPS/STEP CHANGE
| 1c. The '% Complete' column should update automatically | [5 empty] | Progress required for Oct 2016
2. For H-code activities - enter a '1' in the 'Complete' column if it is started, '2' if it is complete
Activity ID | EVMS Code | Activity | Budgeted labor | Budgeted Labor Cost | Procurements? | Total Cost | Percent | Complete (H Code) | % Complete | Value Jan/15 |  | April Value | OCT PROGRESS | NOV PROGRESS | DEC PROGRESS | JAN PROGRESS | FEB PROGRESS | MAR PROGRESS | APR PROGRESS | MAY PROGRESS | JUN PROGRESS | JUL PROGRESS | AUG PROGRESS | SEP PROGRESS | OCT PROGRESS
2427101075 | S | System FMEA (Magnet + Cryogenics) |  |  |  | 8200 |  |  | 100% | 8200 | 8200
| 1 | Vendor Risk Mitigation List - Coil Winding and Potting |  |  |  |  | 17% | 1
| 2 | Vendor Risk Mitigation List - Cold Mass w/o shield |  |  |  |  | 13% | 1 | [5 empty] | 1066
| 3 | Vendor Risk Mitigation List - Shield and Vacuum Vessel w/ Shipping |  |  |  |  | 13% | 1 | [5 empty] | 1066
| 4 | Power Supply and Cabling |  |  |  |  | 9% | 1 | [11 empty] | 738
| 5 | Service Tower, Cryo Duct, Vacuum Vessel Closure & Vacuum System |  |  |  |  | 13% | 1 | [11 empty] | 1066
| 6 | Instruments & Controls |  |  |  |  | 13% | 1 | [11 empty] | 1066
| 7 | Hall Assembly |  |  |  |  | 9% | 1 | [11 empty] | 738
| 8 | Commissioning |  |  |  |  | 13% | 1 | [11 empty] | 1066
2427101080 | H | Magnet Instrumentation Review |  |  |  | 6193 |  | 2 | 100% | 6193 |  |  | 6193 | 6193
2427101085 | S | Instrumentation List (Cryogenics) |  |  |  | 12823 |  |  | 100% | 12823
| 1 | Generate List of Service Can Valves |  |  |  |  | 17.5% | 1 |  | 0
| 2 | Generate List of Service Can Temperature Sensors |  |  |  |  | 17.5% | 1 |  | 0 |  | 2244.025
| 3 | Generate List of Flow Sensors/Controllers |  |  |  |  | 17.5% | 1 |  |  | 2244.025
| 4 | Generate List of Insulating Vacuum Instrumentation |  |  |  |  | 15% | 1 |  | 0 | 1923.45
| 5 | Generate List of Pressure Transducers (PT and DP) |  |  |  |  | 17.5% | 1
| 6 | Generate List of Sub-atmospheric transfer line instrumentation |  |  |  |  | 15% | 1 |  | 0
2427101090 | H | Cryogenics Instrument Review |  |  |  | 6174 |  | 2 | 100% | 6174 |  |  | 6174 | 6174
2427101095 | H | MPS, SOE, PLC Design |  |  |  | 7606 |  | 2 | 100% | 7606 |  | 7606
2427101100 | H | MPS, SOE and PLC Hardware Selection |  |  |  | 1541 |  | 2 | 100% | 1541 |  | 1541
2427101105 | H | Racking Design |  |  |  | 2359 |  | 2 | 100% | 2359 |  |  | 2359
2427101110 | H | Racking Hardware Selection |  |  |  | 771 |  | 2 | 100% | 771 |  |  | 771
2427101120 | S | Quench Protection Design |  |  |  | 6669 |  |  | 100% | 6669
| 1 | Define VT Locations |  |  |  |  | 20% | 1 | [5 empty] | 1333.8
| 2 | Assign QD Channels |  |  |  |  | 20% | 1 | [5 empty] | 1333.8
| 3 | Define Safety Interlocks |  |  |  |  | 10% | 1 | [5 empty] | 666.9
| 4 | Establish Initial Threshold Values |  |  |  |  | 20% | 1 | [5 empty] | 1333.8
| 5 | Create schematic (first draft) |  |  |  |  | 20% | 1 | [5 empty] | 1333.8
| 6 | Create Schematic (final draft) |  |  |  |  | 10% | 1 | [10 empty] | 666.9
2427101125 | H | Quench Protection Review |  |  |  | 1240 |  | 2 | 100% | 1240 |  |  |  | 1240
2427101130 | S | Voltage, Temp, Strain, Load, Flow, etc. requirement |  |  |  | 11169 |  |  | 100% | 11169 | 11169
| 1 | Voltage Tap Requirments |  |  |  |  | 16.7% | 1
| 2 | Temperature Requirements |  |  |  |  | 16.7% | 1
| 3 | Strain Requirements |  |  |  |  | 16.7% | 1
| 4 | Load Requirements |  |  |  |  | 16.7% | 1
| 5 | Flow Requirements |  |  |  |  | 16.7% | 1
| 6 | Instrument Requirements Review |  |  |  |  | 16.5% | 1 |  |  |  |  | 1842.885
2427101135 | S | Wiring Maps |  |  |  | 14464 |  |  | 99.9% | 14449.536
| 1 | Solenoid Instrumentation Wiring Maps |  |  |  |  | 33.3% | 1 |  | 0
| 2 | Cryo Can Instrument Maps |  |  |  |  | 33.3% | 1 |  | 0 |  |  |  |  | 4816.512
| 3 | Voltage Tap Maps |  |  |  |  | 33.3% | 1 | [9 empty] | 4816.512
2427101140 | S | Wiring Diagrams |  |  |  | 13354 |  |  | 100% | 13354 | 13354
| 1 | PLC Local Panel Wiring |  |  |  |  | 20% | 1 | [6 empty] | 2670.8
| 2 | PLC Remote Panel Wiring |  |  |  |  | 20% | 1 | [6 empty] | 2670.8
| 3 | Interlock/Interconnect Panel Wiring |  |  |  |  | 20% | 1 | [6 empty] | 2670.8
| 4 | Voltage Taps/QD/DAQ |  |  |  |  | 20% | 1 | [10 empty] | 2670.8
| 5 | Cryo Can Wiring Diagrams |  |  |  |  | 20% | 1 | [6 empty] | 2670.8
2427101145 | S | Rack Maps |  |  |  | 7804 |  |  | 100% | 7804
| 1 | Generate list of racked equipment |  |  |  |  | 10% | 1 |  |  |  |  | 780.4
| 2 | Rack Layout Drawing 1st Draft |  |  |  |  | 50% | 1 |  |  |  |  | 3902
|  | Rack Layout Drawing Final Draft |  |  |  |  | 40% | 1 | [10 empty] | 3121.6
2427101150 | S | Cable Harnesses Design and Materials |  |  |  | 23787 |  |  | 100% | 23787
| 1 | Cryo Service Can thermometry Harnesses |  |  |  |  | 15% | 1 | [8 empty] | 3568.05
| 2 | Cryo Service Can EV Harnesses |  |  |  |  | 10% | 1 | [8 empty] | 2378.7
| 3 | Pressure transducer and dP Harnesses |  |  |  |  | 2.5% | 1 | [8 empty] | 594.675
| 4 | VT Harnesses |  |  |  |  | 7.5% | 1 | [10 empty] | 1784.025
| 5 | Magnet Instrumentation Harnesses |  |  |  |  | 15% | 1 | [8 empty] | 3568.05
| 6 | Load Cell Harnesses |  |  |  |  | 15% | 1 | [8 empty] | 3568.05
| 7 | LV Chassis Harnesses |  |  |  |  | 10% | 1 | [8 empty] | 2378.7
| 8 | Sub-Atmospheric System Harnesses |  |  |  |  | 10% | 1 | [10 empty] | 2378.7
| 9 | Current Limiting Resistor and Voltage Divider Box |  |  |  |  | 10% | 1 | [10 empty] | 2378.7
| 10 | Purchase non-VT cabling |  |  |  |  | 4.9% | 1 | [5 empty] | 1165.563
| 11 | Purchase VT cabling |  |  |  |  | 0.1% | 1 | [10 empty] | 23.787
2427101155 | S | Hall Cable Layouts |  |  |  | 12244 |  |  | 100% | 12244
| 1 | Cable Tray Layouts (from racks to flex point on space frame) |  |  |  |  | 20% | 1 | [7 empty] | 2448.8
| 2 | Flexible cable layouts |  |  |  |  | 20% | 1 | [7 empty] | 2448.8
| 3 | Magnet Cable Layouts (from feedthrough to flex point at Solenoid) |  |  |  |  | 20% | 1 | [8 empty] | 2448.8
| 4 | Service Can Layouts (from feedthroughs to flex point at Solenoid) |  |  |  |  | 20% | 1 | [8 empty] | 2448.8
| 5 | Sub-Atmospheric System Harnesses |  |  |  |  | 20% | 1 | [8 empty] | 2448.8
2427101160 | H | Drawing review and approvals | . |  |  | 1924 |  |  | 0% | 0
2427101165 | H | Racking Procurement Prep |  |  |  | 771 |  | 2 | 100% | 771 |  |  | 771
2427101170 | H | Racking Procurement |  |  |  | 7000 |  | 2 | 100% | 7000 |  |  | 7000 | 3500
2427101175 | H | MPS, PLC and SOE Procurement Prep |  |  |  | 771 |  | 2 | 100% | 771 |  |  |  | 771
2427101180 | S | MPS, SOE, and PLC delivery to Jlab |  |  |  | 85000 |  |  | 100% | 85040
| 1 | PLC Components (Chassis', Power Supplies, PLC, IO Modules, Comm Modules) |  |  |  |  | 30% | 1
| 2 | Valve Actuation Components |  |  |  |  | 7% | 1 | [5 empty] | 5950
| 3 | Temperature Monitoring |  |  |  |  | 8% | 1 | [5 empty] | 6800
| 4 | Liquid Level |  |  |  |  | 10% | 1 | [9 empty] | 8500
| 5 | Ethernet Communications |  |  |  |  | 7.647% | 1 | [5 empty] | 6500
| 6 | Local HMI |  |  |  |  | 7.3% | 1 | [5 empty] | 6205
| 7 | Machining mounting panels |  |  |  |  | 0.1% | 1 | [6 empty] | 85
| 8 | Rack Infrastructure (Part 1 of 2) |  |  |  |  | 14.9% | 1 | [5 empty] | 12665
| 9 | Rack Infrastructure (Part 1 of 2) |  |  |  |  | 0.1% | 1 | [6 empty] | 85
| 10 | Heater Controller Parts |  |  |  |  | 15% | 1 | [8 empty] | 12750
2427101190 | D | Purchase/Fabricate Copper lugs for connections |  |  |  | 3046 |  | 1 | 100% | 3046 | [6 empty] | 3046
2427101195 | H | LCW Lines |  |  |  | 6000 |  | 2 | 100% | 6000 |  |  |  | 3000 |  |  | 3000
2427101200 | S | PLC Programming |  |  |  | 25956 |  |  | 74.75% | 19402.11 | 19402.11
| 1 | Create IO List |  |  |  |  | 5% | 1
| 2 | Configure IO Modules | PCR |  |  |  | 5% | 1
| 3 | Write FastDAQ Processing Routines (transfer from Torus routines) |  |  |  |  | 10% | 1 | [13 empty] | 2595.6
| 4 | FastDAQ Processing Routines (Modify for Solenoid) |  |  |  |  | 5% | 1 | [14 empty] | 1297.8
| 5 | Write Cryo Control Valve Routines (transfer from Torus routines) |  |  |  |  | 2.5% | 1 | [13 empty] | 648.9
| 6 | Cryo Control Valve Routines (Modify for Solenoid) | PCR |  |  |  | 2.5% | 0.7
| 7 | Write Cryo Control PLC-PLC Routines (transfer from Torus routines) |  |  |  |  | 2.5% | 1 | [13 empty] | 648.9
| 8 | Cryo Control PLC-PLC Routines (Modify for Solenoid) | PCR |  |  |  | 2.5% | 1
| 9 | Write Cryo Control Sub-atmospheric Routines (transfer from Torus routines) |  |  |  |  | 2.5% | 1 | [10 empty] | 648.9
| 10 | Cryo Control Sub-atmospheric Routines (Modify for Solenoid) |  |  |  |  | 2.5% | 1 | [10 empty] | 648.9
| 11 | Write Cryo Control Interlock Routines (transfer from Torus routines) |  |  |  |  | 2.5% | 1 | [13 empty] | 648.9
| 12 | Cryo Control Interlock Routines (Modify for Solenoid) | PCR |  |  |  | 2.5%
| 13 | Write Magnet strain/load Interlock Routines (transfer from Torus routines) |  |  |  |  | 2.5% | 1 | [13 empty] | 648.9
| 14 | Magnet strain/load Interlock Routines (Modify for Solenoid) | PCR |  |  |  | 2.5%
| 15 | Write Magnet liquid level Interlock Routines (transfer from Torus routines) |  |  |  |  | 2.5% | 1 | [13 empty] | 648.9
| 16 | Magnet liquid level Interlock Routines (Modify for Solenoid) | PCR |  |  |  | 2.5%
| 17 | Write Magnet VCL flow Interlock Routines (transfer from Torus routines) |  |  |  |  | 2.5% | 1 | [13 empty] | 648.9
| 18 | Magnet VCL flow Interlock Routines (Modify for Solenoid) | PCR |  |  |  | 2.5%
| 19 | Write Magnet vacuum Interlock Routines (transfer from Torus routines) |  |  |  |  | 2.5% | 1 | [13 empty] | 648.9
| 20 | Magnet vacuum Interlock Routines (Modify for Solenoid) | PCR |  |  |  | 2.5%
| 21 | Write Magnet cryo-related Interlock Routines (transfer from Torus routines) |  |  |  |  | 2.5% | 1 | [13 empty] | 648.9
| 22 | Magnet cryo-related Interlock Routines (Modify for Solenoid) | PCR |  |  |  | 2.5%
| 23 | Write SOE Routine (transfer from Torus routines) |  |  |  |  | 8% | 1 | [13 empty] | 2076.48
| 24 | SOE Routine (Modify for Solenoid) | PCR |  |  |  | 2%
| 25 | Write Software Quench Detector Routine (transfer from Torus routines) |  |  |  |  | 10% | 1 | [13 empty] | 2595.6
| 26 | Software Quench Detector Routine (Modify for Solenoid) | PCR |  |  |  | 5%
| 27 | Write Power Supply Control Routine (transfer from Torus routines) |  |  |  |  | 2.5% | 1 | [12 empty] | 648.9
| 28 | Power Supply Control Routine (Modify for Solenoid) | PCR |  |  |  | 2.5%
2427101210 | H | EPICS Specification |  |  |  | 1492 |  | 2 | 100% | 1492 | [7 empty] | 1492
2427101215 | S | PLC Logic Documentation |  |  |  | 6183 |  |  | 0% | 0
| 1 | Cryo control routine description |  |  |  |  | 14.29%
| 2 | Interlock routine description |  |  |  |  | 14.29%
| 3 | SOE Routine description |  |  |  |  | 14.29%
| 4 | Software QD Description |  |  |  |  | 14.29%
| 5 | Power Supply Routine Description |  |  |  |  | 14.29%
| 6 | Alarm Description |  |  |  |  | 14.29%
| 7 | Recovery procedures |  |  |  |  | 14.3%
2427101220 | S | EPICS Programming |  |  |  | 17304 |  |  | 5% | 865.2
| 1 | Set up base ioc | WS |  |  |  | 5% | 0
| 2 | Configure AB Ethernet/IP Driver |  |  |  |  | 5% | 1 | [15 empty] | 865.2
| 3 | Solenoid Cryogenics - Operator screen | WS |  |  |  | 5%
| 4 | Solenoid Power Supply - Expert screen | WS |  |  |  | 10%
| 5 | Solenoid Power Supply - Operator screen | WS |  |  |  | 7.5%
| 6 | Solenoid Interlock Status - Operator screen | WS |  |  |  | 10%
| 7 | Solenoid Interlock Setup - Expert screen | WS |  |  |  | 10%
| 8 | Solenoid Instruments - Operator screen | WS |  |  |  | 10%
| 9 | Solenoid Vacuum - Expert screen | WS |  |  |  | 10%
| 10 | Solenoid Vacuum - Operator screen | WS |  |  |  | 7.5%
| 11 | Solenoid FastDAQ Config - Expert screen | WS |  |  |  | 10%
| 12 | Write Alarm Routines - Vacuum system | WS |  |  |  | 2%
| 13 | Write Alarm Routines - Cryogenics system | WS |  |  |  | 4%
| 14 | Write Alarm Routines -Power Supply system | WS |  |  |  | 4%
2427101225 | S | Fast DAQ Programming |  |  |  | 10666 |  |  | 72.5% | 7732.85
| 1 | Prepare requirement specification for instrumentation (Slow DAQ/LV Chassis) |  |  |  |  | 5% | 1 | [13 empty] | 533.3
| 2 | Copy and modify Torus Slow DAQ to Solenoid Slow DAQ cRIO (LV Chassis) |  |  |  |  | 5% | 1 | [14 empty] | 533.3
| 3 | Modify LV Solenoid cRio to reflect channel numbers and serial numbers |  |  |  |  | 10% | 1 | [14 empty] | 1066.6
| 4 | Modify lookup tables |  |  |  |  | 7.5% | 1 | [14 empty] | 799.95
| 5 | Test and setup spare LV chassis |  |  |  |  | 7.5% | 1 | [14 empty] | 799.95
| 6 | Test and debug Slow DAQ software using dummy loads on LV chassis |  |  |  |  | 7.5% | 1 | [15 empty] | 799.95
| 7 | Verify Slow DAQ PLC communications |  |  |  |  | 7.5% | 1 | [15 empty] | 799.95
| 8 | Prepare requirement specification for voltage taps (Fast DAQ) |  |  |  |  | 5% | 1 | [14 empty] | 533.3
| 9 | Copy and modify Torus Fast DAQ to Solenoid Fast DAQ cRIO |  |  |  |  | 10% | 1 | [14 empty] | 1066.6
| 10 | Set up test to test Fast DAQ software |  |  |  |  | 7.5% | 1 | [15 empty] | 799.95
| 11 | Test and debug Fast DAQ software | CW |  |  |  | 5%
| 12 | Verify Solenoid Fast Daq PLC communications | CW |  |  |  | 7.5%
| 13 | Verify EPICS Fast Daq communications. | CW |  |  |  | 7.5%
| 14 | Pre-commissioning off-line Debugging / Testing Software | CW |  |  |  | 7.5%
2427101230 | S | Populate Racks and Wire Back Panels |  |  |  | 31295 |  |  | 99% | 30982.05
| 1 | PLC LOCAL Panel Hardware Mounting (LVDTs) |  |  |  |  | 3.4% | 1 | [5 empty] | 1064.03
| 2 | PLC LOCAL Panel Hardware Mounting (PLC Modules) |  |  |  |  | 3.4% | 1 | [5 empty] | 1064.03
| 3 | PLC LOCAL Panel Hardware Mounting (PSUs) |  |  |  |  | 3.4% | 1 | [5 empty] | 1064.03
| 4 | PLC LOCAL Panel Hardware Mounting (Breakers) |  |  |  |  | 3.4% | 1 | [5 empty] | 1064.03
| 5 | PLC LOCAL Panel Hardware Mounting (Terminal Blocks) |  |  |  |  | 3.4% | 1 | [5 empty] | 1064.03
| 6 | PLC LOCAL Panel Wiring (LVDTs to Terminal Blocks) |  |  |  |  | 3.4% | 1 | [6 empty] | 1064.03
| 7 | PLC LOCAL Panel Wiring (PLC Modules to Terminal Blocks) |  |  |  |  | 3.4% | 1 | [6 empty] | 1064.03
| 8 | PLC LOCAL Panel Wiring (PSUs to Terminal Blocks) |  |  |  |  | 3.4% | 1 | [5 empty] | 1064.03
| 9 | PLC LOCAL Panel Wiring (Breakers to Terminal Blocks) |  |  |  |  | 3.4% | 1 | [5 empty] | 1064.03
| 10 | PLC REMOTE Panel Hardware Mounting (LVDTs) |  |  |  |  | 3.4% | 1 | [6 empty] | 1064.03
| 11 | PLC REMOTE Panel Hardware Mounting (PLC Modules) |  |  |  |  | 3.4% | 1 | [5 empty] | 1064.03
| 12 | PLC REMOTE Panel Hardware Mounting (PSUs) |  |  |  |  | 3.4% | 1 | [5 empty] | 1064.03
| 13 | PLC REMOTE Panel Hardware Mounting (Breakers) |  |  |  |  | 3.4% | 1 | [5 empty] | 1064.03
| 14 | PLC REMOTE Panel Hardware Mounting (Terminal Blocks) |  |  |  |  | 3.4% | 1 | [6 empty] | 1064.03
| 15 | PLC REMOTE Panel Wiring (LVDTs to Terminal Blocks) |  |  |  |  | 3.4% | 1 | [6 empty] | 1064.03
| 16 | PLC REMOTE Panel Wiring (PLC Modules to Terminal Blocks) |  |  |  |  | 3.4% | 1 | [7 empty] | 1064.03
| 17 | PLC REMOTE Panel Wiring (PSUs to Terminal Blocks) |  |  |  |  | 3.4% | 1 | [6 empty] | 1064.03
| 18 | PLC REMOTE Panel Wiring (Breakers to Terminal Blocks) |  |  |  |  | 3.4% | 1 | [7 empty] | 1064.03
| 19 | Wire I/O Backpanel (Segment #1) |  |  |  |  | 3.3% | 1 | [8 empty] | 1032.735
| 20 | Wire I/O Backpanel (Segment #2) |  |  |  |  | 3.3% | 1 | [12 empty] | 1032.735
| 21 | Wire I/O Backpanel (Segment #3) |  |  |  |  | 3.3% | 1 | [12 empty] | 1032.735
| 22 | Wire I/O Backpanel (Segment #4) |  |  |  |  | 3.3% | 1 | [12 empty] | 1032.735
| 23 | Wire I/O Backpanel (Segment #5) |  |  |  |  | 3.3% | 1 | [12 empty] | 1032.735
| 24 | Wire I/O Backpanel (Segment #6) |  |  |  |  | 3.3% | 1 | [12 empty] | 1032.735
| 25 | Wire voltage tap back panel (Segment #1) |  |  |  |  | 1.7% | 1 | [15 empty] | 532.015
| 26 | Wire voltage tap back panel (Segment #2) |  |  |  |  | 1.7% | 1 | [15 empty] | 532.015
| 27 | Wire voltage tap back panel (Segment #3) |  |  |  |  | 1.7% | 1 | [15 empty] | 532.015
| 28 | Wire voltage tap back panel (Segment #4) |  |  |  |  | 1.7% | 1 | [15 empty] | 532.015
| 29 | Wire voltage tap back panel (Segment #5) |  |  |  |  | 1.7% | 1 | [15 empty] | 532.015
| 30 | Wire voltage tap back panel (Segment #6) |  |  |  |  | 1.7% | 1 | [15 empty] | 532.015
| 31 | Inter-Rack Wiring |  |  |  |  | 3.4% | 1 | [15 empty] | 1064.03
| 32 | Install Backpanels |  |  |  |  | 3.4% | 1 | [13 empty] | 1064.03
| 33 | Install Temp/Level Meters |  |  |  |  | 1% | 1 | [15 empty] | 312.95
| 34 | Install Heater Control Boxes | ES |  |  |  | 1%
2427101235 | S | Sequence of Events Monitor Build |  |  |  | 11972 |  |  | 100% | 11972
| 1 | Install Relays on Rails |  |  |  |  | 10% | 1 |  | 1197.2 | [5 empty] | 1197.2
| 2 | Wire relays to SOE modules |  |  |  |  | 50% | 1 |  | 5986 | [5 empty] | 5986
| 3 | Wire Interlock Chain |  |  |  |  | 40% | 1 |  | 4788.8 | [5 empty] | 4788.8
2427101240 | S | Harness Builds |  |  |  | 20582 |  |  | 100% | 20582
| 1 | Cryo Service Can thermometry Harnesses - PREP |  |  |  |  | 4% | 1 |  | 0 | [6 empty] | 823.28
| 2 | Cryo Service Can thermometry Harnesses - BUILD |  |  |  |  | 4% | 1 | [8 empty] | 823.28
| 3 | Cryo Service Can thermometry Harnesses - TEST |  |  |  |  | 4% | 1 | [9 empty] | 823.28
| 4 | Cryo Service Can EV Harnesses - PREP |  |  |  |  | 4% | 1 | [8 empty] | 823.28
| 5 | Cryo Service Can EV Harnesses - BUILD |  |  |  |  | 4% | 1 | [8 empty] | 823.28
| 6 | Cryo Service Can EV Harnesses - TEST |  |  |  |  | 4% | 1 | [8 empty] | 823.28
| 7 | Pressure transducer and dP Harnesses - PREP |  |  |  |  | 1% | 1 | [9 empty] | 205.82
| 8 | Pressure transducer and dP Harnesses - BUILD |  |  |  |  | 2% | 1 | [9 empty] | 411.64
| 9 | Pressure transducer and dP Harnesses - TEST |  |  |  |  | 2% | 1 | [9 empty] | 411.64
| 10 | VT Harnesses - PREP |  |  |  |  | 4% | 1 | [11 empty] | 823.28
| 11 | VT Harnesses - BUILD |  |  |  |  | 4% | 1 | [12 empty] | 823.28
| 12 | VT Harnesses - TEST |  |  |  |  | 4% | 1 | [13 empty] | 823.28
| 13 | Magnet Instrumentation Harnesses - PREP |  |  |  |  | 4% | 1 | [8 empty] | 823.28
| 14 | Magnet Instrumentation Harnesses - BUILD |  |  |  |  | 5% | 1 | [8 empty] | 1029.1
| 15 | Magnet Instrumentation Harnesses - TEST |  |  |  |  | 4% | 1 | [8 empty] | 823.28
| 16 | Load Cell Harnesses - PREP |  |  |  |  | 4% | 1 |  | 0 | [6 empty] | 823.28
| 17 | Load Cell Harnesses - BUILD |  |  |  |  | 4% | 1 | [9 empty] | 823.28
| 18 | Load Cell Harnesses - TEST |  |  |  |  | 4% | 1 | [9 empty] | 823.28
| 19 | LV Chassis Harnesses - PREP |  |  |  |  | 2% | 1 | [9 empty] | 411.64
| 20 | LV Chassis Harnesses - BUILD |  |  |  |  | 2% | 1 | [9 empty] | 411.64
| 21 | LV Chassis Harnesses - TEST |  |  |  |  | 2% | 1 | [9 empty] | 411.64
| 22 | Sub-Atmospheric System Harnesses - PREP |  |  |  |  | 4% | 1 | [10 empty] | 823.28
| 23 | Sub-Atmospheric System Harnesses - BUILD |  |  |  |  | 4% | 1 | [10 empty] | 823.28
| 24 | Sub-Atmospheric System Harnesses - TEST |  |  |  |  | 4% | 1 | [10 empty] | 823.28
| 25 | Current Limiting Resistors and Voltage Divider Box |  |  |  |  | 16% | 1 | [13 empty] | 3293.12
2427101245 | S | Interface with Cryo |  |  |  | 17533 |  |  | 100% | 17533
| 1 | Rough draft I&C Interface Control Document |  |  |  |  | 75% | 1 |  | 0 | [7 empty] | 13149.75
| 2 | Final I&C Interface Control Document |  |  |  |  | 25% | 1 |  | 0 | 4383.25 | [8 empty] | 4383.25
2427101250 | H | Test Box Design |  |  |  | 8151 | 100% | 2 | 100% | 8151 | [6 empty] | 8151
2427101255 | S | Test Box Build |  |  |  | 11651 |  |  | 100% | 11651
| 1 | Procure parts |  |  |  |  | 5% | 1 |  | 0 | 582.55 | [5 empty] | 582.55
| 2 | Fabricate front panel |  |  |  |  | 5% | 1 |  | 0 | [7 empty] | 582.55
| 3 | Populate Panel With Switches & Test Ports |  |  |  |  | 30% | 1 | [10 empty] | 3495.3
| 4 | Internal Wiring (point to point) |  |  |  |  | 20% | 1 | [12 empty] | 2330.2
| 5 | Adding harness pigtails |  |  |  |  | 20% | 1 | [12 empty] | 2330.2
| 6 | Testing |  |  |  |  | 20% | 1 | [13 empty] | 2330.2
2427101260 | S | Fast DAQ Wiring |  |  |  | 12477 |  |  | 65% | 8110.05
| 1 | Install NI On Din Rail |  |  |  |  | 5% |  |  | 0
| 2 | Install Isolation Amplifiers |  |  |  |  | 5% | 1 |  | 0 | [12 empty] | 623.85
| 3 | Wire Isolation Amplifiers | ES |  |  |  | 20%
| 4 | Install VT Terminal Blocks & Wire from Terminal Blocks to Isolation Amps |  |  |  |  | 10% | 1 | [15 empty] | 1247.7
| 5 | Bench test (Chassis #1) |  |  |  |  | 7.5% | 1 | [6 empty] | 935.775 |  |  |  |  | 935.775
| 6 | Bench test (Chassis #2) |  |  |  |  | 7.5% | 1 | [6 empty] | 935.775 |  |  |  |  | 935.775
| 7 | Install LV Chassis In Racks (#1) |  |  |  |  | 7.5% | 1 | [13 empty] | 935.775
| 8 | Install LV Chassis In Racks (#2) |  |  |  |  | 7.5% | 1 | [13 empty] | 935.775
| 9 | Wire from LV Chassis to NI | ES |  |  |  | 10%
| 10 | Tie cable interlock wiring with the rest of the interlock system |  |  |  |  | 20% | 1 | [15 empty] | 2495.4
2427101265 | S | Cabing in Hall |  |  |  | 14291 |  |  | 95% | 13576.45
| 1 | Install Cable Tray Between Racks and Flex Point on Space Frame |  |  |  |  | 5% | 1
| 2 | Install Cable Tray Between Racks and Subatmospheric system |  |  |  |  | 5% | 1 | [10 empty] | 714.55
| 3 | I/O Panel field wiring (1 of 4) |  |  |  |  | 15% | 1 | [14 empty] | 2143.65
| 4 | DB9 cable testing |  |  |  |  | 2% | 1 | [15 empty] | 285.82
| 5 | I/O Panel field wiring (2 of 4) |  |  |  |  | 15% | 1 | [14 empty] | 2143.65
| 6 | DB9 cable testing |  |  |  |  | 2% | 1 | [15 empty] | 285.82
| 7 | I/O Panel field wiring (3 of 4) |  |  |  |  | 15% | 1 | [14 empty] | 2143.65
| 8 | DB9 cable testing |  |  |  |  | 2% | 1 | [15 empty] | 285.82
| 9 | I/O Panel field wiring (4 of 4) |  |  |  |  | 15% | 1 | [14 empty] | 2143.65
| 10 | DB9 cable testing |  |  |  |  | 2% | 1 | [15 empty] | 285.82
| 11 | Pull Cables from Racks to Subatmospheric System |  |  |  |  | 5% | 1 | [10 empty] | 714.55
| 12 | Pull Cables from Racks to Flex Point on Space Frame |  |  |  |  | 5% | 1 | [14 empty] | 714.55
| 13 | Pull Cables through flex hoses |  |  |  |  | 5% | 1 | [12 empty] | 714.55
| 14 | Pot voltage tap feedthroughs |  |  |  |  | 2% | 1 | [10 empty] | 285.82
| 15 | Route cables from Flex point at solenoid to feedthroughs/valves/PT's |  |  |  |  | 5%
2427101270 | S | Power Supply Integration/Installation |  |  |  | 15577 |  |  | 100%
| 1 | Design/Install LCW System |  |  |  |  | 20% | 1
| 2 | Connect cabinets together |  |  |  |  | 20% | 1 |  |  |  |  | 3115.4
| 3 | Route interlock cables |  |  |  |  | 1% | 1 | [7 empty] | 155.77
| 4 | Connect Interlock Cables |  |  |  |  | 2% | 1 | [7 empty] | 311.54
| 5 | Route communications cables |  |  |  |  | 1% | 1 | [7 empty] | 155.77
| 6 | Connect Communications Cables |  |  |  |  | 2% | 1 | [7 empty] | 311.54
| 7 | Add test points to QDs |  |  |  |  | 4% | 1 | [9 empty] | 623.08
| 8 | Install QD's In Racks |  |  |  |  | 2% | 1 | [7 empty] | 311.54
| 9 | Install Control Crate In Rack |  |  |  |  | 2% | 1 | [7 empty] | 311.54
| 10 | PSU TOSP |  |  |  |  | 3% | 1 |  |  |  |  | 467.31
| 11 | Risk Hazard Assessment |  |  |  |  | 3% | 1 |  |  |  |  | 467.31
| 12 | Test Set up |  |  |  |  | 5% | 1 | [5 empty] | 778.85
| 13 | Hi-Pot Test |  |  |  |  | 5% | 1 | [5 empty] | 778.85
| 14 | Verify operation through short |  |  |  |  | 25% | 1 | [5 empty] | 3894.25
| 15 | Verify operation with PLC |  |  |  |  | 5% | 1 | [8 empty] | 778.85
2427101275 | S | Cryo Service Box Installation (Electrical/Controls) |  |  |  | 56821 |  |  | 10% | 403033.246 | 61258.385
| 1 | Install Pressure Transducers |  |  |  |  | 10%
| 2 | Install Valve Actuators |  |  |  |  | 10%
| 3 | Install Heaters into Can |  |  |  |  | 10%
| 4 | Run heater power from racks to heater feedthrough |  |  |  |  | 10%
| 5 | Install LN2 Level Probe |  |  |  |  | 10%
| 6 | Install Lhe Level Probe |  |  |  |  | 10%
| 7 | Install LN2 dP Transducer |  |  |  |  | 10%
| 8 | Install Lhe dP Transducer |  |  |  |  | 10%
| 9 | Install Instruments on Sub-Atmospheric System |  |  |  |  | 10% | 1 | [10 empty] | 5682.1
| 10 | Verify operation of valves |  |  |  |  | 10%
2427101280 | S | Current Leads Power & Voltage Tap |  |  |  | 11387 |  |  | 100%
| 1 | Leak and flow check leads |  |  |  |  | 6% | 1 |  |  |  |  | 683.22
| 2 | Prep flexible leads for soldering |  |  |  |  | 10% | 1 | [13 empty] | 1138.7
| 3 | Insulate flexible leads |  |  |  |  | 10% | 1 | [15 empty] | 1138.7
| 4 | Prep AMI lead for soldering / drill holes for backing plate - Lead #1 |  |  |  |  | 5% | 1 | [12 empty] | 569.35
|  | Prep AMI lead for soldering / drill holes for backing plate - Lead #2 |  |  |  |  | 5% | 1 | [12 empty] | 569.35
| 5 | Solder Superconductor (flexible leads) into copper bus-bar extension piece for Lead #1 |  |  |  |  | 15% | 1 | [14 empty] | 1708.05
| 6 | Solder Superconductor (flexible leads) into copper bus-bar extension piece for Lead #2 |  |  |  |  | 15% | 1 | [14 empty] | 1708.05
| 7 | Copper extn to AMI lead #1 |  |  |  |  | 10% | 1 | [14 empty] | 1138.7
| 8 | Copper extn to AMI lead #2 |  |  |  |  | 10% | 1 | [14 empty] | 1138.7
| 9 | Adding voltage taps to Lead #1 |  |  |  |  | 2% | 1 | [15 empty] | 227.74
| 10 | Adding voltage taps to Lead #2 |  |  |  |  | 2% | 1 | [15 empty] | 227.74
| 11 | Adding temperature sensors to Lead #1 |  |  |  |  | 2% | 1 | [15 empty] | 227.74
| 12 | Adding temperature sensors to Lead #2 |  |  |  |  | 2% | 1 | [15 empty] | 227.74
| 13 | Final leak check on completed lead |  |  |  |  | 6% | 1 | [15 empty] | 683.22
2427101285 | S | Final Verification Point-to-Point |  |  |  | 14577 |  |  | 0%
| 1 | Ring out Voltage Tap subsystem from test box to connectors |  |  |  |  | 25%
| 3 | Ring out Magnet Temperature harnesses from terminal block to connectors |  |  |  |  | 25%
| 5 | Ring out Service Can Instruments from Terminal Strips to Connectors |  |  |  |  | 25%
| 6 | Ring out EV/PV harnesses from terminal blocks to valves |  |  |  |  | 25%
2427101290 | H | Fast DAQ Hardware/Software Integration debugging |  |  |  | 2230 |  |  | 0%
2427101295 | S | Solenoid - I and C Commissioning (Pump) |  |  |  | 111150 |  |  | 20.1%
AFTER | 1 | Calibrate Pressure Transducers |  |  |  |  | 8%
AFTER | 2 | Verify Operation and readback of valves with PLC |  |  |  |  | 8%
| 3 | Verify readback of subatmospheric system at PLC |  |  |  |  | 6.7% | 1
| 4 | Verify operation of Subatmospheric System with PLC |  |  |  |  | 6.7% | 1
| 5 | Verify readback of subatmospheric system at meters |  |  |  |  | 6.7% | 1
AFTER | 6 | Verify readback of service can instruments at Meters |  |  |  |  | 8%
BEFORE | 7 | Verify Pump Control |  |  |  |  | 8%
BEFORE | 8 | Verify Pump Valve Control |  |  |  |  | 8%
BEFORE | 9 | Verify Pump Instrument Readback |  |  |  |  | 8%
BEFORE | 10 | Top level check on all interlocks ready for PUMPDOWN |  |  |  |  | 8%
BEFORE | 11 | Magnet vacuum interlocks (PUMPDOWN) |  |  |  |  | 8%
BEFORE | 12 | EPICS screens preliminary offline checks (PUMPDOWN) |  |  |  |  | 8%
BEFORE | 13 | EPICS screens (PUMPDOWN) |  |  |  |  | 8%
24271013 | S | Solenoid - I and C Commissioning (Cool) | [6 empty] | 0%
AFTER | 1 | Verify readback of magnet instruments at meters |  |  |  |  | 5.3%
BEFORE | 2 | Test Operation of Interlocks without Magnet Current |  |  |  |  | 5.3%
AFTER | 3 | Move the solenoid and verify readback of instrumentation during/after |  |  |  |  | 5.3%
AFTER | 4 | Top level check on all interlocks ready for COOLDOWN |  |  |  |  | 21.1%
AFTER | 5 | Cryo Control Valves (COOLDOWN) |  |  |  |  | 10.5%
AFTER | 6 | Cryo-control PLC-PLC (COOLDOWN) |  |  |  |  | 10.5%
AFTER | 7 | Magnet cryo-related interlocks (COOLDOWN) |  |  |  |  | 10.5%
AFTER | 8 | Magnet liquid level interlocks (COOLDOWN) |  |  |  |  | 10.5%
BEFORE | 9 | LV Chassis preliminary offline checks (COOLDOWN) |  |  |  |  | 5.3%
AFTER | 10 | LV Chassis (COOLDOWN) |  |  |  |  | 5.3%
BEFORE | 11 | EPICS screens preliminary offline checks (COOLDOWN) |  |  |  |  | 5.3%
AFTER | 12 | EPICS screens (COOLDOWN) |  |  |  |  | 5.3%
2427101305 | S | Solenoid - I and C Commissioning (Energize) | [6 empty] | 0%
BEFORE | 1 | Inject voltages into Test box and verify readout at FastDAQ/PLC |  |  |  |  | 5%
BEFORE | 2 | Inject voltages into Quench Detector and set initial threshold/balance |  |  |  |  | 5%
AFTER | 3 | Verify readback of service can instruments at FastDAQ/PLC |  |  |  |  | 5%
AFTER | 4 | Verify readback of magnet instruments at FastDAQ/PLC |  |  |  |  | 5%
AFTER | 5 | Energize magnet with small current (~5 A) and verify operation of interlocks |  |  |  |  | 5%
BEFORE | 6 | Verify proper operation of FastDAQ through EPICS screens |  |  |  |  | 5%
AFTER | 7 | Top level check on all interlocks ready for ENERGIZATION |  |  |  |  | 20%
BEFORE | 8 | Fast DAQ Preliminary offline checks (ENERGIZATION) |  |  |  |  | 5%
AFTER | 9 | Fast DAQ (ENERGIZATION) |  |  |  |  | 5%
AFTER | 10 | Magnet strain load interlocks (ENERGIZATION) |  |  |  |  | 5%
AFTER | 11 | Magnet VCL flow interlocks (ENERGIZATION) |  |  |  |  | 5%
AFTER | 12 | SOE (ENERGIZATION) |  |  |  |  | 5%
AFTER | 13 | Software quench detector (ENERGIZATION) |  |  |  |  | 5%
BEFORE | 14 | Power supply control preliminary offline checks (ENERGIZATION) |  |  |  |  | 5%
AFTER | 15 | Power supply control (ENERGIZATION) |  |  |  |  | 5%
BEFORE | 16 | EPICS screens preliminary offline checks (ENERGIZATION) |  |  |  |  | 5%
AFTER | 17 | EPICS screens (ENERGIZATION) |  |  |  |  | 5%
[13 empty] | 34526.525 | 84389.913 | 23925.442 | 20555.36 | 60359.1 | 33897.752 | 27684.472 | 11752.08 | 13149.505 | 23513.06 | 21704 | 15453.38 | 0
[13 empty] | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER
[13 empty] | PROGRESS | PROGRESS | PROGRESS | PROGRESS | PROGRESS | PROGRESS | PROGRESS | PROGRESS | PROGRESS | PROGRESS | PROGRESS | PROGRESS | PROGRESS