## SUB-TEAMS and RESPONSIBILITIES
12GeV Upgrade - HALL B SOLENOID SUB TEAMS
COMPRESSED PLAN C - POST MAGNET DELIVERY - Sub Teams and Responsibilities
Version No. | 73 | Updated with training matrix
Date | 05.08.2017
Plan Owner | R. Fair, 12GeV Magnet Task Force Leader (Ext. 6113 or Cell: 518 334 2877)
RESPONSIBILITIES FOR OPERATION OF HALL B SUPERCONDUCTING MAGNET SYSTEMS
B000000901 –S009 Rev - C Responsibilities and Training Plan for Operation of Hall B Superconducting Magnet Systems
|  | Function | Lead | Sub-Team Lead | Shift Lead
|  | SOTR | J. Hogan
|  | INSTALLATION | R. Miller | J. Hogan, D. Kashy | D. Tilles, D. Insley
|  | VACUUM PUMP DOWN | D. Kashy | G. Biallas, R. Fair | D. Insley, D. Anderson
|  | LEAK CHECKS | D. Kashy | G. Biallas, R. Fair | D. Insley, D. Anderson
|  | PURGE AND PURIFICATION | D. Kashy | R. Fair, Cryo Group | D. Insley, D. Anderson
|  | COOL DOWN | D. Kashy | J. Hogan, Cryo Group | D. Insley, K. Bruhwel
|  | POWER UP | R. Fair | P. Ghoshal, R. Rajput-Ghoshal | K. Bruhwel
|  | I AND C | R. Fair | P. Ghoshal
|  | Electromagnetics | R. Rajput-Ghoshal |  | Work Approach
|  | Cryogenics | J. Matalevich |  | Before Magnet Arrives
|  | Mechanical | J. Matalevich |  | 1. Magnet familiarization - J. Hogan
2. Task familiarization - Sub Team Leader
|  | REVIEWS |  |  | 3. Preparation of HBList, THAs, TOSPs, OSPs, Welding ODH document, hot work permits, any other permits - Sub Team Leader
|  | SST Pressure Systems Review | J. Matalevich |  | 4. Ensuring that all relevant training is up-to-date - Sub Team Leader
|  | Magnet Pressure Systems Review | J. Hogan |  | 5. Identification of spares parts, welding supplies and anything else that we might need - Sub Team Leader
|  | Magnet + SST Pressure Systems Review | J. Hogan, J. Matalevich
|  | Cool Down ERR | R. Fair + Team
|  | Power Up ERR | R. Fair + Team |  | After Magnet Arrives - Before Starting Tasks
1. FMEA related to each major task - G. Biallas
2. Daily 'Tool-box' talks (use HBList) before start of task - Sub Team Leader
3. 30 minute overlap between shifts to handover work - Shift Supervisor
SUB-TEAMS TO EXECUTE COMPRESSED PLAN C
|  | Sub-Team | Sub-Team Lead | Team Members | Supervisor | Tentative Dates Required [Shift] |  |  | Available (Y/N?) | Approved (Y/N)? | Comments (e.g. vacation dates or any specific dates when staff may not be available)
|  | Crane | D. Tilles | T. Ewing | D. Tilles | Early May - End Aug [Long day or 1st Shift] |  |  | YES | YES
|  |  |  | C. Mealer | D. Tilles | Early May - End Aug [Long day or 1st Shift] |  |  | YES | YES
|  | Installation | R. Miller | T. Ewing | D. Tilles | Early May - End Aug [Long day or 1st Shift] |  |  | YES | YES
|  |  |  | C. Mealer | D. Tilles | Early May - End Aug [Long day or 1st Shift] |  |  | YES | YES
|  |  |  | K. Tremblay + alignment team | C. Curtis | Late May [Long day or 1st Shift] | Early Jun [Long day or 1st Shift] |  | YES | YES
|  | Welding | J. Matalevich | J. Noble | S. Thompson | Late May-Late Jun [Long day or 1st Shift] |  |  | YES | YES
|  |  |  | L. Biron | S. Thompson | Late May-Late Jun [Long day or 1st Shift] |  |  | YES | YES
|  |  |  | I. Snowburg | S. Thompson | Late May-Late Jun [Long day or 1st Shift] |  |  | YES | YES | Swing Shift
|  |  |  | J. Foyles | T. Carstens | Late Jun [2nd shift] |  |  | YES | YES | Swing Shift
|  |  |  | C. Mealer | D. Tilles | Late Jun [2nd shift] |  |  | YES | YES | Swing Shift
Swing Shift
|  | Leak Checking / Pressure Testing | D. Kashy | D. Anderson | D. Tilles | Early May - End Aug [Long day or 1st Shift] |  |  | YES | YES
|  |  |  | T. Ewing | D. Tilles | Early May - End Aug [Long day or 1st Shift] |  |  | YES | YES
|  |  |  | D. Insley | D. Tilles | Late May [2nd Shift] | Mid Jun [2nd Shift] | Early Jul [2nd Shift] | YES | YES | Swing Shift
|  |  |  | T. Carstens |  |  |  |  | YES | YES | Owl Shift
|  |  |  | P. Williams | S. Thompson | Late May [2nd Shift] | Mid Jun [2nd Shift] | Early Jul [2nd Shift] | YES | YES | Owl Shift
|  |  |  | J. Heckman | A. DiPette | Late May [3rd Shift] | Mid Jun [2nd Shift] | Early Jul [2nd Shift] | YES | YES | Owl Shift
|  |  |  | G. Marble | A. DiPette | Late May [3rd Shift] | Mid Jun [2nd Shift] | Early Jul [2nd Shift] | YES | YES | Swing Shift
|  |  |  | J. Thomason | A. DiPette | Late May [3rd Shift] | Mid Jun [2nd Shift] | Early Jul [2nd Shift] | YES | YES | Swing Shift
|  | I and C | R. Fair | P. Ghoshal | W. Oren | Late May - End Aug [Long day or 2nd Shift] |  |  | YES | YES | Long day or Swing Shift or Saturday
|  |  |  | P. Campero-Rojas | A. Yegneswaran | Early June - End Aug [Long day or 1st Shift] |  |  | YES | YES | Long day or Swing Shift or Saturday
|  |  |  | T. Lemon | A. Yegneswaran | Early June - End Aug [Long day or 1st Shift] |  |  | YES | YES | Long day or Swing Shift or Saturday
|  |  |  | R. Evans | S. Radovic | Mid Jun [Long day or 2nd Shift] |  |  | YES | YES | Long day or Swing Shift or Saturday
|  |  |  | O. Kumar | S. Philip | End Jul - Early Aug [Long day or 1st Shift] |  |  | YES | YES
|  | Splicing | P. Ghoshal | D. Tucker | J. Fischer | Late May (2 days) [1st Shift] | Mid Jun (3 days) [Long day or 2nd Shift] |  | YES | YES | Long day or Swing Shift or Saturday
|  |  |  | T. DeSalvo | J. Fischer | Late May (2 days) [1st Shift] | Mid Jun (3 days) [Long day or 2nd Shift] |  | YES | YES | Long day or Swing Shift or Saturday
|  | Vacuum System | G. Biallas | D. Anderson | D. Tilles | Early May - End Aug [Long day or 1st Shift] |  |  | YES | YES
|  |  |  | S. Spiegel | T. Carstens | Early June - End Aug [Long day or 1st Shift] |  |  | YES | YES
|  |  |  | B. Shinault | E. Stallworth | Mid-Jul [Long day or 1st Shift] |  |  | YES | YES
|  |  |  | W. Formichelli | E. Stallworth | Mid-Jul [Long day or 1st Shift] |  |  | YES | YES
|  | Standby | R. Fair | N. Sandoval | T. Carstens | Early June - End Aug [After hours] |  |  | YES | YES | Long day or Swing Shift or Saturday
|  |  |  | W. Moore | K. Edwards | Early June - End Aug [After hours] |  |  | YES | YES | Long day or Swing Shift or Saturday
|  |  |  | S. Spiegel | T. Carstens | Early June - End Aug [Long day or 1st Shift] |  |  | YES | YES | Long day or Swing Shift or Saturday
|  |  |  | M. Lester | E. Stallworth | Early June - End Aug [Long day or 1st Shift] |  |  | YES | YES | Long day or Swing Shift or Saturday
|  |  |  | B. Eng | A. Yegneswaran | Early June - End Aug [After hours] |  |  | YES | YES | Long day or Swing Shift or Saturday
|  |  | Total no. team members | 37 | [5 empty] | Team Members | Work Periods
|  |  | No. who may have to work long days, shifts or Saturdays | 26 | [5 empty] | I. Snowburg | Swing Shift
[10 empty] | J. Foyles | Swing Shift
[10 empty] | C. Mealer | Swing Shift
[10 empty] | D. Insley | Swing Shift
[10 empty] | T. Carstens | Owl Shift
[10 empty] | P. Williams | Owl Shift
[10 empty] | J. Heckman | Owl Shift
[10 empty] | G. Marble | Swing Shift
[10 empty] | J. Thomason | Swing Shift
[10 empty] | P. Ghoshal | Long day or Swing Shift or Saturday
[10 empty] | P. Campero-Rojas | Long day or Swing Shift or Saturday
[10 empty] | T. Lemon | Long day or Swing Shift or Saturday
[10 empty] | R. Evans | Long day or Swing Shift or Saturday
[10 empty] | D. Tucker | Long day or Swing Shift or Saturday
[10 empty] | T. DeSalvo | Long day or Swing Shift or Saturday
[10 empty] | N. Sandoval | Long day or Swing Shift or Saturday
[10 empty] | W. Moore | Long day or Swing Shift or Saturday
[10 empty] | S. Spiegel | Long day or Swing Shift or Saturday
[10 empty] | M. Lester | Long day or Swing Shift or Saturday
[10 empty] | B. Eng | Long day or Swing Shift or Saturday
[10 empty] | R. Fair | Long day or Swing Shift or Saturday
[10 empty] | J. Matalevich | Long day or Swing Shift or Saturday
[10 empty] | D. Kashy | Long day or Swing Shift or Saturday
[10 empty] | D. Tilles | Long day or Swing Shift or Saturday
[10 empty] | G. Biallas | Long day or Swing Shift or Saturday
[10 empty] | R. Miller | Long day or Swing Shift or Saturday

## TRAINING MATRIX
12GeV Upgrade - HALL B SOLENOID SUB TEAMS
COMPRESSED PLAN C - POST MAGNET DELIVERY - Sub Teams Training Matrix
Version No. | 7f | Updated training
Date | 05.30.17
Plan Owner | R. Fair, 12GeV Magnet Task Force Leader (Ext. 6113 or Cell: 518 334 2877)
|  | TRAINING MATRIX |  |  | Not taken yet
Not taken but not required for this staff member
Where indicated dates in parentheses are training expiration dates
|  | Staff | SAF302 | SAF202 | SAF202B | SAF307 | SAF104 | SAF111 | SAF103 | SAF801C | SAF116KD
|  |  | Aerial Platform Training | Personal Fall Training | Personal Fall Training (site Specific) | Ladder Safety | Lock, Tag and Try | Hall B Safety Awareness Training | ODH | Radiation Worker 1 | Physics Division Work Governance
|  | D. Anderson | Y | Y | Y | Y | Y | Y | Y | Y | Y
|  | G. Biallas | N | Y | N | Y | Y | Y | Y | Y | Y
|  | L. Biron | Y | Y | Y | Y | Y | Y | Y | Y | Y
|  | P. Campero-Rojas | Y(3/16/20) | Y(3/27/20) | Y(3/27/20) | Y(3/3/19) | N | Y | Y(3/22/18) | Y(03/21/18) | Y(12/31/17)
|  | T. Carstens | Y | Y | Y | Y | Y | Y | Y | Y | Y
|  | T. DeSalvo | Y | Y | Y | Y | Y | Y | Y | Y | Y
|  | B. Eng | Y (03/16/20) | Y | Y (05/02/20) | Y (05/01/19) | N | Y | Y (9/23/2018) | Y (05/05/18) | Y
|  | R. Evans | N | Y | Y | Y | Y | Y | Y | Y | N
|  | T. Ewing | Y | Y | Y | Y | Y | Y | Y | Y | Y
|  | R. Fair | Y | Y | Y (04/26/20) | Y (05/01/19) | Y (12/17/18) | Y | Y (09/29/18) | Y (10/17/2018) | Y (12/31/17)
|  | W. Formichelli | N | Y | Y | Y | Y | Y | Y | Y | Y
|  | J. Foyles | Y | Y | Y | Y | Y | Y | Y | Y | Y
|  | P. Ghoshal | N | Y | Y | Y | Y | Y | Y | Y | Y
|  | J. Heckman | N | Y | Y | Y | Y | Y | Y | Y | Y
|  | D. Insley | Y | Y | Y | Y | Y | Y | Y | Y | Y
|  | D. Kashy | Y | Y | Y | Y | Y | Y | Y | Y | Y
|  | O. Kumar | N | N | N | Y | Y | Y | Y | Y | Y
|  | T. Lemon | Y (03/16/20) | Y (03/27/20) | Y (03/27/20) | Y (01/04/18) | Y (05/01/20) | Y | Y (11/17/17) | Y (01/18/17) | Y
|  | M. Lester | Y | Y | N | Y (09/08/18) | N | Y | Y (07/2118) | Y (08/12/18) | Y
|  | G. Marble | Y | Y | Y | Y | Y | Y | Y | Y | Y
|  | J. Matalevich | N | N | N | N | Y | Y | Y | Y | Y
|  | C. Mealer | Y | Y | Y | Y | Y | Y | Y | Y | Y
|  | R. Miller | N | Y | Y | Y | N | Y | Y | Y | Y
|  | W. Moore | N | N | N | N | N | Y | Y | Y | N
|  | J. Noble | Y | Y | Y | Y | Y | Y | Y | Y | Y
|  | R. Rajput-Ghoshal | Y | Y | Y | Y | Y | Y | Y | Y | Y
|  | N. Sandoval | Y | Y | Y (Dec 2017) | Y (Dec 2017) | Y (Dec 2017) | Y (Dec 2017) | Y (Dec 2017) | Y (Dec 2017) | Y
|  | B. Shinault | N | Y | Y | Y | Y | Y | Y | Y | Y
|  | I. Snowburg | Y | Y | Y | Y | Y | Y | Y | Y | Y
|  | S. Spiegel | Y (01/10/20) | Y (02/28/19) | Y (02/28/19) | Y (04/27/19) | Y (04/11/19) | Y | Y (02/07/19) | Y | Y
|  | J. Thomason | Y | Y | Y | Y | Y | Y | Y | Y | Y
|  | D. Tilles | Y | Y | Y | Y | Y | Y | Y | Y | Y
|  | M. Todd | N | Y | Y | Y | Y | Y | Y | Y | Y
|  | K. Tremblay | N | N | N | N | Y | Y | Y | Y | Y
|  | D. Tucker | Y | Y | Y | Y | Y | Y | Y | Y | Y
|  | P. Williams | N | Y | Y | Y | Y | Y | Y | Y | Y