## Sheet1
RICH Installation Schedule
Date | Task | Manpower Lead
2017-12-18 | Move transport trolley to the EEL building | Doug
| Develop lift plan to place the RICH on the trolley | Mark Loewus
| Develop cable strain reliefs for two 110 mm diameter cable bundles | Cyril
2017-12-19 | Install RICH on trolley | Mark Loewus / Sandro
2018-01-02 | Decable RICH. Prepare crates and cables for transport to the Hall | Marc McMullen
| Disconnect downstream beam line | Doug
| Move forward carriage to maintenance position | Doug
| Install transport skid on to the truck | Doug
| Develop lift plan to put RICH on the truck | Doug
| Develop lift plan to put RICH on the A-frame | Doug
| Develop lift plan to install RICH on the forward carriage | Doug
2017-01-03 | Set up A-frame in the Hall, install strongback on A-frame | Doug
| Transport crates and cables to the Hall | Doug
| Install crates and run cables | Marc McMullen
| Clear space in Target area for RICH and truck | Doug
2017-01-04 | Place RICH on the truck | Doug / Sandro
| Tranport to the Hall | Doug / Sandro
| Place RICH on the A-frame / remove stiffener | Doug / Sandro
| Tranport gas panel to the Hall | Doug / Sandro
| Install gas panel on forward carriage | Doug / Sandro
| Connect N2 purge | Marc McMullen
2017-01-05 | Install RICH on forward carriage | Doug / Sandro
5-7 Jan | Cable RICH | Marc / Sandro
2017-01-08 | As-found survey of RICH | Kelly Tremblay
2017-01-10 | Move forward carriage to installed position | Doug
| Install downstream beam line | Doug
2017-01-11 | Transport spare compressor to the hall and install on forward carriage | Doug
| Remove tooling from the Hall | Doug