## Sheet1
Charge | Recommendation | Response | Status
1 Has the entire beamline and detector configuration been defined, including ownership, maintenance and control during beam operations? | • It was not clear from the presentations who is responsible for construction of the target. This must be defined. | RESPONSE: The target design follows largely the previous BONuS6 layout. It will be made out of similar parts, with similar components. A design drawing for the new target (by M. Zarecky) exists. The ODU group, let by S. Bültmann, will continue to work with a JLab designer to complete all remaining design tasks, and will continue to be responsible for all tests. Some small parts will be made by the Jefferson Lab machine shop. The target will be assembled by the ODU group, with help (if needed) from Jefferson Lab experts or consultants. The existing gas supply system (from BONuS6) will be refurbished by the ODU group with help from Jefferson Lab technicians (G. Jacobs). Operational procedures and safety manuals will be written by S. Bültmann. Once the target is constructed, it will be tested and validated with involvement of a Jefferson Lab engineer (R. Miller) and the assigned design authority, M. Marchlik. | Amrit is aware of their expectation to supply a gas system for this target though it has not been completed as of 1/29/19
2 Are the beam commissioning procedures and machine protection systems sufficiently defined for this stage? | Recommendation: • None |  | Complete
3 What is the status of the equipment towards operation? What are the completion/commissioning schedule and tasks? | Recommendations: • The schedule as presented did not contain float and some dependencies were missing. It needs to be revisited to identify critical paths, efficiencies and to ensure that it is credible. The final schedule should contain at least three months of float before installation. • JLab personnel are relied on in the schedule. The scope and availability should be defined. | RESPONSE: As described above, the updated schedule fulfilling these requirements is attached. We have listed the Jefferson Lab personnel involved in the project by name and confirmed their availability. | I Did not get the schedule
4. Are the responsibilities for carrying out each job identified, and are the manpower and other resources necessary to complete them on time in place? | Recommendation: • The MVT/micromegas must be de-installed before BONUS is installed and re-installed after. o The group responsible for this work should be identified. o The procedures that are involved should also be defined. | RESPONSE: The ODU group has spent significant time observing and discussing with the visiting scientists and engineers from Saclay as they were installing the micro-MEGAs vertex trackers. We have developed a plan that minimizes potential risks and simplifies the changeovers: 1. We will obtain our own set of micro-coax ribbon cables dedicated for the RTPC. That way, the barrel micro-MEGAs can be unmounted as a unit, with their cables attached, and safely stored without disassembly. 2. We agree with the Saclay group that the changeover (both before and after BONUS12 runs) will require the presence, for about 1 week, of a detector engineer and an electronics engineer from Saclay, both to properly safeguard the detector and to help with initial checkout of the electronics after both changeovers. Additionally, Hall B technicians will work with the ODU group to remove the central vertex tracker assembly from the Hall, separate the micro-MEGAs from the SVT, and exchange the Barrel micro-MEGAs with the BONUS12 RTPC. The time plan is laid out in detail as a separate entry in the overall schedule. | Did we get a copy of these plans and procedures?
5. Parameters and status of the target system to be used. The following points must be addressed: a. Have all EHS&Q considerations being included in the design, i.e. pressure vessel requirements and fire risk? b. Have all the operational procedures, like those for changing target material (deuterium, hydrogen, helium) been defined, approved and in place? | Recommendations: • Pressure vessel paperwork and review must be finalized. • The operational procedure documents presented to the committee are not complete and need to be finalized. • Training requirements for operators need to be defined. | RESPONSE: We have identified the path to completion and the responsible personnel (see above). S. Bültmann will complete the required documents (OPS and safety) and training requirements once the target has been built. The final review will involve a second design authority and the Hall B engineer, R. Miller. This can take place anytime after August 1, 2018, when the target will be completed. | Documents and training were not sufficantly addressed in the response. We will take care of it later is not an answer
6. What is the RTPC status? Has it been demonstrated for readiness to operate and to achieve the scientific goals of the experiment? The following points must be addressed: 1. Interfacing with the CLAS12 configuration 2. RTPC operation and calibration 3. GEM reconstruction efficiency 4. d. Readout electronics (what is the event rate that can be handled?) | Recommendations: • If not already the case, the helium envelope around the target is should be exhausted outside the hall. | RESPONSE: This has been already confirmed during the ERR presentation and was done during the previous two experiments using a similar RTPC. | Complete
7. Are the radiation levels expected to be generated in the hall acceptable? Is any local shielding required to minimize the effects of radiation in the hall equipment? | Recommendations: • None. |  | Complete