## Sheet1
TJNAF Project Procurement Plans: FY25 / FY26 / FY27
PD/PM/PCA Estimates as of March 5, 2025 ; Reality will depend on Funding and CD Dates
PROJECT | PROCUREMENT DESCRIPTION | VALUE ($K) estimated | SOLE SOURCE (Y or N) | VENDOR (DOMESTIC (D) or FOREIGN (F)) | CONSTRUCTION TYPE (Fabrication Supply or Construction) | FY25 / FY26 / FY27 (If Known) | COMMENTS
CRE | ARC Renovation | $42,500K | N | D | Con | FY26 | RFP & Award Package Review
CRE | CEBAF Center Renovation | $9,350K | N | D | Con | FY27 | APP, RFP, & Award Package Review
CRE | ARC A/E Construction Support | $1,075K | Y | D | Con | FY26 | Sole source to Clark Nexsen
CRE | ARC Safety Professional Support | $500K | N | D | Con | FY26 | Full time safety professional to support ARC Renovation
CRE | CEBAF Center A/E Construction Support | $750K | Y | D | Con | FY27 | Sole source to Clark Nexsen
CRE | Civil and Site Improvements Design | $400K | Y | D | Con | FY25 | Sole source to Clark Nexsen
MOLLER | Collimators #1 and #2 | $761K | Y | F | Fab | FY25 | Currently out for RFQ
MOLLER | Target Controls and Instrumentation | $165K | TBD | TBD | Fab | FY25 | Vesda H2 sniffer, cables, connectors, chassis components remaining
MOLLER | Cable Management Systems | $207K | TBD | TBD | Fab | FY25 | 80% awarded
MOLLER | US Toroid Bunker (barite concrete) | $142K | TBD | TBD | Fab | FY25 | RFQ deadline 2/15/2025
MOLLER | HV Cabling | $228K | TBD | TBD | Fab | FY25 | Out for bid since 2/14/2025
MOLLER | US Toroid Enclosure | $289K | TBD | TBD | Fab | FY25
MOLLER | Concrete Blocks MPS Hut - 2nd Half | $232K | TBD | TBD | Fab | FY26 | Option in award for 10603075
MOLLER | Thin Quartz Detector Modules | $228K | TBD | TBD | Fab | FY26
MOLLER | Shower Max Detector Modules | $142K | TBD | TBD | Fab | FY26
HPDF
HPDF
HPDF
JLDC | JLDC Shell Design AE Completion of Shell Design | $1,200k | Y | D | Con | FY25 | Sole source to SmithGroup
JLDC | JLDC Shell General Construction | $31,000k | N | D | Con | FY27 | APP, RFP, & Award Package Review
JLDC | JLDC Shell A/E Construction Support | $1,000k | Y | D | Con | FY27 | Sole source to SmithGroup
JLDC | JLDC Shell CM & CX during Construction | $1,000k | Y | D | Con | FY27 | Sole Source to Hill-Baker, may be self-performed
JLDC | JLDC Fitout Design Contract | $3,000k | Y | D | Con | FY25 | Sole source to SmithGroup, after HPDF CD-1
JLDC | JLDC Fitout CM during Design Contract | $600k | Y | D | Con | FY25 | Sole source to Hill-Baker, after HPDF CD-1
JLDC | JLDC Fitout General Construction | $130,000k | N | D | Con | FY28 | APP, RFP, & Award Package Review
JLDC | JLDC Fitout A/E Construction Support | $2,600k | Y | D | Con | FY28 | Sole source to SmithGroup, after HPDF CD-2
JLDC | JLDC Fitout CM & CX during Construction | $3,000k | Y | D | Con | FY28 | Sole source to Hill-Baker, after HPDF CD-2
EIC TJ | 2K Satellite Refrigerator Plant - IR10 | $12,786K |  |  | Fab | FY25 | EIC TJ data doesn't reflect any load leveling or matching to FY funding.
EIC TJ | Silicon Trackers - PED | $5,734K |  |  | Fab | FY26
EIC TJ | JLab Cavity Processing Facility - BCP & Horizontal EP | $2,920K |  |  | Fab | FY25
EIC TJ | ESR APS Magnets - Mag Measurement Procurements Batch 2 | $563K |  |  | Fab | FY25
EIC TJ | ESR APS Magnets - Mag Processing: Storage, Supplies & Equipment (PED) | $396K |  |  | Fab | FY25
EIC TJ | ESR APS Magnets - Mag Parts replacement coils (PED) | $70K |  |  | Fab | FY25
EIC TJ | ESR APS Mag - Magnet Refurbishment Parts - Batch 2 | $1,200K |  |  | Fab | FY25
EIC TJ | ESR APS Magnets - Mag Rebuild Parts - OBL - Batch 2 | $352K |  |  | Fab | FY25
EIC TJ | 591 MHz 1-Cell 1st Art - Cavity | $422K |  |  | Fab | FY25
EIC TJ | 591 MHz 1-Cell 1st Art - Beamline Components | $342K |  |  | Fab | FY26
EIC TJ | 591 MHz 1-Cell 1st Art - End Cans | $302K |  |  | Fab | FY26
EIC TJ | JLab Cavity Processing Facilities - Dewar #9 | $680K |  |  | Fab | FY25
EIC TJ | JLab Cavity Processing Facilities - Misc. Tooling | $554K |  |  | Fab | FY25
EIC TJ | MPGD Trackers - Procurement - FY26 | $764K |  |  | Fab | FY26
EIC TJ | Detector Solenoid - Solenoid Conductor | $1,961K |  |  | Fab
EIC TJ | Detector Solenoid - Magnet Power Supply | $583K |  |  | Fab | FY25
EIC TJ | ESR APS Magnets - Magnet Measurement Procurements - Batch 1 (PED) | $70K |  |  | Fab | FY25
EIC TJ | ESR APS Magnets - Magnet Measurement Stand 1 - MODS to ANL stand (PED) | $91K |  |  | Fab | FY25
EIC TJ | ESR APS Magnets - Magnet Measurement Stand 2 | $90K |  |  | Fab | FY25
EIC TJ | ESR APS Magnets - Magnet Rebuild Parts - Batch 1 (PED) | $61K |  |  | Fab | FY25
EIC TJ | 591 MHz 1-Cell 1st Art - Beamline Gate Valves | $262K |  |  | Fab | FY26
EIC TJ | 591 MHz 1-Cell 1st Art - Helium Vessel | $111K |  |  | Fab | FY25
EIC TJ | 591 MHz 1-Cell 1st Art - Tuner Test Hardware | $95K |  |  | Fab | FY25
EIC TJ | 591 MHz 1-Cell 1st Art - Instrumentation | $91K |  |  | Fab | FY25
EIC TJ | 591 MHz 1-Cell 1st Art - Misc. Parts | $200K |  |  | Fab | FY26
EIC TJ | 591 MHz 1-Cell 1st Art - Shipping Support | $62K |  |  | Fab | FY26
EIC TJ | JLab Cavity Processing Facilities - Ultrasonic Cleaning Station | $212K |  |  | Fab | FY25
EIC TJ | JLab Cavity Processing Facilities - Bake Box | $224K |  |  | Fab | FY26
EIC TJ | 197 MHz Crab Design Verification - Cavity Handling Tooling | $118K |  |  | Fab | FY25
EIC TJ | 197 MHz Crab Design Verification - Crab Cavity Pole | $65K |  |  | Fab | FY25
EIC TJ | Silicon Trackers - Oxford PED - Procurement | $31K |  |  | Fab | FY25
EIC TJ | FTOF - Cooling - PED | $76K |  |  | Fab | FY26
EIC TJ | FTOF - Integration - PED | $76K |  |  | Fab | FY26
EIC TJ | FTOF - Mechanical - PED | $76K |  |  | Fab | FY26
EIC TJ | CERN - VTRX+ Optical Tranceiver Module | $1,397K |  |  | Fab | FY26
EIC TJ | CERN - lpGBT Transceiver ASIC | $71K |  |  | Fab | FY26
EIC TJ | DAQ - DAM Board Hardware - Fabrication Engineering Article | $127K |  |  | Fab | FY25
EIC TJ | RCS Magnet Dipoles - First Article Magnets - Vendor A | $616K |  |  | Fab | FY26
EIC TJ | RCS Magnet Dipoles - First Article Magnets - Vendor B | $616K |  |  | Fab | FY26
EIC TJ | RCS Magnet Dipoles - Production Magnet Material - Vendor A - Groups 1 and 2 | $1,704K |  |  | Fab | FY26
EIC TJ | RCS Magnet Dipoles - Production Magnets - Vendor A - Groups 1 and 2 | $2,300K |  |  | Fab | FY26
EIC TJ | RCS Magnet Dipoles - Production Magnets Material - Vendor B - Groups 1 and 2 | $1,704K |  |  | Fab | FY26
EIC TJ | RCS Magnet Dipoles - Production Magnets - Vendor B - Groups 1 and 2 | $2,300K |  |  | Fab | FY26
EIC TJ | RCS Magnet Dipoles - Magnet Measurement Power Supply | $343K |  |  | Fab | FY26
EIC TJ | RCS Magnet Dipoles - Magnet Measurement Facilities Procurements | $347K |  |  | Fab | FY26
EIC TJ | 197 MHz Crab 1st Art - First Article Cavities - Raw Niobium | $1,034K |  |  | Fab | FY26
EIC TJ | 197 MHz Crab 1st Art - First Article Vacuum Vessel | $403K |  |  | Fab | FY27
EIC TJ | 591MHz 1-Cell Production - Helium Vessel | $1.030K |  |  | Fab | FY27
EIC TJ | 591 MHz 1-Cell Production - Production Mag Shields | $395K |  |  | Fab | FY27
EIC TJ | 591 MHz 1-Cell Production - Production Thermal Shield | $492K |  |  | Fab | FY27
EIC TJ | 591 MHz 1-Cell Production - Production Heat Exchangers | $854K |  |  | Fab | FY27
EIC TJ | 591 MHz 1-Cell Production - Production Vacuum Vessel | $1,665K |  |  | Fab | FY27
EIC TJ | 591 MHz 1-Cell Production - Production Saddles and Stands | $577K |  |  | Fab | FY27
EIC TJ | 591 MHz 1-Cell Production - Production Instrumentation | $846K |  |  | Fab | FY27
EIC TJ | 591 MHz 1-Cell Production - Production Misc. Parts | $1,782K |  |  | Fab | FY27
EIC TJ | JLab Cavity Processing Facilities - Heat Treatment Furnace | $2,023K |  |  | Fab | FY26
EIC TJ | FTOF - Sensor-ASIC Integration | $321K |  |  | Fab | FY26
EIC TJ | RCS Magnet Dipoles - Magnet Measurement Stand | $272K |  |  | Fab | FY26
EIC TJ | 197 MHz Crab 1st Art - First Article Beamline Gate Valves | $121K |  |  | Fab | FY26
EIC TJ | 591 MHz 1-Cell 1st Art - Vacuum Vessel | $201K |  |  | Fab | FY26
EIC TJ | BTOF - Cooling - PED | $229K |  |  | Fab | FY26
EIC TJ | BTOF - Integration - PED | $229K |  |  | Fab | FY26
EIC TJ | BTOF - Mechanical - PED | $229K |  |  | Fab | FY26
EIC TJ | BTOF - Module | $285K |  |  | Fab | FY26
EIC TJ | FTOF - Module Assembly | $327K |  |  | Fab | FY26
EIC TJ | 2K Satellite Refrigerator Plant - IR06 | $13,492K |  |  | Fab | FY27
EIC TJ | 2K Distrib. & 4K HSR - Award 2K Distrib. Systems Sub- Contract - IR10 | $11,253K |  |  | Fab | FY27
EIC TJ | Silicon Trackers - Procurement - FY27 | $5,517K |  |  | Fab | FY27
EIC TJ | 591MHz 1-Cell Production - Beamline Component | $3,021K |  |  | Fab | FY27
EIC TJ | 591MHz 1-Cell Production - Beamline Gate Valves | $3,921K |  |  | Fab | FY27
EIC TJ | 591 MHz 1-Cell Production - Production End Cans | $2,658K |  |  | Fab | FY27
EIC TJ | 591MHz 5-Cell Production - Production Cavities | $4,322K |  |  | Fab | FY27
EIC TJ | 591MHz 5-Cell Production - Beamline Component | $3,207K |  |  | Fab | FY27
EIC TJ | 591MHz 5-Cell Production - Beamline Gate Valves | $3,207K |  |  | Fab | FY27
EIC TJ | MPGD Trackers - Procurement - FY27 | $1,619K |  |  | Fab | FY27
EIC TJ | DAQ - DAM Board Hardware - Fabrication of Production Units | $2,822K |  |  | Fab | FY27
EIC TJ | ESR Quad 2 Magnets - First Article Magnets | $309K |  |  | Fab | FY27
EIC TJ | 197 MHz Crab 1st Art - First Article Cavities | $1,065K |  |  | Fab | FY27
EIC TJ | 197 MHz Crab 1st Art - First Article Helium Vessel | $539K |  |  | Fab | FY27
EIC TJ | 197 MHz Crab 1st Art - First Article Beamline Components | $320K |  |  | Fab | FY27
EIC TJ | 591MHz 1-Cell Production - Cavities | $2,090K |  |  | Fab | FY27
EIC TJ | 591 MHz 1-Cell Production - Production Spaceframes with Thermal Shield Assy | $500K |  |  | Fab | FY27
EIC TJ | 591MHz 5-Cell Production - Helium Vessel | $1,521K |  |  | Fab | FY27
EIC TJ | 591MHz 5-Cell Production - Production Mag Shields | $347K |  |  | Fab | FY27
EIC TJ | 591MHz 5-Cell Production - Production Thermal Shield | $434K |  |  | Fab | FY27
EIC TJ | 591MHz 5-Cell Production - Production Spaceframes with Thermal Shield Assembly | $441K |  |  | Fab | FY27
EIC TJ | 591MHz 5-Cell Production - Production End Cans | $2,329K |  |  | Fab | FY27
EIC TJ | 591MHz 5-Cell Production - Production Heat Exchanger | $750K |  |  | Fab | FY27
EIC TJ | 591MHz 5-Cell Production - Production Vacuum Vessel | $1,255K |  |  | Fab | FY27
EIC TJ | 591MHz 5-Cell Production - Production Saddles and Stands | $508K |  |  | Fab | FY27
EIC TJ | 591MHz 5-Cell Production - Production Instrumentation | $430K |  |  | Fab | FY27
EIC TJ | 2K Distrib&4K HSR -Award Forward Magnet 2K Cryostat/Valve Box SubContract - IR06 | $968K |  |  | Fab | FY27
EIC TJ | hpDIRC - Prisms | $652K |  |  | Fab | FY27
EIC TJ | pfRICH - Mirrors - Inner and Outer Conical Mirror Set | $421K |  |  | Fab | FY27
EIC TJ | BTOF - Sensor - ASIC Integration | $823K |  |  | Fab | FY27
EIC TJ | BTOF - Flex Module - PCB | $1,751K |  |  | Fab | FY27
EIC TJ | FTOF - Sensor | $465K |  |  | Fab | FY27
EIC TJ | Detector Solenoid - Cryocan and CryoFlex Line | $606K |  |  | Fab | FY27
EIC TJ | Inner Gas Barrel Tracking - SALSA FEB | $331K |  |  | Fab | FY27
EIC TJ | BTOF - CTTL AC-LGAD - Service Hybrid - Production | $355K |  |  | Fab | FY27
EIC TJ | FTOF - FTTL AC-LGAD - Service Hybrid & Module - Production - Fab & Asy | $257K |  |  | Fab | FY27
EIC TJ | Forward pECAL - PCB - HV/Anode/LED - Interface Components | $601K |  |  | Fab | FY27
EIC TJ | Forward pECAL - PCB - Assembly | $490K |  |  | Fab | FY27
EIC TJ | Forward LFHCAL - FEB - Readout Electronics | $780K |  |  | Fab | FY27
EIC TJ | Calorimeter Digitizers - Discrete/HGCROC 64-Channel ADC PCB - Supporting PCB and Hardware | $106K |  |  | Fab | FY27
EIC TJ | Electrtronics - Procurements | $1,473K |  |  | Fab | FY27
EIC TJ | DAQ - Fiber Connectors | $329K |  |  | Fab | FY27
EIC TJ | 197 MHz Crab 1st Art - Rail Assembly Tooling | $147K |  |  | Fab | FY27
EIC TJ | 197 MHz Crab 1st Art - First Article Tuner Frames and Thermal Straps | $105K |  |  | Fab | FY27
EIC TJ | 197 MHz Crab 1st Art - First Article Thermal Shield | $140K |  |  | Fab | FY27
EIC TJ | 197 MHz Crab 1st Art - First Article Spaceframes with Thermal Shield Assy | $109K |  |  | Fab | FY27
EIC TJ | 197 MHz Crab 1st Art - First Article End Cans | $265K |  |  | Fab | FY27
EIC TJ | 197 MHz Crab 1st Art - First Article Misc. Parts | $177K |  |  | Fab | FY27
EIC TJ | 591 MHz 1-Cell Production - Production Tuner Frames and Thermal Straps | $224K |  |  | Fab | FY27
EIC TJ | 591MHz 5-Cell Production - Production Tuner Frames and Thermal Straps | $196K |  |  | Fab | FY27
EIC TJ | RCS Harmonic Injection Kicker - 148MHz Cavity Material and Parts | $187K |  |  | Fab | FY27
EIC TJ | RCS Harmonic Injection Kicker - 296MHz Cavity Material and Parts | $150K |  |  | Fab | FY27
EIC TJ | RCS Harmonic Injection Kicker - 148MHz Cavity Fabrication Service | $199K |  |  | Fab | FY27
EIC TJ | RCS Harmonic Injection Kicker - 296MHz Cavity Fabrication Service | $162K |  |  | Fab | FY27
EIC TJ | RCS Harmonic Injection Kicker - First Article - RF Source | $224K |  |  | Fab | FY27
EIC TJ | RCS Harmonic Injection Kicker - Protoype RF Power Distribution Network Hardware | $187K |  |  | Fab | FY27
EIC TJ | RCS Harmonic Injection Kicker - LLRF First Article Chasis Components | $125K |  |  | Fab | FY27
EIC TJ | hpDIRC - Slow Control/GUI/Software Development | $125K |  |  | Fab | FY27
EIC TJ | hpDIRC - Light Monitoring System | $125K |  |  | Fab | FY27
EIC TJ | dRICH - SiPMs and SiPMT PCBoards | $294K |  |  | Fab | FY27
EIC TJ | pfRICH - Aerogel | $225K |  |  | Fab | FY27
EIC TJ | FTOF - Module Mechanics | $128K |  |  | Fab | FY27
EIC TJ | CTOF - Cooling System | $184K |  |  | Fab | FY27
EIC TJ | Electron Endcap Tracking - SALSA FEB | $176K |  |  | Fab | FY27
EIC TJ | Hadron Endcap Tracking - SALSA FEB | $176K |  |  | Fab | FY27
EIC TJ | TOF LV Power Supply Production - FTOF - Supply & Bins | $249K |  |  | Fab | FY27
EIC TJ | TOF HV Power Supply Production - FTOF - HV Modules | $137K |  |  | Fab | FY27
EIC TJ | TOF Patch Panel & Cable Production | $162K |  |  | Fab | FY27
EIC TJ | pfRICH - Sensors - HV Power Supplies | $299K |  |  | Fab | FY27
EIC TJ | dRICH - ALCOR ASIC - Power Supply and Cables | $112K |  |  | Fab | FY27
EIC TJ | FTOF - FTTL AC-LGAD - Service Hybrid & Module - Engineering Article - Components | $182K |  |  | Fab | FY27
EIC TJ | Backward ECAL - PCB - HV/Anode/LED - Interface Components | $124K |  |  | Fab | FY27
EIC TJ | Electronics - Fibers | $208K |  |  | Fab | FY27
EIC TJ | OUTER Barrel HCAL - FEB - Readout Electronics | $101K |  |  | Fab | FY27
EIC TJ | HCAL Insert - FEB - Readout Electronics | $110K |  |  | Fab | FY27
EIC TJ | DAQ - Trunk Fiber | $236K |  |  | Fab | FY27
EIC TJ | DAQ - Computing Infrastructure - Network Switches - PHASE 1 | $175K |  |  | Fab | FY27
EIC TJ | Slow Controls Integration - Network Switch | $140K |  |  | Fab | FY27
EIC TJ | Lepton Polarimetry in ESR - Calorimeter Readout - PMT, HV and Cables | $112K |  |  | Fab | FY27
EIC TJ | Lepton Polarimetry in ESR - Calorimeter - Infrastructure | $125K |  |  | Fab | FY27
EIC TJ | Lepton Polarimetry in RCS - Calorimeter Readout - PMT, HV Cables | $112K |  |  | Fab | FY27
EIC TJ | Lepton Polarimetry in RCS - Calorimeter Infrastructure | $125K |  |  | Fab | FY27