## LLP Items (hidden)
LLP Item/Color
| RCS Quad - First Article | Controls | APS Sextupole Refurbishment
| RCS Sextupole - First Article | Bake out Equipment | APS Quad Refurbishment Parts
| First Article Magnet Vendor | Pumping Stations | APS Quad Rebuilt Parts
| HSR Bellows Weldment | aC Carbon Coating System Power Supplies | 197MHz Crab 1st Article - Niobium
| RF Fingers | Vacuum/gas injection equipment | Backward EMCal PbWO4 Crystals
| Bellows Components | Solenoids | Barrel EMCal Fibers
| Bellows Helper Spring assembly | Machined Parts | Hadron Endcap EMCal Fibers
| Forward HCal Absorber Plates Tungsten | Coating Tubes | Forward HCal SiPMs
| Magnet Power Supply | Forward HCal Absorber Plates Steel
| VRTX+ and lpGBT | Forward HCal Module Casing Steel
EE HCal Steel for Structures
HE HCal Steel for Structures

## LLP Summary Obligation
OBLIGATION PROFILE by FY
EIC CD-3B Proposed Long Lead Procurement List - 08.October.2024
[15 empty] | 1.35 | OBLIGATION PROFILE WITHOUT CONTINGENCY - LLP by FY
L3 WBS | L4 WBS | L4 WBS Description | LLP Category | LLP Justification Item | LLP Item Detail | Number of Awards | LATEST AWARD DATE | LAB | CAM | Procurement Rep | Project Controls Rep | LABOR HOURS | DIRECT MATERIAL COST | Total Cost (Burd&Esc) | Total Cost w/ 35% Contingency | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34
6.04.02 | 6.04.02.01 | ESR Dipole Magnets | ESR Dipole Magnets | Electron Storage Ring (ESR) Dipole Magnets | ESR Dipole Magnets - D1/D3 Vendor I | 1 | 2026-01-13 | BNL | H. Witte | C. Blanchard | Brian Smith | 260 | 2194269 | 2486110.2 | 3356248.77 | 0 | 0 | 0 | 0 | 0 | 0 | 2433509.42 | 29882.83 | 22447.5 | 270.45 | 0 | 0 | 0 | 0 | 0
6.04.02 | 6.04.02.01 | ESR Dipole Magnets |  |  | ESR Dipole Magnets - D1/D3 Vendor II | 1 | 2026-01-13 | BNL | H. Witte | C. Blanchard | Brian Smith | 260 | 2194269 | 2486110.2 | 3356248.77 | 0 | 0 | 0 | 0 | 0 | 0 | 2433509.42 | 29882.83 | 22447.5 | 270.45 | 0 | 0 | 0 | 0 | 0
6.04.02 | 6.04.02.01 | ESR Dipole Magnets |  |  | ESR Dipole Magnets - D2 Vendor I | 1 | 2026-01-13 | BNL | H. Witte | C. Blanchard | Brian Smith | 260 | 2151783 | 2439005.61 | 3292657.5735 | 0 | 0 | 0 | 0 | 0 | 0 | 2386404.83 | 29882.83 | 22447.5 | 270.45 | 0
6.04.02 | 6.04.02.01 | ESR Dipole Magnets |  |  | ESR Dipole Magnets - D2 Vendor II | 1 | 2026-01-13 | BNL | H. Witte | C. Blanchard | Brian Smith | 260 | 2151783 | 2439005.61 | 3292657.5735 | 0 | 0 | 0 | 0 | 0 | 0 | 2386404.83 | 29882.83 | 22447.5 | 270.45 | 0
6.04.02 | 6.04.02.01 | ESR Dipole Magnets |  |  | ESR Dipole Magnets - D1/D2/D3 Production Iron Material | 2 | 2026-10-19 | BNL | H. Witte | C. Blanchard | Brian Smith | 922 | 5325824.49 | 6084367.98 | 8214163.695 | 0 | 0 | 0 | 0 | 0 | 0 | 5833646.87 | 250721.11 | 0 | 0 | 0
6.04.02 | 6.04.02.02 | ESR Sextupole Magnets | APS Sextupole Refurbishment | Advanced Photon Source (APS) Sextupole Magnet Refurbishment, Testing, and Measurement | APS Sextupole Refurbishment & Testing | 1 | 2026-01-23 | BNL | H. Witte | C. Blanchard | Brian Smith | 15493 | 656702.02 | 2900950.06 | 3916282.581 | 0 | 0 | 0 | 0 | 0 | 177353.73 | 1330227.9 | 503871.65 | 487952.05 | 401544.73 | 0
6.04.02 | 6.04.02.04 | ESR Magnet Measurement & Acceptance | ESR Magnet Measurement | ESR Magnetic Measurement and Bench | ESR APS Quad Magnet Measurement & Stand | 1 | 2026-09-18 | BNL | H. Witte | K. Kirkendall | Brian Smith | 5390 | 163934.43 | 1045277.68 | 1411124.868 | 0 | 0 | 0 | 0 | 0 | 0 | 217309.32 | 319984.75 | 499219.99 | 8763.62 | 0
6.04.03 | 6.04.03.01 | ESR Magnet Quads | APS Quad Refurbishment | APS Quadrupole Magnet Refurbishment, Testing and Measurement | APS Quad Rebuild & Refurbishment | 2 | 2025-05-01 | JLAB | S. Philip | M. Laney | Dimitra Riga | 21808 | 1499220.78 | 4141995.16 | 5591693.466 | 0 | 0 | 0 | 0 | 0 | 1967792.11 | 1122261.52 | 1049900.07 | 2041.46 | 0 | 0 | 0 | 0
6.04.03 | 6.04.03.01 | ESR Magnet Quads | ESR Magnet Measurement | ESR APS Quadrupole Magnetic Measurement Stand | APS Quad Magnet Measurement & Stand | 2 | 2025-08-18 | JLAB | S. Philip | M. Laney | Dimitra Riga | 1940 | 577822 | 945227.24 | 1274278.473 | 0 | 0 | 0 | 0 | 0 | 675542.18 | 269685.06 | 0 | 0 | 0 | 0 | 0 | 0
6.10.05 | 6.10.05.01 | Backward Electromagnetic Calorimetry | PbWO4 Crystals | Lead Tungstate Crystals for the Detector Backward Electro-Magnetic (EM) Calorimeter - Batch 3 and Batch 4 | Backward EMCal PbWO4 Crystals - Option 2 - Batch 3 | 1 | 2026-10-23 | BNL | A. Bazilevsky | M. Bryan | Tyler Lewis | 18 | 1180000 | 1341978.69 | 1811671.2315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1341978.69 | 0 | 0 | 0 | 0 | 0
6.10.05 | 6.10.05.01 | Backward Electromagnetic Calorimetry |  |  | Backward EMCal PbWO4 Crystals - Option 3 - Batch 4 | 1 | 2027-08-11 | BNL | A. Bazilevsky | M. Bryan | Tyler Lewis | 304 | 1180000 | 1349514.92 | 1821845.142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1340370.95 | 9143.97 | 0 | 0 | 0 | 0
6.10.05 | 6.10.05.02 | Barrel Electromagnetic Calorimetry | Scintillating Fibers | Scintillating Fibers for the Detector Barrel - Batch 2 and Forward - Batch 2 EM Calorimeters | Barrel EMCal Fibers - Option 1 - Batch 2 | 1 | 2026-04-27 | BNL | A. Bazilevsky | W. Koncelik | Tyler Lewis | 348 | 1453333.33 | 1623192.81 | 2191310.2935 | 0 | 0 | 0 | 0 | 0 | 0 | 1616330.41 | 6862.4 | 0 | 0 | 0 | 0 | 0
6.10.05 | 6.10.05.03 | Forward Electromagnetic Calorimetry |  |  | Hadron Endcap EMCal Fibers - Option 1 - Batch 2 | 1 | 2025-10-01 | BNL | A. Bazilevsky | C. Blanchard | Tyler Lewis | 348 | 489785.5 | 554676.64 | 748813.464 | 0 | 0 | 0 | 0 | 0 | 0 | 554312.66 | 363.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.10.06 | 6.10.06.03 | Forward Hadronic Calorimetry | Forward HCal Steel | Steel for the Detector Forward Hadronic Calorimeter | Forward HCal Steel | 1 | 2025-11-19 | BNL | O. Eyser | M. Bryan | Tyler Lewis | 3 | 981353.1 | 1088530.17 | 1469515.7295 | 0 | 0 | 0 | 0 | 0 | 0 | 1088530.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.10.07 | 6.10.07 | Detector Magnets | Detector Solenoid Magnet | Detector Solenoid Magnet Power Supply | Magnet Power Supply | 1 | 2025-03-31 | JLAB | R. Rajput Ghoshal | M. Laney | Everett Woolsey | 601 | 573598 | 739843.72 | 998789.022 | 0 | 0 | 0 | 0 | 0 | 661896.09 | 25586.3 | 25586.3 | 25663.77 | 1111.26 | 0 | 0 | 0 | 0 | 0
6.10.08 | 6.10.08 | Electronics | Detector Electronics | Detector Electronics Versatile Link Plus Transceiver (VRTX+) and low Power Giga-bit transceiver (1pGBT) | VRTX+ and lpGBT | 2 | 2025-11-20 | JLAB | F. Barbosa | M. Laney | Everett Woolsey | 1176 | 1295082 | 1733364.43 | 2340041.9805 | 0 | 0 | 0 | 0 | 0 | 0 | 1669644.69 | 63719.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.10.10 | 6.10.10.02 | Electron Endcap Structures | Detector Endcap Structures | Detector Endcap Structures – Flux Return Steel | Detector Endcap Steel for Structures | 1 | 2025-09-11 | BNL | R. Sharma | C. Blanchard | Tyler Lewis | 180 | 2750000 | 2985517.24 | 4030448.274 | 0 | 0 | 0 | 0 | 0 | 2957982.32 | 27534.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 49571 | 26818759.65 | 36384668.36 | 49117790.907 | 0 | 0 | 0 | 0 | 0 | 6440566.43 | 23394898.32 | 5022890.96 | 1113811.24 | 412501.41 | 0 | 0 | 0 | 0 | 0
[12 empty] | Total Cost w/ 35% Contingency |  | 49117790.907

## LLP Summary Cost
COST PROFILE by FY
EIC CD-3B Proposed Long Lead Procurement List - 08.October.2024
[15 empty] | 1.35 | COST PROFILE WITHOUT CONTINGENCY - LLP by FY
L3 WBS | L4 WBS | L4 WBS Description | LLP Category | LLP Justification Item | LLP Item Detail | Number of Awards | LATEST AWARD DATE | LAB | CAM | Procurement Rep | Project Controls Rep | LABOR HOURS | DIRECT MATERIAL COST | Total Cost (Burd&Esc) | Total Cost w/ 35% Contingency | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32 | FY33 | FY34
6.04.02 | 6.04.02.01 | ESR Dipole Magnets | ESR Dipole Magnets | Electron Storage Ring (ESR) Dipole Magnets | ESR Dipole Magnets - D1/D3 Vendor I | 1 | 2026-01-13 | BNL | H. Witte | C. Blanchard | Brian Smith | 260 | 2194269 | 2486110.2 | 3356248.77 | 0 | 0 | 0 | 0 | 0 | 0 | 16227.11 | 163232.72 | 1164413.71 | 1142236.66 | 0 | 0 | 0 | 0 | 0
6.04.02 | 6.04.02.01 | ESR Dipole Magnets |  |  | ESR Dipole Magnets - D1/D3 Vendor II | 1 | 2026-01-13 | BNL | H. Witte | C. Blanchard | Brian Smith | 260 | 2194269 | 2486110.2 | 3356248.77 | 0 | 0 | 0 | 0 | 0 | 0 | 16227.11 | 163232.72 | 1164413.71 | 1142236.66 | 0 | 0 | 0
6.04.02 | 6.04.02.01 | ESR Dipole Magnets |  |  | ESR Dipole Magnets - D2 Vendor I | 1 | 2026-01-13 | BNL | H. Witte | C. Blanchard | Brian Smith | 260 | 2151783 | 2439005.61 | 3292657.5735 | 0 | 0 | 0 | 0 | 0 | 0 | 16227.11 | 139444.27 | 1152755.64 | 1130578.59 | 0 | 0 | 0
6.04.02 | 6.04.02.01 | ESR Dipole Magnets |  |  | ESR Dipole Magnets - D2 Vendor II | 1 | 2026-01-13 | BNL | H. Witte | C. Blanchard | Brian Smith | 260 | 2151783 | 2439005.61 | 3292657.5735 | 0 | 0 | 0 | 0 | 0 | 0 | 16227.11 | 139444.27 | 1152755.64 | 1130578.59 | 0
6.04.02 | 6.04.02.01 | ESR Dipole Magnets |  |  | ESR Dipole Magnets - D1/D2/D3 Production Iron Material | 2 | 2026-10-19 | BNL | H. Witte | C. Blanchard | Brian Smith | 922 | 5325824.49 | 6084367.98 | 8214163.695 | 0 | 0 | 0 | 0 | 0 | 0 | 12254.78 | 6072113.2 | 0 | 0 | 0
6.04.02 | 6.04.02.02 | ESR Sextupole Magnets | APS Sextupole Refurbishment | Advanced Photon Source (APS) Sextupole Magnet Refurbishment, Testing, and Measurement | APS Sextupole Refurbishment & Testing | 1 | 2026-01-23 | BNL | H. Witte | C. Blanchard | Brian Smith | 15493 | 656702.02 | 2900950.06 | 3916282.581 | 0 | 0 | 0 | 0 | 0 | 177353.73 | 1330227.9 | 503871.65 | 487952.05 | 401544.73 | 0
6.04.02 | 6.04.02.04 | ESR Magnet Measurement & Acceptance | ESR Magnet Measurement | ESR Magnetic Measurement and Bench | ESR APS Quad Magnet Measurement & Stand | 1 | 2026-09-18 | BNL | H. Witte | K. Kirkendall | Brian Smith | 5390 | 163934.43 | 1045277.68 | 1411124.868 | 0 | 0 | 0 | 0 | 0 | 0 | 35553.86 | 501740.21 | 499219.99 | 8763.62 | 0
6.04.03 | 6.04.03.01 | ESR Magnet Quads | APS Quad Refurbishment | APS Quadrupole Magnet Refurbishment, Testing and Measurement | APS Quad Rebuild & Refurbishment | 2 | 2025-05-01 | JLAB | S. Philip | M. Laney | Dimitra Riga | 21808 | 1499220.78 | 4141995.16 | 5591693.466 | 0 | 0 | 0 | 0 | 0 | 1860177.97 | 1168104.07 | 1098470.61 | 15242.51 | 0 | 0 | 0 | 0
6.04.03 | 6.04.03.01 | ESR Magnet Quads | ESR Magnet Measurement | ESR APS Quadrupole Magnetic Measurement Stand | APS Quad Magnet Measurement & Stand | 2 | 2025-08-18 | JLAB | S. Philip | M. Laney | Dimitra Riga | 1940 | 577822 | 945227.24 | 1274278.473 | 0 | 0 | 0 | 0 | 0 | 22024.29 | 923202.95 | 0 | 0 | 0 | 0
6.10.05 | 6.10.05.01 | Backward Electromagnetic Calorimetry | PbWO4 Crystals | Lead Tungstate Crystals for the Detector Backward Electro-Magnetic (EM) Calorimeter - Batch 3 and Batch 4 | Backward EMCal PbWO4 Crystals - Option 2 - Batch 3 | 1 | 2026-10-23 | BNL | A. Bazilevsky | M. Bryan | Tyler Lewis | 18 | 1180000 | 1341978.69 | 1811671.2315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1341978.69 | 0 | 0 | 0 | 0 | 0
6.10.05 | 6.10.05.01 | Backward Electromagnetic Calorimetry |  |  | Backward EMCal PbWO4 Crystals - Option 3 - Batch 4 | 1 | 2027-08-11 | BNL | A. Bazilevsky | M. Bryan | Tyler Lewis | 304 | 1180000 | 1349514.92 | 1821845.142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2004.83 | 1347510.09 | 0 | 0 | 0 | 0 | 0 | 0
6.10.05 | 6.10.05.02 | Barrel Electromagnetic Calorimetry | Scintillating Fibers | Scintillating Fibers for the Detector Barrel - Batch 2 and Forward - Batch 2 EM Calorimeters | Barrel EMCal Fibers - Option 1 - Batch 2 | 1 | 2026-04-27 | BNL | A. Bazilevsky | W. Koncelik | Tyler Lewis | 348 | 1453333.33 | 1623192.81 | 2191310.2935 | 0 | 0 | 0 | 0 | 0 | 0 | 5007.7 | 1618185.11 | 0 | 0 | 0 | 0 | 0
6.10.05 | 6.10.05.03 | Forward Electromagnetic Calorimetry |  |  | Hadron Endcap EMCal Fibers - Option 1 - Batch 2 | 1 | 2025-10-01 | BNL | A. Bazilevsky | C. Blanchard | Tyler Lewis | 348 | 489785.5 | 554676.64 | 748813.464 | 0 | 0 | 0 | 0 | 0 | 0 | 11283.42 | 543393.22 | 0 | 0 | 0 | 0 | 0
6.10.06 | 6.10.06.03 | Forward Hadronic Calorimetry | Forward HCal Steel | Steel for the Detector Forward Hadronic Calorimeter | Forward HCal Steel | 1 | 2025-11-19 | BNL | O. Eyser | M. Bryan | Tyler Lewis | 3 | 981353.1 | 1088530.17 | 1469515.7295 | 0 | 0 | 0 | 0 | 0 | 0 | 1088530.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.10.07 | 6.10.07 | Detector Magnets | Detector Solenoid Magnet | Detector Solenoid Magnet Power Supply | Magnet Power Supply | 1 | 2025-03-31 | JLAB | R. Rajput Ghoshal | M. Laney | Everett Woolsey | 601 | 573598 | 739843.72 | 998789.022 | 0 | 0 | 0 | 0 | 0 | 16605.53 | 32347.63 | 32347.63 | 32452.47 | 626090.46 | 0 | 0 | 0
6.10.08 | 6.10.08 | Electronics | Detector Electronics | Detector Electronics Versatile Link Plus Transceiver (VRTX+) and low Power Giga-bit transceiver (1pGBT) | VRTX+ and lpGBT | 2 | 2025-11-20 | JLAB | F. Barbosa | M. Laney | Everett Woolsey | 1176 | 1295082 | 1733364.43 | 2340041.9805 | 0 | 0 | 0 | 0 | 0 | 0 | 201935.55 | 1531428.88 | 0 | 0 | 0 | 0 | 0
6.10.10 | 6.10.10.02 | Electron Endcap Structures | Detector Endcap Structures | Detector Endcap Structures – Flux Return Steel | Detector Endcap Steel for Structures | 1 | 2025-09-11 | BNL | R. Sharma | C. Blanchard | Tyler Lewis | 180 | 2750000 | 2985517.24 | 4030448.274 | 0 | 0 | 0 | 0 | 0 | 2143.44 | 2983373.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 49571 | 26818759.65 | 36384668.36 | 49117790.907 | 0 | 0 | 0 | 0 | 0 | 2078304.96 | 7856730.27 | 13850888.01 | 7016715.81 | 5582029.31 | 0 | 0 | 0 | 0 | 0
[12 empty] | Total Cost w/ 35% Contingency |  | 49117790.907

## DELTA Check (hidden)
Cost PVT Total | Obligation PVT Total | 2.A | 2.B + 2.C | 2.B | 2.C
36383548.82 | 36383548.82 | 36383548.82 | 36383548.82 | 29781838.66 | 6601710.16 |  | *The references in this row may need to be updated if the pivot table changes.
CHECK --> | TRUE | [5 empty] | LABOR HOURS | DIRECT MATERIAL COST | Total Cost (Burd&Esc) | Total Cost w/ 35% Contingency
| *This checks that Cells A2:D2 are equal. |  |  |  |  | Data | 49571 | 26818759.65 | 36383548.79 | 49117790.8665
| 0 |  |  |  |  | Cost | 49571 | 26818759.65 | 36384668.36 | 49117790.907
[6 empty] | Ob | 49571 | 26818759.65 | 36384668.36 | 49117790.907
[6 empty] | Cost - Ob | 0 | 0 | 0 | 0
| 2024-10-02 | CD3B_PB-FLOAT-CK |  |  |  | Data - Cost | 0 | 0 | -1119.57 | -0.0405
| 1.A-P6 DATA CD-3B ONLY | 36383548.65
| 1.B- P6 CD3B ONLY (02.Oct.2024) | 36383548.79
-0.14

## Obligation Pivot (hidden)
36383548.82
Values
L3 WBS | L4 WBS | L4 WBS Description | LLP Category | LLP Item | LLP Item Detail | LAB | CAM | ESTIMATOR | PMC REP | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30
6.04.02 | 6.04.02.01 | ESR Dipole Magnets | ESR Dipole Magnets | Electron Storage Ring (ESR) Dipole Magnets | ESR Dipole Magnets - D1/D2/D3 Production Iron Material | BNL | Witte | hwitte | bsmith | 0 | 0 | 0 | 0 | 0 | 0 | 5833646.87 | 250918.83 | 0 | 0 | 0
6.04.02 | 6.04.02.01 | ESR Dipole Magnets |  |  | ESR Dipole Magnets - D1/D3 Vendor I | BNL | Witte | hwitte | bsmith | 0 | 0 | 0 | 0 | 0 | 0 | 2433509.42 | 29882.83 | 22447.5 | 270.45 | 0
6.04.02 | 6.04.02.01 | ESR Dipole Magnets |  |  | ESR Dipole Magnets - D1/D3 Vendor II | BNL | Witte | hwitte | bsmith | 0 | 0 | 0 | 0 | 0 | 0 | 2433509.42 | 29882.83 | 22447.5 | 270.45 | 0
6.04.02 | 6.04.02.01 | ESR Dipole Magnets |  |  | ESR Dipole Magnets - D2 Vendor I | BNL | Witte | hwitte | bsmith | 0 | 0 | 0 | 0 | 0 | 0 | 2386404.83 | 29882.83 | 22447.5 | 270.45 | 0
6.04.02 | 6.04.02.01 | ESR Dipole Magnets |  |  | ESR Dipole Magnets - D2 Vendor II | BNL | Witte | hwitte | bsmith | 0 | 0 | 0 | 0 | 0 | 0 | 2386404.83 | 29882.83 | 22447.5 | 270.45 | 0
6.04.02 | 6.04.02.02 | ESR Sextupole Magnets | APS Sextupole Refurbishment | Advanced Photon Source (APS) Sextupole Magnet Refurbishment, Testing, and Measurement | APS Sextupole Refurbishment & Testing | BNL | Witte | hwitte | bsmith | 0 | 0 | 0 | 0 | 0 | 177353.73 | 1330227.9 | 503871.65 | 487952.05 | 401544.73 | 0
6.04.02 | 6.04.02.04 | ESR Magnet Measurement & Acceptance | ESR Magnet Measurement | ESR Magnetic Measurement and Bench | ESR APS Quad Magnet Measurement & Stand | BNL | Witte | hwitte | bsmith | 0 | 0 | 0 | 0 | 0 | 0 | 217309.32 | 319984.75 | 499219.99 | 8763.62 | 0
6.04.03 | 6.04.03.01 | ESR Magnet Quads | ESR Magnet Measurement | ESR APS Quadrupole Magnetic Measurement Stand | APS Quad Magnet Measurement & Stand | JLAB | Philip | sphilip | driga | 0 | 0 | 0 | 0 | 0 | 675542.18 | 268367.8 | 0 | 0 | 0 | 0
6.04.03 | 6.04.03.01 | ESR Magnet Quads | APS Quad Refurbishment | APS Quadrupole Magnet Refurbishment, Testing and Measurement | APS Quad Rebuild & Refurbishment | JLAB | Philip | sphilip | driga | 0 | 0 | 0 | 0 | 0 | 1967792.11 | 1122261.52 | 1049900.07 | 2041.46 | 0 | 0
6.10.05 | 6.10.05.01 | Backward Electromagnetic Calorimetry | PbWO4 Crystals | Lead Tungstate Crystals for the Detector Backward Electro-Magnetic (EM) Calorimeter - Batch 3 and Batch 4 | Backward EMCal PbWO4 Crystals - Option 2 - Batch 3 | BNL | Bazilevsky | shura | tlewis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1341978.69 | 0 | 0 | 0
6.10.05 | 6.10.05.01 | Backward Electromagnetic Calorimetry |  |  | Backward EMCal PbWO4 Crystals - Option 3 - Batch 4 | BNL | Bazilevsky | shura | tlewis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1340370.95 | 9143.97 | 0 | 0
6.10.05 | 6.10.05.02 | Barrel Electromagnetic Calorimetry | Scintillating Fibers | Scintillating Fibers for the Detector Barrel - Batch 2 and Forward - Batch 2 EM Calorimeters | Barrel EMCal Fibers - Option 1 - Batch 2 | BNL | Bazilevsky | shura | tlewis | 0 | 0 | 0 | 0 | 0 | 0 | 1616330.41 | 6862.4 | 0 | 0 | 0
6.10.05 | 6.10.05.03 | Forward Electromagnetic Calorimetry | Scintillating Fibers | Scintillating Fibers for the Detector Barrel - Batch 2 and Forward - Batch 2 EM Calorimeters | Hadron Endcap EMCal Fibers - Option 1 - Batch 2 | BNL | Bazilevsky | shura | tlewis | 0 | 0 | 0 | 0 | 0 | 0 | 554312.66 | 363.98 | 0 | 0 | 0
6.10.06 | 6.10.06.03 | Forward Hadronic Calorimetry | Forward HCal Steel | Steel for the Detector Forward Hadronic Calorimeter | Forward HCal Steel | BNL | Eyser | keyser | tlewis | 0 | 0 | 0 | 0 | 0 | 0 | 1088530.17 | 0 | 0 | 0 | 0
6.10.07 | 6.10.07 | Detector Magnets | Detector Solenoid Magnet | Detector Solenoid Magnet Power Supply | Magnet Power Supply | JLAB | Rajput-Ghoshal | rrajput | ewoolsey | 0 | 0 | 0 | 0 | 0 | 661896.09 | 25586.3 | 25586.3 | 25663.77 | 1111.26 | 0
6.10.08 | 6.10.08 | Electronics | Detector Electronics | Detector Electronics Versatile Link Plus Transceiver (VRTX+) and low Power Giga-bit transceiver (1pGBT) | VRTX+ and lpGBT | JLAB | Barbosa | fbarbosa | ewoolsey | 0 | 0 | 0 | 0 | 0 | 0 | 1669644.69 | 63719.74 | 0 | 0 | 0
6.10.10 | 6.10.10.02 | Electron Endcap Structures | Detector Endcap Structures | Detector Endcap Structures – Flux Return Steel | Detector Endcap Steel for Structures | BNL | Sharma | rsharma | tlewis | 0 | 0 | 0 | 0 | 0 | 2957982.32 | 27534.92 | 0 | 0 | 0 | 0
Grand Total | [9 empty] | 0 | 0 | 0 | 0 | 0 | 6440566.43 | 23393581.06 | 5023088.68 | 1113811.24 | 412501.41 | 0

## Cost Pivot (hidden)
36383548.82
Values
L3 WBS | L4 WBS | L4 WBS Description | LLP Category | LLP Item | LLP Item Detail | LAB | CAM | ESTIMATOR | PMC REP | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30
6.04.02 | 6.04.02.01 | ESR Dipole Magnets | ESR Dipole Magnets | Electron Storage Ring (ESR) Dipole Magnets | ESR Dipole Magnets - D1/D2/D3 Production Iron Material | BNL | Witte | hwitte | bsmith | 0 | 0 | 0 | 0 | 0 | 0 | 12254.78 | 6072310.92 | 0 | 0 | 0
6.04.02 | 6.04.02.01 | ESR Dipole Magnets |  |  | ESR Dipole Magnets - D1/D3 Vendor I | BNL | Witte | hwitte | bsmith | 0 | 0 | 0 | 0 | 0 | 0 | 16227.11 | 163232.72 | 1164413.71 | 1142236.66 | 0
6.04.02 | 6.04.02.01 | ESR Dipole Magnets |  |  | ESR Dipole Magnets - D1/D3 Vendor II | BNL | Witte | hwitte | bsmith | 0 | 0 | 0 | 0 | 0 | 0 | 16227.11 | 163232.72 | 1164413.71 | 1142236.66 | 0
6.04.02 | 6.04.02.01 | ESR Dipole Magnets |  |  | ESR Dipole Magnets - D2 Vendor I | BNL | Witte | hwitte | bsmith | 0 | 0 | 0 | 0 | 0 | 0 | 16227.11 | 139444.27 | 1152755.64 | 1130578.59 | 0
6.04.02 | 6.04.02.01 | ESR Dipole Magnets |  |  | ESR Dipole Magnets - D2 Vendor II | BNL | Witte | hwitte | bsmith | 0 | 0 | 0 | 0 | 0 | 0 | 16227.11 | 139444.27 | 1152755.64 | 1130578.59 | 0
6.04.02 | 6.04.02.02 | ESR Sextupole Magnets | APS Sextupole Refurbishment | Advanced Photon Source (APS) Sextupole Magnet Refurbishment, Testing, and Measurement | APS Sextupole Refurbishment & Testing | BNL | Witte | hwitte | bsmith | 0 | 0 | 0 | 0 | 0 | 177353.73 | 1330227.9 | 503871.65 | 487952.05 | 401544.73 | 0
6.04.02 | 6.04.02.04 | ESR Magnet Measurement & Acceptance | ESR Magnet Measurement | ESR Magnetic Measurement and Bench | ESR APS Quad Magnet Measurement & Stand | BNL | Witte | hwitte | bsmith | 0 | 0 | 0 | 0 | 0 | 0 | 35553.86 | 501740.21 | 499219.99 | 8763.62 | 0
6.04.03 | 6.04.03.01 | ESR Magnet Quads | ESR Magnet Measurement | ESR APS Quadrupole Magnetic Measurement Stand | APS Quad Magnet Measurement & Stand | JLAB | Philip | sphilip | driga | 0 | 0 | 0 | 0 | 0 | 22024.29 | 921885.69 | 0 | 0 | 0 | 0
6.04.03 | 6.04.03.01 | ESR Magnet Quads | APS Quad Refurbishment | APS Quadrupole Magnet Refurbishment, Testing and Measurement | APS Quad Rebuild & Refurbishment | JLAB | Philip | sphilip | driga | 0 | 0 | 0 | 0 | 0 | 1860177.97 | 1168104.07 | 1098470.61 | 15242.51 | 0 | 0
6.10.05 | 6.10.05.01 | Backward Electromagnetic Calorimetry | PbWO4 Crystals | Lead Tungstate Crystals for the Detector Backward Electro-Magnetic (EM) Calorimeter - Batch 3 and Batch 4 | Backward EMCal PbWO4 Crystals - Option 2 - Batch 3 | BNL | Bazilevsky | shura | tlewis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1341978.69 | 0 | 0 | 0
6.10.05 | 6.10.05.01 | Backward Electromagnetic Calorimetry |  |  | Backward EMCal PbWO4 Crystals - Option 3 - Batch 4 | BNL | Bazilevsky | shura | tlewis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2004.83 | 1347510.09 | 0 | 0
6.10.05 | 6.10.05.02 | Barrel Electromagnetic Calorimetry | Scintillating Fibers | Scintillating Fibers for the Detector Barrel - Batch 2 and Forward - Batch 2 EM Calorimeters | Barrel EMCal Fibers - Option 1 - Batch 2 | BNL | Bazilevsky | shura | tlewis | 0 | 0 | 0 | 0 | 0 | 0 | 5007.7 | 1618185.11 | 0 | 0 | 0
6.10.05 | 6.10.05.03 | Forward Electromagnetic Calorimetry | Scintillating Fibers | Scintillating Fibers for the Detector Barrel - Batch 2 and Forward - Batch 2 EM Calorimeters | Hadron Endcap EMCal Fibers - Option 1 - Batch 2 | BNL | Bazilevsky | shura | tlewis | 0 | 0 | 0 | 0 | 0 | 0 | 11283.42 | 543393.22 | 0 | 0 | 0
6.10.06 | 6.10.06.03 | Forward Hadronic Calorimetry | Forward HCal Steel | Steel for the Detector Forward Hadronic Calorimeter | Forward HCal Steel | BNL | Eyser | keyser | tlewis | 0 | 0 | 0 | 0 | 0 | 0 | 1088530.17 | 0 | 0 | 0 | 0
6.10.07 | 6.10.07 | Detector Magnets | Detector Solenoid Magnet | Detector Solenoid Magnet Power Supply | Magnet Power Supply | JLAB | Rajput-Ghoshal | rrajput | ewoolsey | 0 | 0 | 0 | 0 | 0 | 16605.53 | 32347.63 | 32347.63 | 32452.47 | 626090.46 | 0
6.10.08 | 6.10.08 | Electronics | Detector Electronics | Detector Electronics Versatile Link Plus Transceiver (VRTX+) and low Power Giga-bit transceiver (1pGBT) | VRTX+ and lpGBT | JLAB | Barbosa | fbarbosa | ewoolsey | 0 | 0 | 0 | 0 | 0 | 0 | 201935.55 | 1531428.88 | 0 | 0 | 0
6.10.10 | 6.10.10.02 | Electron Endcap Structures | Detector Endcap Structures | Detector Endcap Structures – Flux Return Steel | Detector Endcap Steel for Structures | BNL | Sharma | rsharma | tlewis | 0 | 0 | 0 | 0 | 0 | 2143.44 | 2983373.8 | 0 | 0 | 0 | 0
Grand Total | [9 empty] | 0 | 0 | 0 | 0 | 0 | 2078304.96 | 7855413.01 | 13851085.73 | 7016715.81 | 5582029.31 | 0

## 2.B and 2.C Data (hidden)
WBS | L3 WBS | L3 WBS DESCRIPTION | L4 WBS | L4 WBS Description | LLP Category | LLP Item | LLP Item Detail | CAM | ESTIMATOR | PMC REP | LAB | BNL_Procurement Designation | FY2020 | FY2021 | FY2022 | FY2023 | FY2024 | FY2025 | FY2026 | FY2027 | FY2028 | FY2029 | FY2030 | FY2031 | FY2032 | FY2033 | FY2034 | FY2035 | FY2036
6.10.10.02 | 6.10.10 | Integration, Installation and Infrastructure | 6.10.10.02 | Electron Endcap Structures | Detector Endcap Structures | Detector Endcap Structures – Flux Return Steel | Detector Endcap Steel for Structures | Sharma | rsharma | tlewis | BNL | A.PP085 | 0 | 0 | 0 | 0 | 0 | 2143.44 | 27534.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.10.05.02.01 | 6.10.05 | Electromagnetic Calorimetry | 6.10.05.02 | Barrel Electromagnetic Calorimetry | Scintillating Fibers | Scintillating Fibers for the Detector Barrel - Batch 2 and Forward - Batch 2 EM Calorimeters | Barrel EMCal Fibers - Option 1 - Batch 2 | Bazilevsky | shura | tlewis | BNL | A.PP091.B | 0 | 0 | 0 | 0 | 0 | 0 | 5007.7 | 6862.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.02.02 | 6.04.02 | Electron Storage Ring Magnets - Dipole, Sextupole | 6.04.02.02 | ESR Sextupole Magnets | APS Sextupole Refurbishment | Advanced Photon Source (APS) Sextupole Magnet Refurbishment, Testing, and Measurement | APS Sextupole Refurbishment & Testing | Witte | hwitte | bsmith | BNL | B | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.10.05.01.01 | 6.10.05 | Electromagnetic Calorimetry | 6.10.05.01 | Backward Electromagnetic Calorimetry | PbWO4 Crystals | Lead Tungstate Crystals for the Detector Backward Electro-Magnetic (EM) Calorimeter - Batch 3 and Batch 4 | Backward EMCal PbWO4 Crystals - Option 2 - Batch 3 | Bazilevsky | shura | tlewis | BNL | D.APP47.C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3612.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.10.05.01.01 | 6.10.05 | Electromagnetic Calorimetry | 6.10.05.01 | Backward Electromagnetic Calorimetry | PbWO4 Crystals | Lead Tungstate Crystals for the Detector Backward Electro-Magnetic (EM) Calorimeter - Batch 3 and Batch 4 | Backward EMCal PbWO4 Crystals - Option 3 - Batch 4 | Bazilevsky | shura | tlewis | BNL | D.APP47.D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2004.83 | 9143.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.02.01 | 6.04.02 | Electron Storage Ring Magnets - Dipole, Sextupole | 6.04.02.01 | ESR Dipole Magnets | ESR Dipole Magnets | Electron Storage Ring (ESR) Dipole Magnets | ESR Dipole Magnets - D1/D3 Vendor I | Witte | hwitte | bsmith | BNL | D.APP62.A | 0 | 0 | 0 | 0 | 0 | 0 | 10854.18 | 22450.28 | 15014.95 | 180.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.02.01 | 6.04.02 | Electron Storage Ring Magnets - Dipole, Sextupole | 6.04.02.01 | ESR Dipole Magnets | ESR Dipole Magnets | Electron Storage Ring (ESR) Dipole Magnets | ESR Dipole Magnets - D1/D3 Vendor II | Witte | hwitte | bsmith | BNL | D.APP62.B | 0 | 0 | 0 | 0 | 0 | 0 | 10854.18 | 22450.28 | 15014.95 | 180.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.02.01 | 6.04.02 | Electron Storage Ring Magnets - Dipole, Sextupole | 6.04.02.01 | ESR Dipole Magnets | ESR Dipole Magnets | Electron Storage Ring (ESR) Dipole Magnets | ESR Dipole Magnets - D2 Vendor I | Witte | hwitte | bsmith | BNL | D.APP63.A | 0 | 0 | 0 | 0 | 0 | 0 | 10854.18 | 22450.28 | 15014.95 | 180.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.02.01 | 6.04.02 | Electron Storage Ring Magnets - Dipole, Sextupole | 6.04.02.01 | ESR Dipole Magnets | ESR Dipole Magnets | Electron Storage Ring (ESR) Dipole Magnets | ESR Dipole Magnets - D2 Vendor II | Witte | hwitte | bsmith | BNL | D.APP63.B | 0 | 0 | 0 | 0 | 0 | 0 | 10854.18 | 22450.28 | 15014.95 | 180.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.02.01 | 6.04.02 | Electron Storage Ring Magnets - Dipole, Sextupole | 6.04.02.01 | ESR Dipole Magnets | ESR Dipole Magnets | Electron Storage Ring (ESR) Dipole Magnets | ESR Dipole Magnets - D1/D2/D3 Production Iron Material | Witte | hwitte | bsmith | BNL | D.APP64 | 0 | 0 | 0 | 0 | 0 | 0 | 12254.78 | 165607.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.02.02 | 6.04.02 | Electron Storage Ring Magnets - Dipole, Sextupole | 6.04.02.02 | ESR Sextupole Magnets | APS Sextupole Refurbishment | Advanced Photon Source (APS) Sextupole Magnet Refurbishment, Testing, and Measurement | APS Sextupole Refurbishment & Testing | Witte | hwitte | bsmith | BNL | Labor - 092 | 0 | 0 | 0 | 0 | 0 | 155281.45 | 622256.06 | 503871.65 | 487952.05 | 401544.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.02.04 | 6.04.02 | Electron Storage Ring Magnets - Dipole, Sextupole | 6.04.02.04 | ESR Magnet Measurement & Acceptance | ESR Magnet Measurement | ESR Magnetic Measurement and Bench | ESR APS Quad Magnet Measurement & Stand | Witte | hwitte | bsmith | BNL | Labor - 105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 499219.99 | 8763.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.10.08 | 6.10.08 | Electronics | 6.10.08 | Electronics | Detector Electronics | Detector Electronics Versatile Link Plus Transceiver (VRTX+) and low Power Giga-bit transceiver (1pGBT) | VRTX+ and lpGBT | Barbosa | fbarbosa | ewoolsey | JLAB | P.S1033 | 0 | 0 | 0 | 0 | 0 | 0 | 106928.9 | 25717.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.10.08 | 6.10.08 | Electronics | 6.10.08 | Electronics | Detector Electronics | Detector Electronics Versatile Link Plus Transceiver (VRTX+) and low Power Giga-bit transceiver (1pGBT) | VRTX+ and lpGBT | Barbosa | fbarbosa | ewoolsey | JLAB | P.S1131 | 0 | 0 | 0 | 0 | 0 | 0 | 95006.65 | 38002.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.02.04 | 6.04.02 | Electron Storage Ring Magnets - Dipole, Sextupole | 6.04.02.04 | ESR Magnet Measurement & Acceptance | ESR Magnet Measurement | ESR Magnetic Measurement and Bench | ESR APS Quad Magnet Measurement & Stand | Witte | hwitte | bsmith | BNL | P.S1135 | 0 | 0 | 0 | 0 | 0 | 0 | 35553.86 | 319984.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.02.01 | 6.04.02 | Electron Storage Ring Magnets - Dipole, Sextupole | 6.04.02.01 | ESR Dipole Magnets | ESR Dipole Magnets | Electron Storage Ring (ESR) Dipole Magnets | ESR Dipole Magnets - D1/D2/D3 Production Iron Material | Witte | hwitte | bsmith | BNL | P.S1138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.03.01.01.03 | 6.04.03 | Electron Storage Ring Magnets - Quadrupole, Corrector | 6.04.03.01 | ESR Magnet Quads | ESR Magnet Measurement | ESR APS Quadrupole Magnetic Measurement Stand | APS Quad Magnet Measurement & Stand | Philip | sphilip | driga | JLAB | P.S1143 | 0 | 0 | 0 | 0 | 0 | 13686.84 | 240298.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.03.01.01.02 | 6.04.03 | Electron Storage Ring Magnets - Quadrupole, Corrector | 6.04.03.01 | ESR Magnet Quads | APS Quad Refurbishment | APS Quadrupole Magnet Refurbishment, Testing and Measurement | APS Quad Rebuild & Refurbishment | Philip | sphilip | driga | JLAB | S.P.541 | 0 | 0 | 0 | 0 | 0 | 280810.81 | 803035.92 | 723078.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.10.05.03.01 | 6.10.05 | Electromagnetic Calorimetry | 6.10.05.03 | Forward Electromagnetic Calorimetry | Scintillating Fibers | Scintillating Fibers for the Detector Barrel - Batch 2 and Forward - Batch 2 EM Calorimeters | Hadron Endcap EMCal Fibers - Option 1 - Batch 2 | Bazilevsky | shura | tlewis | BNL | S.P175.B | 0 | 0 | 0 | 0 | 0 | 0 | 11283.42 | 363.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.10.07 | 6.10.07 | Detector Magnets | 6.10.07 | Detector Magnets | Detector Solenoid Magnet | Detector Solenoid Magnet Power Supply | Magnet Power Supply | Rajput-Ghoshal | rrajput | ewoolsey | JLAB | S.P322 | 0 | 0 | 0 | 0 | 0 | 13129.06 | 25586.3 | 25586.3 | 25663.77 | 1111.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.10.06.03 | 6.10.06 | Hadronic Calorimetry | 6.10.06.03 | Forward Hadronic Calorimetry | Forward HCal Steel | Steel for the Detector Forward Hadronic Calorimeter | Forward HCal Steel | Eyser | keyser | tlewis | BNL | S.P442.B | 0 | 0 | 0 | 0 | 0 | 0 | 495.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.02.02 | 6.04.02 | Electron Storage Ring Magnets - Dipole, Sextupole | 6.04.02.02 | ESR Sextupole Magnets | APS Sextupole Refurbishment | Advanced Photon Source (APS) Sextupole Magnet Refurbishment, Testing, and Measurement | APS Sextupole Refurbishment & Testing | Witte | hwitte | bsmith | BNL | S.P540 | 0 | 0 | 0 | 0 | 0 | 0 | 2644.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.03.01.01.02 | 6.04.03 | Electron Storage Ring Magnets - Quadrupole, Corrector | 6.04.03.01 | ESR Magnet Quads | APS Quad Refurbishment | APS Quadrupole Magnet Refurbishment, Testing and Measurement | APS Quad Rebuild & Refurbishment | Philip | sphilip | driga | JLAB | S.P542 | 0 | 0 | 0 | 0 | 0 | 22183.34 | 319225.6 | 326821.16 | 2041.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.03.01.01.03 | 6.04.03 | Electron Storage Ring Magnets - Quadrupole, Corrector | 6.04.03.01 | ESR Magnet Quads | ESR Magnet Measurement | ESR APS Quadrupole Magnetic Measurement Stand | APS Quad Magnet Measurement & Stand | Philip | sphilip | driga | JLAB | S.P543 | 0 | 0 | 0 | 0 | 0 | 8337.45 | 28069.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.02.01 | 6.04.02 | Electron Storage Ring Magnets - Dipole, Sextupole | 6.04.02.01 | ESR Dipole Magnets | ESR Dipole Magnets | Electron Storage Ring (ESR) Dipole Magnets | ESR Dipole Magnets - D1/D3 Vendor I | Witte | hwitte | bsmith | BNL | T.098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.02.01 | 6.04.02 | Electron Storage Ring Magnets - Dipole, Sextupole | 6.04.02.01 | ESR Dipole Magnets | ESR Dipole Magnets | Electron Storage Ring (ESR) Dipole Magnets | ESR Dipole Magnets - D1/D3 Vendor II | Witte | hwitte | bsmith | BNL | T.103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.02.01 | 6.04.02 | Electron Storage Ring Magnets - Dipole, Sextupole | 6.04.02.01 | ESR Dipole Magnets | ESR Dipole Magnets | Electron Storage Ring (ESR) Dipole Magnets | ESR Dipole Magnets - D2 Vendor I | Witte | hwitte | bsmith | BNL | T.104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.02.01 | 6.04.02 | Electron Storage Ring Magnets - Dipole, Sextupole | 6.04.02.01 | ESR Dipole Magnets | ESR Dipole Magnets | Electron Storage Ring (ESR) Dipole Magnets | ESR Dipole Magnets - D2 Vendor II | Witte | hwitte | bsmith | BNL | T.107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.03.01.01.02 | 6.04.03 | Electron Storage Ring Magnets - Quadrupole, Corrector | 6.04.03.01 | ESR Magnet Quads | APS Quad Refurbishment | APS Quadrupole Magnet Refurbishment, Testing and Measurement | APS Quad Rebuild & Refurbishment | Philip | sphilip | driga | JLAB | T.LLP027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.03.01.01.02 | 6.04.03 | Electron Storage Ring Magnets - Quadrupole, Corrector | 6.04.03.01 | ESR Magnet Quads | APS Quad Refurbishment | APS Quadrupole Magnet Refurbishment, Testing and Measurement | APS Quad Rebuild & Refurbishment | Philip | sphilip | driga | JLAB | T.LLP028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.10.10.02 | 6.10.10 | Integration, Installation and Infrastructure | 6.10.10.02 | Electron Endcap Structures | Detector Endcap Structures | Detector Endcap Structures – Flux Return Steel | Detector Endcap Steel for Structures | Sharma | rsharma | tlewis | BNL | A.PP085 | 0 | 0 | 0 | 0 | 0 | 0 | 2955838.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.10.05.02.01 | 6.10.05 | Electromagnetic Calorimetry | 6.10.05.02 | Barrel Electromagnetic Calorimetry | Scintillating Fibers | Scintillating Fibers for the Detector Barrel - Batch 2 and Forward - Batch 2 EM Calorimeters | Barrel EMCal Fibers - Option 1 - Batch 2 | Bazilevsky | shura | tlewis | BNL | A.PP091.B | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1611322.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.02.02 | 6.04.02 | Electron Storage Ring Magnets - Dipole, Sextupole | 6.04.02.02 | ESR Sextupole Magnets | APS Sextupole Refurbishment | Advanced Photon Source (APS) Sextupole Magnet Refurbishment, Testing, and Measurement | APS Sextupole Refurbishment & Testing | Witte | hwitte | bsmith | BNL | B | 0 | 0 | 0 | 0 | 0 | 22072.28 | 12518.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.10.05.01.01 | 6.10.05 | Electromagnetic Calorimetry | 6.10.05.01 | Backward Electromagnetic Calorimetry | PbWO4 Crystals | Lead Tungstate Crystals for the Detector Backward Electro-Magnetic (EM) Calorimeter - Batch 3 and Batch 4 | Backward EMCal PbWO4 Crystals - Option 2 - Batch 3 | Bazilevsky | shura | tlewis | BNL | D.APP47.C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1338366.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.10.05.01.01 | 6.10.05 | Electromagnetic Calorimetry | 6.10.05.01 | Backward Electromagnetic Calorimetry | PbWO4 Crystals | Lead Tungstate Crystals for the Detector Backward Electro-Magnetic (EM) Calorimeter - Batch 3 and Batch 4 | Backward EMCal PbWO4 Crystals - Option 3 - Batch 4 | Bazilevsky | shura | tlewis | BNL | D.APP47.D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1338366.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.02.01 | 6.04.02 | Electron Storage Ring Magnets - Dipole, Sextupole | 6.04.02.01 | ESR Dipole Magnets | ESR Dipole Magnets | Electron Storage Ring (ESR) Dipole Magnets | ESR Dipole Magnets - D1/D3 Vendor I | Witte | hwitte | bsmith | BNL | D.APP62.A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 133349.89 | 1141966.21 | 1141966.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.02.01 | 6.04.02 | Electron Storage Ring Magnets - Dipole, Sextupole | 6.04.02.01 | ESR Dipole Magnets | ESR Dipole Magnets | Electron Storage Ring (ESR) Dipole Magnets | ESR Dipole Magnets - D1/D3 Vendor II | Witte | hwitte | bsmith | BNL | D.APP62.B | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 133349.89 | 1141966.21 | 1141966.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.02.01 | 6.04.02 | Electron Storage Ring Magnets - Dipole, Sextupole | 6.04.02.01 | ESR Dipole Magnets | ESR Dipole Magnets | Electron Storage Ring (ESR) Dipole Magnets | ESR Dipole Magnets - D2 Vendor I | Witte | hwitte | bsmith | BNL | D.APP63.A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109561.44 | 1130308.14 | 1130308.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.02.01 | 6.04.02 | Electron Storage Ring Magnets - Dipole, Sextupole | 6.04.02.01 | ESR Dipole Magnets | ESR Dipole Magnets | Electron Storage Ring (ESR) Dipole Magnets | ESR Dipole Magnets - D2 Vendor II | Witte | hwitte | bsmith | BNL | D.APP63.B | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109561.44 | 1130308.14 | 1130308.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.02.01 | 6.04.02 | Electron Storage Ring Magnets - Dipole, Sextupole | 6.04.02.01 | ESR Dipole Magnets | ESR Dipole Magnets | Electron Storage Ring (ESR) Dipole Magnets | ESR Dipole Magnets - D1/D2/D3 Production Iron Material | Witte | hwitte | bsmith | BNL | D.APP64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5821392.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.02.02 | 6.04.02 | Electron Storage Ring Magnets - Dipole, Sextupole | 6.04.02.02 | ESR Sextupole Magnets | APS Sextupole Refurbishment | Advanced Photon Source (APS) Sextupole Magnet Refurbishment, Testing, and Measurement | APS Sextupole Refurbishment & Testing | Witte | hwitte | bsmith | BNL | Labor - 092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.02.04 | 6.04.02 | Electron Storage Ring Magnets - Dipole, Sextupole | 6.04.02.04 | ESR Magnet Measurement & Acceptance | ESR Magnet Measurement | ESR Magnetic Measurement and Bench | ESR APS Quad Magnet Measurement & Stand | Witte | hwitte | bsmith | BNL | Labor - 105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.10.08 | 6.10.08 | Electronics | 6.10.08 | Electronics | Detector Electronics | Detector Electronics Versatile Link Plus Transceiver (VRTX+) and low Power Giga-bit transceiver (1pGBT) | VRTX+ and lpGBT | Barbosa | fbarbosa | ewoolsey | JLAB | P.S1033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1396700.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.10.08 | 6.10.08 | Electronics | 6.10.08 | Electronics | Detector Electronics | Detector Electronics Versatile Link Plus Transceiver (VRTX+) and low Power Giga-bit transceiver (1pGBT) | VRTX+ and lpGBT | Barbosa | fbarbosa | ewoolsey | JLAB | P.S1131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71008.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.02.04 | 6.04.02 | Electron Storage Ring Magnets - Dipole, Sextupole | 6.04.02.04 | ESR Magnet Measurement & Acceptance | ESR Magnet Measurement | ESR Magnetic Measurement and Bench | ESR APS Quad Magnet Measurement & Stand | Witte | hwitte | bsmith | BNL | P.S1135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 181755.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.02.01 | 6.04.02 | Electron Storage Ring Magnets - Dipole, Sextupole | 6.04.02.01 | ESR Dipole Magnets | ESR Dipole Magnets | Electron Storage Ring (ESR) Dipole Magnets | ESR Dipole Magnets - D1/D2/D3 Production Iron Material | Witte | hwitte | bsmith | BNL | P.S1138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85311.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.03.01.01.03 | 6.04.03 | Electron Storage Ring Magnets - Quadrupole, Corrector | 6.04.03.01 | ESR Magnet Quads | ESR Magnet Measurement | ESR APS Quadrupole Magnetic Measurement Stand | APS Quad Magnet Measurement & Stand | Philip | sphilip | driga | JLAB | P.S1143 | 0 | 0 | 0 | 0 | 0 | 0 | 90147.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.03.01.01.02 | 6.04.03 | Electron Storage Ring Magnets - Quadrupole, Corrector | 6.04.03.01 | ESR Magnet Quads | APS Quad Refurbishment | APS Quadrupole Magnet Refurbishment, Testing and Measurement | APS Quad Rebuild & Refurbishment | Philip | sphilip | driga | JLAB | S.P.541 | 0 | 0 | 0 | 0 | 0 | 1199807.07 | 32641.5 | 48570.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.10.05.03.01 | 6.10.05 | Electromagnetic Calorimetry | 6.10.05.03 | Forward Electromagnetic Calorimetry | Scintillating Fibers | Scintillating Fibers for the Detector Barrel - Batch 2 and Forward - Batch 2 EM Calorimeters | Hadron Endcap EMCal Fibers - Option 1 - Batch 2 | Bazilevsky | shura | tlewis | BNL | S.P175.B | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 543029.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.10.07 | 6.10.07 | Detector Magnets | 6.10.07 | Detector Magnets | Detector Solenoid Magnet | Detector Solenoid Magnet Power Supply | Magnet Power Supply | Rajput-Ghoshal | rrajput | ewoolsey | JLAB | S.P322 | 0 | 0 | 0 | 0 | 0 | 3476.47 | 6761.33 | 6761.33 | 6788.7 | 624979.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.10.06.03 | 6.10.06 | Hadronic Calorimetry | 6.10.06.03 | Forward Hadronic Calorimetry | Forward HCal Steel | Steel for the Detector Forward Hadronic Calorimeter | Forward HCal Steel | Eyser | keyser | tlewis | BNL | S.P442.B | 0 | 0 | 0 | 0 | 0 | 0 | 1088034.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.02.02 | 6.04.02 | Electron Storage Ring Magnets - Dipole, Sextupole | 6.04.02.02 | ESR Sextupole Magnets | APS Sextupole Refurbishment | Advanced Photon Source (APS) Sextupole Magnet Refurbishment, Testing, and Measurement | APS Sextupole Refurbishment & Testing | Witte | hwitte | bsmith | BNL | S.P540 | 0 | 0 | 0 | 0 | 0 | 0 | 692809.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.03.01.01.02 | 6.04.03 | Electron Storage Ring Magnets - Quadrupole, Corrector | 6.04.03.01 | ESR Magnet Quads | APS Quad Refurbishment | APS Quadrupole Magnet Refurbishment, Testing and Measurement | APS Quad Rebuild & Refurbishment | Philip | sphilip | driga | JLAB | S.P542 | 0 | 0 | 0 | 0 | 0 | 351770.75 | 13201.05 | 0 | 13201.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.03.01.01.03 | 6.04.03 | Electron Storage Ring Magnets - Quadrupole, Corrector | 6.04.03.01 | ESR Magnet Quads | ESR Magnet Measurement | ESR APS Quadrupole Magnetic Measurement Stand | APS Quad Magnet Measurement & Stand | Philip | sphilip | driga | JLAB | S.P543 | 0 | 0 | 0 | 0 | 0 | 0 | 563370.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.02.01 | 6.04.02 | Electron Storage Ring Magnets - Dipole, Sextupole | 6.04.02.01 | ESR Dipole Magnets | ESR Dipole Magnets | Electron Storage Ring (ESR) Dipole Magnets | ESR Dipole Magnets - D1/D3 Vendor I | Witte | hwitte | bsmith | BNL | T.098 | 0 | 0 | 0 | 0 | 0 | 0 | 5372.93 | 7432.55 | 7432.55 | 89.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.02.01 | 6.04.02 | Electron Storage Ring Magnets - Dipole, Sextupole | 6.04.02.01 | ESR Dipole Magnets | ESR Dipole Magnets | Electron Storage Ring (ESR) Dipole Magnets | ESR Dipole Magnets - D1/D3 Vendor II | Witte | hwitte | bsmith | BNL | T.103 | 0 | 0 | 0 | 0 | 0 | 0 | 5372.93 | 7432.55 | 7432.55 | 89.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.02.01 | 6.04.02 | Electron Storage Ring Magnets - Dipole, Sextupole | 6.04.02.01 | ESR Dipole Magnets | ESR Dipole Magnets | Electron Storage Ring (ESR) Dipole Magnets | ESR Dipole Magnets - D2 Vendor I | Witte | hwitte | bsmith | BNL | T.104 | 0 | 0 | 0 | 0 | 0 | 0 | 5372.93 | 7432.55 | 7432.55 | 89.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.02.01 | 6.04.02 | Electron Storage Ring Magnets - Dipole, Sextupole | 6.04.02.01 | ESR Dipole Magnets | ESR Dipole Magnets | Electron Storage Ring (ESR) Dipole Magnets | ESR Dipole Magnets - D2 Vendor II | Witte | hwitte | bsmith | BNL | T.107 | 0 | 0 | 0 | 0 | 0 | 0 | 5372.93 | 7432.55 | 7432.55 | 89.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.03.01.01.02 | 6.04.03 | Electron Storage Ring Magnets - Quadrupole, Corrector | 6.04.03.01 | ESR Magnet Quads | APS Quad Refurbishment | APS Quadrupole Magnet Refurbishment, Testing and Measurement | APS Quad Rebuild & Refurbishment | Philip | sphilip | driga | JLAB | T.LLP027 | 0 | 0 | 0 | 0 | 0 | 2803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.03.01.01.02 | 6.04.03 | Electron Storage Ring Magnets - Quadrupole, Corrector | 6.04.03.01 | ESR Magnet Quads | APS Quad Refurbishment | APS Quadrupole Magnet Refurbishment, Testing and Measurement | APS Quad Rebuild & Refurbishment | Philip | sphilip | driga | JLAB | T.LLP028 | 0 | 0 | 0 | 0 | 0 | 2803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0

## 2.C and 4 Data (hidden)
WBS | L3 WBS | L3 WBS DESCRIPTION | L4 WBS | L4 WBS Description | LLP Category | LLP Item | LLP Item Detail | CAM | ESTIMATOR | PMC REP | LAB | BNL_Procurement Designation | FY2020 | FY2021 | FY2022 | FY2023 | FY2024 | FY2025 | FY2026 | FY2027 | FY2028 | FY2029 | FY2030 | FY2031 | FY2032 | FY2033 | FY2034 | FY2035 | FY2036
6.10.10.02 | 6.10.10 | Integration, Installation and Infrastructure | 6.10.10.02 | Electron Endcap Structures | Detector Endcap Structures | Detector Endcap Structures – Flux Return Steel | Detector Endcap Steel for Structures | Sharma | rsharma | tlewis | BNL | A.PP085 | 0 | 0 | 0 | 0 | 0 | 2143.44 | 27534.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.10.05.02.01 | 6.10.05 | Electromagnetic Calorimetry | 6.10.05.02 | Barrel Electromagnetic Calorimetry | Scintillating Fibers | Scintillating Fibers for the Detector Barrel - Batch 2 and Forward - Batch 2 EM Calorimeters | Barrel EMCal Fibers - Option 1 - Batch 2 | Bazilevsky | shura | tlewis | BNL | A.PP091.B | 0 | 0 | 0 | 0 | 0 | 0 | 5007.7 | 6862.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.02.02 | 6.04.02 | Electron Storage Ring Magnets - Dipole, Sextupole | 6.04.02.02 | ESR Sextupole Magnets | APS Sextupole Refurbishment | Advanced Photon Source (APS) Sextupole Magnet Refurbishment, Testing, and Measurement | APS Sextupole Refurbishment & Testing | Witte | hwitte | bsmith | BNL | B | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.10.05.01.01 | 6.10.05 | Electromagnetic Calorimetry | 6.10.05.01 | Backward Electromagnetic Calorimetry | PbWO4 Crystals | Lead Tungstate Crystals for the Detector Backward Electro-Magnetic (EM) Calorimeter - Batch 3 and Batch 4 | Backward EMCal PbWO4 Crystals - Option 2 - Batch 3 | Bazilevsky | shura | tlewis | BNL | D.APP47.C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3612.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.10.05.01.01 | 6.10.05 | Electromagnetic Calorimetry | 6.10.05.01 | Backward Electromagnetic Calorimetry | PbWO4 Crystals | Lead Tungstate Crystals for the Detector Backward Electro-Magnetic (EM) Calorimeter - Batch 3 and Batch 4 | Backward EMCal PbWO4 Crystals - Option 3 - Batch 4 | Bazilevsky | shura | tlewis | BNL | D.APP47.D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2004.83 | 9143.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.02.01 | 6.04.02 | Electron Storage Ring Magnets - Dipole, Sextupole | 6.04.02.01 | ESR Dipole Magnets | ESR Dipole Magnets | Electron Storage Ring (ESR) Dipole Magnets | ESR Dipole Magnets - D1/D3 Vendor I | Witte | hwitte | bsmith | BNL | D.APP62.A | 0 | 0 | 0 | 0 | 0 | 0 | 10854.18 | 22450.28 | 15014.95 | 180.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.02.01 | 6.04.02 | Electron Storage Ring Magnets - Dipole, Sextupole | 6.04.02.01 | ESR Dipole Magnets | ESR Dipole Magnets | Electron Storage Ring (ESR) Dipole Magnets | ESR Dipole Magnets - D1/D3 Vendor II | Witte | hwitte | bsmith | BNL | D.APP62.B | 0 | 0 | 0 | 0 | 0 | 0 | 10854.18 | 22450.28 | 15014.95 | 180.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.02.01 | 6.04.02 | Electron Storage Ring Magnets - Dipole, Sextupole | 6.04.02.01 | ESR Dipole Magnets | ESR Dipole Magnets | Electron Storage Ring (ESR) Dipole Magnets | ESR Dipole Magnets - D2 Vendor I | Witte | hwitte | bsmith | BNL | D.APP63.A | 0 | 0 | 0 | 0 | 0 | 0 | 10854.18 | 22450.28 | 15014.95 | 180.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.02.01 | 6.04.02 | Electron Storage Ring Magnets - Dipole, Sextupole | 6.04.02.01 | ESR Dipole Magnets | ESR Dipole Magnets | Electron Storage Ring (ESR) Dipole Magnets | ESR Dipole Magnets - D2 Vendor II | Witte | hwitte | bsmith | BNL | D.APP63.B | 0 | 0 | 0 | 0 | 0 | 0 | 10854.18 | 22450.28 | 15014.95 | 180.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.02.01 | 6.04.02 | Electron Storage Ring Magnets - Dipole, Sextupole | 6.04.02.01 | ESR Dipole Magnets | ESR Dipole Magnets | Electron Storage Ring (ESR) Dipole Magnets | ESR Dipole Magnets - D1/D2/D3 Production Iron Material | Witte | hwitte | bsmith | BNL | D.APP64 | 0 | 0 | 0 | 0 | 0 | 0 | 12254.78 | 165607.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.02.02 | 6.04.02 | Electron Storage Ring Magnets - Dipole, Sextupole | 6.04.02.02 | ESR Sextupole Magnets | APS Sextupole Refurbishment | Advanced Photon Source (APS) Sextupole Magnet Refurbishment, Testing, and Measurement | APS Sextupole Refurbishment & Testing | Witte | hwitte | bsmith | BNL | Labor - 092 | 0 | 0 | 0 | 0 | 0 | 155281.45 | 622256.06 | 503871.65 | 487952.05 | 401544.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.02.04 | 6.04.02 | Electron Storage Ring Magnets - Dipole, Sextupole | 6.04.02.04 | ESR Magnet Measurement & Acceptance | ESR Magnet Measurement | ESR Magnetic Measurement and Bench | ESR APS Quad Magnet Measurement & Stand | Witte | hwitte | bsmith | BNL | Labor - 105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 499219.99 | 8763.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.10.08 | 6.10.08 | Electronics | 6.10.08 | Electronics | Detector Electronics | Detector Electronics Versatile Link Plus Transceiver (VRTX+) and low Power Giga-bit transceiver (1pGBT) | VRTX+ and lpGBT | Barbosa | fbarbosa | ewoolsey | JLAB | P.S1033 | 0 | 0 | 0 | 0 | 0 | 0 | 106928.9 | 25717.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.10.08 | 6.10.08 | Electronics | 6.10.08 | Electronics | Detector Electronics | Detector Electronics Versatile Link Plus Transceiver (VRTX+) and low Power Giga-bit transceiver (1pGBT) | VRTX+ and lpGBT | Barbosa | fbarbosa | ewoolsey | JLAB | P.S1131 | 0 | 0 | 0 | 0 | 0 | 0 | 95006.65 | 38002.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.02.04 | 6.04.02 | Electron Storage Ring Magnets - Dipole, Sextupole | 6.04.02.04 | ESR Magnet Measurement & Acceptance | ESR Magnet Measurement | ESR Magnetic Measurement and Bench | ESR APS Quad Magnet Measurement & Stand | Witte | hwitte | bsmith | BNL | P.S1135 | 0 | 0 | 0 | 0 | 0 | 0 | 35553.86 | 319984.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.02.01 | 6.04.02 | Electron Storage Ring Magnets - Dipole, Sextupole | 6.04.02.01 | ESR Dipole Magnets | ESR Dipole Magnets | Electron Storage Ring (ESR) Dipole Magnets | ESR Dipole Magnets - D1/D2/D3 Production Iron Material | Witte | hwitte | bsmith | BNL | P.S1138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.03.01.01.03 | 6.04.03 | Electron Storage Ring Magnets - Quadrupole, Corrector | 6.04.03.01 | ESR Magnet Quads | ESR Magnet Measurement | ESR APS Quadrupole Magnetic Measurement Stand | APS Quad Magnet Measurement & Stand | Philip | sphilip | driga | JLAB | P.S1143 | 0 | 0 | 0 | 0 | 0 | 13686.84 | 240298.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.03.01.01.02 | 6.04.03 | Electron Storage Ring Magnets - Quadrupole, Corrector | 6.04.03.01 | ESR Magnet Quads | APS Quad Refurbishment | APS Quadrupole Magnet Refurbishment, Testing and Measurement | APS Quad Rebuild & Refurbishment | Philip | sphilip | driga | JLAB | S.P.541 | 0 | 0 | 0 | 0 | 0 | 280810.81 | 803035.92 | 723078.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.10.05.03.01 | 6.10.05 | Electromagnetic Calorimetry | 6.10.05.03 | Forward Electromagnetic Calorimetry | Scintillating Fibers | Scintillating Fibers for the Detector Barrel - Batch 2 and Forward - Batch 2 EM Calorimeters | Hadron Endcap EMCal Fibers - Option 1 - Batch 2 | Bazilevsky | shura | tlewis | BNL | S.P175.B | 0 | 0 | 0 | 0 | 0 | 0 | 11283.42 | 363.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.10.07 | 6.10.07 | Detector Magnets | 6.10.07 | Detector Magnets | Detector Solenoid Magnet | Detector Solenoid Magnet Power Supply | Magnet Power Supply | Rajput-Ghoshal | rrajput | ewoolsey | JLAB | S.P322 | 0 | 0 | 0 | 0 | 0 | 13129.06 | 25586.3 | 25586.3 | 25663.77 | 1111.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.10.06.03 | 6.10.06 | Hadronic Calorimetry | 6.10.06.03 | Forward Hadronic Calorimetry | Forward HCal Steel | Steel for the Detector Forward Hadronic Calorimeter | Forward HCal Steel | Eyser | keyser | tlewis | BNL | S.P442.B | 0 | 0 | 0 | 0 | 0 | 0 | 495.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.02.02 | 6.04.02 | Electron Storage Ring Magnets - Dipole, Sextupole | 6.04.02.02 | ESR Sextupole Magnets | APS Sextupole Refurbishment | Advanced Photon Source (APS) Sextupole Magnet Refurbishment, Testing, and Measurement | APS Sextupole Refurbishment & Testing | Witte | hwitte | bsmith | BNL | S.P540 | 0 | 0 | 0 | 0 | 0 | 0 | 2644.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.03.01.01.02 | 6.04.03 | Electron Storage Ring Magnets - Quadrupole, Corrector | 6.04.03.01 | ESR Magnet Quads | APS Quad Refurbishment | APS Quadrupole Magnet Refurbishment, Testing and Measurement | APS Quad Rebuild & Refurbishment | Philip | sphilip | driga | JLAB | S.P542 | 0 | 0 | 0 | 0 | 0 | 22183.34 | 319225.6 | 326821.16 | 2041.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.03.01.01.03 | 6.04.03 | Electron Storage Ring Magnets - Quadrupole, Corrector | 6.04.03.01 | ESR Magnet Quads | ESR Magnet Measurement | ESR APS Quadrupole Magnetic Measurement Stand | APS Quad Magnet Measurement & Stand | Philip | sphilip | driga | JLAB | S.P543 | 0 | 0 | 0 | 0 | 0 | 8337.45 | 28069.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.02.01 | 6.04.02 | Electron Storage Ring Magnets - Dipole, Sextupole | 6.04.02.01 | ESR Dipole Magnets | ESR Dipole Magnets | Electron Storage Ring (ESR) Dipole Magnets | ESR Dipole Magnets - D1/D3 Vendor I | Witte | hwitte | bsmith | BNL | T.098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.02.01 | 6.04.02 | Electron Storage Ring Magnets - Dipole, Sextupole | 6.04.02.01 | ESR Dipole Magnets | ESR Dipole Magnets | Electron Storage Ring (ESR) Dipole Magnets | ESR Dipole Magnets - D1/D3 Vendor II | Witte | hwitte | bsmith | BNL | T.103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.02.01 | 6.04.02 | Electron Storage Ring Magnets - Dipole, Sextupole | 6.04.02.01 | ESR Dipole Magnets | ESR Dipole Magnets | Electron Storage Ring (ESR) Dipole Magnets | ESR Dipole Magnets - D2 Vendor I | Witte | hwitte | bsmith | BNL | T.104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.02.01 | 6.04.02 | Electron Storage Ring Magnets - Dipole, Sextupole | 6.04.02.01 | ESR Dipole Magnets | ESR Dipole Magnets | Electron Storage Ring (ESR) Dipole Magnets | ESR Dipole Magnets - D2 Vendor II | Witte | hwitte | bsmith | BNL | T.107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.03.01.01.02 | 6.04.03 | Electron Storage Ring Magnets - Quadrupole, Corrector | 6.04.03.01 | ESR Magnet Quads | APS Quad Refurbishment | APS Quadrupole Magnet Refurbishment, Testing and Measurement | APS Quad Rebuild & Refurbishment | Philip | sphilip | driga | JLAB | T.LLP027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.03.01.01.02 | 6.04.03 | Electron Storage Ring Magnets - Quadrupole, Corrector | 6.04.03.01 | ESR Magnet Quads | APS Quad Refurbishment | APS Quadrupole Magnet Refurbishment, Testing and Measurement | APS Quad Rebuild & Refurbishment | Philip | sphilip | driga | JLAB | T.LLP028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.10.10.02 | 6.10.10 | Integration, Installation and Infrastructure | 6.10.10.02 | Electron Endcap Structures | Detector Endcap Structures | Detector Endcap Structures – Flux Return Steel | Detector Endcap Steel for Structures | Sharma | rsharma | tlewis | BNL | A.PP085 | 0 | 0 | 0 | 0 | 0 | 2955838.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.10.05.02.01 | 6.10.05 | Electromagnetic Calorimetry | 6.10.05.02 | Barrel Electromagnetic Calorimetry | Scintillating Fibers | Scintillating Fibers for the Detector Barrel - Batch 2 and Forward - Batch 2 EM Calorimeters | Barrel EMCal Fibers - Option 1 - Batch 2 | Bazilevsky | shura | tlewis | BNL | A.PP091.B | 0 | 0 | 0 | 0 | 0 | 0 | 1611322.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.02.02 | 6.04.02 | Electron Storage Ring Magnets - Dipole, Sextupole | 6.04.02.02 | ESR Sextupole Magnets | APS Sextupole Refurbishment | Advanced Photon Source (APS) Sextupole Magnet Refurbishment, Testing, and Measurement | APS Sextupole Refurbishment & Testing | Witte | hwitte | bsmith | BNL | B | 0 | 0 | 0 | 0 | 0 | 22072.28 | 12518.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.10.05.01.01 | 6.10.05 | Electromagnetic Calorimetry | 6.10.05.01 | Backward Electromagnetic Calorimetry | PbWO4 Crystals | Lead Tungstate Crystals for the Detector Backward Electro-Magnetic (EM) Calorimeter - Batch 3 and Batch 4 | Backward EMCal PbWO4 Crystals - Option 2 - Batch 3 | Bazilevsky | shura | tlewis | BNL | D.APP47.C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1338366.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.10.05.01.01 | 6.10.05 | Electromagnetic Calorimetry | 6.10.05.01 | Backward Electromagnetic Calorimetry | PbWO4 Crystals | Lead Tungstate Crystals for the Detector Backward Electro-Magnetic (EM) Calorimeter - Batch 3 and Batch 4 | Backward EMCal PbWO4 Crystals - Option 3 - Batch 4 | Bazilevsky | shura | tlewis | BNL | D.APP47.D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1338366.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.02.01 | 6.04.02 | Electron Storage Ring Magnets - Dipole, Sextupole | 6.04.02.01 | ESR Dipole Magnets | ESR Dipole Magnets | Electron Storage Ring (ESR) Dipole Magnets | ESR Dipole Magnets - D1/D3 Vendor I | Witte | hwitte | bsmith | BNL | D.APP62.A | 0 | 0 | 0 | 0 | 0 | 0 | 2417282.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.02.01 | 6.04.02 | Electron Storage Ring Magnets - Dipole, Sextupole | 6.04.02.01 | ESR Dipole Magnets | ESR Dipole Magnets | Electron Storage Ring (ESR) Dipole Magnets | ESR Dipole Magnets - D1/D3 Vendor II | Witte | hwitte | bsmith | BNL | D.APP62.B | 0 | 0 | 0 | 0 | 0 | 0 | 2417282.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.02.01 | 6.04.02 | Electron Storage Ring Magnets - Dipole, Sextupole | 6.04.02.01 | ESR Dipole Magnets | ESR Dipole Magnets | Electron Storage Ring (ESR) Dipole Magnets | ESR Dipole Magnets - D2 Vendor I | Witte | hwitte | bsmith | BNL | D.APP63.A | 0 | 0 | 0 | 0 | 0 | 0 | 2370177.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.02.01 | 6.04.02 | Electron Storage Ring Magnets - Dipole, Sextupole | 6.04.02.01 | ESR Dipole Magnets | ESR Dipole Magnets | Electron Storage Ring (ESR) Dipole Magnets | ESR Dipole Magnets - D2 Vendor II | Witte | hwitte | bsmith | BNL | D.APP63.B | 0 | 0 | 0 | 0 | 0 | 0 | 2370177.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.02.01 | 6.04.02 | Electron Storage Ring Magnets - Dipole, Sextupole | 6.04.02.01 | ESR Dipole Magnets | ESR Dipole Magnets | Electron Storage Ring (ESR) Dipole Magnets | ESR Dipole Magnets - D1/D2/D3 Production Iron Material | Witte | hwitte | bsmith | BNL | D.APP64 | 0 | 0 | 0 | 0 | 0 | 0 | 5821392.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.02.02 | 6.04.02 | Electron Storage Ring Magnets - Dipole, Sextupole | 6.04.02.02 | ESR Sextupole Magnets | APS Sextupole Refurbishment | Advanced Photon Source (APS) Sextupole Magnet Refurbishment, Testing, and Measurement | APS Sextupole Refurbishment & Testing | Witte | hwitte | bsmith | BNL | Labor - 092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.02.04 | 6.04.02 | Electron Storage Ring Magnets - Dipole, Sextupole | 6.04.02.04 | ESR Magnet Measurement & Acceptance | ESR Magnet Measurement | ESR Magnetic Measurement and Bench | ESR APS Quad Magnet Measurement & Stand | Witte | hwitte | bsmith | BNL | Labor - 105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.10.08 | 6.10.08 | Electronics | 6.10.08 | Electronics | Detector Electronics | Detector Electronics Versatile Link Plus Transceiver (VRTX+) and low Power Giga-bit transceiver (1pGBT) | VRTX+ and lpGBT | Barbosa | fbarbosa | ewoolsey | JLAB | P.S1033 | 0 | 0 | 0 | 0 | 0 | 0 | 1396700.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.10.08 | 6.10.08 | Electronics | 6.10.08 | Electronics | Detector Electronics | Detector Electronics Versatile Link Plus Transceiver (VRTX+) and low Power Giga-bit transceiver (1pGBT) | VRTX+ and lpGBT | Barbosa | fbarbosa | ewoolsey | JLAB | P.S1131 | 0 | 0 | 0 | 0 | 0 | 0 | 71008.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.02.04 | 6.04.02 | Electron Storage Ring Magnets - Dipole, Sextupole | 6.04.02.04 | ESR Magnet Measurement & Acceptance | ESR Magnet Measurement | ESR Magnetic Measurement and Bench | ESR APS Quad Magnet Measurement & Stand | Witte | hwitte | bsmith | BNL | P.S1135 | 0 | 0 | 0 | 0 | 0 | 0 | 181755.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.02.01 | 6.04.02 | Electron Storage Ring Magnets - Dipole, Sextupole | 6.04.02.01 | ESR Dipole Magnets | ESR Dipole Magnets | Electron Storage Ring (ESR) Dipole Magnets | ESR Dipole Magnets - D1/D2/D3 Production Iron Material | Witte | hwitte | bsmith | BNL | P.S1138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85311.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.03.01.01.03 | 6.04.03 | Electron Storage Ring Magnets - Quadrupole, Corrector | 6.04.03.01 | ESR Magnet Quads | ESR Magnet Measurement | ESR APS Quadrupole Magnetic Measurement Stand | APS Quad Magnet Measurement & Stand | Philip | sphilip | driga | JLAB | P.S1143 | 0 | 0 | 0 | 0 | 0 | 90147.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.03.01.01.02 | 6.04.03 | Electron Storage Ring Magnets - Quadrupole, Corrector | 6.04.03.01 | ESR Magnet Quads | APS Quad Refurbishment | APS Quadrupole Magnet Refurbishment, Testing and Measurement | APS Quad Rebuild & Refurbishment | Philip | sphilip | driga | JLAB | S.P.541 | 0 | 0 | 0 | 0 | 0 | 1281019.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.10.05.03.01 | 6.10.05 | Electromagnetic Calorimetry | 6.10.05.03 | Forward Electromagnetic Calorimetry | Scintillating Fibers | Scintillating Fibers for the Detector Barrel - Batch 2 and Forward - Batch 2 EM Calorimeters | Hadron Endcap EMCal Fibers - Option 1 - Batch 2 | Bazilevsky | shura | tlewis | BNL | S.P175.B | 0 | 0 | 0 | 0 | 0 | 0 | 543029.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.10.07 | 6.10.07 | Detector Magnets | 6.10.07 | Detector Magnets | Detector Solenoid Magnet | Detector Solenoid Magnet Power Supply | Magnet Power Supply | Rajput-Ghoshal | rrajput | ewoolsey | JLAB | S.P322 | 0 | 0 | 0 | 0 | 0 | 648767.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.10.06.03 | 6.10.06 | Hadronic Calorimetry | 6.10.06.03 | Forward Hadronic Calorimetry | Forward HCal Steel | Steel for the Detector Forward Hadronic Calorimeter | Forward HCal Steel | Eyser | keyser | tlewis | BNL | S.P442.B | 0 | 0 | 0 | 0 | 0 | 0 | 1088034.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.02.02 | 6.04.02 | Electron Storage Ring Magnets - Dipole, Sextupole | 6.04.02.02 | ESR Sextupole Magnets | APS Sextupole Refurbishment | Advanced Photon Source (APS) Sextupole Magnet Refurbishment, Testing, and Measurement | APS Sextupole Refurbishment & Testing | Witte | hwitte | bsmith | BNL | S.P540 | 0 | 0 | 0 | 0 | 0 | 0 | 692809.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.03.01.01.02 | 6.04.03 | Electron Storage Ring Magnets - Quadrupole, Corrector | 6.04.03.01 | ESR Magnet Quads | APS Quad Refurbishment | APS Quadrupole Magnet Refurbishment, Testing and Measurement | APS Quad Rebuild & Refurbishment | Philip | sphilip | driga | JLAB | S.P542 | 0 | 0 | 0 | 0 | 0 | 378172.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.03.01.01.03 | 6.04.03 | Electron Storage Ring Magnets - Quadrupole, Corrector | 6.04.03.01 | ESR Magnet Quads | ESR Magnet Measurement | ESR APS Quadrupole Magnetic Measurement Stand | APS Quad Magnet Measurement & Stand | Philip | sphilip | driga | JLAB | S.P543 | 0 | 0 | 0 | 0 | 0 | 563370.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.02.01 | 6.04.02 | Electron Storage Ring Magnets - Dipole, Sextupole | 6.04.02.01 | ESR Dipole Magnets | ESR Dipole Magnets | Electron Storage Ring (ESR) Dipole Magnets | ESR Dipole Magnets - D1/D3 Vendor I | Witte | hwitte | bsmith | BNL | T.098 | 0 | 0 | 0 | 0 | 0 | 0 | 5372.93 | 7432.55 | 7432.55 | 89.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.02.01 | 6.04.02 | Electron Storage Ring Magnets - Dipole, Sextupole | 6.04.02.01 | ESR Dipole Magnets | ESR Dipole Magnets | Electron Storage Ring (ESR) Dipole Magnets | ESR Dipole Magnets - D1/D3 Vendor II | Witte | hwitte | bsmith | BNL | T.103 | 0 | 0 | 0 | 0 | 0 | 0 | 5372.93 | 7432.55 | 7432.55 | 89.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.02.01 | 6.04.02 | Electron Storage Ring Magnets - Dipole, Sextupole | 6.04.02.01 | ESR Dipole Magnets | ESR Dipole Magnets | Electron Storage Ring (ESR) Dipole Magnets | ESR Dipole Magnets - D2 Vendor I | Witte | hwitte | bsmith | BNL | T.104 | 0 | 0 | 0 | 0 | 0 | 0 | 5372.93 | 7432.55 | 7432.55 | 89.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.02.01 | 6.04.02 | Electron Storage Ring Magnets - Dipole, Sextupole | 6.04.02.01 | ESR Dipole Magnets | ESR Dipole Magnets | Electron Storage Ring (ESR) Dipole Magnets | ESR Dipole Magnets - D2 Vendor II | Witte | hwitte | bsmith | BNL | T.107 | 0 | 0 | 0 | 0 | 0 | 0 | 5372.93 | 7432.55 | 7432.55 | 89.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.03.01.01.02 | 6.04.03 | Electron Storage Ring Magnets - Quadrupole, Corrector | 6.04.03.01 | ESR Magnet Quads | APS Quad Refurbishment | APS Quadrupole Magnet Refurbishment, Testing and Measurement | APS Quad Rebuild & Refurbishment | Philip | sphilip | driga | JLAB | T.LLP027 | 0 | 0 | 0 | 0 | 0 | 2803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.04.03.01.01.02 | 6.04.03 | Electron Storage Ring Magnets - Quadrupole, Corrector | 6.04.03.01 | ESR Magnet Quads | APS Quad Refurbishment | APS Quadrupole Magnet Refurbishment, Testing and Measurement | APS Quad Rebuild & Refurbishment | Philip | sphilip | driga | JLAB | T.LLP028 | 0 | 0 | 0 | 0 | 0 | 2803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0

## 4-Obligation Profile (hidden)
|  | Total Sum Check | [18 empty] | For Formulas: | CD3A.SCOPE
Nonlabor
|  | BNL_Procurement Designation | TOTAL | FY2020 | FY2021 | FY2022 | FY2023 | FY2024 | FY2025 | FY2026 | FY2027 | FY2028 | FY2029 | FY2030 | FY2031 | FY2032 | FY2033 | FY2034 | FY2035 | FY2036 |  | DOE.IRA
Delta | SUMIFS | TOTAL | 29781838.66 | 0 | 0 | 0 | 0 | 0 | 5944994.04 | 21014982.05 | 2791774.17 | 29730.2 | 358.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | DOE.DOE
0 |  | A.PP085 | 2955838.88 | 0 | 0 | 0 | 0 | 0 | 2955838.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | DOE.DET
0 |  | A.PP091.B | 1611322.71 | 0 | 0 | 0 | 0 | 0 | 0 | 1611322.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | SUMIFS | B | 34590.55 | 0 | 0 | 0 | 0 | 0 | 22072.28 | 12518.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | D.APP47.C | 1338366.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1338366.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | D.APP47.D | 1338366.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1338366.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | D.APP62.A | 2417282.31 | 0 | 0 | 0 | 0 | 0 | 0 | 2417282.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | D.APP62.B | 2417282.31 | 0 | 0 | 0 | 0 | 0 | 0 | 2417282.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | D.APP63.A | 2370177.72 | 0 | 0 | 0 | 0 | 0 | 0 | 2370177.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | D.APP63.B | 2370177.72 | 0 | 0 | 0 | 0 | 0 | 0 | 2370177.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | D.APP64 | 5821392.09 | 0 | 0 | 0 | 0 | 0 | 0 | 5821392.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | Labor - 092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | Labor - 105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | P.S1033 | 1396700.51 | 0 | 0 | 0 | 0 | 0 | 0 | 1396700.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | P.S1131 | 71008.63 | 0 | 0 | 0 | 0 | 0 | 0 | 71008.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | P.S1135 | 181755.46 | 0 | 0 | 0 | 0 | 0 | 0 | 181755.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | P.S1138 | 85311.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85311.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | P.S1143 | 90147.12 | 0 | 0 | 0 | 0 | 0 | 90147.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | S.P.541 | 1281019.11 | 0 | 0 | 0 | 0 | 0 | 1281019.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | S.P175.B | 543029.24 | 0 | 0 | 0 | 0 | 0 | 0 | 543029.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | S.P322 | 648767.03 | 0 | 0 | 0 | 0 | 0 | 648767.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | S.P442.B | 1088034.32 | 0 | 0 | 0 | 0 | 0 | 0 | 1088034.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | S.P540 | 692809.04 | 0 | 0 | 0 | 0 | 0 | 0 | 692809.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | S.P542 | 378172.85 | 0 | 0 | 0 | 0 | 0 | 378172.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  | S.P543 | 563370.77 | 0 | 0 | 0 | 0 | 0 | 563370.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | SUMIFS | T.098 | 20327.58 | 0 | 0 | 0 | 0 | 0 | 0 | 5372.93 | 7432.55 | 7432.55 | 89.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | SUMIFS | T.103 | 20327.58 | 0 | 0 | 0 | 0 | 0 | 0 | 5372.93 | 7432.55 | 7432.55 | 89.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | SUMIFS | T.104 | 20327.58 | 0 | 0 | 0 | 0 | 0 | 0 | 5372.93 | 7432.55 | 7432.55 | 89.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | SUMIFS | T.107 | 20327.58 | 0 | 0 | 0 | 0 | 0 | 0 | 5372.93 | 7432.55 | 7432.55 | 89.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | SUMIFS | T.LLP027 | 2803 | 0 | 0 | 0 | 0 | 0 | 2803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | SUMIFS | T.LLP028 | 2803 | 0 | 0 | 0 | 0 | 0 | 2803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## 3-Contract Awards (hidden)
Total Sum Check | [18 empty] | For Formulas: | CD3B.SCOPE
| 0.21 | 0.21 | [17 empty] | Nonlabor
BNL_Procurement Designation | TOTAL | FY2020 | FY2021 | FY2022 | FY2023 | FY2024 | FY2025 | FY2026 | FY2027 | FY2028 | FY2029 | FY2030 | FY2031 | FY2032 | FY2033 | FY2034 | FY2035 | FY2036 |  | DOE.IRA
TOTAL | 0.21 | 0 | 0 | 0 | 0 | 0 | 0.06 | 0.12 | 0.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | DOE.DOE
A.PP085 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | DOE.DET
A.PP091.B | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Contract Award
B | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | DOE.DETL
D.APP47.C | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D.APP47.D | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D.APP62.A | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D.APP62.B | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D.APP63.A | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D.APP63.B | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D.APP64 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Labor - 092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Labor - 105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P.S1033 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P.S1131 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P.S1135 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P.S1138 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P.S1143 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S.P.541 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S.P175.B | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S.P322 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S.P442.B | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S.P540 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S.P542 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S.P543 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T.098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T.103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T.104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T.107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T.LLP027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T.LLP028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## 2.C-Cost Profile Labor ONLY (hidden)
Total Sum Check | [18 empty] | For Formulas: | CD3B.SCOPE
New Procurements Check | CHECK | [18 empty] | Labor
BNL_Procurement Designation | TOTAL | FY2020 | FY2021 | FY2022 | FY2023 | FY2024 | FY2025 | FY2026 | FY2027 | FY2028 | FY2029 | FY2030 | FY2031 | FY2032 | FY2033 | FY2034 | FY2035 | FY2036 |  | DOE.IRA
TOTAL | 6601710.16 | 0 | 0 | 0 | 0 | 0 | 495572.39 | 2378599.01 | 2231314.51 | 1084081.04 | 412143.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | DOE.DOE
A.PP085 | 29678.36 | 0 | 0 | 0 | 0 | 0 | 2143.44 | 27534.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | DOE.DET
A.PP091.B | 11870.1 | 0 | 0 | 0 | 0 | 0 | 0 | 5007.7 | 6862.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | DOE.DETL
B | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D.APP47.C | 3612.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3612.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D.APP47.D | 11148.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2004.83 | 9143.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D.APP62.A | 48500.31 | 0 | 0 | 0 | 0 | 0 | 0 | 10854.18 | 22450.28 | 15014.95 | 180.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D.APP62.B | 48500.31 | 0 | 0 | 0 | 0 | 0 | 0 | 10854.18 | 22450.28 | 15014.95 | 180.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D.APP63.A | 48500.31 | 0 | 0 | 0 | 0 | 0 | 0 | 10854.18 | 22450.28 | 15014.95 | 180.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D.APP63.B | 48500.31 | 0 | 0 | 0 | 0 | 0 | 0 | 10854.18 | 22450.28 | 15014.95 | 180.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D.APP64 | 177861.88 | 0 | 0 | 0 | 0 | 0 | 0 | 12254.78 | 165607.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Labor - 092 | 2170905.94 | 0 | 0 | 0 | 0 | 0 | 155281.45 | 622256.06 | 503871.65 | 487952.05 | 401544.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Labor - 105 | 507983.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 499219.99 | 8763.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P.S1033 | 132645.98 | 0 | 0 | 0 | 0 | 0 | 0 | 106928.9 | 25717.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P.S1131 | 133009.31 | 0 | 0 | 0 | 0 | 0 | 0 | 95006.65 | 38002.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P.S1135 | 355538.61 | 0 | 0 | 0 | 0 | 0 | 0 | 35553.86 | 319984.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P.S1138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P.S1143 | 253985.23 | 0 | 0 | 0 | 0 | 0 | 13686.84 | 240298.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S.P.541 | 1806925.64 | 0 | 0 | 0 | 0 | 0 | 280810.81 | 803035.92 | 723078.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S.P175.B | 11647.4 | 0 | 0 | 0 | 0 | 0 | 0 | 11283.42 | 363.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S.P322 | 91076.69 | 0 | 0 | 0 | 0 | 0 | 13129.06 | 25586.3 | 25586.3 | 25663.77 | 1111.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S.P442.B | 495.85 | 0 | 0 | 0 | 0 | 0 | 0 | 495.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S.P540 | 2644.53 | 0 | 0 | 0 | 0 | 0 | 0 | 2644.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S.P542 | 670271.56 | 0 | 0 | 0 | 0 | 0 | 22183.34 | 319225.6 | 326821.16 | 2041.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S.P543 | 36406.86 | 0 | 0 | 0 | 0 | 0 | 8337.45 | 28069.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T.098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T.103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T.104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T.107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T.LLP027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T.LLP028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## 2.B-Cost Profile NL ONLY (hidden)
Total Sum Check | [18 empty] | For Formulas: | CD3B.SCOPE
New Procurements Check | CHECK | [18 empty] | Nonlabor
BNL_Procurement Designation | TOTAL | FY2020 | FY2021 | FY2022 | FY2023 | FY2024 | FY2025 | FY2026 | FY2027 | FY2028 | FY2029 | FY2030 | FY2031 | FY2032 | FY2033 | FY2034 | FY2035 | FY2036 |  | DOE.IRA
TOTAL | 29781838.66 | 0 | 0 | 0 | 0 | 0 | 1582732.57 | 5476814 | 11619771.22 | 5932634.77 | 5169886.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | DOE.DOE
A.PP085 | 2955838.88 | 0 | 0 | 0 | 0 | 0 | 0 | 2955838.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | DOE.DET
A.PP091.B | 1611322.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1611322.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | DOE.DETL
B | 34590.55 | 0 | 0 | 0 | 0 | 0 | 22072.28 | 12518.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D.APP47.C | 1338366.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1338366.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D.APP47.D | 1338366.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1338366.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D.APP62.A | 2417282.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 133349.89 | 1141966.21 | 1141966.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D.APP62.B | 2417282.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 133349.89 | 1141966.21 | 1141966.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D.APP63.A | 2370177.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109561.44 | 1130308.14 | 1130308.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D.APP63.B | 2370177.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109561.44 | 1130308.14 | 1130308.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D.APP64 | 5821392.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5821392.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Labor - 092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Labor - 105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P.S1033 | 1396700.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1396700.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P.S1131 | 71008.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71008.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P.S1135 | 181755.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 181755.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P.S1138 | 85311.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85311.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P.S1143 | 90147.12 | 0 | 0 | 0 | 0 | 0 | 0 | 90147.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S.P.541 | 1281019.11 | 0 | 0 | 0 | 0 | 0 | 1199807.07 | 32641.5 | 48570.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S.P175.B | 543029.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 543029.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S.P322 | 648767.03 | 0 | 0 | 0 | 0 | 0 | 3476.47 | 6761.33 | 6761.33 | 6788.7 | 624979.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S.P442.B | 1088034.32 | 0 | 0 | 0 | 0 | 0 | 0 | 1088034.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S.P540 | 692809.04 | 0 | 0 | 0 | 0 | 0 | 0 | 692809.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S.P542 | 378172.85 | 0 | 0 | 0 | 0 | 0 | 351770.75 | 13201.05 | 0 | 13201.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S.P543 | 563370.77 | 0 | 0 | 0 | 0 | 0 | 0 | 563370.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T.098 | 20327.58 | 0 | 0 | 0 | 0 | 0 | 0 | 5372.93 | 7432.55 | 7432.55 | 89.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T.103 | 20327.58 | 0 | 0 | 0 | 0 | 0 | 0 | 5372.93 | 7432.55 | 7432.55 | 89.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T.104 | 20327.58 | 0 | 0 | 0 | 0 | 0 | 0 | 5372.93 | 7432.55 | 7432.55 | 89.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T.107 | 20327.58 | 0 | 0 | 0 | 0 | 0 | 0 | 5372.93 | 7432.55 | 7432.55 | 89.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T.LLP027 | 2803 | 0 | 0 | 0 | 0 | 0 | 2803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T.LLP028 | 2803 | 0 | 0 | 0 | 0 | 0 | 2803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## 2.A-Cost Profile - L and NL (hidden)
| Total Sum Check | [18 empty] | For Formulas: | CD3B.SCOPE
| New Procurements Check | CHECK | [18 empty] | Nonlabor
|  | TOTAL | FY2020 | FY2021 | FY2022 | FY2023 | FY2024 | FY2025 | FY2026 | FY2027 | FY2028 | FY2029 | FY2030 | FY2031 | FY2032 | FY2033 | FY2034 | FY2035 | FY2036 |  | DOE.IRA
BNL_Procurement Designation | TOTAL | 36383548.82 | 0 | 0 | 0 | 0 | 0 | 2078304.96 | 7855413.01 | 13851085.73 | 7016715.81 | 5582029.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | DOE.DOE
A.PP085 | A.PP085 | 2985517.24 | 0 | 0 | 0 | 0 | 0 | 2143.44 | 2983373.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | DOE.DET
A.PP091.B | A.PP091.B | 1623192.81 | 0 | 0 | 0 | 0 | 0 | 0 | 5007.7 | 1618185.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | DOE.DETL
B | B | 34590.55 | 0 | 0 | 0 | 0 | 0 | 22072.28 | 12518.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D.APP47.C | D.APP47.C | 1341978.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1341978.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D.APP47.D | D.APP47.D | 1349514.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2004.83 | 1347510.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D.APP62.A | D.APP62.A | 2465782.62 | 0 | 0 | 0 | 0 | 0 | 0 | 10854.18 | 155800.17 | 1156981.16 | 1142147.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D.APP62.B | D.APP62.B | 2465782.62 | 0 | 0 | 0 | 0 | 0 | 0 | 10854.18 | 155800.17 | 1156981.16 | 1142147.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D.APP63.A | D.APP63.A | 2418678.03 | 0 | 0 | 0 | 0 | 0 | 0 | 10854.18 | 132011.72 | 1145323.09 | 1130489.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D.APP63.B | D.APP63.B | 2418678.03 | 0 | 0 | 0 | 0 | 0 | 0 | 10854.18 | 132011.72 | 1145323.09 | 1130489.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D.APP64 | D.APP64 | 5999253.97 | 0 | 0 | 0 | 0 | 0 | 0 | 12254.78 | 5986999.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Labor - 092 | Labor - 092 | 2170905.94 | 0 | 0 | 0 | 0 | 0 | 155281.45 | 622256.06 | 503871.65 | 487952.05 | 401544.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Labor - 105 | Labor - 105 | 507983.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 499219.99 | 8763.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P.S1033 | P.S1033 | 1529346.49 | 0 | 0 | 0 | 0 | 0 | 0 | 106928.9 | 1422417.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P.S1131 | P.S1131 | 204017.94 | 0 | 0 | 0 | 0 | 0 | 0 | 95006.65 | 109011.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P.S1135 | P.S1135 | 537294.07 | 0 | 0 | 0 | 0 | 0 | 0 | 35553.86 | 501740.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P.S1138 | P.S1138 | 85311.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85311.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P.S1143 | P.S1143 | 344132.35 | 0 | 0 | 0 | 0 | 0 | 13686.84 | 330445.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S.P.541 | S.P.541 | 3087944.75 | 0 | 0 | 0 | 0 | 0 | 1480617.88 | 835677.42 | 771649.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S.P175.B | S.P175.B | 554676.64 | 0 | 0 | 0 | 0 | 0 | 0 | 11283.42 | 543393.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S.P322 | S.P322 | 739843.72 | 0 | 0 | 0 | 0 | 0 | 16605.53 | 32347.63 | 32347.63 | 32452.47 | 626090.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S.P442.B | S.P442.B | 1088530.17 | 0 | 0 | 0 | 0 | 0 | 0 | 1088530.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S.P540 | S.P540 | 695453.57 | 0 | 0 | 0 | 0 | 0 | 0 | 695453.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S.P542 | S.P542 | 1048444.41 | 0 | 0 | 0 | 0 | 0 | 373954.09 | 332426.65 | 326821.16 | 15242.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S.P543 | S.P543 | 599777.63 | 0 | 0 | 0 | 0 | 0 | 8337.45 | 591440.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T.098 | T.098 | 20327.58 | 0 | 0 | 0 | 0 | 0 | 0 | 5372.93 | 7432.55 | 7432.55 | 89.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T.103 | T.103 | 20327.58 | 0 | 0 | 0 | 0 | 0 | 0 | 5372.93 | 7432.55 | 7432.55 | 89.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T.104 | T.104 | 20327.58 | 0 | 0 | 0 | 0 | 0 | 0 | 5372.93 | 7432.55 | 7432.55 | 89.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T.107 | T.107 | 20327.58 | 0 | 0 | 0 | 0 | 0 | 0 | 5372.93 | 7432.55 | 7432.55 | 89.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T.LLP027 | T.LLP027 | 2803 | 0 | 0 | 0 | 0 | 0 | 2803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T.LLP028 | T.LLP028 | 2803 | 0 | 0 | 0 | 0 | 0 | 2803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## 1.B- P6 CD3B ONLY (02.Oct.2024) (hidden)
TRIM Proc Des | LLPITEM # | LLP ITEM | LLP Category # | LLP Category | Activity ID | Original Duration | Start | Finish | Labor Hours | Budgeted Labor Cost | Direct Mat'l Cost | Budgeted Nonlabor Cost | Budgeted Total Cost | Total Float
D.APP47.C | ITEM002.A | Backward EMCal PbWO4 Crystals - Option 2 - Batch 3 | LLP027 | Scintillating Fibers | D.APP47.C | 198d | 2026-10-23 | 46610 | 18 | 3612.57 | 1180000 | 1338366.12 | 1341978.69 | 846d
D.APP47.D | ITEM002.B | Backward EMCal PbWO4 Crystals - Option 3 - Batch 4 | LLP028 | Scintillating Fibers | D.APP47.D | 199d | 2027-08-11 | 46899 | 304 | 11148.8 | 1180000 | 1338366.12 | 1349514.93 | 846d
D.APP62.A | ITEM098 | ESR Dipole Magnets - D1/D3 Vendor I | LLP029 | Scintillating Fibers | D.APP62.A | 681d | 2026-01-13 | 47030 | 260 | 48500.28 | 2180269 | 2417282.31 | 2465782.6 | 280d
D.APP62.B | ITEM103 | ESR Dipole Magnets - D1/D3 Vendor II | LLP030 | Scintillating Fibers | D.APP62.B | 681d | 2026-01-13 | 47030 | 260 | 48500.28 | 2180269 | 2417282.31 | 2465782.6 | 280d
D.APP63.A | ITEM104 | ESR Dipole Magnets - D2 Vendor I | LLP031 | Scintillating Fibers | D.APP63.A | 681d | 2026-01-13 | 47030 | 260 | 48500.28 | 2137783 | 2370177.73 | 2418678.02 | 285d
D.APP63.B | ITEM107 | ESR Dipole Magnets - D2 Vendor II | LLP032 | Scintillating Fibers | D.APP63.B | 681d | 2026-01-13 | 47030 | 260 | 48500.28 | 2137783 | 2370177.73 | 2418678.02 | 285d
D.APP64 | ITEM108 | ESR Dipole Magnets - D1/D2/D3 Production Iron Material | LLP033 | Scintillating Fibers | D.APP64 | 250d | 2026-05-07 | 46517 | 922 | 177861.87 | 5250607.52 | 5821392.08 | 5999253.96 | 280d
A.PP085 | ITEM093 | Detector Endcap Steel for Structures | LLP034 | Scintillating Fibers | A.PP085 | 181d | 2025-09-11 | 46177 | 180 | 29678.36 | 2750000 | 2955838.88 | 2985517.23 | 804d
A.PP091.B | ITEM078.A | Barrel EMCal Fibers - Option 1 - Batch 2 | LLP035 | Scintillating Fibers | A.PP091.B | 257d | 2026-04-27 | 46514 | 348 | 11870.09 | 1453333.33 | 1611322.71 | 1623192.8 | 220d
S.P175.B | ITEM077.A | Hadron Endcap EMCal Fibers - Option 1 - Batch 2 | LLP036 | Scintillating Fibers | S.P175.B | 257d | 2025-10-01 | 46309 | 348 | 11647.4 | 489785.5 | 543029.24 | 554676.64 | 1071d
S.P322 | ITEM091 | Magnet Power Supply | LLP037 | Scintillating Fibers | S.P322 | 885d | 2025-03-31 | 47043 | 601 | 91076.68 | 573598 | 648767.04 | 739843.72 | 735d
S.P442.B | ITEM005 | Forward HCal Steel | LLP038 | Scintillating Fibers | S.P442.B | 61d | 2025-11-19 | 46073 | 3 | 495.85 | 981353.1 | 1088034.32 | 1088530.17 | 968d
S.P540 | ITEM092 | APS Sextupole Refurbishment & Testing | LLP039 | Scintillating Fibers | S.P540 | 81d | 2026-01-23 | 46161 | 16 | 2644.53 | 624879.46 | 692809.04 | 695453.57 | 472d
S.P.541 | ITEM089 | APS Quad Rebuild & Refurbishment | LLP040 | Scintillating Fibers | S.P.541 | 571d | 2025-05-01 | 46622 | 15996 | 1806925.73 | 1167477.38 | 1281019.1 | 3087944.83 | 595d
S.P542 | ITEM089 | APS Quad Rebuild & Refurbishment | LLP041 | Scintillating Fibers | S.P542 | 608d | 2025-05-01 | 46674 | 5812 | 670271.54 | 327743.4 | 378172.86 | 1048444.4 | 883d
S.P543 | ITEM096 | APS Quad Magnet Measurement & Stand | LLP042 | Scintillating Fibers | S.P543 | 131d | 2025-08-18 | 46085 | 260 | 36406.87 | 500160 | 563370.77 | 599777.63 | 771d
P.S1143 | ITEM096 | APS Quad Magnet Measurement & Stand | LLP043 | Scintillating Fibers | P.S1143 | 334d | 2025-05-21 | 46290 | 1680 | 253985.23 | 77662 | 90147.12 | 344132.35 | 742d
P.S1135 | ITEM105 | ESR APS Quad Magnet Measurement & Stand | LLP044 | Scintillating Fibers | P.S1135 | 80d | 2026-09-18 | 46406 | 2200 | 355538.6 | 163934.43 | 181755.46 | 537294.06 | 554d
P.S1033 | ITEM099 | VRTX+ and lpGBT | LLP045 | Scintillating Fibers | P.S1033 | 295d | 2025-10-14 | 46379 | 588 | 132645.98 | 1235776 | 1396700.5 | 1529346.48 | 1472d
P.S1131 | ITEM099 | VRTX+ and lpGBT | LLP046 | Scintillating Fibers | P.S1131 | 295d | 2025-11-20 | 46428 | 588 | 133009.32 | 59306 | 71008.63 | 204017.95 | 1165d
P.S1138 | ITEM108 | ESR Dipole Magnets - D1/D2/D3 Production Iron Material | LLP047 | Scintillating Fibers | P.S1138 | 138d | 2026-10-19 | 46517 | 0 | 0 | 75216.97 | 85311.73 | 85311.73 | 280d
B | ITEM092 | APS Sextupole Refurbishment & Testing | LLP048 | Scintillating Fibers | B | 250d | 2025-04-01 | 46113 | 0 | 0 | 31822.56 | 34590.55 | 34590.55 | 1384d
T | #N/A | #N/A | LLP049 | Scintillating Fibers | T | 681d
T.LLP027 | ITEM089 | APS Quad Rebuild & Refurbishment | LLP050 | Scintillating Fibers | T.LLP027 | 91d | 2025-05-02 | 45911 | 0 | 0 | 2000 | 2803 | 2803 | 613d
T.LLP028 | ITEM089 | APS Quad Rebuild & Refurbishment | LLP051 | Scintillating Fibers | T.LLP028 | 91d | 2025-05-02 | 45911 | 0 | 0 | 2000 | 2803 | 2803 | 685d
Labor - 092 | ITEM092 | APS Sextupole Refurbishment & Testing | LLP052 | Scintillating Fibers | Labor - 092 | 990d | 2025-04-01 |  | 15477 | 2170905.93 | 0 | 0 | 2170905.93 | 644d
Labor - 105 | ITEM105 | ESR APS Quad Magnet Measurement & Stand | LLP053 | Scintillating Fibers | Labor - 105 |  |  |  | 3190 | 507983.61 | 0 | 0 | 507983.61
T.103 | ITEM103 | ESR Dipole Magnets - D1/D3 Vendor II | LLP054 | Scintillating Fibers | T.103 | [5 empty] | 14000 | 20327.58 | 20327.58
T.098 | ITEM098 | ESR Dipole Magnets - D1/D3 Vendor I | LLP055 | Scintillating Fibers | T.098 | [5 empty] | 14000 | 20327.58 | 20327.58
T.107 | ITEM107 | ESR Dipole Magnets - D2 Vendor II | LLP056 | Scintillating Fibers | T.107 | [5 empty] | 14000 | 20327.58 | 20327.58
T.104 | ITEM104 | ESR Dipole Magnets - D2 Vendor I | LLP057 | Scintillating Fibers | T.104 | [5 empty] | 14000 | 20327.58 | 20327.58

## 1.A-P6 DATA CD-3B ONLY (hidden)
LLP Item Detail | Penny | Activity ID | Activity Name | BNL_WBS_Hierarchical | WBS Name | BNL_Fund_Source | Start | Finish | BNL_PMC Rep | BNL_WPM | Budgeted Cost | BNL_EDIA | BNL_EVT | Resource Type | EIC_OPC-TEC | EIC_LLP | EIC_Partner Scope | BNL_Phase | EIC_SubSystem Code | EIC_Action Code | BNL_Procurement Designation | EIC_APP CODE | EIC_LLP Category | EIC_LLP Item | EIC_LLP Item Detail | BNL_CAM | BNL_Estimator | FY2020 | FY2021 | FY2022 | FY2023 | FY2024 | FY2025 | FY2026 | FY2027 | FY2028 | FY2029 | FY2030 | FY2031 | FY2032 | FY2033 | FY2034 | FY2035 | FY2036
|  | E0402_01600 | ESR Dipole Magnets - D1/D3 - First Article Magnet - Vendor I - Test Magnet | 6.04.02.01 | ESR Dipole Magnets | DOE.IRA | 2026-10-30 | 2026-12-01 | bsmith | hwitte | 4013.96 |  | PPkg.K | Labor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | NC_MAG |  | D.APP62.A | APP00538 | LLP037 | ITEM110 | ITEM098 | Witte | hwitte | FY2027: 4013.96
|  | E0402_01600 | ESR Dipole Magnets - D1/D3 - First Article Magnet - Vendor I - Test Magnet | 6.04.02.01 | ESR Dipole Magnets | DOE.IRA | 2026-10-30 | 2026-12-01 | bsmith | hwitte | 3421.37 |  | PPkg.K | Labor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | NC_MAG |  | D.APP62.A | APP00538 | LLP037 | ITEM110 | ITEM098 | Witte | hwitte | FY2027: 3421.37
ESR Dipole Magnets - D1/D3 Vendor I | Contract Award | E0402_01520 | ESR Dipole Magnets - D1/D3 - First Article/Production Magnets - Vendor I - OBL - Obligation Activity | 6.04.02.01 | ESR Dipole Magnets | DOE.DOE | 2026-01-13 | 2026-01-13 | bsmith | hwitte | 0.01 |  | % Comp.C.NA | Nonlabor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | NC_MAG | OBL | D.APP62.A | APP00538 | LLP037 | ITEM110 | ITEM098 | Witte |  | FY2026: 0.01
|  | E0402_01520 | ESR Dipole Magnets - D1/D3 - First Article/Production Magnets - Vendor I - OBL - Obligation Activity | 6.04.02.01 | ESR Dipole Magnets | DOE.DOE | 2026-01-13 | 2026-01-13 | bsmith | hwitte | 2417282.31 |  | % Comp.C.NA | Nonlabor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | NC_MAG | OBL | D.APP62.A | APP00538 | LLP037 | ITEM110 | ITEM098 | Witte |  | FY2026: 2417282.31
ESR Dipole Magnets - D1/D3 Vendor II | Contract Award | E0402_01810 | ESR Dipole Magnets - D1/D3 - First Article/Production Magnets - Vendor II - OBL - Obligation Activity | 6.04.02.01 | ESR Dipole Magnets | DOE.DOE | 2026-01-13 | 2026-01-13 | bsmith | hwitte | 0.01 |  | % Comp.C.NA | Nonlabor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | NC_MAG | OBL | D.APP62.B | APP00538 | LLP037 | ITEM110 | ITEM103 | Witte |  | FY2026: 0.01
|  | E0402_01810 | ESR Dipole Magnets - D1/D3 - First Article/Production Magnets - Vendor II - OBL - Obligation Activity | 6.04.02.01 | ESR Dipole Magnets | DOE.DOE | 2026-01-13 | 2026-01-13 | bsmith | hwitte | 2417282.31 |  | % Comp.C.NA | Nonlabor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | NC_MAG | OBL | D.APP62.B | APP00538 | LLP037 | ITEM110 | ITEM103 | Witte |  | FY2026: 2417282.31
|  | E0402_01560 | ESR Dipole Magnets - D1/D3 - First Article/Production Magnets - Vendor I - TR Effort (Vendor Fab Oversight) | 6.04.02.01 | ESR Dipole Magnets | DOE.IRA | 2026-01-14 | 2028-10-04 | bsmith | hwitte | 18896.04 |  | PPkg.K | Labor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | NC_MAG |  | D.APP62.A | APP00538 | LLP037 | ITEM110 | ITEM098 | Witte | hwitte | FY2026: 4994.55; FY2027: 6909.13; FY2028: 6909.13; FY2029: 83.24
|  | E0402_01560 | ESR Dipole Magnets - D1/D3 - First Article/Production Magnets - Vendor I - TR Effort (Vendor Fab Oversight) | 6.04.02.01 | ESR Dipole Magnets | DOE.IRA | 2026-01-14 | 2028-10-04 | bsmith | hwitte | 22168.91 |  | PPkg.K | Labor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | NC_MAG |  | D.APP62.A | APP00538 | LLP037 | ITEM110 | ITEM098 | Witte | hwitte | FY2026: 5859.63; FY2027: 8105.82; FY2028: 8105.82; FY2029: 97.66
|  | E0402_01830 | ESR Dipole Magnets - D1/D3 - First Article/Production Magnets - Vendor II - TR Effort (Vendor Fab Oversight) | 6.04.02.01 | ESR Dipole Magnets | DOE.DOE | 2026-01-14 | 2028-10-04 | bsmith | hwitte | 18896.04 |  | PPkg.K | Labor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | NC_MAG |  | D.APP62.B | APP00538 | LLP037 | ITEM110 | ITEM103 | Witte | hwitte | FY2026: 4994.55; FY2027: 6909.13; FY2028: 6909.13; FY2029: 83.24
|  | E0402_01830 | ESR Dipole Magnets - D1/D3 - First Article/Production Magnets - Vendor II - TR Effort (Vendor Fab Oversight) | 6.04.02.01 | ESR Dipole Magnets | DOE.DOE | 2026-01-14 | 2028-10-04 | bsmith | hwitte | 22168.91 |  | PPkg.K | Labor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | NC_MAG |  | D.APP62.B | APP00538 | LLP037 | ITEM110 | ITEM103 | Witte | hwitte | FY2026: 5859.63; FY2027: 8105.82; FY2028: 8105.82; FY2029: 97.66
|  | E0402_01850 | ESR Dipole Magnets - D1/D3 - First Article Magnet - Vendor II - Test Magnet | 6.04.02.01 | ESR Dipole Magnets | DOE.DOE | 2026-10-30 | 2026-12-01 | bsmith | hwitte | 4013.96 |  | PPkg.K | Labor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | NC_MAG |  | D.APP62.B | APP00538 | LLP037 | ITEM110 | ITEM103 | Witte | hwitte | FY2027: 4013.96
|  | E0402_01850 | ESR Dipole Magnets - D1/D3 - First Article Magnet - Vendor II - Test Magnet | 6.04.02.01 | ESR Dipole Magnets | DOE.DOE | 2026-10-30 | 2026-12-01 | bsmith | hwitte | 3421.37 |  | PPkg.K | Labor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | NC_MAG |  | D.APP62.B | APP00538 | LLP037 | ITEM110 | ITEM103 | Witte | hwitte | FY2027: 3421.37
|  | E0402_01570 | ESR Dipole Magnets - D1/D3 - First Article Magnet - Vendor I - RCV | 6.04.02.01 | ESR Dipole Magnets | DOE.IRA | 2026-10-29 | 2026-10-29 | bsmith | hwitte | 133349.89 |  | PPkg.K | Nonlabor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | NC_MAG | RCV | D.APP62.A | APP00538 | LLP037 | ITEM110 | ITEM098 | Witte | hwitte | FY2027: 133349.89
|  | E0402_01840 | ESR Dipole Magnets - D1/D3 - First Article Magnet - Vendor II - RCV | 6.04.02.01 | ESR Dipole Magnets | DOE.DOE | 2026-10-29 | 2026-10-29 | bsmith | hwitte | 133349.89 |  | PPkg.K | Nonlabor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | NC_MAG | RCV | D.APP62.B | APP00538 | LLP037 | ITEM110 | ITEM103 | Witte | hwitte | FY2027: 133349.89
|  | E0402_01645 | ESR Dipole Magnets - D1/D3 - Production Magnets Batch#1 32 Magnets - Vendor I - RCV - AS03 | 6.04.02.01 | ESR Dipole Magnets | DOE.DOE | 2028-05-10 | 2028-05-10 | bsmith | hwitte | 1141966.21 |  | PPkg.K | Nonlabor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | NC_MAG | RCV | D.APP62.A | APP00538 | LLP037 | ITEM110 | ITEM098 | Witte | hwitte | FY2028: 1141966.21
|  | E0402_01865 | ESR Dipole Magnets - D1/D3 - Production Magnets Batch#1 32 Magnets - Vendor II - RCV - AS03 | 6.04.02.01 | ESR Dipole Magnets | DOE.DOE | 2028-05-10 | 2028-05-10 | bsmith | hwitte | 1141966.21 |  | PPkg.K | Nonlabor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | NC_MAG | RCV | D.APP62.B | APP00538 | LLP037 | ITEM110 | ITEM103 | Witte | hwitte | FY2028: 1141966.21
|  | E0402_00240 | ESR Dipole Magnets - D2 - First Article Magnet - Vendor I - Test Magnet | 6.04.02.01 | ESR Dipole Magnets | DOE.DOE | 2026-10-30 | 2026-12-01 | bsmith | hwitte | 4013.96 |  | PPkg.K | Labor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | NC_MAG |  | D.APP63.A | APP00539 | LLP037 | ITEM110 | ITEM104 | Witte | hwitte | FY2027: 4013.96
|  | E0402_00240 | ESR Dipole Magnets - D2 - First Article Magnet - Vendor I - Test Magnet | 6.04.02.01 | ESR Dipole Magnets | DOE.DOE | 2026-10-30 | 2026-12-01 | bsmith | hwitte | 3421.37 |  | PPkg.K | Labor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | NC_MAG |  | D.APP63.A | APP00539 | LLP037 | ITEM110 | ITEM104 | Witte | hwitte | FY2027: 3421.37
ESR Dipole Magnets - D2 Vendor I | Contract Award | E0402_00205 | ESR Dipole Magnets - D2 - First Article/Production Magnets - Vendor I - OBL - Obligation Activity | 6.04.02.01 | ESR Dipole Magnets | DOE.DOE | 2026-01-13 | 2026-01-13 | bsmith | hwitte | 0.01 |  | % Comp.C.NA | Nonlabor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | NC_MAG | OBL | D.APP63.A | APP00539 | LLP037 | ITEM110 | ITEM104 | Witte |  | FY2026: 0.01
|  | E0402_00205 | ESR Dipole Magnets - D2 - First Article/Production Magnets - Vendor I - OBL - Obligation Activity | 6.04.02.01 | ESR Dipole Magnets | DOE.DOE | 2026-01-13 | 2026-01-13 | bsmith | hwitte | 2370177.73 |  | % Comp.C.NA | Nonlabor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | NC_MAG | OBL | D.APP63.A | APP00539 | LLP037 | ITEM110 | ITEM104 | Witte |  | FY2026: 2370177.73
ESR Dipole Magnets - D2 Vendor II | Contract Award | E0402_00362 | ESR Dipole Magnets - D2 - First Article/Production Magnets - Vendor II - OBL - Obligation Activity | 6.04.02.01 | ESR Dipole Magnets | DOE.DOE | 2026-01-13 | 2026-01-13 | bsmith | hwitte | 0.01 |  | % Comp.C.NA | Nonlabor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | NC_MAG | OBL | D.APP63.B | APP00539 | LLP037 | ITEM110 | ITEM107 | Witte |  | FY2026: 0.01
|  | E0402_00362 | ESR Dipole Magnets - D2 - First Article/Production Magnets - Vendor II - OBL - Obligation Activity | 6.04.02.01 | ESR Dipole Magnets | DOE.DOE | 2026-01-13 | 2026-01-13 | bsmith | hwitte | 2370177.73 |  | % Comp.C.NA | Nonlabor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | NC_MAG | OBL | D.APP63.B | APP00539 | LLP037 | ITEM110 | ITEM107 | Witte |  | FY2026: 2370177.73
|  | E0402_00220 | ESR Dipole Magnets - D2 - First Article/Production Magnets - Vendor I - TR Effort (Vendor Fab Oversight) | 6.04.02.01 | ESR Dipole Magnets | DOE.DOE | 2026-01-14 | 2028-10-04 | bsmith | hwitte | 18896.04 |  | PPkg.K | Labor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | NC_MAG |  | D.APP63.A | APP00539 | LLP037 | ITEM110 | ITEM104 | Witte | hwitte | FY2026: 4994.55; FY2027: 6909.13; FY2028: 6909.13; FY2029: 83.24
|  | E0402_00220 | ESR Dipole Magnets - D2 - First Article/Production Magnets - Vendor I - TR Effort (Vendor Fab Oversight) | 6.04.02.01 | ESR Dipole Magnets | DOE.DOE | 2026-01-14 | 2028-10-04 | bsmith | hwitte | 22168.91 |  | PPkg.K | Labor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | NC_MAG |  | D.APP63.A | APP00539 | LLP037 | ITEM110 | ITEM104 | Witte | hwitte | FY2026: 5859.63; FY2027: 8105.82; FY2028: 8105.82; FY2029: 97.66
|  | E0402_00390 | ESR Dipole Magnets - D2 - First Article/Production Magnets - Vendor II - TR Effort (Vendor Fab Oversight) | 6.04.02.01 | ESR Dipole Magnets | DOE.DOE | 2026-01-14 | 2028-10-04 | bsmith | hwitte | 18896.04 |  | PPkg.K | Labor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | NC_MAG |  | D.APP63.B | APP00539 | LLP037 | ITEM110 | ITEM107 | Witte | hwitte | FY2026: 4994.55; FY2027: 6909.13; FY2028: 6909.13; FY2029: 83.24
|  | E0402_00390 | ESR Dipole Magnets - D2 - First Article/Production Magnets - Vendor II - TR Effort (Vendor Fab Oversight) | 6.04.02.01 | ESR Dipole Magnets | DOE.DOE | 2026-01-14 | 2028-10-04 | bsmith | hwitte | 22168.91 |  | PPkg.K | Labor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | NC_MAG |  | D.APP63.B | APP00539 | LLP037 | ITEM110 | ITEM107 | Witte | hwitte | FY2026: 5859.63; FY2027: 8105.82; FY2028: 8105.82; FY2029: 97.66
|  | E0402_00410 | ESR Dipole Magnets - D2 - First Article Magnet - Vendor II - Test Magnet | 6.04.02.01 | ESR Dipole Magnets | DOE.DOE | 2026-10-30 | 2026-12-01 | bsmith | hwitte | 4013.96 |  | PPkg.K | Labor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | NC_MAG |  | D.APP63.B | APP00539 | LLP037 | ITEM110 | ITEM107 | Witte | hwitte | FY2027: 4013.96
|  | E0402_00410 | ESR Dipole Magnets - D2 - First Article Magnet - Vendor II - Test Magnet | 6.04.02.01 | ESR Dipole Magnets | DOE.DOE | 2026-10-30 | 2026-12-01 | bsmith | hwitte | 3421.37 |  | PPkg.K | Labor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | NC_MAG |  | D.APP63.B | APP00539 | LLP037 | ITEM110 | ITEM107 | Witte | hwitte | FY2027: 3421.37
|  | E0402_00230 | ESR Dipole Magnets - D2 - First Article Magnet - Vendor I - RCV | 6.04.02.01 | ESR Dipole Magnets | DOE.DOE | 2026-10-29 | 2026-10-29 | bsmith | hwitte | 109561.44 |  | PPkg.K | Nonlabor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | NC_MAG | RCV | D.APP63.A | APP00539 | LLP037 | ITEM110 | ITEM104 | Witte | hwitte | FY2027: 109561.44
|  | E0402_00400 | ESR Dipole Magnets - D2 - First Article Magnet - Vendor II - RCV / Delivery | 6.04.02.01 | ESR Dipole Magnets | DOE.DOE | 2026-10-29 | 2026-10-29 | bsmith | hwitte | 109561.44 |  | PPkg.K | Nonlabor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | NC_MAG | RCV | D.APP63.B | APP00539 | LLP037 | ITEM110 | ITEM107 | Witte | hwitte | FY2027: 109561.44
|  | E0402_00285 | ESR Dipole Magnets - D2 - Production Magnets Batch #1 16 Magnets - Vendor I - RCV - AS03 | 6.04.02.01 | ESR Dipole Magnets | DOE.DOE | 2028-05-10 | 2028-05-10 | bsmith | hwitte | 1130308.14 |  | PPkg.K | Nonlabor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | NC_MAG | RCV | D.APP63.A | APP00539 | LLP037 | ITEM110 | ITEM104 | Witte | hwitte | FY2028: 1130308.14
|  | E0402_00455 | ESR Dipole Magnets - D2 - Production Magnets Batch#1 16 Magnets - Vendor II - RCV - AS03 | 6.04.02.01 | ESR Dipole Magnets | DOE.DOE | 2028-05-10 | 2028-05-10 | bsmith | hwitte | 1130308.14 |  | PPkg.K | Nonlabor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | NC_MAG | RCV | D.APP63.B | APP00539 | LLP037 | ITEM110 | ITEM107 | Witte | hwitte | FY2028: 1130308.14
ESR Dipole Magnets - D1/D2/D3 Production Iron Material | Contract Award | E0402_00885 | ESR Dipole Magnets - D2 & D1/D3 - Iron Material - OBL - Obligation Activity | 6.04.02.01 | ESR Dipole Magnets | DOE.DOE | 2026-05-07 | 2026-05-07 | bsmith | hwitte | 0.01 |  | % Comp.C.NA | Nonlabor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | NC_MAG | OBL | D.APP64 | APP00879 | LLP037 | ITEM110 | ITEM108 | Witte |  | FY2026: 0.01
|  | E0402_00885 | ESR Dipole Magnets - D2 & D1/D3 - Iron Material - OBL - Obligation Activity | 6.04.02.01 | ESR Dipole Magnets | DOE.DOE | 2026-05-07 | 2026-05-07 | bsmith | hwitte | 5821392.08 |  | % Comp.C.NA | Nonlabor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | NC_MAG | OBL | D.APP64 | APP00879 | LLP037 | ITEM110 | ITEM108 | Witte |  | FY2026: 5821392.08
|  | E0402_00895 | ESR Dipole Magnets - D2 - Iron Material - RCV | 6.04.02.01 | ESR Dipole Magnets | DOE.DOE | 2027-04-26 | 2027-04-26 | bsmith | hwitte | 814994.89 |  | PPkg.K | Nonlabor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | NC_MAG | RCV | D.APP64 | APP00879 | LLP037 | ITEM110 | ITEM108 | Witte | hwitte | FY2027: 814994.89
|  | E0402_00915 | ESR Dipole Magnets - D1/D3 - Iron Material - RCV | 6.04.02.01 | ESR Dipole Magnets | DOE.DOE | 2027-04-26 | 2027-04-26 | bsmith | hwitte | 5006397.2 |  | PPkg.K | Nonlabor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | NC_MAG | RCV | D.APP64 | APP00879 | LLP037 | ITEM110 | ITEM108 | Witte | hwitte | FY2027: 5006397.2
|  | E0402_01650 | ESR Dipole Magnets - D1/D3 - Production Magnets Batch#2 32 Magnets - Vendor I - RCV - AS01 | 6.04.02.01 | ESR Dipole Magnets | DOE.DOE | 2028-10-04 | 2028-10-04 | bsmith | hwitte | 1141966.21 |  | PPkg.K | Nonlabor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | NC_MAG | RCV | D.APP62.A | APP00538 | LLP037 | ITEM110 | ITEM098 | Witte | hwitte | FY2029: 1141966.21
|  | E0402_01870 | ESR Dipole Magnets - D1/D3 - Production Magnets Batch#2 32 Magnets - Vendor II - RCV - AS01 | 6.04.02.01 | ESR Dipole Magnets | DOE.DOE | 2028-10-04 | 2028-10-04 | bsmith | hwitte | 1141966.21 |  | PPkg.K | Nonlabor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | NC_MAG | RCV | D.APP62.B | APP00538 | LLP037 | ITEM110 | ITEM103 | Witte | hwitte | FY2029: 1141966.21
|  | E0402_00288 | ESR Dipole Magnets - D2 - Production Magnets Batch #2 16 Magnets - Vendor I - RCV - AS01 | 6.04.02.01 | ESR Dipole Magnets | DOE.DOE | 2028-10-04 | 2028-10-04 | bsmith | hwitte | 1130308.14 |  | PPkg.K | Nonlabor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | NC_MAG | RCV | D.APP63.A | APP00539 | LLP037 | ITEM110 | ITEM104 | Witte | hwitte | FY2029: 1130308.14
|  | E0402_00460 | ESR Dipole Magnets - D2 - Production Magnets Batch#2 16 Magnets - Vendor II - RCV - AS01 | 6.04.02.01 | ESR Dipole Magnets | DOE.DOE | 2028-10-04 | 2028-10-04 | bsmith | hwitte | 1130308.14 |  | PPkg.K | Nonlabor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | NC_MAG | RCV | D.APP63.B | APP00539 | LLP037 | ITEM110 | ITEM107 | Witte | hwitte | FY2029: 1130308.14
|  | E0402_00925 | ESR Dipole Magnets - D1/D3 - Iron Material - Loading/Unloading | 6.04.02.01 | ESR Dipole Magnets | DOE.DOE | 2027-04-27 | 2027-05-10 | bsmith | hwitte | 126582.29 |  | PPkg.K | Labor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | NC_MAG |  | D.APP64 | APP00879 | LLP037 | ITEM110 | ITEM108 | Witte | hwitte | FY2027: 126582.29
|  | E0402_00900 | ESR Dipole Magnets - D2 - Iron Material - Loading/Unloading | 6.04.02.01 | ESR Dipole Magnets | DOE.DOE | 2027-04-27 | 2027-05-10 | bsmith | hwitte | 20642.65 |  | PPkg.K | Labor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | NC_MAG |  | D.APP64 | APP00879 | LLP037 | ITEM110 | ITEM108 | Witte | hwitte | FY2027: 20642.65
|  | E0402_01835 | ESR Dipole Magnets - D1/D3 - First Article/Production Magnets - Vendor II - TR Effort Travel | 6.04.02.01 | ESR Dipole Magnets | DOE.DOE | 2026-01-14 | 2028-10-04 | bsmith | hwitte | 20327.58 |  | PPkg.K | Nonlabor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | NC_MAG |  | T.103 | APP00538 | LLP037 | ITEM110 | ITEM103 | Witte | hwitte | FY2026: 5372.93; FY2027: 7432.55; FY2028: 7432.55; FY2029: 89.55
|  | E0402_01565 | ESR Dipole Magnets - D1/D3 - First Article/Production Magnets - Vendor I - TR Effort Travel | 6.04.02.01 | ESR Dipole Magnets | DOE.DOE | 2026-01-14 | 2028-10-04 | bsmith | hwitte | 20327.58 |  | PPkg.K | Nonlabor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | NC_MAG |  | T.098 | APP00538 | LLP037 | ITEM110 | ITEM098 | Witte | hwitte | FY2026: 5372.93; FY2027: 7432.55; FY2028: 7432.55; FY2029: 89.55
|  | E0402_00395 | ESR Dipole Magnets - D2 - First Article/Production Magnets - Vendor II - TR Effort Travel | 6.04.02.01 | ESR Dipole Magnets | DOE.DOE | 2026-01-14 | 2028-10-04 | bsmith | hwitte | 20327.58 |  | PPkg.K | Nonlabor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | NC_MAG |  | T.107 | APP00539 | LLP037 | ITEM110 | ITEM107 | Witte | hwitte | FY2026: 5372.93; FY2027: 7432.55; FY2028: 7432.55; FY2029: 89.55
|  | E0402_00225 | ESR Dipole Magnets - D2 - First Article/Production Magnets - Vendor I - TR Effort Travel | 6.04.02.01 | ESR Dipole Magnets | DOE.DOE | 2026-01-14 | 2028-10-04 | bsmith | hwitte | 20327.58 |  | PPkg.K | Nonlabor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | NC_MAG |  | T.104 | APP00539 | LLP037 | ITEM110 | ITEM104 | Witte | hwitte | FY2026: 5372.93; FY2027: 7432.55; FY2028: 7432.55; FY2029: 89.55
ESR Dipole Magnets - D1/D2/D3 Production Iron Material | Contract Award | E0402_00980 | ESR Dipole Magnets - D2 & D1/D3 - Transport Iron To Vendors - OBL - Obligation Activity | 6.04.02.01 | ESR Dipole Magnets | DOE.DOE | 2026-10-19 | 2026-10-19 | bsmith | hwitte | 0.01 |  | % Comp.C.NA | Nonlabor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | NC_MAG | OBL | P.S1138 |  | LLP037 | ITEM110 | ITEM108 | Witte |  | FY2027: 0.01
|  | E0402_00980 | ESR Dipole Magnets - D2 & D1/D3 - Transport Iron To Vendors - OBL - Obligation Activity | 6.04.02.01 | ESR Dipole Magnets | DOE.DOE | 2026-10-19 | 2026-10-19 | bsmith | hwitte | 85311.73 |  | % Comp.C.NA | Nonlabor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | NC_MAG | OBL | P.S1138 |  | LLP037 | ITEM110 | ITEM108 | Witte |  | FY2027: 85311.73
|  | E0402_00990 | ESR Dipole Magnets - D2 & D1/D3 - Transport Iron To Vendors - RCV | 6.04.02.01 | ESR Dipole Magnets | DOE.DOE | 2027-05-10 | 2027-05-10 | bsmith | hwitte | 85311.73 |  | PPkg.K | Nonlabor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | NC_MAG | RCV | P.S1138 |  | LLP037 | ITEM110 | ITEM108 | Witte | hwitte | FY2027: 85311.73
|  | E0402_00930 | ESR Dipole Magnets - D2 & D1/D3 - Iron Material - TR Effort (Vendor Fab Oversight) | 6.04.02.01 | ESR Dipole Magnets | DOE.DOE | 2026-05-08 | 2027-05-10 | bsmith | hwitte | 14097.59 |  | PPkg.K | Labor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | NC_MAG |  | D.APP64 | APP00879 | LLP037 | ITEM110 | ITEM108 | Witte | hwitte | FY2026: 5639.04; FY2027: 8458.55
|  | E0402_00930 | ESR Dipole Magnets - D2 & D1/D3 - Iron Material - TR Effort (Vendor Fab Oversight) | 6.04.02.01 | ESR Dipole Magnets | DOE.DOE | 2026-05-08 | 2027-05-10 | bsmith | hwitte | 16539.35 |  | PPkg.K | Labor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | NC_MAG |  | D.APP64 | APP00879 | LLP037 | ITEM110 | ITEM108 | Witte | hwitte | FY2026: 6615.74; FY2027: 9923.61
|  | E0402_05900 | ESR Magnets - APS Sextupole - Magnet Testing - 40 Magnets - AS01 | 6.04.02.02 | ESR Sextupole Magnets | DOE.DOE | 2025-07-18 | 2025-11-03 | bsmith | hwitte | 101127.31 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | BNL | Construction.Test & Accept | NC_MAG |  | Labor - 092 |  | LLP043 | ITEM111 | ITEM092 | Witte | hwitte | FY2025: 70114.94; FY2026: 31012.38
|  | E0402_05920 | ESR Magnets - APS Sextupole - Magnet Testing - 56 Magnets - AS07 | 6.04.02.02 | ESR Sextupole Magnets | DOE.DOE | 2026-04-09 | 2026-09-08 | bsmith | hwitte | 144977.39 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | BNL | Construction.Test & Accept | NC_MAG |  | Labor - 092 |  | LLP043 | ITEM111 | ITEM092 | Witte | hwitte | FY2026: 144977.39
|  | E0402_05940 | ESR Magnets - APS Sextupole - Magnet Testing - 56 Magnets - AS09 | 6.04.02.02 | ESR Sextupole Magnets | DOE.DOE | 2027-02-12 | 2027-07-14 | bsmith | hwitte | 150051.6 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | BNL | Construction.Test & Accept | NC_MAG |  | Labor - 092 |  | LLP043 | ITEM111 | ITEM092 | Witte | hwitte | FY2027: 150051.6
|  | E0402_05960 | ESR Magnets - APS Sextupole - Magnet Testing - 56 Magnets - AS11 | 6.04.02.02 | ESR Sextupole Magnets | DOE.DOE | 2027-12-16 | 2028-05-16 | bsmith | hwitte | 155303.4 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | BNL | Construction.Test & Accept | NC_MAG |  | Labor - 092 |  | LLP043 | ITEM111 | ITEM092 | Witte | hwitte | FY2028: 155303.4
|  | E0402_05980 | ESR Magnets - APS Sextupole - Magnet Testing - 56 Magnets - AS05 | 6.04.02.02 | ESR Sextupole Magnets | DOE.DOE | 2028-10-18 | 2029-03-22 | bsmith | hwitte | 160739.02 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | BNL | Construction.Test & Accept | NC_MAG |  | Labor - 092 |  | LLP043 | ITEM111 | ITEM092 | Witte | hwitte | FY2029: 160739.02
|  | E0402_05800 | ESR Magnets - APS Sextupole - Refurbish Magnets - 40 Magnets - AS01 | 6.04.02.02 | ESR Sextupole Magnets | DOE.DOE | 2025-04-01 | 2025-11-03 | bsmith | hwitte | 100590.36 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | BNL | Construction.Test & Accept | NC_MAG |  | Labor - 092 |  | LLP043 | ITEM111 | ITEM092 | Witte | hwitte | FY2025: 85166.51; FY2026: 15423.85
|  | E0402_05820 | ESR Magnets - APS Sextupole - Refurbish Magnets - 56 Magnets - AS07 | 6.04.02.02 | ESR Sextupole Magnets | DOE.DOE | 2025-11-04 | 2026-09-08 | bsmith | hwitte | 144977.39 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | BNL | Construction.Test & Accept | NC_MAG |  | Labor - 092 |  | LLP043 | ITEM111 | ITEM092 | Witte | hwitte | FY2026: 144977.39
|  | E0402_05840 | ESR Magnets - APS Sextupole - Refurbish Magnets - 56 Magnets - AS09 | 6.04.02.02 | ESR Sextupole Magnets | DOE.DOE | 2026-09-09 | 2027-07-14 | bsmith | hwitte | 149664.99 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | BNL | Construction.Test & Accept | NC_MAG |  | Labor - 092 |  | LLP043 | ITEM111 | ITEM092 | Witte | hwitte | FY2026: 11403.05; FY2027: 138261.94
|  | E0402_05860 | ESR Magnets - APS Sextupole - Refurbish Magnets - 56 Magnets - AS11 | 6.04.02.02 | ESR Sextupole Magnets | DOE.DOE | 2027-07-15 | 2028-05-16 | bsmith | hwitte | 153927.93 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | BNL | Construction.Test & Accept | NC_MAG |  | Labor - 092 |  | LLP043 | ITEM111 | ITEM092 | Witte | hwitte | FY2027: 40314.46; FY2028: 113613.47
|  | E0402_05880 | ESR Magnets - APS Sextupole - Refurbish Magnets - 56 Magnets - AS05 | 6.04.02.02 | ESR Sextupole Magnets | DOE.DOE | 2028-05-17 | 2029-03-22 | bsmith | hwitte | 158305.93 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | BNL | Construction.Test & Accept | NC_MAG |  | Labor - 092 |  | LLP043 | ITEM111 | ITEM092 | Witte | hwitte | FY2028: 70860.75; FY2029: 87445.18
|  | E0402_05790 | ESR Magnets - APS Sextupole - Refurbishment Consumables | 6.04.02.02 | ESR Sextupole Magnets | DOE.DOE | 2025-04-01 | 2025-11-03 | bsmith | hwitte | 6249.04 |  | % Comp.C | Nonlabor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | NC_MAG |  | B |  | LLP043 | ITEM111 | ITEM092 | Witte | hwitte | FY2025: 5290.85; FY2026: 958.19
|  | E0402_05780 | ESR Magnets - APS Sextupole - Hazardous Waste Disposal Containers | 6.04.02.02 | ESR Sextupole Magnets | DOE.DOE | 2025-04-01 | 2026-04-01 | bsmith | hwitte | 12630.76 |  | % Comp.C.Appor | Nonlabor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | NC_MAG |  | B |  | LLP043 | ITEM111 | ITEM092 | Witte | hwitte | FY2025: 6416.43; FY2026: 6214.33
|  | E0402_05770 | ESR Magnets - APS Sextupole - Machine parts for Testing Fixtures | 6.04.02.02 | ESR Sextupole Magnets | DOE.DOE | 2025-04-01 | 2025-05-27 | bsmith | hwitte | 10365 |  | % Comp.C | Nonlabor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | NC_MAG |  | B |  | LLP043 | ITEM111 | ITEM092 | Witte | hwitte | FY2025: 10365
|  | E0402_05990 | ESR Magnets - APS Sextupole - Re-Test Rebuilt Magnets | 6.04.02.02 | ESR Sextupole Magnets | DOE.DOE | 2025-11-04 | 2027-07-14 | bsmith | hwitte | 69451.42 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | BNL | Construction.Test & Accept | NC_MAG |  | Labor - 092 |  | LLP043 | ITEM111 | ITEM092 | Witte | hwitte | FY2026: 37371.48; FY2027: 32079.94
|  | E0402_05765 | ESR Magnets - APS Sextupole - Replacement Coils - RCV | 6.04.02.02 | ESR Sextupole Magnets | DOE.DOE | 2026-05-19 | 2026-05-19 | bsmith | hwitte | 692809.04 |  | PPkg.K | Nonlabor | TEC | CD3B.SCOPE | BNL | Construction.Test & Accept | NC_MAG | RCV | S.P540 | APP00823 | LLP043 | ITEM111 | ITEM092 | Witte | hwitte | FY2026: 692809.04
|  | E0402_05760 | ESR Magnets - APS Sextupole - Replacement Coils - TR Effort (Vendor Fab Oversight) | 6.04.02.02 | ESR Sextupole Magnets | DOE.DOE | 2026-01-26 | 2026-05-18 | bsmith | hwitte | 2644.53 |  | PPkg.K | Labor | TEC | CD3B.SCOPE | BNL | Construction.Test & Accept | NC_MAG |  | S.P540 | APP00823 | LLP043 | ITEM111 | ITEM092 | Witte | hwitte | FY2026: 2644.53
APS Sextupole Refurbishment & Testing | Contract Award | E0402_05752 | ESR Magnets - APS Sextupole - Replacement Coils - OBL - Obligation Activity | 6.04.02.02 | ESR Sextupole Magnets | DOE.DOE | 2026-01-23 | 2026-01-23 | bsmith | hwitte | 0.01 |  | % Comp.C.NA | Nonlabor | TEC | CD3B.SCOPE | BNL | Construction.Test & Accept | NC_MAG | OBL | S.P540 | APP00823 | LLP034 | ITEM111 | ITEM092 | Witte |  | FY2026: 0.01
|  | E0402_05752 | ESR Magnets - APS Sextupole - Replacement Coils - OBL - Obligation Activity | 6.04.02.02 | ESR Sextupole Magnets | DOE.DOE | 2026-01-23 | 2026-01-23 | bsmith | hwitte | 692809.04 |  | % Comp.C.NA | Nonlabor | TEC | CD3B.SCOPE | BNL | Construction.Test & Accept | NC_MAG | OBL | S.P540 | APP00823 | LLP034 | ITEM111 | ITEM092 | Witte |  | FY2026: 692809.04
|  | E0402_04680 | ESR Dipole - Magnetic Measurement / Acceptance - 96 Magnets - AS03 | 6.04.02.04 | ESR Magnet Measurement & Acceptance | DOE.DOE | 2028-01-07 | 2028-05-10 | bsmith | hwitte | 2655.84 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | BNL | Construction.Test & Accept | NC_MAG |  | Labor - 105 |  | LLP042 | ITEM112 | ITEM105 | Witte | hwitte | FY2028: 2655.84
|  | E0402_04680 | ESR Dipole - Magnetic Measurement / Acceptance - 96 Magnets - AS03 | 6.04.02.04 | ESR Magnet Measurement & Acceptance | DOE.DOE | 2028-01-07 | 2028-05-10 | bsmith | hwitte | 6728.12 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | BNL | Construction.Test & Accept | NC_MAG |  | Labor - 105 |  | LLP042 | ITEM112 | ITEM105 | Witte | hwitte | FY2028: 6728.12
|  | E0402_04680 | ESR Dipole - Magnetic Measurement / Acceptance - 96 Magnets - AS03 | 6.04.02.04 | ESR Magnet Measurement & Acceptance | DOE.DOE | 2028-01-07 | 2028-05-10 | bsmith | hwitte | 2655.84 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | BNL | Construction.Test & Accept | NC_MAG |  | Labor - 105 |  | LLP042 | ITEM112 | ITEM105 | Witte | hwitte | FY2028: 2655.84
|  | E0402_04680 | ESR Dipole - Magnetic Measurement / Acceptance - 96 Magnets - AS03 | 6.04.02.04 | ESR Magnet Measurement & Acceptance | DOE.DOE | 2028-01-07 | 2028-05-10 | bsmith | hwitte | 72351.73 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | BNL | Construction.Test & Accept | NC_MAG |  | Labor - 105 |  | LLP042 | ITEM112 | ITEM105 | Witte | hwitte | FY2028: 72351.73
|  | E0402_04680 | ESR Dipole - Magnetic Measurement / Acceptance - 96 Magnets - AS03 | 6.04.02.04 | ESR Magnet Measurement & Acceptance | DOE.DOE | 2028-01-07 | 2028-05-10 | bsmith | hwitte | 169447.1 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | BNL | Construction.Test & Accept | NC_MAG |  | Labor - 105 |  | LLP042 | ITEM112 | ITEM105 | Witte | hwitte | FY2028: 169447.1
|  | E0402_04700 | ESR Dipole - Magnetic Measurement / Acceptance - 96 Magnets - AS01 | 6.04.02.04 | ESR Magnet Measurement & Acceptance | DOE.DOE | 2028-06-01 | 2028-10-04 | bsmith | hwitte | 2659.04 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | BNL | Construction.Test & Accept | NC_MAG |  | Labor - 105 |  | LLP042 | ITEM112 | ITEM105 | Witte | hwitte | FY2028: 2567.35; FY2029: 91.69
|  | E0402_04700 | ESR Dipole - Magnetic Measurement / Acceptance - 96 Magnets - AS01 | 6.04.02.04 | ESR Magnet Measurement & Acceptance | DOE.DOE | 2028-06-01 | 2028-10-04 | bsmith | hwitte | 6736.24 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | BNL | Construction.Test & Accept | NC_MAG |  | Labor - 105 |  | LLP042 | ITEM112 | ITEM105 | Witte | hwitte | FY2028: 6503.95; FY2029: 232.28
|  | E0402_04700 | ESR Dipole - Magnetic Measurement / Acceptance - 96 Magnets - AS01 | 6.04.02.04 | ESR Magnet Measurement & Acceptance | DOE.DOE | 2028-06-01 | 2028-10-04 | bsmith | hwitte | 2659.04 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | BNL | Construction.Test & Accept | NC_MAG |  | Labor - 105 |  | LLP042 | ITEM112 | ITEM105 | Witte | hwitte | FY2028: 2567.35; FY2029: 91.69
|  | E0402_04700 | ESR Dipole - Magnetic Measurement / Acceptance - 96 Magnets - AS01 | 6.04.02.04 | ESR Magnet Measurement & Acceptance | DOE.DOE | 2028-06-01 | 2028-10-04 | bsmith | hwitte | 72439.05 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | BNL | Construction.Test & Accept | NC_MAG |  | Labor - 105 |  | LLP042 | ITEM112 | ITEM105 | Witte | hwitte | FY2028: 69941.16; FY2029: 2497.9
|  | E0402_04700 | ESR Dipole - Magnetic Measurement / Acceptance - 96 Magnets - AS01 | 6.04.02.04 | ESR Magnet Measurement & Acceptance | DOE.DOE | 2028-06-01 | 2028-10-04 | bsmith | hwitte | 169651.61 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | BNL | Construction.Test & Accept | NC_MAG |  | Labor - 105 |  | LLP042 | ITEM112 | ITEM105 | Witte | hwitte | FY2028: 163801.55; FY2029: 5850.06
|  | E0402_06000 | ESR Magnets - APS Sextupole - Magnetic Measurement - 40 Magnets - AS01 | 6.04.02.04 | ESR Magnet Measurement & Acceptance | DOE.DOE | 2025-11-04 | 2026-02-03 | bsmith | hwitte | 991.7 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | BNL | Construction.Test & Accept | NC_MAG |  | Labor - 092 |  | LLP043 | ITEM111 | ITEM092 | Witte | hwitte | FY2026: 991.7
|  | E0402_06000 | ESR Magnets - APS Sextupole - Magnetic Measurement - 40 Magnets - AS01 | 6.04.02.04 | ESR Magnet Measurement & Acceptance | DOE.DOE | 2025-11-04 | 2026-02-03 | bsmith | hwitte | 2644.53 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | BNL | Construction.Test & Accept | NC_MAG |  | Labor - 092 |  | LLP043 | ITEM111 | ITEM092 | Witte | hwitte | FY2026: 2644.53
|  | E0402_06000 | ESR Magnets - APS Sextupole - Magnetic Measurement - 40 Magnets - AS01 | 6.04.02.04 | ESR Magnet Measurement & Acceptance | DOE.DOE | 2025-11-04 | 2026-02-03 | bsmith | hwitte | 991.7 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | BNL | Construction.Test & Accept | NC_MAG |  | Labor - 092 |  | LLP043 | ITEM111 | ITEM092 | Witte | hwitte | FY2026: 991.7
|  | E0402_06000 | ESR Magnets - APS Sextupole - Magnetic Measurement - 40 Magnets - AS01 | 6.04.02.04 | ESR Magnet Measurement & Acceptance | DOE.DOE | 2025-11-04 | 2026-02-03 | bsmith | hwitte | 28123.68 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | BNL | Construction.Test & Accept | NC_MAG |  | Labor - 092 |  | LLP043 | ITEM111 | ITEM092 | Witte | hwitte | FY2026: 28123.68
|  | E0402_06000 | ESR Magnets - APS Sextupole - Magnetic Measurement - 40 Magnets - AS01 | 6.04.02.04 | ESR Magnet Measurement & Acceptance | DOE.DOE | 2025-11-04 | 2026-02-03 | bsmith | hwitte | 66016.49 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | BNL | Construction.Test & Accept | NC_MAG |  | Labor - 092 |  | LLP043 | ITEM111 | ITEM092 | Witte | hwitte | FY2026: 66016.49
|  | E0402_06020 | ESR Magnets - APS Sextupole - Magnetic Measurement - 56 Magnets - AS07 | 6.04.02.04 | ESR Magnet Measurement & Acceptance | DOE.DOE | 2026-06-12 | 2026-09-08 | bsmith | hwitte | 1487.55 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | BNL | Construction.Test & Accept | NC_MAG |  | Labor - 092 |  | LLP043 | ITEM111 | ITEM092 | Witte | hwitte | FY2026: 1487.55
|  | E0402_06020 | ESR Magnets - APS Sextupole - Magnetic Measurement - 56 Magnets - AS07 | 6.04.02.04 | ESR Magnet Measurement & Acceptance | DOE.DOE | 2026-06-12 | 2026-09-08 | bsmith | hwitte | 3636.24 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | BNL | Construction.Test & Accept | NC_MAG |  | Labor - 092 |  | LLP043 | ITEM111 | ITEM092 | Witte | hwitte | FY2026: 3636.24
|  | E0402_06020 | ESR Magnets - APS Sextupole - Magnetic Measurement - 56 Magnets - AS07 | 6.04.02.04 | ESR Magnet Measurement & Acceptance | DOE.DOE | 2026-06-12 | 2026-09-08 | bsmith | hwitte | 1487.55 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | BNL | Construction.Test & Accept | NC_MAG |  | Labor - 092 |  | LLP043 | ITEM111 | ITEM092 | Witte | hwitte | FY2026: 1487.55
|  | E0402_06020 | ESR Magnets - APS Sextupole - Magnetic Measurement - 56 Magnets - AS07 | 6.04.02.04 | ESR Magnet Measurement & Acceptance | DOE.DOE | 2026-06-12 | 2026-09-08 | bsmith | hwitte | 39417.44 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | BNL | Construction.Test & Accept | NC_MAG |  | Labor - 092 |  | LLP043 | ITEM111 | ITEM092 | Witte | hwitte | FY2026: 39417.44
|  | E0402_06020 | ESR Magnets - APS Sextupole - Magnetic Measurement - 56 Magnets - AS07 | 6.04.02.04 | ESR Magnet Measurement & Acceptance | DOE.DOE | 2026-06-12 | 2026-09-08 | bsmith | hwitte | 92293.64 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | BNL | Construction.Test & Accept | NC_MAG |  | Labor - 092 |  | LLP043 | ITEM111 | ITEM092 | Witte | hwitte | FY2026: 92293.64
|  | E0402_06040 | ESR Magnets - APS Sextupole - Magnetic Measurement - 56 Magnets - AS09 | 6.04.02.04 | ESR Magnet Measurement & Acceptance | DOE.DOE | 2027-04-19 | 2027-07-14 | bsmith | hwitte | 1539.62 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | BNL | Construction.Test & Accept | NC_MAG |  | Labor - 092 |  | LLP043 | ITEM111 | ITEM092 | Witte | hwitte | FY2027: 1539.62
|  | E0402_06040 | ESR Magnets - APS Sextupole - Magnetic Measurement - 56 Magnets - AS09 | 6.04.02.04 | ESR Magnet Measurement & Acceptance | DOE.DOE | 2027-04-19 | 2027-07-14 | bsmith | hwitte | 3763.5 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | BNL | Construction.Test & Accept | NC_MAG |  | Labor - 092 |  | LLP043 | ITEM111 | ITEM092 | Witte | hwitte | FY2027: 3763.5
|  | E0402_06040 | ESR Magnets - APS Sextupole - Magnetic Measurement - 56 Magnets - AS09 | 6.04.02.04 | ESR Magnet Measurement & Acceptance | DOE.DOE | 2027-04-19 | 2027-07-14 | bsmith | hwitte | 1539.62 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | BNL | Construction.Test & Accept | NC_MAG |  | Labor - 092 |  | LLP043 | ITEM111 | ITEM092 | Witte | hwitte | FY2027: 1539.62
|  | E0402_06040 | ESR Magnets - APS Sextupole - Magnetic Measurement - 56 Magnets - AS09 | 6.04.02.04 | ESR Magnet Measurement & Acceptance | DOE.DOE | 2027-04-19 | 2027-07-14 | bsmith | hwitte | 40797.05 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | BNL | Construction.Test & Accept | NC_MAG |  | Labor - 092 |  | LLP043 | ITEM111 | ITEM092 | Witte | hwitte | FY2027: 40797.05
|  | E0402_06040 | ESR Magnets - APS Sextupole - Magnetic Measurement - 56 Magnets - AS09 | 6.04.02.04 | ESR Magnet Measurement & Acceptance | DOE.DOE | 2027-04-19 | 2027-07-14 | bsmith | hwitte | 95523.92 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | BNL | Construction.Test & Accept | NC_MAG |  | Labor - 092 |  | LLP043 | ITEM111 | ITEM092 | Witte | hwitte | FY2027: 95523.92
|  | E0402_06060 | ESR Magnets - APS Sextupole - Magnetic Measurement - 56 Magnets - AS11 | 6.04.02.04 | ESR Magnet Measurement & Acceptance | DOE.DOE | 2028-02-23 | 2028-05-16 | bsmith | hwitte | 1593.5 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | BNL | Construction.Test & Accept | NC_MAG |  | Labor - 092 |  | LLP043 | ITEM111 | ITEM092 | Witte | hwitte | FY2028: 1593.5
|  | E0402_06060 | ESR Magnets - APS Sextupole - Magnetic Measurement - 56 Magnets - AS11 | 6.04.02.04 | ESR Magnet Measurement & Acceptance | DOE.DOE | 2028-02-23 | 2028-05-16 | bsmith | hwitte | 3895.23 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | BNL | Construction.Test & Accept | NC_MAG |  | Labor - 092 |  | LLP043 | ITEM111 | ITEM092 | Witte | hwitte | FY2028: 3895.23
|  | E0402_06060 | ESR Magnets - APS Sextupole - Magnetic Measurement - 56 Magnets - AS11 | 6.04.02.04 | ESR Magnet Measurement & Acceptance | DOE.DOE | 2028-02-23 | 2028-05-16 | bsmith | hwitte | 1593.5 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | BNL | Construction.Test & Accept | NC_MAG |  | Labor - 092 |  | LLP043 | ITEM111 | ITEM092 | Witte | hwitte | FY2028: 1593.5
|  | E0402_06060 | ESR Magnets - APS Sextupole - Magnetic Measurement - 56 Magnets - AS11 | 6.04.02.04 | ESR Magnet Measurement & Acceptance | DOE.DOE | 2028-02-23 | 2028-05-16 | bsmith | hwitte | 42224.95 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | BNL | Construction.Test & Accept | NC_MAG |  | Labor - 092 |  | LLP043 | ITEM111 | ITEM092 | Witte | hwitte | FY2028: 42224.95
|  | E0402_06060 | ESR Magnets - APS Sextupole - Magnetic Measurement - 56 Magnets - AS11 | 6.04.02.04 | ESR Magnet Measurement & Acceptance | DOE.DOE | 2028-02-23 | 2028-05-16 | bsmith | hwitte | 98867.25 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | BNL | Construction.Test & Accept | NC_MAG |  | Labor - 092 |  | LLP043 | ITEM111 | ITEM092 | Witte | hwitte | FY2028: 98867.25
|  | E0402_06080 | ESR Magnets - APS Sextupole - Magnetic Measurement - 56 Magnets - AS05 | 6.04.02.04 | ESR Magnet Measurement & Acceptance | DOE.DOE | 2028-12-26 | 2029-03-22 | bsmith | hwitte | 1649.27 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | BNL | Construction.Test & Accept | NC_MAG |  | Labor - 092 |  | LLP043 | ITEM111 | ITEM092 | Witte | hwitte | FY2029: 1649.27
|  | E0402_06080 | ESR Magnets - APS Sextupole - Magnetic Measurement - 56 Magnets - AS05 | 6.04.02.04 | ESR Magnet Measurement & Acceptance | DOE.DOE | 2028-12-26 | 2029-03-22 | bsmith | hwitte | 4031.56 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | BNL | Construction.Test & Accept | NC_MAG |  | Labor - 092 |  | LLP043 | ITEM111 | ITEM092 | Witte | hwitte | FY2029: 4031.56
|  | E0402_06080 | ESR Magnets - APS Sextupole - Magnetic Measurement - 56 Magnets - AS05 | 6.04.02.04 | ESR Magnet Measurement & Acceptance | DOE.DOE | 2028-12-26 | 2029-03-22 | bsmith | hwitte | 1649.27 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | BNL | Construction.Test & Accept | NC_MAG |  | Labor - 092 |  | LLP043 | ITEM111 | ITEM092 | Witte | hwitte | FY2029: 1649.27
|  | E0402_06080 | ESR Magnets - APS Sextupole - Magnetic Measurement - 56 Magnets - AS05 | 6.04.02.04 | ESR Magnet Measurement & Acceptance | DOE.DOE | 2028-12-26 | 2029-03-22 | bsmith | hwitte | 43702.82 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | BNL | Construction.Test & Accept | NC_MAG |  | Labor - 092 |  | LLP043 | ITEM111 | ITEM092 | Witte | hwitte | FY2029: 43702.82
|  | E0402_06080 | ESR Magnets - APS Sextupole - Magnetic Measurement - 56 Magnets - AS05 | 6.04.02.04 | ESR Magnet Measurement & Acceptance | DOE.DOE | 2028-12-26 | 2029-03-22 | bsmith | hwitte | 102327.61 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | BNL | Construction.Test & Accept | NC_MAG |  | Labor - 092 |  | LLP043 | ITEM111 | ITEM092 | Witte | hwitte | FY2029: 102327.61
ESR APS Quad Magnet Measurement & Stand | Contract Award | E0402_06190 | ESR Magnets - Magnet Measurement Bench - OBL - Obligation Activity | 6.04.02.04 | ESR Magnet Measurement & Acceptance | DOE.DOE | 2026-09-18 | 2026-09-18 | bsmith | hwitte | 0.01 |  | % Comp.C.NA | Nonlabor | TEC | CD3B.SCOPE | BNL | Construction.Test & Accept | NC_MAG | OBL | P.S1135 |  | LLP042 | ITEM112 | ITEM105 | Witte |  | FY2026: 0.01
|  | E0402_06190 | ESR Magnets - Magnet Measurement Bench - OBL - Obligation Activity | 6.04.02.04 | ESR Magnet Measurement & Acceptance | DOE.DOE | 2026-09-18 | 2026-09-18 | bsmith | hwitte | 181755.46 |  | % Comp.C.NA | Nonlabor | TEC | CD3B.SCOPE | BNL | Construction.Test & Accept | NC_MAG | OBL | P.S1135 |  | LLP042 | ITEM112 | ITEM105 | Witte |  | FY2026: 181755.46
|  | E0402_06210 | ESR Magnets - Magnet Measurement Bench - RCV | 6.04.02.04 | ESR Magnet Measurement & Acceptance | DOE.DOE | 2027-01-19 | 2027-01-19 | bsmith | hwitte | 181755.46 |  | PPkg.K | Nonlabor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | NC_MAG | RCV | P.S1135 |  | LLP042 | ITEM112 | ITEM105 | Witte | hwitte | FY2027: 181755.46
|  | E0402_06230 | ESR Magnets - Magnet Measurement Bench - TR Effort (Vendor Fab Oversight & Bench Configuration) | 6.04.02.04 | ESR Magnet Measurement & Acceptance | DOE.DOE | 2026-09-21 | 2027-01-19 | bsmith | hwitte | 150031.07 |  | PPkg.K | Labor | TEC | CD3B.SCOPE | BNL | Construction.Test & Accept | NC_MAG |  | P.S1135 |  | LLP042 | ITEM112 | ITEM105 | Witte | hwitte | FY2026: 15003.11; FY2027: 135027.97
|  | E0402_06230 | ESR Magnets - Magnet Measurement Bench - TR Effort (Vendor Fab Oversight & Bench Configuration) | 6.04.02.04 | ESR Magnet Measurement & Acceptance | DOE.DOE | 2026-09-21 | 2027-01-19 | bsmith | hwitte | 117498.99 |  | PPkg.K | Labor | TEC | CD3B.SCOPE | BNL | Construction.Test & Accept | NC_MAG |  | P.S1135 |  | LLP042 | ITEM112 | ITEM105 | Witte | hwitte | FY2026: 11749.9; FY2027: 105749.1
|  | E0402_06230 | ESR Magnets - Magnet Measurement Bench - TR Effort (Vendor Fab Oversight & Bench Configuration) | 6.04.02.04 | ESR Magnet Measurement & Acceptance | DOE.DOE | 2026-09-21 | 2027-01-19 | bsmith | hwitte | 88008.53 |  | PPkg.K | Labor | TEC | CD3B.SCOPE | BNL | Construction.Test & Accept | NC_MAG |  | P.S1135 |  | LLP042 | ITEM112 | ITEM105 | Witte | hwitte | FY2026: 8800.85; FY2027: 79207.68
|  | E0402_06085 | ESR Magnets - APS Sextupole - Magnet Measurement Consumables | 6.04.02.04 | ESR Magnet Measurement & Acceptance | DOE.DOE | 2025-11-04 | 2026-02-03 | bsmith | hwitte | 5345.75 |  | % Comp.C | Nonlabor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | NC_MAG |  | B |  | LLP043 | ITEM111 | ITEM092 | Witte | hwitte | FY2026: 5345.75
|  | E0403_03440 | ESR APS Magnets - Group 2: 17-79 - Refurbish Quads - Batch 2 | 6.04.03.01.01.02 | ESR Magnet APS Quad Fabrication | DOE.DOE | 2025-06-17 | 2025-10-07 | driga | sphilip | 7189.84 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2025: 6728.96; FY2026: 460.89
|  | E0403_03440 | ESR APS Magnets - Group 2: 17-79 - Refurbish Quads - Batch 2 | 6.04.03.01.01.02 | ESR Magnet APS Quad Fabrication | DOE.DOE | 2025-06-17 | 2025-10-07 | driga | sphilip | 36672.9 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2025: 34322.07; FY2026: 2350.83
|  | E0403_03440 | ESR APS Magnets - Group 2: 17-79 - Refurbish Quads - Batch 2 | 6.04.03.01.01.02 | ESR Magnet APS Quad Fabrication | DOE.DOE | 2025-06-17 | 2025-10-07 | driga | sphilip | 122489.94 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2025: 114638.02; FY2026: 7851.92
|  | E0403_03440 | ESR APS Magnets - Group 2: 17-79 - Refurbish Quads - Batch 2 | 6.04.03.01.01.02 | ESR Magnet APS Quad Fabrication | DOE.DOE | 2025-06-17 | 2025-10-07 | driga | sphilip | 43607.97 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2025: 40812.59; FY2026: 2795.38
|  | E0403_03440 | ESR APS Magnets - Group 2: 17-79 - Refurbish Quads - Batch 2 | 6.04.03.01.01.02 | ESR Magnet APS Quad Fabrication | DOE.DOE | 2025-06-17 | 2025-10-07 | driga | sphilip | 66381.02 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2025: 62125.83; FY2026: 4255.19
|  | E0403_03460 | ESR APS Magnets - Group 3: 80-141 - Refurbish Quads - Batch 2 | 6.04.03.01.01.02 | ESR Magnet APS Quad Fabrication | DOE.DOE | 2026-01-30 | 2026-05-19 | driga | sphilip | 44106.93 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2026: 44106.93
|  | E0403_03460 | ESR APS Magnets - Group 3: 80-141 - Refurbish Quads - Batch 2 | 6.04.03.01.01.02 | ESR Magnet APS Quad Fabrication | DOE.DOE | 2026-01-30 | 2026-05-19 | driga | sphilip | 67140.55 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2026: 67140.55
|  | E0403_03460 | ESR APS Magnets - Group 3: 80-141 - Refurbish Quads - Batch 2 | 6.04.03.01.01.02 | ESR Magnet APS Quad Fabrication | DOE.DOE | 2026-01-30 | 2026-05-19 | driga | sphilip | 7243.5 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2026: 7243.5
|  | E0403_03460 | ESR APS Magnets - Group 3: 80-141 - Refurbish Quads - Batch 2 | 6.04.03.01.01.02 | ESR Magnet APS Quad Fabrication | DOE.DOE | 2026-01-30 | 2026-05-19 | driga | sphilip | 123891.47 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2026: 123891.47
|  | E0403_03460 | ESR APS Magnets - Group 3: 80-141 - Refurbish Quads - Batch 2 | 6.04.03.01.01.02 | ESR Magnet APS Quad Fabrication | DOE.DOE | 2026-01-30 | 2026-05-19 | driga | sphilip | 37129.36 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2026: 37129.36
|  | E0403_03480 | ESR APS Magnets - Group 4: 142-203 - Refurbish Quads - Batch 2 | 6.04.03.01.01.02 | ESR Magnet APS Quad Fabrication | DOE.DOE | 2026-05-20 | 2026-09-10 | driga | sphilip | 44106.93 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2026: 44106.93
|  | E0403_03480 | ESR APS Magnets - Group 4: 142-203 - Refurbish Quads - Batch 2 | 6.04.03.01.01.02 | ESR Magnet APS Quad Fabrication | DOE.DOE | 2026-05-20 | 2026-09-10 | driga | sphilip | 67140.55 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2026: 67140.55
|  | E0403_03480 | ESR APS Magnets - Group 4: 142-203 - Refurbish Quads - Batch 2 | 6.04.03.01.01.02 | ESR Magnet APS Quad Fabrication | DOE.DOE | 2026-05-20 | 2026-09-10 | driga | sphilip | 7243.5 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2026: 7243.5
|  | E0403_03480 | ESR APS Magnets - Group 4: 142-203 - Refurbish Quads - Batch 2 | 6.04.03.01.01.02 | ESR Magnet APS Quad Fabrication | DOE.DOE | 2026-05-20 | 2026-09-10 | driga | sphilip | 123891.47 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2026: 123891.47
|  | E0403_03480 | ESR APS Magnets - Group 4: 142-203 - Refurbish Quads - Batch 2 | 6.04.03.01.01.02 | ESR Magnet APS Quad Fabrication | DOE.DOE | 2026-05-20 | 2026-09-10 | driga | sphilip | 37129.36 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2026: 37129.36
|  | E0403_03500 | ESR APS Magnets - Group 5: 204-265 - Refurbish Quads - Batch 2 | 6.04.03.01.01.02 | ESR Magnet APS Quad Fabrication | DOE.DOE | 2026-09-11 | 2027-01-11 | driga | sphilip | 45192.64 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2026: 8111.5; FY2027: 37081.14
|  | E0403_03500 | ESR APS Magnets - Group 5: 204-265 - Refurbish Quads - Batch 2 | 6.04.03.01.01.02 | ESR Magnet APS Quad Fabrication | DOE.DOE | 2026-09-11 | 2027-01-11 | driga | sphilip | 68793.24 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2026: 12347.51; FY2027: 56445.74
|  | E0403_03500 | ESR APS Magnets - Group 5: 204-265 - Refurbish Quads - Batch 2 | 6.04.03.01.01.02 | ESR Magnet APS Quad Fabrication | DOE.DOE | 2026-09-11 | 2027-01-11 | driga | sphilip | 7421.8 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2026: 1332.12; FY2027: 6089.68
|  | E0403_03500 | ESR APS Magnets - Group 5: 204-265 - Refurbish Quads - Batch 2 | 6.04.03.01.01.02 | ESR Magnet APS Quad Fabrication | DOE.DOE | 2026-09-11 | 2027-01-11 | driga | sphilip | 126941.11 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2026: 22784.3; FY2027: 104156.81
|  | E0403_03500 | ESR APS Magnets - Group 5: 204-265 - Refurbish Quads - Batch 2 | 6.04.03.01.01.02 | ESR Magnet APS Quad Fabrication | DOE.DOE | 2026-09-11 | 2027-01-11 | driga | sphilip | 38043.31 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2026: 6828.29; FY2027: 31215.03
|  | E0403_03520 | ESR APS Magnets - Group 6: 266-327 - Refurbish Quads - Batch 2 | 6.04.03.01.01.02 | ESR Magnet APS Quad Fabrication | DOE.DOE | 2027-01-12 | 2027-04-30 | driga | sphilip | 45430.14 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2027: 45430.14
|  | E0403_03520 | ESR APS Magnets - Group 6: 266-327 - Refurbish Quads - Batch 2 | 6.04.03.01.01.02 | ESR Magnet APS Quad Fabrication | DOE.DOE | 2027-01-12 | 2027-04-30 | driga | sphilip | 69154.77 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2027: 69154.77
|  | E0403_03520 | ESR APS Magnets - Group 6: 266-327 - Refurbish Quads - Batch 2 | 6.04.03.01.01.02 | ESR Magnet APS Quad Fabrication | DOE.DOE | 2027-01-12 | 2027-04-30 | driga | sphilip | 7460.8 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2027: 7460.8
|  | E0403_03520 | ESR APS Magnets - Group 6: 266-327 - Refurbish Quads - Batch 2 | 6.04.03.01.01.02 | ESR Magnet APS Quad Fabrication | DOE.DOE | 2027-01-12 | 2027-04-30 | driga | sphilip | 127608.22 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2027: 127608.22
|  | E0403_03520 | ESR APS Magnets - Group 6: 266-327 - Refurbish Quads - Batch 2 | 6.04.03.01.01.02 | ESR Magnet APS Quad Fabrication | DOE.DOE | 2027-01-12 | 2027-04-30 | driga | sphilip | 38243.24 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2027: 38243.24
|  | E0403_03560 | ESR APS Magnets - Group 2: 9-44 - Rebuild Quads - Batch 2 | 6.04.03.01.01.02 | ESR Magnet APS Quad Fabrication | DOE.DOE | 2025-10-08 | 2026-01-29 | driga | sphilip | 43817.71 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | NC_MAG |  | S.P542 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2026: 43817.71
|  | E0403_03560 | ESR APS Magnets - Group 2: 9-44 - Rebuild Quads - Batch 2 | 6.04.03.01.01.02 | ESR Magnet APS Quad Fabrication | DOE.DOE | 2025-10-08 | 2026-01-29 | driga | sphilip | 66700.29 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | NC_MAG |  | S.P542 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2026: 66700.29
|  | E0403_03560 | ESR APS Magnets - Group 2: 9-44 - Rebuild Quads - Batch 2 | 6.04.03.01.01.02 | ESR Magnet APS Quad Fabrication | DOE.DOE | 2025-10-08 | 2026-01-29 | driga | sphilip | 7243.5 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | NC_MAG |  | S.P542 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2026: 7243.5
|  | E0403_03560 | ESR APS Magnets - Group 2: 9-44 - Rebuild Quads - Batch 2 | 6.04.03.01.01.02 | ESR Magnet APS Quad Fabrication | DOE.DOE | 2025-10-08 | 2026-01-29 | driga | sphilip | 123129.84 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | NC_MAG |  | S.P542 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2026: 123129.84
|  | E0403_03560 | ESR APS Magnets - Group 2: 9-44 - Rebuild Quads - Batch 2 | 6.04.03.01.01.02 | ESR Magnet APS Quad Fabrication | DOE.DOE | 2025-10-08 | 2026-01-29 | driga | sphilip | 36938.95 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | NC_MAG |  | S.P542 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2026: 36938.95
|  | E0403_03570 | ESR APS Magnets - Group 3: 45-80 - Rebuild Quads - Batch 2 | 6.04.03.01.01.02 | ESR Magnet APS Quad Fabrication | DOE.DOE | 2027-05-03 | 2027-08-13 | driga | sphilip | 45132.24 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | NC_MAG |  | S.P542 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2027: 45132.24
|  | E0403_03570 | ESR APS Magnets - Group 3: 45-80 - Rebuild Quads - Batch 2 | 6.04.03.01.01.02 | ESR Magnet APS Quad Fabrication | DOE.DOE | 2027-05-03 | 2027-08-13 | driga | sphilip | 68701.3 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | NC_MAG |  | S.P542 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2027: 68701.3
|  | E0403_03570 | ESR APS Magnets - Group 3: 45-80 - Rebuild Quads - Batch 2 | 6.04.03.01.01.02 | ESR Magnet APS Quad Fabrication | DOE.DOE | 2027-05-03 | 2027-08-13 | driga | sphilip | 7460.8 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | NC_MAG |  | S.P542 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2027: 7460.8
|  | E0403_03570 | ESR APS Magnets - Group 3: 45-80 - Rebuild Quads - Batch 2 | 6.04.03.01.01.02 | ESR Magnet APS Quad Fabrication | DOE.DOE | 2027-05-03 | 2027-08-13 | driga | sphilip | 126823.74 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | NC_MAG |  | S.P542 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2027: 126823.74
|  | E0403_03570 | ESR APS Magnets - Group 3: 45-80 - Rebuild Quads - Batch 2 | 6.04.03.01.01.02 | ESR Magnet APS Quad Fabrication | DOE.DOE | 2027-05-03 | 2027-08-13 | driga | sphilip | 38047.12 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | NC_MAG |  | S.P542 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2027: 38047.12
|  | E0403_02176 | ESR APS Magnets - Magnet Refbuild Parts - TR Effort - Travel | 6.04.03.01.01.02 | ESR Magnet APS Quad Fabrication | DOE.DOE | 2025-05-02 | 2025-09-11 | driga | sphilip | 2803 |  | % Comp.C.Appor | Nonlabor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | NC_MAG |  | T.LLP027 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2025: 2803
|  | E0403_02022 | ESR APS Magnets - Magnet Refurbishment Parts - OBL - Obligation Activity - Batch 2 | 6.04.03.01.01.02 | ESR Magnet APS Quad Fabrication | DOE.DOE | 2025-05-01 | 2025-05-01 | driga | sphilip | 348228.69 |  | PPkg.K | Nonlabor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | NC_MAG | OBL | S.P.541 | APP00880 | LLP032 | ITEM113 | ITEM089 | Philip |  | FY2025: 348228.69
|  | E0403_02022 | ESR APS Magnets - Magnet Refurbishment Parts - OBL - Obligation Activity - Batch 2 | 6.04.03.01.01.02 | ESR Magnet APS Quad Fabrication | DOE.DOE | 2025-05-01 | 2025-05-01 | driga | sphilip | 851578.38 |  | PPkg.K | Nonlabor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | NC_MAG | OBL | S.P.541 | APP00880 | LLP032 | ITEM113 | ITEM089 | Philip |  | FY2025: 851578.38
APS Quad Rebuild & Refurbishment | Contract Award | E0403_02022 | ESR APS Magnets - Magnet Refurbishment Parts - OBL - Obligation Activity - Batch 2 | 6.04.03.01.01.02 | ESR Magnet APS Quad Fabrication | DOE.DOE | 2025-05-01 | 2025-05-01 | driga | sphilip | 0.01 |  | PPkg.K | Nonlabor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | NC_MAG | OBL | S.P.541 | APP00880 | LLP032 | ITEM113 | ITEM089 | Philip |  | FY2025: 0.01
|  | E0403_02025 | ESR APS Magnets - Magnet Refurbishment Parts - TR Effort - Labor | 6.04.03.01.01.02 | ESR Magnet APS Quad Fabrication | DOE.DOE | 2025-05-02 | 2025-09-11 | driga | sphilip | 22183.34 |  | PPkg.K | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | NC_MAG |  | S.P.541 | APP00880 | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2025: 22183.34
|  | E0403_02026 | ESR APS Magnets - Magnet Refurbishment Parts - RCV - Batch 2 | 6.04.03.01.01.02 | ESR Magnet APS Quad Fabrication | DOE.DOE | 2025-09-11 | 2025-09-11 | driga | sphilip | 348228.69 |  | PPkg.K | Nonlabor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | NC_MAG | RCV | S.P.541 | APP00880 | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2025: 348228.69
|  | E0403_02026 | ESR APS Magnets - Magnet Refurbishment Parts - RCV - Batch 2 | 6.04.03.01.01.02 | ESR Magnet APS Quad Fabrication | DOE.DOE | 2025-09-11 | 2025-09-11 | driga | sphilip | 851578.38 |  | PPkg.K | Nonlabor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | NC_MAG | RCV | S.P.541 | APP00880 | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2025: 851578.38
|  | E0403_02024 | ESR APS Magnets - Magnet Refurbishment Parts - TR Effort - Travel | 6.04.03.01.01.02 | ESR Magnet APS Quad Fabrication | DOE.DOE | 2025-05-02 | 2025-09-11 | driga | sphilip | 2803 |  | PPkg.K | Nonlabor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | NC_MAG |  | T.LLP028 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2025: 2803
APS Quad Rebuild & Refurbishment | Contract Award | E0403_02174 | ESR APS Magnets - Magnet Rebuild Parts - OBL - Obligation Activity - Batch 2 | 6.04.03.01.01.02 | ESR Magnet APS Quad Fabrication | DOE.DOE | 2025-05-01 | 2025-05-01 | driga | sphilip | 0.01 |  | PPkg.K | Nonlabor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | NC_MAG | OBL | S.P542 | APP00881 | LLP032 | ITEM113 | ITEM089 | Philip |  | FY2025: 0.01
|  | E0403_02174 | ESR APS Magnets - Magnet Rebuild Parts - OBL - Obligation Activity - Batch 2 | 6.04.03.01.01.02 | ESR Magnet APS Quad Fabrication | DOE.DOE | 2025-05-01 | 2025-05-01 | driga | sphilip | 348228.69 |  | PPkg.K | Nonlabor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | NC_MAG | OBL | S.P542 | APP00881 | LLP032 | ITEM113 | ITEM089 | Philip |  | FY2025: 348228.69
|  | E0403_02174 | ESR APS Magnets - Magnet Rebuild Parts - OBL - Obligation Activity - Batch 2 | 6.04.03.01.01.02 | ESR Magnet APS Quad Fabrication | DOE.DOE | 2025-05-01 | 2025-05-01 | driga | sphilip | 3542.06 |  | PPkg.K | Nonlabor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | NC_MAG | OBL | S.P542 | APP00881 | LLP032 | ITEM113 | ITEM089 | Philip |  | FY2025: 3542.06
|  | E0403_02177 | ESR APS Magnets - Magnet Rebuild Parts - TR Effort - Labor | 6.04.03.01.01.02 | ESR Magnet APS Quad Fabrication | DOE.DOE | 2025-05-02 | 2025-09-11 | driga | sphilip | 22183.34 |  | PPkg.K | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | NC_MAG |  | S.P542 | APP00881 | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2025: 22183.34
|  | E0403_02178 | ESR APS Magnets - Magnet Rebuild Parts - RCV - Batch 2 | 6.04.03.01.01.02 | ESR Magnet APS Quad Fabrication | DOE.DOE | 2025-09-11 | 2025-09-11 | driga | sphilip | 348228.69 |  | PPkg.K | Nonlabor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | NC_MAG | RCV | S.P542 | APP00881 | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2025: 348228.69
|  | E0403_02178 | ESR APS Magnets - Magnet Rebuild Parts - RCV - Batch 2 | 6.04.03.01.01.02 | ESR Magnet APS Quad Fabrication | DOE.DOE | 2025-09-11 | 2025-09-11 | driga | sphilip | 3542.06 |  | PPkg.K | Nonlabor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | NC_MAG | RCV | S.P542 | APP00881 | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2025: 3542.06
|  | E0403_03840 | ESR APS Magnets - Production Quads Group 2 - QTY:63 - Measure 20% Refurbished Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2025-10-10 | 2025-11-24 | driga | sphilip | 1446.13 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2026: 1446.13
|  | E0403_03840 | ESR APS Magnets - Production Quads Group 2 - QTY:63 - Measure 20% Refurbished Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2025-10-10 | 2025-11-24 | driga | sphilip | 2201.33 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2026: 2201.33
|  | E0403_03840 | ESR APS Magnets - Production Quads Group 2 - QTY:63 - Measure 20% Refurbished Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2025-10-10 | 2025-11-24 | driga | sphilip | 571.22 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2026: 571.22
|  | E0403_03840 | ESR APS Magnets - Production Quads Group 2 - QTY:63 - Measure 20% Refurbished Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2025-10-10 | 2025-11-24 | driga | sphilip | 399.69 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2026: 399.69
|  | E0403_03860 | ESR APS Magnets - Production Quads Group 2 - QTY:63 - Analysis and Final Inspection of Refurbished Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2025-11-04 | 2025-11-24 | driga | sphilip | 3808.14 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2026: 3808.14
|  | E0403_03860 | ESR APS Magnets - Production Quads Group 2 - QTY:63 - Analysis and Final Inspection of Refurbished Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2025-11-04 | 2025-11-24 | driga | sphilip | 1100.66 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2026: 1100.66
|  | E0403_03860 | ESR APS Magnets - Production Quads Group 2 - QTY:63 - Analysis and Final Inspection of Refurbished Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2025-11-04 | 2025-11-24 | driga | sphilip | 1332.31 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2026: 1332.31
|  | E0403_03800 | ESR APS Magnets - Production Quads Group 2 - QTY:63 - QC Refurbished Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2025-10-08 | 2025-11-20 | driga | sphilip | 18510.45 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2026: 18510.45
|  | E0403_03800 | ESR APS Magnets - Production Quads Group 2 - QTY:63 - QC Refurbished Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2025-10-08 | 2025-11-20 | driga | sphilip | 28177.02 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2026: 28177.02
|  | E0403_03800 | ESR APS Magnets - Production Quads Group 2 - QTY:63 - QC Refurbished Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2025-10-08 | 2025-11-20 | driga | sphilip | 4263.4 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2026: 4263.4
|  | E0403_03800 | ESR APS Magnets - Production Quads Group 2 - QTY:63 - QC Refurbished Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2025-10-08 | 2025-11-20 | driga | sphilip | 6093.02 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2026: 6093.02
|  | E0403_03920 | ESR APS Magnets - Production Quads Group 3 - QTY:62 - Measure 20% Refurbished Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2026-06-08 | 2026-07-23 | driga | sphilip | 1446.13 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2026: 1446.13
|  | E0403_03920 | ESR APS Magnets - Production Quads Group 3 - QTY:62 - Measure 20% Refurbished Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2026-06-08 | 2026-07-23 | driga | sphilip | 2201.33 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2026: 2201.33
|  | E0403_03920 | ESR APS Magnets - Production Quads Group 3 - QTY:62 - Measure 20% Refurbished Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2026-06-08 | 2026-07-23 | driga | sphilip | 571.22 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2026: 571.22
|  | E0403_03920 | ESR APS Magnets - Production Quads Group 3 - QTY:62 - Measure 20% Refurbished Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2026-06-08 | 2026-07-23 | driga | sphilip | 399.69 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2026: 399.69
|  | E0403_03940 | ESR APS Magnets - Production Quads Group 3 - QTY:62 - Analysis and Final Inspection of Refurbished Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2026-07-24 | 2026-08-13 | driga | sphilip | 3808.14 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2026: 3808.14
|  | E0403_03940 | ESR APS Magnets - Production Quads Group 3 - QTY:62 - Analysis and Final Inspection of Refurbished Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2026-07-24 | 2026-08-13 | driga | sphilip | 1100.66 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2026: 1100.66
|  | E0403_03940 | ESR APS Magnets - Production Quads Group 3 - QTY:62 - Analysis and Final Inspection of Refurbished Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2026-07-24 | 2026-08-13 | driga | sphilip | 1332.31 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2026: 1332.31
|  | E0403_03880 | ESR APS Magnets - Production Quads Group 3 - QTY:62 - QC Refurbished Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2026-05-20 | 2026-07-07 | driga | sphilip | 18510.45 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2026: 18510.45
|  | E0403_03880 | ESR APS Magnets - Production Quads Group 3 - QTY:62 - QC Refurbished Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2026-05-20 | 2026-07-07 | driga | sphilip | 28177.02 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2026: 28177.02
|  | E0403_03880 | ESR APS Magnets - Production Quads Group 3 - QTY:62 - QC Refurbished Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2026-05-20 | 2026-07-07 | driga | sphilip | 4263.4 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2026: 4263.4
|  | E0403_03880 | ESR APS Magnets - Production Quads Group 3 - QTY:62 - QC Refurbished Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2026-05-20 | 2026-07-07 | driga | sphilip | 6093.02 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2026: 6093.02
|  | E0403_04000 | ESR APS Magnets - Production Quads Group 4 - QTY:62 - Measure 20% Refurbished Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2026-09-15 | 2026-10-28 | driga | sphilip | 1473.24 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2026: 552.47; FY2027: 920.78
|  | E0403_04000 | ESR APS Magnets - Production Quads Group 4 - QTY:62 - Measure 20% Refurbished Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2026-09-15 | 2026-10-28 | driga | sphilip | 2242.6 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2026: 840.98; FY2027: 1401.63
|  | E0403_04000 | ESR APS Magnets - Production Quads Group 4 - QTY:62 - Measure 20% Refurbished Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2026-09-15 | 2026-10-28 | driga | sphilip | 581.93 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2026: 218.22; FY2027: 363.71
|  | E0403_04000 | ESR APS Magnets - Production Quads Group 4 - QTY:62 - Measure 20% Refurbished Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2026-09-15 | 2026-10-28 | driga | sphilip | 407.19 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2026: 152.7; FY2027: 254.49
|  | E0403_04020 | ESR APS Magnets - Production Quads Group 4 - QTY:62 - Analysis and Final Inspection of Refurbished Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2026-10-29 | 2026-11-18 | driga | sphilip | 3922.38 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2027: 3922.38
|  | E0403_04020 | ESR APS Magnets - Production Quads Group 4 - QTY:62 - Analysis and Final Inspection of Refurbished Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2026-10-29 | 2026-11-18 | driga | sphilip | 1133.68 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2027: 1133.68
|  | E0403_04020 | ESR APS Magnets - Production Quads Group 4 - QTY:62 - Analysis and Final Inspection of Refurbished Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2026-10-29 | 2026-11-18 | driga | sphilip | 1372.28 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2027: 1372.28
|  | E0403_03960 | ESR APS Magnets - Production Quads Group 4 - QTY:62 - QC Refurbished Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2026-09-11 | 2026-10-26 | driga | sphilip | 18822.81 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2026: 8234.98; FY2027: 10587.83
|  | E0403_03960 | ESR APS Magnets - Production Quads Group 4 - QTY:62 - QC Refurbished Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2026-09-11 | 2026-10-26 | driga | sphilip | 28652.51 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2026: 12535.47; FY2027: 16117.03
|  | E0403_03960 | ESR APS Magnets - Production Quads Group 4 - QTY:62 - QC Refurbished Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2026-09-11 | 2026-10-26 | driga | sphilip | 4335.35 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2026: 1896.71; FY2027: 2438.63
|  | E0403_03960 | ESR APS Magnets - Production Quads Group 4 - QTY:62 - QC Refurbished Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2026-09-11 | 2026-10-26 | driga | sphilip | 6195.84 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2026: 2710.68; FY2027: 3485.16
|  | E0403_04080 | ESR APS Magnets - Production Quads Group 5 - QTY:62 - Measure 20% Refurbished Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2027-01-14 | 2027-03-01 | driga | sphilip | 1489.51 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2027: 1489.51
|  | E0403_04080 | ESR APS Magnets - Production Quads Group 5 - QTY:62 - Measure 20% Refurbished Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2027-01-14 | 2027-03-01 | driga | sphilip | 2267.37 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2027: 2267.37
|  | E0403_04080 | ESR APS Magnets - Production Quads Group 5 - QTY:62 - Measure 20% Refurbished Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2027-01-14 | 2027-03-01 | driga | sphilip | 588.36 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2027: 588.36
|  | E0403_04080 | ESR APS Magnets - Production Quads Group 5 - QTY:62 - Measure 20% Refurbished Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2027-01-14 | 2027-03-01 | driga | sphilip | 411.68 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2027: 411.68
|  | E0403_04100 | ESR APS Magnets - Production Quads Group 5 - QTY:62 - Analysis and Final Inspection of Refurbished Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2027-03-02 | 2027-03-22 | driga | sphilip | 3922.38 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2027: 3922.38
|  | E0403_04100 | ESR APS Magnets - Production Quads Group 5 - QTY:62 - Analysis and Final Inspection of Refurbished Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2027-03-02 | 2027-03-22 | driga | sphilip | 1133.68 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2027: 1133.68
|  | E0403_04100 | ESR APS Magnets - Production Quads Group 5 - QTY:62 - Analysis and Final Inspection of Refurbished Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2027-03-02 | 2027-03-22 | driga | sphilip | 1372.28 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2027: 1372.28
|  | E0403_04040 | ESR APS Magnets - Production Quads Group 5 - QTY:62 - QC Refurbished Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2027-01-12 | 2027-02-25 | driga | sphilip | 19065.76 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2027: 19065.76
|  | E0403_04040 | ESR APS Magnets - Production Quads Group 5 - QTY:62 - QC Refurbished Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2027-01-12 | 2027-02-25 | driga | sphilip | 29022.33 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2027: 29022.33
|  | E0403_04040 | ESR APS Magnets - Production Quads Group 5 - QTY:62 - QC Refurbished Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2027-01-12 | 2027-02-25 | driga | sphilip | 4391.3 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2027: 4391.3
|  | E0403_04040 | ESR APS Magnets - Production Quads Group 5 - QTY:62 - QC Refurbished Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2027-01-12 | 2027-02-25 | driga | sphilip | 6275.81 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2027: 6275.81
|  | E0403_04160 | ESR APS Magnets - Production Quads Group 6 - QTY:62 - Measure 20% Refurbished Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2027-05-05 | 2027-06-21 | driga | sphilip | 1489.51 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2027: 1489.51
|  | E0403_04160 | ESR APS Magnets - Production Quads Group 6 - QTY:62 - Measure 20% Refurbished Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2027-05-05 | 2027-06-21 | driga | sphilip | 2267.37 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2027: 2267.37
|  | E0403_04160 | ESR APS Magnets - Production Quads Group 6 - QTY:62 - Measure 20% Refurbished Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2027-05-05 | 2027-06-21 | driga | sphilip | 588.36 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2027: 588.36
|  | E0403_04160 | ESR APS Magnets - Production Quads Group 6 - QTY:62 - Measure 20% Refurbished Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2027-05-05 | 2027-06-21 | driga | sphilip | 411.68 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2027: 411.68
|  | E0403_04180 | ESR APS Magnets - Production Quads Group 6 - QTY:62 - Analysis and Final Inspection of Refurbished Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2027-06-22 | 2027-07-13 | driga | sphilip | 3922.38 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2027: 3922.38
|  | E0403_04180 | ESR APS Magnets - Production Quads Group 6 - QTY:62 - Analysis and Final Inspection of Refurbished Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2027-06-22 | 2027-07-13 | driga | sphilip | 1133.68 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2027: 1133.68
|  | E0403_04180 | ESR APS Magnets - Production Quads Group 6 - QTY:62 - Analysis and Final Inspection of Refurbished Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2027-06-22 | 2027-07-13 | driga | sphilip | 1372.28 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2027: 1372.28
|  | E0403_04120 | ESR APS Magnets - Production Quads Group 6 - QTY:62 - QC Refurbished Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2027-05-03 | 2027-06-16 | driga | sphilip | 19065.76 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2027: 19065.76
|  | E0403_04120 | ESR APS Magnets - Production Quads Group 6 - QTY:62 - QC Refurbished Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2027-05-03 | 2027-06-16 | driga | sphilip | 29022.33 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2027: 29022.33
|  | E0403_04120 | ESR APS Magnets - Production Quads Group 6 - QTY:62 - QC Refurbished Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2027-05-03 | 2027-06-16 | driga | sphilip | 4391.3 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2027: 4391.3
|  | E0403_04120 | ESR APS Magnets - Production Quads Group 6 - QTY:62 - QC Refurbished Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2027-05-03 | 2027-06-16 | driga | sphilip | 6275.81 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2027: 6275.81
|  | E0403_04280 | ESR APS Magnets - Production Quads Group 2 - QTY:36 - QC Rebuilt Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2026-01-30 | 2026-02-24 | driga | sphilip | 16338.76 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P542 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2026: 16338.76
|  | E0403_04280 | ESR APS Magnets - Production Quads Group 2 - QTY:36 - QC Rebuilt Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2026-01-30 | 2026-02-24 | driga | sphilip | 3533.11 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P542 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2026: 3533.11
|  | E0403_04280 | ESR APS Magnets - Production Quads Group 2 - QTY:36 - QC Rebuilt Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2026-01-30 | 2026-02-24 | driga | sphilip | 2472.18 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P542 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2026: 2472.18
|  | E0403_04280 | ESR APS Magnets - Production Quads Group 2 - QTY:36 - QC Rebuilt Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2026-01-30 | 2026-02-24 | driga | sphilip | 10733.49 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P542 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2026: 10733.49
|  | E0403_04340 | ESR APS Magnets - Production Quads Group 2 - QTY:36 - Analysis and Final Inspection of Rebuilt Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2026-02-25 | 2026-03-06 | driga | sphilip | 243.3 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P542 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2026: 243.3
|  | E0403_04340 | ESR APS Magnets - Production Quads Group 2 - QTY:36 - Analysis and Final Inspection of Rebuilt Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2026-02-25 | 2026-03-06 | driga | sphilip | 1125.12 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P542 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2026: 1125.12
|  | E0403_04340 | ESR APS Magnets - Production Quads Group 2 - QTY:36 - Analysis and Final Inspection of Rebuilt Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2026-02-25 | 2026-03-06 | driga | sphilip | 170.24 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P542 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2026: 170.24
|  | E0403_04340 | ESR APS Magnets - Production Quads Group 2 - QTY:36 - Analysis and Final Inspection of Rebuilt Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2026-02-25 | 2026-03-06 | driga | sphilip | 739.13 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P542 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2026: 739.13
|  | E0403_04320 | ESR APS Magnets - Production Quads Group 2 - QTY:36 - Measure Rebuilt Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2026-01-30 | 2026-02-24 | driga | sphilip | 1271.88 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P542 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2026: 1271.88
|  | E0403_04320 | ESR APS Magnets - Production Quads Group 2 - QTY:36 - Measure Rebuilt Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2026-01-30 | 2026-02-24 | driga | sphilip | 835.54 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P542 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2026: 835.54
|  | E0403_04320 | ESR APS Magnets - Production Quads Group 2 - QTY:36 - Measure Rebuilt Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2026-01-30 | 2026-02-24 | driga | sphilip | 192.45 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P542 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2026: 192.45
|  | E0403_04320 | ESR APS Magnets - Production Quads Group 2 - QTY:36 - Measure Rebuilt Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2026-01-30 | 2026-02-24 | driga | sphilip | 275.03 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P542 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2026: 275.03
|  | E0403_04350 | ESR APS Magnets - Production Quads Group 3 - QTY:36 - QC Rebuilt Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2027-08-16 | 2027-09-09 | driga | sphilip | 16828.92 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P542 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2027: 16828.92
|  | E0403_04350 | ESR APS Magnets - Production Quads Group 3 - QTY:36 - QC Rebuilt Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2027-08-16 | 2027-09-09 | driga | sphilip | 3639.1 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P542 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2027: 3639.1
|  | E0403_04350 | ESR APS Magnets - Production Quads Group 3 - QTY:36 - QC Rebuilt Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2027-08-16 | 2027-09-09 | driga | sphilip | 2546.35 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P542 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2027: 2546.35
|  | E0403_04350 | ESR APS Magnets - Production Quads Group 3 - QTY:36 - QC Rebuilt Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2027-08-16 | 2027-09-09 | driga | sphilip | 11055.49 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P542 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2027: 11055.49
|  | E0403_04365 | ESR APS Magnets - Production Quads Group 3 - QTY:36 - Analysis and Final Inspection of Rebuilt Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2027-09-10 | 2027-09-21 | driga | sphilip | 250.6 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P542 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2027: 250.6
|  | E0403_04365 | ESR APS Magnets - Production Quads Group 3 - QTY:36 - Analysis and Final Inspection of Rebuilt Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2027-09-10 | 2027-09-21 | driga | sphilip | 1158.88 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P542 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2027: 1158.88
|  | E0403_04365 | ESR APS Magnets - Production Quads Group 3 - QTY:36 - Analysis and Final Inspection of Rebuilt Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2027-09-10 | 2027-09-21 | driga | sphilip | 175.35 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P542 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2027: 175.35
|  | E0403_04365 | ESR APS Magnets - Production Quads Group 3 - QTY:36 - Analysis and Final Inspection of Rebuilt Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2027-09-10 | 2027-09-21 | driga | sphilip | 761.31 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P542 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2027: 761.31
|  | E0403_04360 | ESR APS Magnets - Production Quads Group 3 - QTY:36 - Measure Rebuilt Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2027-08-16 | 2027-09-09 | driga | sphilip | 1310.04 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P542 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2027: 1310.04
|  | E0403_04360 | ESR APS Magnets - Production Quads Group 3 - QTY:36 - Measure Rebuilt Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2027-08-16 | 2027-09-09 | driga | sphilip | 860.61 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P542 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2027: 860.61
|  | E0403_04360 | ESR APS Magnets - Production Quads Group 3 - QTY:36 - Measure Rebuilt Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2027-08-16 | 2027-09-09 | driga | sphilip | 198.22 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P542 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2027: 198.22
|  | E0403_04360 | ESR APS Magnets - Production Quads Group 3 - QTY:36 - Measure Rebuilt Quads | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.DOE | 2027-08-16 | 2027-09-09 | driga | sphilip | 283.28 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | S.P542 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2027: 283.28
APS Quad Magnet Measurement & Stand | Contract Award | E0403_01693 | ESR APS Magnets - Magnet Measurement Stand 2 - OBL - Obligation Activity | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.IRA | 2025-05-21 | 2025-05-21 | driga | sphilip | 0.01 |  | % Comp.C | Nonlabor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | NC_MAG | OBL | P.S1143 |  | LLP042 | ITEM114 | ITEM096 | Philip |  | FY2025: 0.01
|  | E0403_01693 | ESR APS Magnets - Magnet Measurement Stand 2 - OBL - Obligation Activity | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.IRA | 2025-05-21 | 2025-05-21 | driga | sphilip | 90147.12 |  | % Comp.C | Nonlabor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | NC_MAG | OBL | P.S1143 |  | LLP042 | ITEM114 | ITEM096 | Philip |  | FY2025: 90147.12
|  | E0403_01694 | ESR APS Magnets - Magnet Measurement Stand 2 - TR Effort - Labor | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.IRA | 2025-05-22 | 2026-01-21 | driga | sphilip | 3682.91 |  | PPkg.K | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | NC_MAG |  | P.S1143 |  | LLP042 | ITEM114 | ITEM096 | Philip | sphilip | FY2025: 2058.77; FY2026: 1624.14
|  | E0403_01694 | ESR APS Magnets - Magnet Measurement Stand 2 - TR Effort - Labor | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.IRA | 2025-05-22 | 2026-01-21 | driga | sphilip | 14984.55 |  | PPkg.K | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | NC_MAG |  | P.S1143 |  | LLP042 | ITEM114 | ITEM096 | Philip | sphilip | FY2025: 8376.45; FY2026: 6608.09
|  | E0403_01694 | ESR APS Magnets - Magnet Measurement Stand 2 - TR Effort - Labor | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.IRA | 2025-05-22 | 2026-01-21 | driga | sphilip | 5816.79 |  | PPkg.K | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | NC_MAG |  | P.S1143 |  | LLP042 | ITEM114 | ITEM096 | Philip | sphilip | FY2025: 3251.62; FY2026: 2565.17
|  | E0403_01696 | ESR APS Magnets - Magnet Measurement Stand 2 - RCV | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.IRA | 2026-01-21 | 2026-01-21 | driga | sphilip | 90147.12 |  | PPkg.K | Nonlabor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | NC_MAG | RCV | P.S1143 |  | LLP042 | ITEM114 | ITEM096 | Philip | sphilip | FY2026: 90147.12
|  | E0403_03685 | ESR APS Magnets - Assemble Measurement Stand 2 | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.IRA | 2026-04-21 | 2026-08-27 | driga | sphilip | 70359.68 |  | PPkg.K | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Assemble | NC_MAG |  | P.S1143 |  | LLP042 | ITEM114 | ITEM096 | Philip | sphilip | FY2026: 70359.68
|  | E0403_03685 | ESR APS Magnets - Assemble Measurement Stand 2 | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.IRA | 2026-04-21 | 2026-08-27 | driga | sphilip | 60417.55 |  | PPkg.K | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Assemble | NC_MAG |  | P.S1143 |  | LLP042 | ITEM114 | ITEM096 | Philip | sphilip | FY2026: 60417.55
|  | E0403_03685 | ESR APS Magnets - Assemble Measurement Stand 2 | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.IRA | 2026-04-21 | 2026-08-27 | driga | sphilip | 15853.23 |  | PPkg.K | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Assemble | NC_MAG |  | P.S1143 |  | LLP042 | ITEM114 | ITEM096 | Philip | sphilip | FY2026: 15853.23
|  | E0403_03685 | ESR APS Magnets - Assemble Measurement Stand 2 | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.IRA | 2026-04-21 | 2026-08-27 | driga | sphilip | 8603.77 |  | PPkg.K | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Assemble | NC_MAG |  | P.S1143 |  | LLP042 | ITEM114 | ITEM096 | Philip | sphilip | FY2026: 8603.77
|  | E0403_03705 | ESR APS Magnets - Commission Measurement Stand 2 | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.IRA | 2026-08-28 | 2026-09-25 | driga | sphilip | 11826.12 |  | PPkg.K | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | P.S1143 |  | LLP042 | ITEM114 | ITEM096 | Philip | sphilip | FY2026: 11826.12
|  | E0403_03705 | ESR APS Magnets - Commission Measurement Stand 2 | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.IRA | 2026-08-28 | 2026-09-25 | driga | sphilip | 30465.12 |  | PPkg.K | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | P.S1143 |  | LLP042 | ITEM114 | ITEM096 | Philip | sphilip | FY2026: 30465.12
|  | E0403_03705 | ESR APS Magnets - Commission Measurement Stand 2 | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.IRA | 2026-08-28 | 2026-09-25 | driga | sphilip | 31975.52 |  | PPkg.K | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Test & Accept | NC_MAG |  | P.S1143 |  | LLP042 | ITEM114 | ITEM096 | Philip | sphilip | FY2026: 31975.52
|  | E0403_01677 | ESR APS Magnets - Magnet Measurement Procurements - TR Effort - Labor | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.IRA | 2025-08-19 | 2026-03-04 | driga | sphilip | 18913.69 |  | PPkg.K | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | NC_MAG |  | S.P543 | APP00882 | LLP042 | ITEM114 | ITEM096 | Philip | sphilip | FY2025: 4331.38; FY2026: 14582.31
|  | E0403_01677 | ESR APS Magnets - Magnet Measurement Procurements - TR Effort - Labor | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.IRA | 2025-08-19 | 2026-03-04 | driga | sphilip | 17493.17 |  | PPkg.K | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | NC_MAG |  | S.P543 | APP00882 | LLP042 | ITEM114 | ITEM096 | Philip | sphilip | FY2025: 4006.07; FY2026: 13487.1
|  | E0403_01679 | ESR APS Magnets - Magnet Measurement Procurements - RCV - Batch 2 | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.IRA | 2026-03-04 | 2026-03-04 | driga | sphilip | 215142.08 |  | PPkg.K | Nonlabor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | NC_MAG | RCV | S.P543 | APP00882 | LLP042 | ITEM114 | ITEM096 | Philip | sphilip | FY2026: 215142.08
|  | E0403_01679 | ESR APS Magnets - Magnet Measurement Procurements - RCV - Batch 2 | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.IRA | 2026-03-04 | 2026-03-04 | driga | sphilip | 348228.69 |  | PPkg.K | Nonlabor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | NC_MAG | RCV | S.P543 | APP00882 | LLP042 | ITEM114 | ITEM096 | Philip | sphilip | FY2026: 348228.69
APS Quad Magnet Measurement & Stand | Contract Award | E0403_01676 | ESR APS Magnets - Magnet Measurement Procurements - OBL - Obligation Activity - Batch 2 | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.IRA | 2025-08-18 | 2025-08-18 | driga | sphilip | 0.01 |  | PPkg.K | Nonlabor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | NC_MAG | OBL | S.P543 | APP00882 | LLP042 | ITEM114 | ITEM096 | Philip |  | FY2025: 0.01
|  | E0403_01676 | ESR APS Magnets - Magnet Measurement Procurements - OBL - Obligation Activity - Batch 2 | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.IRA | 2025-08-18 | 2025-08-18 | driga | sphilip | 348228.69 |  | PPkg.K | Nonlabor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | NC_MAG | OBL | S.P543 | APP00882 | LLP042 | ITEM114 | ITEM096 | Philip |  | FY2025: 348228.69
|  | E0403_01676 | ESR APS Magnets - Magnet Measurement Procurements - OBL - Obligation Activity - Batch 2 | 6.04.03.01.01.03 | ESR Magnet APS Quad Test | DOE.IRA | 2025-08-18 | 2025-08-18 | driga | sphilip | 215142.08 |  | PPkg.K | Nonlabor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | NC_MAG | OBL | S.P543 | APP00882 | LLP042 | ITEM114 | ITEM096 | Philip |  | FY2025: 215142.08
|  | E0403_04420 | ESR APS Magnets - Production Quads Group 2 - QTY.63 - Ship Refurbished Quadrupole Magnets to BNL | 6.04.03.01.01.04 | ESR Magnet APS Quad & Sextupole Shipment | DOE.DOE | 2026-01-15 | 2026-01-15 | driga | sphilip | 16451.32 |  | PPkg.K | Nonlabor | TEC | CD3B.SCOPE | JLAB | Construction.Ship | NC_MAG |  | S.P.541 | APP00880 | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2026: 16451.32
|  | E0403_04460 | ESR APS Magnets - Production Quads Group 3 - QTY.62 - Ship Refurbished Quadrupole Magnets to BNL | 6.04.03.01.01.04 | ESR Magnet APS Quad & Sextupole Shipment | DOE.DOE | 2026-09-24 | 2026-09-24 | driga | sphilip | 16190.18 |  | PPkg.K | Nonlabor | TEC | CD3B.SCOPE | JLAB | Construction.Ship | NC_MAG |  | S.P.541 | APP00880 | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2026: 16190.18
|  | E0403_04400 | ESR APS Magnets - Production Quads Group 2 - QTY.63 - Prepare to Ship Refurbished Quadrupole Magnets to BNL | 6.04.03.01.01.04 | ESR Magnet APS Quad & Sextupole Shipment | DOE.DOE | 2025-11-25 | 2026-01-14 | driga | sphilip | 3632.19 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Ship | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2026: 3632.19
|  | E0403_04400 | ESR APS Magnets - Production Quads Group 2 - QTY.63 - Prepare to Ship Refurbished Quadrupole Magnets to BNL | 6.04.03.01.01.04 | ESR Magnet APS Quad & Sextupole Shipment | DOE.DOE | 2025-11-25 | 2026-01-14 | driga | sphilip | 2386.11 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Ship | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2026: 2386.11
|  | E0403_04500 | ESR APS Magnets - Production Quads Group 4 - QTY.62 - Ship Refurbished Quadrupole Magnets to BNL | 6.04.03.01.01.04 | ESR Magnet APS Quad & Sextupole Shipment | DOE.DOE | 2027-01-11 | 2027-01-11 | driga | sphilip | 16190.18 |  | PPkg.K | Nonlabor | TEC | CD3B.SCOPE | JLAB | Construction.Ship | NC_MAG |  | S.P.541 | APP00880 | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2027: 16190.18
|  | E0403_04440 | ESR APS Magnets - Production Quads Group 3 - QTY.62 - Prepare to Ship Refurbished Quadrupole Magnets to BNL | 6.04.03.01.01.04 | ESR Magnet APS Quad & Sextupole Shipment | DOE.DOE | 2026-08-14 | 2026-09-23 | driga | sphilip | 3577.16 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Ship | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2026: 3577.16
|  | E0403_04440 | ESR APS Magnets - Production Quads Group 3 - QTY.62 - Prepare to Ship Refurbished Quadrupole Magnets to BNL | 6.04.03.01.01.04 | ESR Magnet APS Quad & Sextupole Shipment | DOE.DOE | 2026-08-14 | 2026-09-23 | driga | sphilip | 2349.96 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Ship | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2026: 2349.96
|  | E0403_04540 | ESR APS Magnets - Production Quads Group 5 - QTY.62 - Ship Refurbished Quadrupole Magnets to BNL | 6.04.03.01.01.04 | ESR Magnet APS Quad & Sextupole Shipment | DOE.DOE | 2027-04-30 | 2027-04-30 | driga | sphilip | 16190.18 |  | PPkg.K | Nonlabor | TEC | CD3B.SCOPE | JLAB | Construction.Ship | NC_MAG |  | S.P.541 | APP00880 | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2027: 16190.18
|  | E0403_04480 | ESR APS Magnets - Production Quads Group 4 - QTY.62 - Prepare to Ship Refurbished Quadrupole Magnets to BNL | 6.04.03.01.01.04 | ESR Magnet APS Quad & Sextupole Shipment | DOE.DOE | 2026-11-19 | 2027-01-08 | driga | sphilip | 3684.48 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Ship | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2027: 3684.48
|  | E0403_04480 | ESR APS Magnets - Production Quads Group 4 - QTY.62 - Prepare to Ship Refurbished Quadrupole Magnets to BNL | 6.04.03.01.01.04 | ESR Magnet APS Quad & Sextupole Shipment | DOE.DOE | 2026-11-19 | 2027-01-08 | driga | sphilip | 2420.46 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Ship | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2027: 2420.46
|  | E0403_04580 | ESR APS Magnets - Production Quads Group 6 - QTY.62 - Ship Refurbished Quadrupole Magnets to BNL | 6.04.03.01.01.04 | ESR Magnet APS Quad & Sextupole Shipment | DOE.DOE | 2027-08-23 | 2027-08-23 | driga | sphilip | 16190.18 |  | PPkg.K | Nonlabor | TEC | CD3B.SCOPE | JLAB | Construction.Ship | NC_MAG |  | S.P.541 | APP00880 | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2027: 16190.18
|  | E0403_04520 | ESR APS Magnets - Production Quads Group 5 - QTY.62 - Prepare to Ship Refurbished Quadrupole Magnets to BNL | 6.04.03.01.01.04 | ESR Magnet APS Quad & Sextupole Shipment | DOE.DOE | 2027-03-23 | 2027-04-29 | driga | sphilip | 3684.48 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Ship | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2027: 3684.48
|  | E0403_04520 | ESR APS Magnets - Production Quads Group 5 - QTY.62 - Prepare to Ship Refurbished Quadrupole Magnets to BNL | 6.04.03.01.01.04 | ESR Magnet APS Quad & Sextupole Shipment | DOE.DOE | 2027-03-23 | 2027-04-29 | driga | sphilip | 2420.46 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Ship | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2027: 2420.46
|  | E0403_04560 | ESR APS Magnets - Production Quads Group 6 - QTY.62 - Prepare to Ship Refurbished Quadrupole Magnets to BNL | 6.04.03.01.01.04 | ESR Magnet APS Quad & Sextupole Shipment | DOE.DOE | 2027-07-14 | 2027-08-20 | driga | sphilip | 3684.48 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Ship | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2027: 3684.48
|  | E0403_04560 | ESR APS Magnets - Production Quads Group 6 - QTY.62 - Prepare to Ship Refurbished Quadrupole Magnets to BNL | 6.04.03.01.01.04 | ESR Magnet APS Quad & Sextupole Shipment | DOE.DOE | 2027-07-14 | 2027-08-20 | driga | sphilip | 2420.46 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Ship | NC_MAG |  | S.P.541 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2027: 2420.46
|  | E0403_04660 | ESR APS Magnets - Production Quads Group 2 - QTY.36 - Ship Rebuilt Quadrupole Magnets to BNL | 6.04.03.01.01.04 | ESR Magnet APS Quad & Sextupole Shipment | DOE.DOE | 2026-03-31 | 2026-03-31 | driga | sphilip | 13201.05 |  | PPkg.K | Nonlabor | TEC | CD3B.SCOPE | JLAB | Construction.Ship | NC_MAG |  | S.P542 | APP00881 | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2026: 13201.05
|  | E0403_04700 | ESR APS Magnets - Production Quads Group 3 - QTY.36 - Ship Rebuilt Quadrupole Magnets to BNL | 6.04.03.01.01.04 | ESR Magnet APS Quad & Sextupole Shipment | DOE.DOE | 2027-10-14 | 2027-10-14 | driga | sphilip | 13201.05 |  | PPkg.K | Nonlabor | TEC | CD3B.SCOPE | JLAB | Construction.Ship | NC_MAG |  | S.P542 | APP00881 | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2028: 13201.05
|  | E0403_04640 | ESR APS Magnets - Production Quads Group 2 - QTY.36 - Prepare to Ship Rebuilt Quadrupole Magnets to BNL | 6.04.03.01.01.04 | ESR Magnet APS Quad & Sextupole Shipment | DOE.DOE | 2026-03-09 | 2026-03-30 | driga | sphilip | 2091.26 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Ship | NC_MAG |  | S.P542 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2026: 2091.26
|  | E0403_04640 | ESR APS Magnets - Production Quads Group 2 - QTY.36 - Prepare to Ship Rebuilt Quadrupole Magnets to BNL | 6.04.03.01.01.04 | ESR Magnet APS Quad & Sextupole Shipment | DOE.DOE | 2026-03-09 | 2026-03-30 | driga | sphilip | 1373.82 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Ship | NC_MAG |  | S.P542 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2026: 1373.82
|  | E0403_04680 | ESR APS Magnets - Production Quads Group 3 - QTY.36 - Prepare to Ship Rebuilt Quadrupole Magnets to BNL | 6.04.03.01.01.04 | ESR Magnet APS Quad & Sextupole Shipment | DOE.DOE | 2027-09-22 | 2027-10-13 | driga | sphilip | 2190.35 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Ship | NC_MAG |  | S.P542 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2027: 958.28; FY2028: 1232.07
|  | E0403_04680 | ESR APS Magnets - Production Quads Group 3 - QTY.36 - Prepare to Ship Rebuilt Quadrupole Magnets to BNL | 6.04.03.01.01.04 | ESR Magnet APS Quad & Sextupole Shipment | DOE.DOE | 2027-09-22 | 2027-10-13 | driga | sphilip | 1438.92 |  | % Comp.C | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Ship | NC_MAG |  | S.P542 |  | LLP034 | ITEM113 | ITEM089 | Philip | sphilip | FY2027: 629.53; FY2028: 809.39
|  | E1005_01660 | Electron Endcap EMCal - PWO Crystals - Vendor Delivery Batch 4 - RCV | 6.10.05.01.01 | Backward EMCal Blocks | DOE.DETL | 2028-05-26 | 2028-05-26 | tlewis | shura | 1338366.12 |  | PPkg.K | Nonlabor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | DET | RCV | D.APP47.D | APP00525 | LLP017 | ITEM115 | ITEM002.B | Bazilevsky | shura | FY2028: 1338366.12
|  | E1005_01680 | Electron Endcap EMCal - PWO Crystals - Test, Final Acceptance | 6.10.05.01.01 | Backward EMCal Blocks | DOE.DOE | 2027-08-11 | 2028-05-26 | tlewis | shura | 7432.26 |  | PPkg.K | Labor | TEC | CD3B.SCOPE | BNL | Construction.Test & Accept | DET |  | D.APP47.D | APP00525 | LLP017 | ITEM115 | ITEM002.B | Bazilevsky | shura | FY2027: 1344.53; FY2028: 6087.73
|  | E1005_01680 | Electron Endcap EMCal - PWO Crystals - Test, Final Acceptance | 6.10.05.01.01 | Backward EMCal Blocks | DOE.DOE | 2027-08-11 | 2028-05-26 | tlewis | shura | 0 |  | PPkg.K | Labor | TEC | CD3B.SCOPE | BNL | Construction.Test & Accept | DET |  | D.APP47.D | APP00525 | LLP017 | ITEM115 | ITEM002.B | Bazilevsky | shura
Backward EMCal PbWO4 Crystals - Option 2 - Batch 3 | Contract Award | E1005_01520 | Electron Endcap EMCal - PWO Crystals Batch 3 - OBL - Obligation Activity | 6.10.05.01.01 | Backward EMCal Blocks | DOE.DET | 2026-10-23 | 2026-10-23 | tlewis | shura | 0.01 |  | % Comp.C | Nonlabor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | DET | OBL | D.APP47.C | APP00525 | LLP017 | ITEM115 | ITEM002.A | Bazilevsky |  | FY2027: 0.01
|  | E1005_01520 | Electron Endcap EMCal - PWO Crystals Batch 3 - OBL - Obligation Activity | 6.10.05.01.01 | Backward EMCal Blocks | DOE.DET | 2026-10-23 | 2026-10-23 | tlewis | shura | 1338366.12 |  | % Comp.C | Nonlabor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | DET | OBL | D.APP47.C | APP00525 | LLP017 | ITEM115 | ITEM002.A | Bazilevsky |  | FY2027: 1338366.12
Backward EMCal PbWO4 Crystals - Option 3 - Batch 4 | Contract Award | E1005_01600 | Electron Endcap EMCal - PWO Crystals Batch 4 - OBL - Obligation Activity | 6.10.05.01.01 | Backward EMCal Blocks | DOE.DOE | 2027-08-11 | 2027-08-11 | tlewis | shura | 0.01 |  | % Comp.C | Nonlabor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | DET | OBL | D.APP47.D | APP00525 | LLP017 | ITEM115 | ITEM002.B | Bazilevsky |  | FY2027: 0.01
|  | E1005_01600 | Electron Endcap EMCal - PWO Crystals Batch 4 - OBL - Obligation Activity | 6.10.05.01.01 | Backward EMCal Blocks | DOE.DOE | 2027-08-11 | 2027-08-11 | tlewis | shura | 1338366.12 |  | % Comp.C | Nonlabor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | DET | OBL | D.APP47.D | APP00525 | LLP017 | ITEM115 | ITEM002.B | Bazilevsky |  | FY2027: 1338366.12
|  | E1005_01540 | Electron Endcap EMCal - PWO Crystals Batch 3 - TR Effort | 6.10.05.01.01 | Backward EMCal Blocks | DOE.DETL | 2026-10-26 | 2027-08-10 | tlewis | shura | 3612.57 |  | PPkg.K | Labor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | DET |  | D.APP47.C | APP00525 | LLP017 | ITEM115 | ITEM002.A | Bazilevsky | shura | FY2027: 3612.57
|  | E1005_01620 | Electron Endcap EMCal - PWO Crystals Batch 4 - TR Effort | 6.10.05.01.01 | Backward EMCal Blocks | DOE.DETL | 2027-08-12 | 2028-05-25 | tlewis | shura | 3716.54 |  | PPkg.K | Labor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | DET |  | D.APP47.D | APP00525 | LLP017 | ITEM115 | ITEM002.B | Bazilevsky | shura | FY2027: 660.3; FY2028: 3056.24
|  | E1005_01580 | Electron Endcap EMCal - PWO Crystals - Vendor Delivery Batch 3 - RCV | 6.10.05.01.01 | Backward EMCal Blocks | DOE.DETL | 2027-08-11 | 2027-08-11 | tlewis | shura | 1338366.12 |  | PPkg.K | Nonlabor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | DET | RCV | D.APP47.C | APP00525 | LLP017 | ITEM115 | ITEM002.A | Bazilevsky | shura | FY2027: 1338366.12
Barrel EMCal Fibers - Option 1 - Batch 2 | Contract Award | E1005_04660 | Barrel EMCal - Scintillation Fibers - Batch 2 - OBL - Obligation Activity | 6.10.05.02.01 | Barrel EMCal Sectors | DOE.DOE | 2026-04-27 | 2026-04-27 | tlewis | shura | 0.01 |  | % Comp.C | Nonlabor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | DET | OBL | A.PP091.B | APP00622 | LLP027 | ITEM116 | ITEM078.A | Bazilevsky |  | FY2026: 0.01
|  | E1005_04660 | Barrel EMCal - Scintillation Fibers - Batch 2 - OBL - Obligation Activity | 6.10.05.02.01 | Barrel EMCal Sectors | DOE.DOE | 2026-04-27 | 2026-04-27 | tlewis | shura | 1611322.71 |  | % Comp.C | Nonlabor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | DET | OBL | A.PP091.B | APP00622 | LLP027 | ITEM116 | ITEM078.A | Bazilevsky |  | FY2026: 1611322.71
|  | E1005_04720 | Barrel EMCal - Scintillation Fibers - RCV | 6.10.05.02.01 | Barrel EMCal Sectors | DOE.DOE | 2027-05-07 | 2027-05-07 | tlewis | shura | 1611322.71 |  | PPkg.K | Nonlabor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | DET | RCV | A.PP091.B | APP00622 | LLP027 | ITEM116 | ITEM078.A | Bazilevsky | shura | FY2027: 1611322.71
|  | E1005_04700 | Barrel EMCal - Scintillation Single Clad Fibers - TR Effort | 6.10.05.02.01 | Barrel EMCal Sectors | DOE.DOE | 2026-04-28 | 2027-05-06 | tlewis | shura | 11870.09 |  | PPkg.K | Labor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | DET |  | A.PP091.B | APP00622 | LLP027 | ITEM116 | ITEM078.A | Bazilevsky | shura | FY2026: 5007.7; FY2027: 6862.4
|  | E1005_04700 | Barrel EMCal - Scintillation Single Clad Fibers - TR Effort | 6.10.05.02.01 | Barrel EMCal Sectors | DOE.DOE | 2026-04-28 | 2027-05-06 | tlewis | shura | 0 |  | PPkg.K | Labor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | DET |  | A.PP091.B | APP00622 | LLP027 | ITEM116 | ITEM078.A | Bazilevsky | shura
Hadron Endcap EMCal Fibers - Option 1 - Batch 2 | Contract Award | E1005_11220 | Hadron Endcap EMCal - Scinillation Fibers - Batch 2 - OBL - Obligation Activity | 6.10.05.03.01 | Forward EMCal Blocks | DOE.DOE | 2025-10-01 | 2025-10-01 | tlewis | shura | 0.01 |  | % Comp.C | Nonlabor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | DET | OBL | S.P175.B | APP00028 | LLP027 | ITEM116 | ITEM077.A | Bazilevsky |  | FY2026: 0.01
|  | E1005_11220 | Hadron Endcap EMCal - Scinillation Fibers - Batch 2 - OBL - Obligation Activity | 6.10.05.03.01 | Forward EMCal Blocks | DOE.DOE | 2025-10-01 | 2025-10-01 | tlewis | shura | 543029.24 |  | % Comp.C | Nonlabor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | DET | OBL | S.P175.B | APP00028 | LLP027 | ITEM116 | ITEM077.A | Bazilevsky |  | FY2026: 543029.24
|  | E1005_11280 | Hadron Endcap EMCal - Scinillation Fibers - RCV | 6.10.05.03.01 | Forward EMCal Blocks | DOE.DOE | 2026-10-14 | 2026-10-14 | tlewis | shura | 543029.24 |  | PPkg.K | Nonlabor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | DET | RCV | S.P175.B | APP00028 | LLP027 | ITEM116 | ITEM077.A | Bazilevsky | shura | FY2027: 543029.24
|  | E1005_11260 | Hadron Endcap EMCal - Scinillation Fibers - TR Effort | 6.10.05.03.01 | Forward EMCal Blocks | DOE.DOE | 2025-10-02 | 2026-10-13 | tlewis | shura | 11647.4 |  | PPkg.K | Labor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | DET |  | S.P175.B | APP00028 | LLP027 | ITEM116 | ITEM077.A | Bazilevsky | shura | FY2026: 11283.42; FY2027: 363.98
|  | E1005_11260 | Hadron Endcap EMCal - Scinillation Fibers - TR Effort | 6.10.05.03.01 | Forward EMCal Blocks | DOE.DOE | 2025-10-02 | 2026-10-13 | tlewis | shura | 0 |  | PPkg.K | Labor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | DET |  | S.P175.B | APP00028 | LLP027 | ITEM116 | ITEM077.A | Bazilevsky | shura
|  | E1006_07460 | LFHCal - 8M Absorber plates steel - RCV | 6.10.06.03 | Forward Hadronic Calorimetry | DOE.DOE | 2026-02-20 | 2026-02-20 | tlewis | keyser | 1088034.32 |  | PPkg.K | Nonlabor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | DET | RCV | S.P442.B | APP00534 | LLP021 | ITEM117 | ITEM005 | Eyser | keyser | FY2026: 1088034.32
|  | E1006_07420 | LFHCal - 8M Absorber plates steel - TR Effort | 6.10.06.03 | Forward Hadronic Calorimetry | DOE.DOE | 2025-11-20 | 2026-02-19 | tlewis | keyser | 495.85 |  | PPkg.K | Labor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | DET |  | S.P442.B | APP00534 | LLP021 | ITEM117 | ITEM005 | Eyser | keyser | FY2026: 495.85
Forward HCal Steel | Contract Award | E1006_07397 | LFHCal - 8M Absorber plates steel - Batch 2 - OBL - Obligation Activity | 6.10.06.03 | Forward Hadronic Calorimetry | DOE.IRA | 2025-11-19 | 2025-11-19 | tlewis | keyser | 0.01 |  | % Comp.C.NA | Nonlabor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | DET | OBL | S.P442.B | APP00534 | LLP021 | ITEM117 | ITEM005 | Eyser |  | FY2026: 0.01
|  | E1006_07397 | LFHCal - 8M Absorber plates steel - Batch 2 - OBL - Obligation Activity | 6.10.06.03 | Forward Hadronic Calorimetry | DOE.IRA | 2025-11-19 | 2025-11-19 | tlewis | keyser | 1088034.32 |  | % Comp.C.NA | Nonlabor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | DET | OBL | S.P442.B | APP00534 | LLP021 | ITEM117 | ITEM005 | Eyser |  | FY2026: 1088034.32
|  | E1007_03180 | Detector Solenoid - Magnet Power Supply - JLAB - TR Effort | 6.10.07 | Detector Magnets | DOE.DOE | 2025-04-01 | 2028-10-16 | ewoolsey | rrajput | 68172.42 |  | PPkg.K | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | DET |  | S.P322 | APP00563 | LLP022 | ITEM118 | ITEM091 | Rajput-Ghoshal | rrajput | FY2025: 9838.52; FY2026: 19134.76; FY2027: 19134.76; FY2028: 19212.23; FY2029: 852.16
|  | E1007_03220 | Detector Solenoid - Magnet Power Supply - RCV | 6.10.07 | Detector Magnets | DOE.DOE | 2028-10-17 | 2028-10-17 | ewoolsey | rrajput | 276449.4 |  | PPkg.K | Nonlabor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | DET | RCV | S.P322 | APP00563 | LLP022 | ITEM118 | ITEM091 | Rajput-Ghoshal | rrajput | FY2029: 276449.4
|  | E1007_03220 | Detector Solenoid - Magnet Power Supply - RCV | 6.10.07 | Detector Magnets | DOE.DOE | 2028-10-17 | 2028-10-17 | ewoolsey | rrajput | 348228.69 |  | PPkg.K | Nonlabor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | DET | RCV | S.P322 | APP00563 | LLP022 | ITEM118 | ITEM091 | Rajput-Ghoshal | rrajput | FY2029: 348228.69
Magnet Power Supply | Contract Award | E1007_03160 | Detector Solenoid - Magnet Power Supply - OBL - Obligation Activity | 6.10.07 | Detector Magnets | DOE.DOE | 2025-03-31 | 2025-03-31 | ewoolsey | rrajput | 0.01 |  | % Comp.C.NA | Nonlabor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | DET | OBL | S.P322 | APP00563 | LLP022 | ITEM118 | ITEM091 | Rajput-Ghoshal |  | FY2025: 0.01
|  | E1007_03160 | Detector Solenoid - Magnet Power Supply - OBL - Obligation Activity | 6.10.07 | Detector Magnets | DOE.DOE | 2025-03-31 | 2025-03-31 | ewoolsey | rrajput | 276449.4 |  | % Comp.C.NA | Nonlabor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | DET | OBL | S.P322 | APP00563 | LLP022 | ITEM118 | ITEM091 | Rajput-Ghoshal |  | FY2025: 276449.4
|  | E1007_03160 | Detector Solenoid - Magnet Power Supply - OBL - Obligation Activity | 6.10.07 | Detector Magnets | DOE.DOE | 2025-03-31 | 2025-03-31 | ewoolsey | rrajput | 348228.69 |  | % Comp.C.NA | Nonlabor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | DET | OBL | S.P322 | APP00563 | LLP022 | ITEM118 | ITEM091 | Rajput-Ghoshal |  | FY2025: 348228.69
|  | E1007_03181 | Detector Solenoid - Magnet Power Supply - BNL - TR Effort | 6.10.07 | Detector Magnets | DOE.DOE | 2025-04-01 | 2028-10-16 | ewoolsey | rrajput | 22904.26 |  | PPkg.K | Labor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | DET |  | S.P322 | APP00563 | LLP022 | ITEM118 | ITEM091 | Rajput-Ghoshal | rrajput | FY2025: 3290.54; FY2026: 6451.54; FY2027: 6451.54; FY2028: 6451.54; FY2029: 259.1
|  | E1007_03182 | Detector Solenoid - Magnet Power Supply - JLAB - TR Effort Travel | 6.10.07 | Detector Magnets | DOE.DOE | 2025-04-01 | 2028-10-16 | ewoolsey | rrajput | 24088.95 |  | PPkg.K | Nonlabor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | DET |  | S.P322 | APP00563 | LLP022 | ITEM118 | ITEM091 | Rajput-Ghoshal | rrajput | FY2025: 3476.47; FY2026: 6761.33; FY2027: 6761.33; FY2028: 6788.7; FY2029: 301.11
|  | E1008_02013 | CERN - VTRX+ Optical Tranceiver Module - RCV | 6.10.08 | Electronics | DOE.DOE | 2026-12-23 | 2026-12-23 | ewoolsey | fbarbosa | 1037502.61 |  | PPkg.K | Nonlabor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | DET | RCV | P.S1033 | APP00840 | LLP038 | ITEM119 | ITEM099 | Barbosa | fbarbosa | FY2027: 1037502.61
|  | E1008_02013 | CERN - VTRX+ Optical Tranceiver Module - RCV | 6.10.08 | Electronics | DOE.DOE | 2026-12-23 | 2026-12-23 | ewoolsey | fbarbosa | 359197.9 |  | PPkg.K | Nonlabor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | DET | RCV | P.S1033 | APP00840 | LLP038 | ITEM119 | ITEM099 | Barbosa | fbarbosa | FY2027: 359197.9
VRTX+ and lpGBT | Contract Award | E1008_02010 | CERN - VTRX+ Optical Tranceiver Module - OBL - Obligation Activity | 6.10.08 | Electronics | DOE.DOE | 2025-10-14 | 2025-10-14 | ewoolsey | fbarbosa | 0.01 |  | % Comp.C.NA | Nonlabor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | DET | OBL | P.S1033 | APP00840 | LLP038 | ITEM119 | ITEM099 | Barbosa |  | FY2026: 0.01
|  | E1008_02010 | CERN - VTRX+ Optical Tranceiver Module - OBL - Obligation Activity | 6.10.08 | Electronics | DOE.DOE | 2025-10-14 | 2025-10-14 | ewoolsey | fbarbosa | 1037502.61 |  | % Comp.C.NA | Nonlabor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | DET | OBL | P.S1033 | APP00840 | LLP038 | ITEM119 | ITEM099 | Barbosa |  | FY2026: 1037502.61
|  | E1008_02010 | CERN - VTRX+ Optical Tranceiver Module - OBL - Obligation Activity | 6.10.08 | Electronics | DOE.DOE | 2025-10-14 | 2025-10-14 | ewoolsey | fbarbosa | 359197.9 |  | % Comp.C.NA | Nonlabor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | DET | OBL | P.S1033 | APP00840 | LLP038 | ITEM119 | ITEM099 | Barbosa |  | FY2026: 359197.9
|  | E1008_02027 | CERN - lpGBT Transceiver ASIC - RCV | 6.10.08 | Electronics | DOE.DOE | 2027-02-10 | 2027-02-10 | ewoolsey | fbarbosa | 71008.63 |  | PPkg.K | Nonlabor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | DET | RCV | P.S1131 |  | LLP038 | ITEM119 | ITEM099 | Barbosa | fbarbosa | FY2027: 71008.63
VRTX+ and lpGBT | Contract Award | E1008_02024 | CERN - lpGBT Transceiver ASIC - OBL - Obligation Activity | 6.10.08 | Electronics | DOE.DOE | 2025-11-20 | 2025-11-20 | ewoolsey | fbarbosa | 0.01 |  | % Comp.C.NA | Nonlabor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | DET | OBL | P.S1131 |  | LLP038 | ITEM119 | ITEM099 | Barbosa |  | FY2026: 0.01
|  | E1008_02024 | CERN - lpGBT Transceiver ASIC - OBL - Obligation Activity | 6.10.08 | Electronics | DOE.DOE | 2025-11-20 | 2025-11-20 | ewoolsey | fbarbosa | 71008.63 |  | % Comp.C.NA | Nonlabor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | DET | OBL | P.S1131 |  | LLP038 | ITEM119 | ITEM099 | Barbosa |  | FY2026: 71008.63
|  | E1008_02011 | CERN - VTRX+ Optical Tranceiver Module - TR Effort | 6.10.08 | Electronics | DOE.DOE | 2025-10-15 | 2026-12-22 | ewoolsey | fbarbosa | 132645.98 |  | PPkg.K | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | DET |  | P.S1033 | APP00840 | LLP038 | ITEM119 | ITEM099 | Barbosa | fbarbosa | FY2026: 106928.9; FY2027: 25717.08
|  | E1008_02025 | CERN - lpGBT Transceiver ASIC - TR Effort | 6.10.08 | Electronics | DOE.DOE | 2025-11-21 | 2027-02-09 | ewoolsey | fbarbosa | 133009.32 |  | PPkg.K | Labor | TEC | CD3B.SCOPE | JLAB | Construction.Fabricate | DET |  | P.S1131 |  | LLP038 | ITEM119 | ITEM099 | Barbosa | fbarbosa | FY2026: 95006.65; FY2027: 38002.66
|  | E1010_08880 | Electron Endcap Structures - EE HCal -TR effort | 6.10.10.02 | Electron Endcap Structures | DOE.DOE | 2025-09-12 | 2026-06-03 | tlewis | rsharma | 14839.18 |  | PPkg.K | Labor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | DET |  | A.PP085 | APP00585 | LLP035 | ITEM120 | ITEM093 | Sharma | rsharma | FY2025: 1071.72; FY2026: 13767.46
Detector Endcap Steel for Structures | Contract Award | E1010_08860 | Electron Endcap Structures - EE HCal and HE HCal - OBL - Obligation Activity | 6.10.10.02 | Electron Endcap Structures | DOE.DOE | 2025-09-11 | 2025-09-11 | tlewis | rsharma | 0.01 |  | % Comp.C | Nonlabor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | DET | OBL | A.PP085 | APP00585 | LLP035 | ITEM120 | ITEM093 | Sharma |  | FY2025: 0.01
|  | E1010_08860 | Electron Endcap Structures - EE HCal and HE HCal - OBL - Obligation Activity | 6.10.10.02 | Electron Endcap Structures | DOE.DOE | 2025-09-11 | 2025-09-11 | tlewis | rsharma | 2955838.88 |  | % Comp.C | Nonlabor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | DET | OBL | A.PP085 | APP00585 | LLP035 | ITEM120 | ITEM093 | Sharma |  | FY2025: 2955838.88
|  | E1010_08940 | Electron Endcap Structures - EE HCal - RCV - Phase 1 | 6.10.10.02 | Electron Endcap Structures | DOE.DOE | 2026-06-04 | 2026-06-04 | tlewis | rsharma | 1343563.13 |  | PPkg.K | Nonlabor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | DET | RCV | A.PP085 | APP00585 | LLP035 | ITEM120 | ITEM093 | Sharma | rsharma | FY2026: 1343563.13
|  | E1010_09440 | Hadron Endcap Structures - HE HCal - RCV - Phase 1 | 6.10.10.03 | Hadron Endcap Structures | DOE.DOE | 2026-06-04 | 2026-06-04 | tlewis | rsharma | 1612275.75 |  | PPkg.K | Nonlabor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | DET | RCV | A.PP085 | APP00585 | LLP035 | ITEM120 | ITEM093 | Sharma | rsharma | FY2026: 1612275.75
|  | E1010_09410 | Hadron Endcap Structures - HE HCal - TR Effort | 6.10.10.03 | Hadron Endcap Structures | DOE.DOE | 2025-09-12 | 2026-06-03 | tlewis | rsharma | 14839.18 |  | PPkg.K | Labor | TEC | CD3B.SCOPE | BNL | Construction.Fabricate | DET |  | A.PP085 | APP00585 | LLP035 | ITEM120 | ITEM093 | Sharma | rsharma | FY2025: 1071.72; FY2026: 13767.46

## VLKUP (hidden)
Code Value | Description | Code Value | Description | LLP Category | Description | LLP Item | Description |  | BNL_Estimator | Description | BNL_PMC Rep | Description | BNL_CAM | Description | BNL_WPM | Description | LLP Item Detail | Description
6 | EIC | Code Value | Description | Code Value | Description | Code Value | Description | Color | mpaniccia | M. Paniccia | Code Value | Description | Code Value | Description | Code Value | Description | Code Value | Description
6.01 | Project Management | (New) | (New Code Value) | LLP000 | Top Level Milestones | ITEM001 | RCS Vacuum Chambers and Bellows | 0000FF | Jaroslav | A. Jaroslav | ebockhold | Erik Bockholdt | Savransky | D. Savransky | mpaniccia | M. Paniccia | ITEM001 | RCS Vacuum Chambers and Bellows
6.01.01 | Project Management | A | Acquisition Plan (APP) =>$2M<$5M | LLP001 | RCS Quad Magnets | ITEM002 | Backward EMCal PbWO4 Crystals | 0000FF | keyser | O. Eyser | driga | Dimitra Riga | Sereno | N. Sereno | nsereno | N. Sereno | ITEM002 | Backward EMCal PbWO4 Crystals
6.01.01.01 | Project Management - BNL | A.PP001 | IR Vacuum - Central Detector Chamber | LLP002 | RCS Sextupole Magnets | ITEM002.A | Backward EMCal PbWO4 Crystals - Option 2 - Batch 3 | 0000FF | Gaskell | D. Gaskell | jdavis | Drew Davis | Jaroslav | A. Jaroslav | fbock | F. Bock | ITEM002.A | Backward EMCal PbWO4 Crystals - Option 2 - Batch 3
6.01.01.01.01 | Project Management - BNL | A.PP001.A | IR Vacuum - Central Detector Chamber - First Article | LLP003 | RCS Dipole | ITEM002.B | Backward EMCal PbWO4 Crystals - Option 3 - Batch 4 | 0000FF | shura | A. Bazilevsky | egolnar | Elliott Golnar | Bazilevsky | A. Bazilevsky | sphilip | S. Philip - JLab | ITEM002.B | Backward EMCal PbWO4 Crystals - Option 3 - Batch 4
6.01.01.01.02 | Committees | A.PP001.B | IR Vacuum - Central Detector Chamber - Production | LLP004 | RCS Vacuum Chambers and Bellows | ITEM003 | Forward HCal Scintillating Tiles | 0000FF | ullrich | T. Ullrich | pkessler | Phillip Kessler | Fast | J. Fast | huque | N. Huque | ITEM003 | Forward HCal Scintillating Tiles
6.01.01.01.03 | Technical Integration | A.PP002 | PS CAEN - Corrector, Quads & Dipole PS | LLP005 | 400 MeV Injector RF System | ITEM004 | Forward HCal SiPMs | 0000FF | ldesanto | L. DeSanto | kkrug | Kelly Krug | Schaefer | C. Schaefer | jharris | J. Harris | ITEM004 | Forward HCal SiPMs
6.01.01.02 | Project Management - TJ | A.PP003 | 197 MHz FPC Couplers | LLP006 | Actively Cooled Beam Screen (ACBS) | ITEM005 | Forward HCal Steel | 0000FF | dchan | D. Chan | glayden | Gerald Layden | Rainey | W. Rainey | pkessler | P. Kessler | ITEM005 | Forward HCal Steel
6.01.01.02.01 | Project Management - TJ | A.PP004 | RCS Vacuum Pumps | LLP007 | RF Bellows Upgrade | ITEM006 | MPGD Trackers | 0000FF | Adam | J. Adam | tlewis | Tyler Lewis | Kessler | P. Kessler | Jaroslav | A. Jaroslav - JLab | ITEM006 | MPGD Trackers
6.01.01.02.02 | Systems Engineering - TJ | A.PP005 | Main Dipole / Arc Quads / Arc Sext | LLP008 | aC Carbon Coating System (ACCS) | ITEM007 | RF 591 FA Procurements <$25k | 0000FF | jml | J. Landgraf | lloewus | Lisa Loewus | Conway | Z. Conway | keyser | O. Eyser | ITEM007 | RF 591 FA Procurements <$25k
6.01.02 | Environmental Safety and Health | A.PP006 | Silicon Trackers | LLP009 | Control Valves | ITEM007.A | Helium Assembly/Welding Tooling | 0000FF | tallerico | T. Tallerica | apatil | Amol Patil | Eyser | O. Eyser | Gaskell | D. Gaskell - JLab | ITEM007.A | Helium Assembly/Welding Tooling
6.01.02.01 | ESH - BNL | A.PP007 | Backward Hadronic Calorimetry | LLP010 | HSR BPM Cryo Cables | ITEM007.B | Cavity/Helium Vessel Handling Tooling | 0000FF | michalsk | T. Michalski | jtolle | Tradd Tolle | Cheng | G. Cheng | shura | A. Bazilevsky | ITEM007.B | Cavity/Helium Vessel Handling Tooling
6.01.02.02 | ESH - TJ | A.PP007.A | Backward Hadronic Calorimetry - Phase A | LLP011 | HSR BPM Cryo Buttons | ITEM007.C | Misc. Cavity Processing Tooling | 0000FF | Yang | S. Yang | Davis | Drew Davis | Bhandari | B. Bhandari | ullrich | T. Ullrich | ITEM007.C | Misc. Cavity Processing Tooling
6.01.03 | Project and Mission Support | A.PP007.B | Backward Hadronic Calorimetry - Phase B | LLP012 | Backward EMCal PbWO4 Crystals (Possible In-Kind) | ITEM007.D | FPC Installation Tool | 0000FF | baggett | K. Baggett | ewoolsey | Everett Woolsey | Gallagher | B. Gallagher | ldesanto | L. DeSanto | ITEM007.D | FPC Installation Tool
6.01.03.01 | Project and Mission Support - BNL | A.PP008 | Detector R&D - Purchase 2 | LLP013 | Superconducting Strand | ITEM007.E | End Can Support (return) Tooling | 0000FF | abbot | D. Abbot | nzandi | Nick Zandi | Fedotov | A. Fedotov | dchan | D. Chan | ITEM007.E | End Can Support (return) Tooling
6.01.03.01.01 | Project Support Management - BNL | A.PP010 | EMCal PbW04 Crystals | LLP014 | 591 MHz 1-Cell FA Cryomodule | ITEM007.F | End Can Support (Supply) Tooling | 0000FF | yzhang | Y. Zhang | rnavarrol | Rodolfo Navarro Lozada | Benson | S. Benson | Adam | J. Adam - check if in use | ITEM007.F | End Can Support (Supply) Tooling
6.01.03.01.02 | Business Operations - BNL | A.PP011 | Construction Manager as Advisor (CMa) Services | LLP015 | Satellite Plant IR10 | ITEM007.G | Misc. Rail Support Tooling | 0000FF | fmicolon | F. Micolon | mahmed | Maqsood Ahmed | Satogata | T. Satogata | jml | J. Landgraf | ITEM007.G | Misc. Rail Support Tooling
6.01.03.01.03 | Project Controls - BNL | A.PP011.A | Pre-Construction Phase | LLP016 | PID Silicon Photomultipliers | ITEM007.H | Alignment fixtures | 0000FF | wittmer | W. Wittmer | BNL2 | BNL TBD | Wittmer | W. Wittmer | tallerico | T. Tallerico | ITEM007.H | Alignment fixtures
6.01.03.01.04 | Office Management - BNL | A.PP011.B | Construction Phase | LLP017 | PbWO4 Crystals | ITEM007.I | Tuner | 0000FF | drees | A. Drees | ncampbell | Nathan Campbell | Landgraf | J. Landgraf | michalsk | T. Michalski - JLab | ITEM007.I | Tuner
6.01.03.01.05 | Procurement - BNL | A.PP012 | RCS-PSC/PSI/REG BTPs | LLP018 | EMCal SiPMs | ITEM007.J | SpaceFrame Assembly Tooling | 0000FF | rsharma | R. Sharma | etumibay | Elise Tumibay | Wilson | K. Wilson | Yang | S. Yang | ITEM007.J | SpaceFrame Assembly Tooling
6.01.03.01.06 | Information Technology - BNL | A.PP013 | B1pF Production - Coil Assembly (not used) | LLP019 | Backward HCal | ITEM007.K | Vacuum Vessel support Tooling | 0000FF | rsrinivas | R. Srinivasan | bsmith | Brian Smith | Xiao | B. Xiao | baggett | K. Baggett - JLab | ITEM007.K | Vacuum Vessel support Tooling
6.01.03.01.07 | Human Resources - BNL | A.PP014 | Substation Installation Contract | LLP020 | HCal SiPMs | ITEM007.L | Misc. Cryostat Assembly Tooling | 0000FF | Rossi | P. Rossi |  |  | Blednykh | A. Blednykh | abbot | D. Abbot | ITEM007.L | Misc. Cryostat Assembly Tooling
6.01.03.01.08 | Document Control | A.PP015 | Corrector & Injection Bump Supplies | LLP021 | Forward HCal Steel | ITEM007.M | Test Cave U-Tubes | 0000FF | cramirezl | C. Ramirez Lockward |  |  | Rathmann | F. Rathmann | aferguson | A. Ferguson | ITEM007.M | Test Cave U-Tubes
6.01.03.01.09 | Risk Management - BNL | A.PP016 | Q2pF - Coil Assembly (not used) | LLP022 | Detector Solenoid Magnet | ITEM007.N | Misc. Assembly/Test/Shipping Tooling | 0000FF | dalesio | B. Dalesio |  |  | Aschenauer | E. Aschenauer | fedotov | A. Fedotov | ITEM007.N | Misc. Assembly/Test/Shipping Tooling
6.01.03.02 | Project and Mission Support - TJ | A.PP017 | Q1ApF - Coil Assembly (not used) | LLP023 | Unit Substation Transformers for Buildings | ITEM008 | Detector Magnets | 0000FF | blednykh | A. Blednykh |  |  | Anerella | M. Anerella | schaefer | C. Schaefer | ITEM008 | Detector Magnets
6.01.03.02.01 | Admin Support - TJ | A.PP018 | Q1BpF - Coil Assembly (not used) | LLP024 | Basic Procurement <$25k | ITEM009 | Unit Substation Transformers for Buildings - LLP | 0000FF | MIllerT | T. Miller |  |  | Mahler | G. Mahler | yzhang | Y. Zhang - JLab | ITEM009 | Unit Substation Transformers for Buildings - LLP
6.01.03.02.02 | Project Controls - TJ | A.PP019 | 69kV /20 MVA Transformer x 2 | LLP025 | Travel | ITEM010 | First Article Magnet Vendor | 0000FF | michnoff | R. Michnoff |  |  | Micolon | F. Micolon | fmicolon | F. Micolon | ITEM010 | First Article Magnet Vendor
6.01.03.02.03 | Procurement Support - TJ | A.PP020 | HV DC Gun PS 600 kV | LLP026 | ESR Vacuum System | ITEM011 | Production Magnets and Material Vendor | 0000FF | weiss | D. Weiss |  |  | Xu | W. Xu | wittmer | W. Wittmer - check if in use | ITEM011 | Production Magnets and Material Vendor
6.01.03.02.04 | Risk Management - TJ | A.PP021 | RCS-SR H,V Corrector | LLP027 | Scintillating Fibers | ITEM012 | RCS Quad - First Article | 0000FF | stiegler | L. Stiegler |  |  | Hetzel | C. Hetzel | drees | A. Drees | ITEM012 | RCS Quad - First Article
6.01.04 | Quality Assurance | A.PP022 | RCS-SR Cables | LLP028 | ESR Quad Magnets (No longer LLP) | ITEM013 | RCS Sextupole - First Article | 0000FF | porretto | C. Porretto |  |  | Sandberg | J. Sandberg | mthelen | M. Thelen | ITEM013 | RCS Sextupole - First Article
6.01.04.01 | Quality Assurance - BNL | A.PP023 | CRAB 2 Power Transmitter | LLP029 | Satellite Plant IR06 | ITEM014 | Satellite Plant IR10 | 0000FF | mahler | G. Mahler |  |  | Nehring | T. Nehring | rsharma | R. Sharma | ITEM014 | Satellite Plant IR10
6.01.04.02 | Quality Assurance - TJ | A.PP023.A | First Article - RF-CRAB-2-PWR | LLP030 | 197 MHz Crab FA Cryomodule | ITEM015 | 400 MeV Injector RF System | 0000FF | nehring | T. Nehring |  |  | Blaskiewicz | M. Blaskiewicz | rsrinivas | R. Srinivasan | ITEM015 | 400 MeV Injector RF System
6.02 | Accelerator Development and R&D | A.PP023.B | Production - RF-CRAB-2-PWR | LLP031 | Overhead 13.8kV & Switching | ITEM016 | First Article Cavities (591 1-Cell 1st Article) | 0000FF | hammons | L. Hammons |  |  | Liu | C. Liu | Rossi | P. Rossi - check if in use | ITEM016 | First Article Cavities (591 1-Cell 1st Article)
6.02.01 | Accelerator Development and R&D Management | A.PP024 | HR Machine Protection Beam Abort Kicker Electrical Components | LLP032 | APS Quad Magnets | ITEM017 | First Article Beamline Components (591 1-Cell 1st Article) | 0000FF | skaritka | J. Skaritka |  |  | Hammons | L. Hammons | cramirezl | C. Ramirez Lockward | ITEM017 | First Article Beamline Components (591 1-Cell 1st Article)
6.02.01.01 | Accelerator Development and R&D Management - BNL | A.PP025 | Vacuum Fabrication Facility Construction | LLP033 | Barrel Detector Structures | ITEM018 | First Article Beamline Gate Valves (591 1-Cell 1st Article) | 0000FF | jpjamilk | J. Jamilkowski |  |  | Gaskell | D. Gaskell | dalesio | B. Dalesio | ITEM018 | First Article Beamline Gate Valves (591 1-Cell 1st Article)
6.02.01.01.01 | Accelerator Development Management - BNL | A.PP026 | HR SS Mod Vacuum - valves and pumps - Vendor Fabrication | LLP034 | APS Quad Refurbishment | ITEM019 | First Article End Cans (591 1-Cell 1st Article) | 0000FF | TBD | To Be Determined |  |  | Folz | C. Folz | blednykh | A. Blednykh | ITEM019 | First Article End Cans (591 1-Cell 1st Article)
6.02.01.01.02 | R&D Management - BNL | A.PP029 | Detector Silicon Photomultipliers | LLP035 | Detector Endcap Structures | ITEM020 | First Article Vacuum Vessel (591 1-Cell 1st Article) | 0000FF | Fallier | M. Fallier - retired |  |  | Hatton | D. Hatton | MIllerT | T. Miller - check if in use | ITEM020 | First Article Vacuum Vessel (591 1-Cell 1st Article)
6.02.01.02 | Accelerator Development and R&D Management - TJ | A.PP030 | Quads and Sextupoles-PDU+DCCT Chassis+PSC/PSI/REG BTPs | LLP036 | Hadron Endcap Structures | ITEM021 | First Article Misc. Parts (591 1-Cell 1st Article) | 0000FF | elke | E. Aschenauer |  |  | Wang | E.D. Wang | michnoff | R. Michnoff | ITEM021 | First Article Misc. Parts (591 1-Cell 1st Article)
6.02.02 | Accelerator Physics and Design | A.PP031 | IR Warm Magnets | LLP037 | ESR Dipole Magnets | ITEM022 | Magnet Measurement Stand (RCS-Dipoles) | 0000FF | wfischer | W. Fischer |  |  | Zaltsman | A. Zaltsman | weiss | D. Weiss | ITEM022 | Magnet Measurement Stand (RCS-Dipoles)
6.02.02.01 | Accelerator Design | A.PP032 | Main House Construction - PreFab Metal Building, Ductbank and Civil Work | LLP038 | Detector Electronics | ITEM023 | HSR Vacuum Beam Screen Profile Material | 0000FF | hwitte | H. Witte |  |  | Huang | H. Huang | stiegler | L. Stiegler | ITEM023 | HSR Vacuum Beam Screen Profile Material
6.02.02.02 | Beam Dynamics | A.PP033 | RCS Vacuum Chambers and Bellows | LLP039 | RCS BPM Buttons | ITEM024 | Electron Endcap HCal Cradles | 0000FF | ksmith | K. Smith |  |  | Skaritka | J. Skaritka | porretto | C. Porretto | ITEM024 | Electron Endcap HCal Cradles
6.02.02.03 | Beam Measurement & Control Codes | A.PP034 | CRAB 1 Power Transmitter | LLP040 | 2K Distribution & 4K HSR Connection | ITEM025 | Electron Endcap HCal SiPMs | 0000FF | brownk | K. Brown |  |  | Lavelle | C. Lavelle | mahler | G. Mahler | ITEM025 | Electron Endcap HCal SiPMs
6.02.03 | Accelerator Systems R&D | A.PP034.A | First Article - RF-CRAB-1-PWR | LLP041 | 2K Cryostat/Valve Box | ITEM026 | Electron Endcap HCal Return Flux Steel | 0000FF | Tsai | O. Tsai |  |  | Lambiase | R. Lambiase | nehring | T. Nehring | ITEM026 | Electron Endcap HCal Return Flux Steel
6.02.03.01 | Polarized Electron Source R&D | A.PP034.B | Production - RF-CRAB-1-PWR | LLP042 | ESR Magnet Measurement | ITEM027 | Barrel HCal SiPMs | 0000FF | mac | G. McIntyre - retired |  |  | McIntyre | G. McIntyre | hammons | L. Hammons | ITEM027 | Barrel HCal SiPMs
6.02.03.02 | IR Design and Magnet Prototyping | A.PP035 | HR Injection System Upgrade Pulsed Devices | LLP043 | APS Sextupole Refurbishment | ITEM028 | Shipping Support (591 1-Cell 1st Art) | 0000FF | Babzien | M. Babzien |  |  | Minty | M. Minty | skaritka | J. Skaritka | ITEM028 | Shipping Support (591 1-Cell 1st Art)
6.02.03.02.01 | IR Magnet Design and Layout | A.PP036 | 400 MeV Linac (De Chirp RF Cavity) |  |  | ITEM029 | First Article Helium Vessel (591 1-Cell 1st Art) | 0000FF | blaskiewicz | M. Blaskiewicz |  |  | Gassner | D. Gassner | jpjamilk | J. Jamilkowski | ITEM029 | First Article Helium Vessel (591 1-Cell 1st Art)
6.02.03.02.02 | IR Magnet Prototyping | A.PP037 | 400 kW & 150 kW Standby Gen & 3-Position Auto Trans Switches |  |  | ITEM030 | Cavity String Support Tooling (591 1-Cell 1st Art) | 0000FF | ccullen | C. Cullen |  |  | Montag | C. Montag | TBD | To Be Determined | ITEM030 | Cavity String Support Tooling (591 1-Cell 1st Art)
6.02.03.02.02.01 | B1pF Prototype | A.PP038 | Network Systems |  |  | ITEM031 | First Article Mag Shields (591 1-Cell 1st Art) | 0000FF | pkfeng | PK Feng |  |  | Petrone | A. Petrone | Fallier | M. Fallier - retired | ITEM031 | First Article Mag Shields (591 1-Cell 1st Art)
6.02.03.02.02.02 | Q1ABpF Prototype | A.PP039 | Collared Dipoles |  |  | ITEM032 | First Article Thermal Shield (591 1-Cell 1st Art) | 0000FF | cfolz | C. Folz |  |  | Ranjbar | V. Ranjbar | elke | E. Aschenauer | ITEM032 | First Article Thermal Shield (591 1-Cell 1st Art)
6.02.03.02.02.03 | Collared Magnet Wind/Cure Tests | A.PP039.A |  |  |  | ITEM033 | First Article Spaceframe with Thermal Shield Assembly (591 1-Cell 1st Art) | 0000FF | Fox | K. Fox |  |  | Ptitsyn | V. Ptitsyn | wfischer | W. Fischer | ITEM033 | First Article Spaceframe with Thermal Shield Assembly (591 1-Cell 1st Art)
6.02.03.03 | Hadron Ring Vacuum Chamber Upgrade | A.PP039.B |  |  |  | ITEM034 | First Article Heat Exchangers (591 1-Cell 1st Art) | 0000FF | gassner | D. Gassner |  |  | Witte | H. Witte | hwitte | H. Witte | ITEM034 | First Article Heat Exchangers (591 1-Cell 1st Art)
6.02.03.04 | Proton & Electron Fast Kickers | A.PP040 | Load Center 480v Switchboards & Panelboards |  |  | ITEM035 | First Article Saddles and Stands (591 1-Cell 1st Art) | 0000FF | dhatton | D. Hatton - retired |  |  | Marneris | I. Marneris | Witte | H. Witte | ITEM035 | First Article Saddles and Stands (591 1-Cell 1st Art)
6.02.03.04.01 | HSR Injection Kicker | A.PP043 | ERL 591-5 Cell RF 50KW PWR: Amplifier |  |  | ITEM036 | First Article Instrumentation (591 1-Cell 1st Art) | 0000FF | Hershcovitc | A. Hershcovitch |  |  | TBD | To Be Determined | ksmith | K. Smith | ITEM036 | First Article Instrumentation (591 1-Cell 1st Art)
6.02.03.04.02 | ESR Injection/Extraction Kicker | A.PP045 | eSR Quad - Vendor I |  |  | ITEM037 | HSR Beam Screens Cooling Tube | 0000FF | huanghai | H. Huang |  |  | Than | R. Than | brownk | K. Brown | ITEM037 | HSR Beam Screens Cooling Tube
6.02.03.05 | Vacuum Systems Development | A.PP046 | eSR Quad - Vendor II |  |  | ITEM038 | HSR Beam Screen Guides | 0000FF | lambiase | R. Lambiase |  |  | Smith | K. Smith | Tsai | O. Tsai - check if in use | ITEM038 | HSR Beam Screen Guides
6.02.03.05.01 | Electron Storage Ring Vacuum Development | A.PP047 | hpDIRC: Photosensors, Multi-Cathode PMTs |  |  | ITEM039 | HSR Beam screens miscellaneous parts | 0000FF | jritter | J. Ritter |  |  | Tsoupas | N. Tsoupas | mac | G. McIntyre - retired | ITEM039 | HSR Beam screens miscellaneous parts
6.02.03.05.02 | Detector Interface Vacuum Development | A.PP048 | Detector Tracking - TPC Material |  |  | ITEM040 | Laser welding equipment for guides and skate brackets | 0000FF | raparia | D. Raparia |  |  | Willeke | F. Willeke | Babzien | M. Babzien - check if in use | ITEM040 | Laser welding equipment for guides and skate brackets
6.02.03.05.03 | HSR Beam Screen and Interconnect Development | A.PP048.A |  |  |  | ITEM041 | HSR Cutting Equipment | 0000FF | Gould | O. Gould |  |  | Wu | Q. Wu | blaskiewicz | M. Blaskiewicz | ITEM041 | HSR Cutting Equipment
6.02.03.06 | Cooling R&D | A.PP048.B |  |  |  | ITEM042 | HSR Part Marking Equipment | 0000FF | lavellec | C. Lavelle |  |  | Zhang | A. Zhang | ccullen | C. Cullen | ITEM042 | HSR Part Marking Equipment
6.02.03.07 | Hadron Polarimetry | A.PP049 | Detector Tracking - Hadron Endcap Low rapidity Si |  |  | ITEM043 | Beam screens fixturing and tooling | 0000FF | mapes | M. Mapes |  |  | Kiselev | A. Kiselev | pkfeng | PK Feng | ITEM043 | Beam screens fixturing and tooling
6.02.03.08 | RCS Corrector Power Supply | A.PP049.A |  |  |  | ITEM044 | Controls | 0000FF | marneris | I. Marneris |  |  | Schmidke | W. Schmidke | cfolz | C. Folz | ITEM044 | Controls
6.03 | Electron Injector | A.PP049.B |  |  |  | ITEM045 | Bake out Equipment | 0000FF | minty | M. Minty |  |  | Tsai | O. Tsai | Fox | K. Fox - check if in use | ITEM045 | Bake out Equipment
6.03.01 | Electron Injector Management | A.PP050 | Detector Tracking - Lepton Endcap Low rapidity Si |  |  | ITEM046 | Pumping Stations | 0000FF | montagc | C. Montag |  |  | Tuozzolo | J. Tuozzolo | gassner | D. Gassner | ITEM046 | Pumping Stations
6.03.01.01 | Electron Injector Management - BNL | A.PP050.A |  |  |  | ITEM047 | aC Carbon Coating System Power Supplies | 0000FF | Morris | J. Morris |  |  | Weiss | D. Weiss | dhatton | D. Hatton - retired | ITEM047 | aC Carbon Coating System Power Supplies
6.03.01.02 | Electron Injector Management - TJ | A.PP050.B |  |  |  | ITEM048 | Vacuum/gas injection equipment | 0000FF | mpalmer | M. Palmer |  |  | Bruno | D. Bruno | Hershcovitc | A. Hershcovitch - check if in use | ITEM048 | Vacuum/gas injection equipment
6.03.02 | Rapid Cycling Synchrotron | A.PP051 | Detector Magnets |  |  | ITEM049 | Superconducting Strand - Direct Wind Magnets | 0000FF | pankows | S. Pankowski |  |  | Golnar | E. Golnar | huanghai | H. Huang | ITEM049 | Superconducting Strand - Direct Wind Magnets
6.03.02.01 | RCS Magnets - BNL | A.PP051.A |  |  |  | ITEM050 | PID Silicon Photomultipliers | 0000FF | Parker | B. Parker |  |  | Jamilkowski | J. Jamilkowski | lambiase | R. Lambiase | ITEM050 | PID Silicon Photomultipliers
6.03.02.01.01 | RCS Quad Magnets | A.PP051.B |  |  |  | ITEM051 | BPM Cables | 0000FF | apetrone | A. Petrone |  |  | Litvinenko | V. Litvinenko | jritter | J. Ritter | ITEM051 | BPM Cables
6.03.02.01.02 | RCS Sextupole Magnets | A.PP052 | RCS Harmonic Injection Kicker Placeholder |  |  | ITEM052 | BPM Buttons | 0000FF | Pogorelsky | Pogorelsky, Igor |  |  | Turbush | H. Turbush | raparia | D. Raparia | ITEM052 | BPM Buttons
6.03.02.01.03 | RCS Corrector Magnets | A.PP053 | Beamline Gate Valves (591 1-Cell Production CMs) |  |  | ITEM053 | Electron Endcap HCal Absorber Structure | 0000FF | vadimp | V. Ptitsyn |  |  | Militscher | F. Militscher | Gould | O. Gould - check if in use | ITEM053 | Electron Endcap HCal Absorber Structure
6.03.02.01.04 | RCS Girders - Design & Procurement | A.PP054 | Beamline Components (591 1-Cell Production CMs) |  |  | ITEM054 | Forward HCal Module Casing Steel | 0000FF | vranjbar | V. Ranjbar |  |  | Morris | J. Morris | lavellec | C. Lavelle | ITEM054 | Forward HCal Module Casing Steel
6.03.02.01.05 | RCS Magnet Measuring Stations | A.PP055 | End Cans (591 1-Cell Production CMs) |  |  | ITEM055 | Superconducting Cable - Production Magnets | 0000FF | reich | J. Reich |  |  | Pinayev | I. Pinayev | mapes | M. Mapes | ITEM055 | Superconducting Cable - Production Magnets
6.03.02.01.06 | RCS Girders - Assembly & Integration | A.PP056 | Beamline Gate Valves (591 5-Cell Production CMs) |  |  | ITEM056 | Backward EMCal PbWO4 Crystals (Possible In-Kind Procurement 1) | 0000FF | scaduto | J. Scaduto |  |  | Reich | J. Reich | marneris | I. Marneris | ITEM056 | Backward EMCal PbWO4 Crystals (Possible In-Kind Procurement 1)
6.03.02.02 | RCS Dipole Magnets | A.PP057 | Beamline Components (591 5-Cell Production CMs) |  |  | ITEM057 | Backward EMCal PbWO4 Crystals (Possible In-Kind Procurement 2) | 0000FF | ythan | R. Than |  |  | Stiegler | L. Stiegler | minty | M. Minty | ITEM057 | Backward EMCal PbWO4 Crystals (Possible In-Kind Procurement 2)
6.03.02.02.01 | RCS Magnet Dipoles Design | A.PP058 | Production Cavities (591 5-Cell Production) |  |  | ITEM058 | Forward EMCal SiPMs | 0000FF | ctheisen | C. Theisen |  |  | Porretto | C. Porretto | montagc | C. Montag | ITEM058 | Forward EMCal SiPMs
6.03.02.02.02 | RCS Magnet Dipoles Fabricate | A.PP060 | Production Cavities (197 MHz Crab Production) |  |  | ITEM059 | Magnet Measurement Facilities and Procurements (RCS-Dipoles) | 0000FF | Trbojevic | D. Trbojevic |  |  | Porretto | C. Porretto | Morris | J. Morris - check if in use | ITEM059 | Magnet Measurement Facilities and Procurements (RCS-Dipoles)
6.03.02.02.03 | RCS Magnet Dipoles Test | A.PP061 | Production Cavities (394 MHz Crab Production) |  |  | ITEM060 | Magnet Measurement Power Supply (RCS-Dipoles) | 0000FF | tsoupas | N. Tsoupas |  |  | Theisen | C. Theisen | mpalmer | M. Palmer | ITEM060 | Magnet Measurement Power Supply (RCS-Dipoles)
6.03.02.02.04 | RCS Magnet Dipoles Ship | A.PP062 | Centeral Timing and Tracking Layer Detector (CTTL) |  |  | ITEM061 | Backward EMCal SiPMs | 0000FF | wange | E. Wang |  |  | Williams | J. Williams | pankows | S. Pankowski | ITEM061 | Backward EMCal SiPMs
6.03.02.03 | RCS Power Supplies | A.PP063 | Backward EMCal PbWO4 Crystals |  |  | ITEM062 | Barrel EMCal SiPMs | 0000FF | willeke | F. Willeke |  |  | Yeck | J. Yeck | Parker | B. Parker - check if in use | ITEM062 | Barrel EMCal SiPMs
6.03.02.04 | RCS Vacuum | A.PP063.A | Backward EMCal PbWO4 Crystals |  |  | ITEM063 | Solenoid Conductor | 0000FF | qiowu | Q. Wu |  |  | Verdu Andre | S. Verdu Andres | apetrone | A. Petrone | ITEM063 | Solenoid Conductor
6.03.02.04.01 | RCS Vacuum Chamber and Bellows | A.PP063.B | Backward EMCal PbWO4 Crystals |  |  | ITEM064 | HSR Laser welding equipment for cooling tube | 0000FF | zaltsman | A. Zaltsman |  |  | Ullrich | T. Ullrich | Pogorelsky | Pogorelsky, Igor - check if in use | ITEM064 | HSR Laser welding equipment for cooling tube
6.03.02.04.02 | RCS Vacuum Valves | A.PP063.C | Backward EMCal PbWO4 Crystals |  |  | ITEM065 | Bellows Helper Spring assembly | 0000FF | arling | A. Zhang -no longer in use |  |  | Alexander | S. Alexander | vadimp | V. Ptitsyn | ITEM065 | Bellows Helper Spring assembly
6.03.02.04.03 | RCS Vacuum Pumps | A.PP063.D | Backward EMCal PbWO4 Crystals |  |  | ITEM066 | RF Fingers | 0000FF | ayk | A. Kiselev |  |  | Dalesio | B. Dalesio | vranjbar | V. Ranjbar | ITEM066 | RF Fingers
6.03.02.04.04 | RCS Vacuum Monitoring and Control | A.PP064 | Backward Hadronic Calorimetry |  |  | ITEM067 | Bellows Components | 0000FF | Lessard | E. Lessard |  |  | Drees | A. Drees | reich | J. Reich | ITEM067 | Bellows Components
6.03.02.04.05 | RCS Vacuum Utilities (Racks) | A.PP065 | Calorimeter Digitizers |  |  | ITEM068 | Solenoids | 0000FF | wschmidke | W. Schmidke |  |  | Krug | K. Krug | scaduto | J. Scaduto | ITEM068 | Solenoids
6.03.02.04.06 | RCS Vacuum Pre-Tunnel Assembly | A.PP066 | Forward HCal Scintillating Tiles |  |  | ITEM069 | Machined Parts | 0000FF | tuozzolo | J. Tuozzolo |  |  | Sharma | R. Sharma | ythan | R. Than | ITEM069 | Machined Parts
6.03.02.05 | RCS Instrumentation | A.PP066.A | Forward HCal Scintillating Tiles |  |  | ITEM070 | Control Valves | 0000FF | chetzel | C. Hetzel |  |  | Rossi | P. Rossi | ctheisen | C. Theisen | ITEM070 | Control Valves
6.03.02.05.01 | RCS Beam Position Monitors | A.PP066.B | Forward HCal Scintillating Tiles |  |  | ITEM071 | Coating Tubes | 0000FF | Robert-Demolaize | G. Robert-Demolaize |  |  | Lari | L. Lari | Trbojevic | D. Trbojevic - check if in use | ITEM071 | Coating Tubes
6.03.02.05.02 | RCS Current and Charge Monitors | A.PP066.C | Forward HCal Scintillating Tiles |  |  | ITEM072 | Travel | 0000FF | Mernick | K. Mernick |  |  | Yang | S. Yang | tsoupas | N. Tsoupas | ITEM072 | Travel
6.03.02.05.03 | RCS Profile and Emittance Monitors | A.PP067 | Detector DAQ |  |  | ITEM073 | First Article Assembly & Test | 0000FF | wxu | W. Xu |  |  | Michalski | T. Michalski | wange | E. Wang | ITEM073 | First Article Assembly & Test
6.03.02.05.04 | RCS Synchrotron Radiation Monitor | A.PP068 | Forward HCal SiPMs |  |  | ITEM074 | First Article Test & Accept - Labor (removed) | 0000FF | jsandberg | J. Sandberg |  |  | Orfin | P. Orfin | willeke | F. Willeke | ITEM074 | First Article Test & Accept - Labor (removed)
6.03.03 | Transfer Lines and Injection/Extraction Elements | A.PP068.A | Forward HCal SiPMs - Initial Award |  |  | ITEM075 | Beam Tube Sleeve - Option 1 | 0000FF | cliu1 | C. Liu |  |  | Wiseman | M. Wiseman | qiowu | Q. Wu | ITEM075 | Beam Tube Sleeve - Option 1
6.03.03.01 | Transfer Lines Magnets | A.PP068.B | Forward HCal SiPMs - Option 1 |  |  | ITEM076 | Vacuum Fabrication Facility Construction | 0000FF | mda | M. Anerella |  |  | Baggett | K. Baggett | zaltsman | A. Zaltsman | ITEM076 | Vacuum Fabrication Facility Construction
6.03.03.02 | Transfer Lines Power Supplies | A.PP068.C | Forward HCal SiPMs - Option 2 |  |  | ITEM077 | Hadron Endcap EMCal Fibers | 0000FF | vl | V. Litvinenko |  |  | Daly | E. Daly | arling | A. Zhang -no longer in use | ITEM077 | Hadron Endcap EMCal Fibers
6.03.03.03 | Transfer Lines Vacuum | A.PP069 | RCS-Dipoles |  |  | ITEM077.A | Hadron Endcap EMCal Fibers - Option 1 - Batch 2 | 0000FF | pinayev | I. Pinayev |  |  | Tallerico | T. Tallerico | denny | P. Denny | ITEM077.A | Hadron Endcap EMCal Fibers - Option 1 - Batch 2
6.03.03.04 | Transfer Lines Instrumentation | A.PP070 | Girder for SHC Beam Transport Magnets |  |  | ITEM078 | Barrel EMCal Fibers | 0000FF | Phillips | D. Phillips |  |  | Narayan | G. Narayan | ayk | A. Kiselev | ITEM078 | Barrel EMCal Fibers
6.03.03.04.01 | TL Beam Position Monitors | A.PP071 | 2K Satellite Plant U-Tibes |  |  | ITEM078.A | Barrel EMCal Fibers - Option 1 - Batch 2 | 0000FF | Inacker | P. Inacker |  |  | Rimmer | R. Rimmer | Lessard | E. Lessard - check if in use | ITEM078.A | Barrel EMCal Fibers - Option 1 - Batch 2
6.03.03.04.02 | TL Current and Charge Monitors | A.PP072 | 2K Cryo Distribution & 4K HSR Connection - IR10 |  |  | ITEM079 | Forward HCal Absorber Plates Tungsten | 0000FF | bruno | D. Bruno |  |  | Matalevich | J. Matalevich | wschmidke | W. Schmidke | ITEM079 | Forward HCal Absorber Plates Tungsten
6.03.03.04.03 | TL Profile and Emittance Monitors | A.PP073 | Electron Endcap HCal - Scintillating Megatiles |  |  | ITEM080 | ESR Quad Magnets | 0000FF | Brutus | J. C. Brutus |  |  | Ent | R. Ent | tuozzolo | J. Tuozzolo | ITEM080 | ESR Quad Magnets
6.03.03.05 | Pulsed Devices | A.PP074 | Forward HCal Absorber Plates Steel |  |  | ITEM081 | Magnet Measurement Facility | 0000FF | egolnar | E. Golnar |  |  | Eng | B. Eng | chetzel | C. Hetzel | ITEM081 | Magnet Measurement Facility
6.03.03.05.01 | RCS Injection - Pulsed Bump | A.PP074.A | Forward HCal Absorber Plates Steel |  |  | ITEM082 | Magnet Measurement Stand | 0000FF | hokula | H.Turbush |  |  | Zihlmann | B. Zihlmann | Robert-Demolaize | G. Robert-Demolaize - check if in use | ITEM082 | Magnet Measurement Stand
6.03.03.05.02 | RCS Injection - Slow Pulsed Septum | A.PP074.B | Forward HCal Absorber Plates Steel |  |  | ITEM083 | Satellite Plant IR02 | 0000FF | militscher | F. Militscher - retired |  |  | Rajput-Ghoshal | R. Rajput Ghoshal | Mernick | K. Mernick - check if in use | ITEM083 | Satellite Plant IR02
6.03.03.05.03 | RCS Extraction - Pulsed Bump | A.PP074.C | Forward HCal Absorber Plates Steel |  |  | ITEM084 | HSR Bellows Weldment | 0000FF | williamsj | J. Williams |  |  | Sourikova | I. Sourikova | wxu | W. Xu | ITEM084 | HSR Bellows Weldment
6.03.03.05.04 | RCS Extraction - Kicker | A.PP075 | Common Platform - PS Controller - Implementation |  |  | ITEM085 | Superconducting Strand - Collared Magnets | 0000FF | Smart | L. Smart |  |  | Jordan | K. Jordan | jsandberg | J. Sandberg | ITEM085 | Superconducting Strand - Collared Magnets
6.03.03.05.05 | RCS Extraction - Pulsed Septum | A.PP076 | Transformers - LLP |  |  | ITEM086 | Satellite Plant IR06 | 0000FF | Altinbas | Z. Altinbas |  |  | Y. Zhang | Y. Zhang | cliu1 | C. Liu | ITEM086 | Satellite Plant IR06
6.03.03.05.06 | ESR Injection & Extraction - Strip-line Kickers | A.PP077 | Overhead 13.8 kV lines - Pad Mount SW's - Fabrication |  |  | ITEM087 | 197MHz Crab 1st Article - Niobium | 0000FF | Curcio | A. Curcio - chck if in use |  |  | Denny | P. Denny | mda | M. Anerella | ITEM087 | 197MHz Crab 1st Article - Niobium
6.03.03.05.07 | ESR Injection - Pulsed Bump | A.PP078 | Overhead 13.8 kV lines - Construction |  |  | ITEM088 | Pad-Mounted Switches | 0000FF | sverdu | S. Verdu Andres |  |  | Barbosa | F. Barbosa | vl | V. Litvinenko | ITEM088 | Pad-Mounted Switches
6.03.03.05.08 | ESR Injection - Slow Pulsed Septum | A.PP079 | HSR Bellows Weldment |  |  | ITEM089 | APS Quad Rebuild & Refurbishment | 0000FF | alexander | S. Alexander |  |  | Abbott | D. Abbott | pinayev | I. Pinayev | ITEM089 | APS Quad Rebuild & Refurbishment
6.03.03.05.09 | ESR Machine Protection - Single Turn Extraction Kicker | A.PP080 | ESR Vacuum Chambers |  |  | ITEM090 | Flux Return Bars | 0000FF | Xiao | B. Xiao |  |  | Furletova | Y. Furletova | Phillips | D. Phillips - check if in use | ITEM090 | Flux Return Bars
6.03.04 | Electron Pre-Injector | A.PP081 | ESR Vacuum Stands |  |  | ITEM091 | Magnet Power Supply | 0000FF | dnassar | D. Nassar |  |  | Nassar | D. Nassar | Inacker | P. Inacker - check if in use | ITEM091 | Magnet Power Supply
6.03.04.01 | 400 MeV Injector | A.PP082 | ESR Vacuum Non-Arc Chambers |  |  | ITEM092 | APS Sextupole Refurbishment & Testing | 0000FF | zconway | Z. Conway |  |  | Srinivasan | R. Srinivasan | bruno | D. Bruno | ITEM092 | APS Sextupole Refurbishment & Testing
6.03.04.01.01 | 400 MeV Injector Power Supplies | A.PP083 | ESR Vacuum Special Straight Section Chambers |  |  | ITEM093 | Detector Endcap Steel for Structures | 0000FF | rrajput | R. Rajput-Ghoshal |  |  | Wahl | B. Wahl | Brutus | J. C. Brutus - check if in use | ITEM093 | Detector Endcap Steel for Structures
6.03.04.01.02 | 400 MeV Injector Vacuum | A.PP084 | ESR Vacuum Remaining Arc Chambers |  |  | ITEM094 | HE HCal Steel for Structures | 0000FF | yfuletova | Y. Furletova |  |  | Harris | J. Harris | egolnar | E. Golnar | ITEM094 | HE HCal Steel for Structures
6.03.04.01.03 | 400 MeV Injector RF Systems | A.PP085 | Detector Endcap Structure Steel |  |  | ITEM095 | APS Quad Rebuilt Parts <DELETE> | 0000FF | kkrug | K. Krug |  |  | Huque | N. Huque | hokula | H.Turbush | ITEM095 | APS Quad Rebuilt Parts <DELETE>
6.03.04.01.04 | 400 MeV Injector Instrumentation | A.PP086 | Detector Infrastructure Hadron Endcap HCal |  |  | ITEM096 | APS Quad Magnet Measurement & Stand | 0000FF | bzihlmann | B. Zihlmann |  |  | Nagaitsev | S. Nagaitsev | militscher | F. Militscher - retired | ITEM096 | APS Quad Magnet Measurement & Stand
6.03.04.01.04.01 | 400 MeV Beam Position Monitors | A.PP087 | Forward HCal - Absorber Plates Tungsten and Module Casing Steel |  |  | ITEM097 | APS Quad Magnet Measurement Facilities <DELETE> | 0000FF | beng | B. Eng |  |  | Philip | S. Philip | williamsj | J. Williams | ITEM097 | APS Quad Magnet Measurement Facilities <DELETE>
6.03.04.01.04.02 | 400 MeV Current and Charge Monitors | A.PP087.A | Forward HCal - Absorber Plates Tungsten and Module Casing Steel - Initial Award |  |  | ITEM098 | ESR Dipole Magnets - D1/D3 Vendor I | 0000FF | fbarbosa | F. Barbosa |  |  | Shell | B. Shell | Smart | L. Smart - check if in use | ITEM098 | ESR Dipole Magnets - D1/D3 Vendor I
6.03.04.01.04.03 | 400 MeV Profile and Emittance Monitors | A.PP087.B | Forward HCal - Absorber Plates Tungsten and Module Casing Steel - Option 1 |  |  | ITEM099 | VRTX+ and lpGBT | 0000FF | edaly | E. Daly |  |  |  |  | Altinbas | Z. Altinbas - check if in use | ITEM099 | VRTX+ and lpGBT
6.03.04.01.04.04 | 400 MeV Beam Loss Monitors | A.PP087.C | Forward HCal - Absorber Plates Tungsten and Module Casing Steel - Option 2 |  |  | ITEM100 | RCS BPM Buttons | 0000FF | porfin | P. Orfin |  |  |  |  | Curcio | A. Curcio - chck if in use | ITEM100 | RCS BPM Buttons
6.03.04.02 | Polarized Electron Source | A.PP087.D | Forward HCal - Absorber Plates Tungsten and Module Casing Steel - Option 3 |  |  | ITEM101 | 2K Cryostat/Valve Box | 0000FF | bgallaghe1 | B. Gallagher |  |  |  |  | sverdu | S. Verdu Andres | ITEM101 | 2K Cryostat/Valve Box
6.03.04.02.01 | Polarized Electron Source Magnets | A.PP087.E | Forward HCal - Absorber Plates Tungsten and Module Casing Steel - Option 4 |  |  | ITEM102 | 2K Cryo Dist & 4K HSR Connections | 0000FF | rrimmer | R. Rimmer |  |  |  |  | alexander | S. Alexander | ITEM102 | 2K Cryo Dist & 4K HSR Connections
6.03.04.02.02 | Polarized Electron Source Vacuum System | A.PP088 | SALSA FEB (Inner Gas Barrel Tracking) |  |  | ITEM103 | ESR Dipole Magnets - D1/D3 Vendor II | 0000FF | mwiseman | M. Wiseman |  |  |  |  | Xiao | B. Xiao - check if in use | ITEM103 | ESR Dipole Magnets - D1/D3 Vendor II
6.03.04.02.03 | Polarized Electron Source Laser | A.PP089 | Detector Computing - DAM Board Hardware - Fabrication |  |  | ITEM104 | ESR Dipole Magnets - D2 Vendor I | 0000FF | Matalevich | J. Matalevich |  |  |  |  | dnassar | D. Nassar | ITEM104 | ESR Dipole Magnets - D2 Vendor I
6.03.04.02.04 | Polarized Electron Source Main Vessel | A.PP090 | Discrete / HGCROC 64-Channel ADC PCB, Supporting PCB, and Hardware (Calorimeter Digitizers) |  |  | ITEM105 | ESR APS Quad Magnet Measurement & Stand | 0000FF | llari | L. Lari |  |  |  |  | zconway | Z. Conway | ITEM105 | ESR APS Quad Magnet Measurement & Stand
6.03.04.02.05 | Polarized Electron Source Cathode Assembly | A.PP091 | Barrel EMCal Scintillation Fibers |  |  | ITEM106 | ESR Dipole Magnets - Magnet Measurement Bench <DELETE> | 0000FF | gnarayan | G. Narayan |  |  |  |  | rrajput | R. Rajput-Ghoshal | ITEM106 | ESR Dipole Magnets - Magnet Measurement Bench <DELETE>
6.03.04.02.06 | Polarized Electron Source Instrumentation | A.PP091.A | Barrel EMCal Scintillation Fibers - Initial Award |  |  | ITEM107 | ESR Dipole Magnets - D2 Vendor II | 0000FF | alung | A. Lung |  |  |  |  | yfuletova | Y. Furletova - JLab | ITEM107 | ESR Dipole Magnets - D2 Vendor II
6.04 | Electron Storage Ring | A.PP091.B | Barrel EMCal Scintillation Fibers - Option 1 |  |  | ITEM108 | ESR Dipole Magnets - D1/D2/D3 Production Iron Material | 0000FF | rent | R. Ent |  |  |  |  | kkrug | K. Krug | ITEM108 | ESR Dipole Magnets - D1/D2/D3 Production Iron Material
6.04.01 | Electron Storage Ring Management | A.PP091.C | Barrel EMCal Scintillation Fibers - Option 2 |  |  | ITEM109 | ESR Magnet Measurement & Measurement Bench | 0000FF | Satogata | T. Satogata |  |  |  |  | frathmann | F. Rathmann | ITEM109 | ESR Magnet Measurement & Measurement Bench
6.04.01.01 | ESR Management - BNL | A.PP091.D | Barrel EMCal Scintillation Fibers - Option 3 |  |  | ITEM110 | Electron Storage Ring (ESR) Dipole Magnets | 0000FF | isourikova | I. Sourikova |  |  |  |  | bzihlmann | B. Zihlmann - JLab | ITEM110 | Electron Storage Ring (ESR) Dipole Magnets
6.04.01.02 | ESR Management - TJ | A.PP092 | ESR Hardware and Seals |  |  | ITEM111 | Advanced Photon Source (APS) Sextupole Magnet Refurbishment, Testing, and Measurement | 0000FF | snagaitsev | S. Nagaitsev |  |  |  |  | beng | B. Eng - JLab | ITEM111 | Advanced Photon Source (APS) Sextupole Magnet Refurbishment, Testing, and Measurement
6.04.02 | Electron Storage Ring Magnets - Dipole, Sextupole | A.PP093 | ESR Bellows |  |  | ITEM112 | ESR Magnetic Measurement and Bench | 0000FF | sphilip | S. Philip |  |  |  |  | fbarbosa | F. Barbosa - JLab | ITEM112 | ESR Magnetic Measurement and Bench
6.04.02.01 | ESR Dipole Magnets | A.PP094 | ESR Vacumm Pumps |  |  | ITEM113 | APS Quadrupole Magnet Refurbishment, Testing and Measurement | 0000FF | [6 empty] | edaly | E. Daly - JLab | ITEM113 | APS Quadrupole Magnet Refurbishment, Testing and Measurement
6.04.02.02 | ESR Sextupole Magnets | A.PP095 | Mobile Pump Station |  |  | ITEM114 | ESR APS Quadrupole Magnetic Measurement Stand | 0000FF | [6 empty] | porfin | P. Orfin | ITEM114 | ESR APS Quadrupole Magnetic Measurement Stand
6.04.02.03 | ESR Girders - Design & Procurement | A.PP096 | HSR Pumps |  |  | ITEM115 | Lead Tungstate Crystals for the Detector Backward Electro-Magnetic (EM) Calorimeter - Batch 3 and Batch 4 | 0000FF | [6 empty] | bgallaghe1 | B. Gallagher | ITEM115 | Lead Tungstate Crystals for the Detector Backward Electro-Magnetic (EM) Calorimeter - Batch 3 and Batch 4
6.04.02.04 | ESR Magnet Measurement & Acceptance | A.PP097 | Beam Screens for Triplets |  |  | ITEM116 | Scintillating Fibers for the Detector Barrel - Batch 2 and Forward - Batch 2 EM Calorimeters | 0000FF | [6 empty] | rrimmer | R. Rimmer - JLab | ITEM116 | Scintillating Fibers for the Detector Barrel - Batch 2 and Forward - Batch 2 EM Calorimeters
6.04.02.05 | ESR Girders - Assembly & Integration | A.PP098 | ESR Chambers Stands |  |  | ITEM117 | Steel for the Detector Forward Hadronic Calorimeter | 0000FF | [6 empty] | snagaitsev | S. Nagaitsev | ITEM117 | Steel for the Detector Forward Hadronic Calorimeter
6.04.03 | Electron Storage Ring Magnets - Quadrupole, Corrector | A.PP099 | MPGD Trackers |  |  | ITEM118 | Detector Solenoid Magnet Power Supply | 0000FF | [6 empty] | Matalevich | J. Matalevich - JLab | ITEM118 | Detector Solenoid Magnet Power Supply
6.04.03.01 | ESR Magnet Quads | A.PP100 | HSR BPM Cryo Cables |  |  | ITEM119 | Detector Electronics Versatile Link Plus Transceiver (VRTX+) and low Power Giga-bit transceiver (1pGBT) | 0000FF | [6 empty] | llari | L. Lari | ITEM119 | Detector Electronics Versatile Link Plus Transceiver (VRTX+) and low Power Giga-bit transceiver (1pGBT)
6.04.03.01.01 | ESR Magnet APS Quad | A.PP100.A | HSR BPM Cryo Cables - Design Verification Units - Initial Award |  |  | ITEM120 | Detector Endcap Structures – Flux Return Steel | 0000FF | [6 empty] | gnarayan | G. Narayan | ITEM120 | Detector Endcap Structures – Flux Return Steel
6.04.03.01.01.01 | ESR Magnet APS Quad Design | A.PP100.B | HSR BPM Cryo Cables - Production - Option | [11 empty] | jfast | J. Fast - JLab
6.04.03.01.01.02 | ESR Magnet APS Quad Fabricate | A.PP101 | Superconducting Strand - Collared Magnets | [11 empty] | rent | R. Ent - JLab
6.04.03.01.01.03 | ESR Magnet APS Quad Test | A.PP102 | 2K Distribution System Installation Contract - NonLabor, OnSite - IR06, IR10 | [11 empty] | Satogata | T. Satogata - JLab
6.04.03.01.01.04 | ESR Magnet APS Quad Ship | A.PP103 | 591 MHz - 600 kW Klystron | [11 empty] | isourikova | I. Sourikova
6.04.03.01.02 | ESR Magnet Quad #2 | A.PP104 | Solenoid Conductor | [11 empty] | bbhandari | B. Bhandari
6.04.03.01.02.01 | ESR Magnet Quad 2 Design | A.PP105 | Detector R&D - JLAB - Procurements - FY27 | [11 empty] | wrainey | W. Rainey
6.04.03.01.02.02 | ESR Magnet Quad 2 Fabricate | A.PP106 | Barrel EMCal - Production - Sensor Wafer | [11 empty] | sbenson | S. Benson
6.04.03.01.02.03 | ESR Magnet Quad 2 Test | A.PP107 | Tracking FY 25 Procurements | [11 empty] | hoffman | C. Hoffman
6.04.03.01.02.04 | ESR Magnet Quad 2 Ship | A.PP108 | Tracking FY 28 Procurements
6.04.03.02 | ESR Magnet Correctors | A.PP109 | (MPGD) Trackers FY 26 Procurements
6.04.03.02.01 | ESR Magnet Correctors Design | A.PP110 | 2K Cryogenic Distribution & 4K HSR Connections - Procurement
6.04.03.02.02 | ESR Magnet Correctors Fabricate | A.PP111 | 2K Distribution System Installation Contract - IR06, IR10
6.04.03.02.03 | ESR Magnet Correctors Test | A.PP112 | Detector R&D - BNL - Procurements - FY26
6.04.03.02.04 | ESR Magnet Correctors Ship | A.PP113 | BTOF - Sensor
6.04.04 | Electron Storage Ring Power Supplies | A.PP114 | BTOF - Sensor - ASIC Integration
6.04.05 | Electron Storage Ring Vacuum System | A.PP115 | U-Tubes
6.04.05.01 | ESR Vacuum Chamber and Bellows | A.PP116 | dRICH - ALCOR FEB - Readout Electronics
6.04.05.02 | ESR Vacuum Valves | A.PP117 | Low Q2 - Silcon - First and Second Station
6.04.05.03 | ESR Vacuum Pumps | A.PP118 | ZDC - EMCAL PbWO4 - Crystals
6.04.05.04 | ESR Vacuum Monitoring and Control | A.PP119 | CMTF Procurement
6.04.05.05 | ESR Vacuum Utilities (racks, cooling water) | A.PP120 | RCS Arc Vacuum Chambers
6.04.05.06 | ESR Vacuum Chambers Pre-Tunnel Assembly | A.PP120.A | RCS Arc Vacuum Chambers - Lot 1-2
6.04.05.07 | Vacuum Support Equipment | A.PP120.B | RCS Arc Vacuum Chambers - Lot 3-6
6.04.06 | Electron Storage Ring Instrumentation | ACT | Actuals
6.04.06.01 | ESR Beam Position Monitors | B | Basic Procurement <$25k (Does not Obligate)
6.04.06.02 | ESR Current and Charge Monitors | B.001 | Corrector & Injection Bump Supplies Electrolytic Caps
6.04.06.03 | ESR Tune Meter and Bunch-by-Bunch Longitudinal Feedback Systems | B.002 | 2 Ch PCS - Manufacturing
6.04.06.04 | ESR Synchrotron and X-ray Radiation Monitors | B.003 | MCPCIC - Manufacturing
6.04.06.05 | ESR Beam Loss Monitors | B.004 | Racks - Manufacturing
6.05 | Hadron Ring | B.005 | RoxTech Seal - Manufacturing
6.05.01 | Hadron Ring Management | B.006 | DCCT - Manufacturing
6.05.01.01 | Hadron Ring Management - BNL | B.007 | FWD & Diodes to Ground - Manufacturing
6.05.01.02 | Hadron Ring Management - TJ | B.007.A | Helium Assembly/Welding Tooling
6.05.02 | Hadron Ring Straight Sections Modifications | B.007.B | Cavity/Helium Vessel Handling Tooling
6.05.02.01 | Hadron Ring Straight Sections Modifications Magnets | B.007.C | Misc. Cavity Processing Tooling
6.05.02.02 | Hadron Ring Straight Sections Modifications Power Supplies | B.007.D | FPC Installation Tool
6.05.02.03 | Hadron Ring Straight Sections Modifications Vacuum System | B.007.E | End Can Support (return) Tooling
6.05.02.03.01 | HSR SS Vacuum Chambers & Bellows | B.007.F | End Can Support (Supply) Tooling
6.05.02.03.02 | HSR Vacuum Valves | B.007.G | Misc. Rail Support Tooling
6.05.02.03.03 | HSR Vacuum Pumps | B.007.H | Alignment fixtures
6.05.02.03.04 | HSR Vacuum Monitor & Control | B.007.I | Tuner
6.05.02.03.05 | HSR Vacuum Utilities | B.007.J | SpaceFrame Assembly Tooling
6.05.02.03.06 | HSR Vacuum Pre-Tunnel Assembly | B.007.K | Vacuum Vessel support Tooling
6.05.03 | Hadron Ring Injection System Upgrade | B.007.L | Misc. Cryostat Assembly Tooling
6.05.03.01 | HR Injection System Upgrade Magnets | B.007.M | Test Cave U-Tubes
6.05.03.02 | HR Injection System Upgrade Power Supplies | B.007.N | Misc. Assembly/Test/Shipping Tooling
6.05.03.03 | HR Injection System Upgrade Vacuum System | B.008 | APS Quad Refurbishment Parts
6.05.03.04 | HR Injection System Upgrade Pulsed Devices | B.009 | APS Quad Rebuilt Parts
6.05.04 | HR SC Magnet Beam Pipe Upgrade | B.010 | Forward HCal Module Casting Steel
6.05.04.01 | Actively Cooled Beam Screen (ACBS) | B.011 | VRTX+ and IpGBT
6.05.04.02 | RF Bellows Upgrade | B.012 | BTOF - Test Article - Phase I
6.05.04.03 | Amorphous Carbon Coating System (ACCS) | B.013 | BTOF - Module - Final Design
6.05.04.04 | Cryostat Modifications | B.014 | DAQ - Detector Computing - Consumables
6.05.04.05 | Fabrication, Integration and Coating | B.015 | DAQ - Fiber Patch Panels
6.05.05 | Hadron Ring Beam Instrumentation Upgrade | B.017 | INSERT - Module Casting Steel
6.05.05.01 | Hadron Ring BPM Upgrade | B.018 | DAQ - Computing Infrastructure - Network Cable and Patch Panels
6.05.05.02 | Hadron Ring Injection Transfer Line Instrumentation | B.019 | DAQ - Computing Infrastructure - Development Server Type 1
6.05.05.03 | Hadron Ring Instrumentation Upgrade | B.020 | DAQ - Computing Infrastructure - Analysis Server First Article Type 2
6.05.06 | Hadron Ring Additional Snakes | B.021 | DAQ - Computing Infrastructure - Readout Server First Article Type 3
6.05.07 | Hadron Cooling | B.022 | DAQ - Computing Infrastructure - Network Switch Blades
6.05.07.01 | Strong Hadron Cooling (SHC) Design | B.023 | DAQ - Computing Infrastructure - Network Cables
6.05.07.02 | Low Energy Cooling (LEC) Design | B.024 | DAQ - Computing Infrastructure - Network Switch Blades
6.05.07.03 | Electron Source | B.025 | DAQ - Computing Infrastructure - Network Cables
6.05.07.04 | Hadron Cooling Beam Transport Vacuum Systems | B.026 | Slow Controls Integration - Network Fibers
6.05.07.05 | Hadron Cooling Instrumentation | B.027 | Slow Controls Integration - Racks
6.05.07.05.01 | Hadron Cooling Beam Position Monitors | B.028 | hpDIRC - DIRC Bar Box - Refurb Material
6.05.07.05.02 | Hadron Cooling Charge and Current Monitors | B.029 | Tune Meter Measurement Electronics - Prototype Material
6.05.07.05.03 | Hadron Cooling Profile and Emittance Monitors | B.030 | Corrector & Injection Bump Supplies Electrolytic Caps
6.05.07.05.04 | Hadron Cooling Beam Loss Monitors | B.031 | BTOF - CTTL AC-LGAD - Service Hybrid - Readout PCB - Final Design
6.05.07.05.05 | Hadron Cooling Synchrotron Radiation Monitors | B.032 | BTOF - CTTL AC-LGAD - Service Hybrid - Power PCB - Final Design
6.05.07.06 | Hadron Cooling Power Supplies and Cables | B.033 | BTOF - CTTL AC-LGAD - Service Hybrid - Readout PCB - Final Fabrication
6.05.07.07 | HSR Modification for Hadron Cooling | B.034 | BTOF - CTTL AC-LGAD - Service Hybrid - Power PCB - Final Fabrication
6.05.08 | SHC Energy Recovery Linac (ERL) | B.035 | BTOF - CTTL AC-LGAD - Service Hybrid - Engineering Article - QA/QC
6.05.08.01 | ERL Design & Specifications | B.036 | TOF LV Power Supply Design - BTOF - Power Board Test Assembly
6.05.08.01.01 | ERL Beamline Design | B.037 | TOF LV Power Supply Production - BTOF - Distribution Board
6.05.08.01.02 | ERL Subsystem Specifications | B.038 | TOF LV Power Supply Production - FTOF - Distribution Board
6.05.08.01.03 | ERL Subsystem Integration | B.039 | TOF HV Power Supply Design Validation
6.05.08.01.04 | ERL System Commissioning | B.040 | TOF HV Power Supply Production - BTOF - HV Crate
6.05.08.02 | ERL Beam Transport Magnets | B.041 | TOF HV Power Supply Production - BTOF - HV Modules
6.05.08.02.01 | ERL Beam Transport Magnets Design | B.042 | TOF HV Power Supply Production - BTOF - HV Multipair Cables
6.05.08.02.02 | ERL Beam Transport Magnets Fabrication | B.043 | TOF HV Power Supply Production - FTOF - HV Crate
6.05.08.02.03 | ERL Beam Transport Magnets Testing | B.044 | TOF HV Power Supply Production - FTOF - HV Multipair Cables
6.05.08.02.04 | ERL Beam Transport Magnets Ship | B.045 | BTOF LV Cable Feed (1k)
6.05.08.03 | ERL Vacuum Systems | B.046 | FTOF - FTTL AC-LGAD - Service Hybrid & Module - Readout PCB - Design
6.05.08.03.01 | ERL Vacuum Systems Design | B.047 | FTOF - FTTL AC-LGAD - Service Hybrid & Module - Module PCB - Design
6.05.08.03.02 | ERL Vacuum Systems Fabricate | B.048 | FTOF - FTTL AC-LGAD - Service Hybrid & Module - Power PCB - Design
6.05.08.04 | ERL Specific Beam Diagnostics | B.049 | FTOF - FTTL AC-LGAD - Service Hybrid & Module - Readout PCB - Initial
6.05.08.04.01 | ERL Specific Beam Diagnostics Design | B.050 | FTOF - FTTL AC-LGAD - Service Hybrid & Module - Module PCB - Initial
6.05.08.04.02 | ERL Specific Beam Diagnostics Fabricate | B.051 | FTOF - FTTL AC-LGAD - Service Hybrid & Module - Power PCB - Initial
6.05.08.04.03 | ERL Specific Beam Diagnostics Ship | B.052 | FTOF - FTTL AC-LGAD - Service Hybrid & Module - Readout PCB - Final
6.05.08.05 | ERL Specific Beam Intercepting Elements | B.053 | FTOF - FTTL AC-LGAD - Service Hybrid & Module - Module PCB - Final
6.05.08.05.01 | ERL Specific Beam Intercepting Elements Design | B.054 | FTOF - FTTL AC-LGAD - Service Hybrid & Module - Power PCB - Final
6.05.08.05.02 | ERL Specific Beam Intercepting Elements Fabricate | B.055 | ESR APS Magnets - Parts and fixtures
6.05.08.06 | ERL Beamline Mechanical Interfaces | B.056 | FTOF - FTTL AC-LGAD - Service Hybrid & Module - Production - Fab & Asy
6.05.08.06.01 | ERL Beamline Mechanical Interfaces Design | B.057 | Backward ECAL - RDO Powered Crate
6.05.08.06.02 | ERL Beamline Mechanical Interfaces Fabricate | B.058 | Forward pECAL - RDO Powered Crate
6.06 | Interaction Regions and Detector Interface | B.059 | HCAL Insert - Engineering Test Article H2GCROC FEB
6.06.01 | Interaction Regions and Detector Interface Management | B.060 | HCAL Insert - Bias Power Supply Cables
6.06.01.01 | IR and Detector Interface Management - BNL | B.061 | HCAL Insert - Bias Power Supply for Sensors
6.06.01.02 | IR and Detector Interface Management - TJ | B.062 | HCAL Insert - LV Circuit Board Power Supply
6.06.02 | Interaction Region (IR) | B.063 | HCAL Insert - LV Power Supply Cables
6.06.02.01 | IR Magnets | B.064 | HCAL Insert - BIAS Power Patch Panel
6.06.02.01.01 | Direct Wind Magnets | B.065 | HCAL Insert - LV Power Patch Panel
6.06.02.01.02 | Collared Magnets | B.066 | HCAL Insert - Electronics and Readout Assembly HW
6.06.02.01.03 | IR Warm Magnets | B.067 | TOF LV Power Supply Production - BTOF - Power Board
6.06.02.01.04 | IR Cryostat Integration and Magnet Test | B.068 | HCAL Insert - Fibers, FEB-RDO Cables
6.06.02.01.05 | IR Magnet Cryostats | B.069 | Roman Pots - AC-LGAD - Service Hybrid & Module - Readout PCB - Final
6.06.02.02 | IR Spin Rotator Magnets | B.070 | Roman Pots - AC-LGAD - Service Hybrid & Module - Module PCB - Final
6.06.02.03 | IR Power Supplies | B.071 | Roman Pots - AC-LGAD - Service Hybrid & Module - Power PCB - Final
6.06.02.04 | IR Vacuum | B.072 | Roman Pots - AC-LGAD - Service Hybrid & Module - Engineering Article - Components
6.06.02.05 | IR Instrumentation | B.074 | Roman Pots - AC-LGAD - Service Hybrid & Module - Engineering Article - Fab and Asy
6.06.02.05.01 | IR Beam Position Monitors | B.075 | Roman Pots - AC-LGAD - Service Hybrid & Module - Production - Fab and Asy
6.06.02.05.02 | IR Orbit Feedback | B.076 | Lepton Polarimetry in RCS - Calorimeter Monitoring System
6.06.02.05.03 | IR Beam Loss Monitors | B.077 | Lepton Polarimetry in RCS - Calorimeter - Machine Shop and Shipping
6.06.02.06 | Matching Magnets | B.078 | Lepton Polarimetry in RCS - Pulsed Laser - Low Duty Cycle
6.06.02.07 | Cables | B.079 | Lepton Polarimetry in ESR - Calorimeter - Machine Shop and Shipping
6.06.03 | Machine-Detector Integration | B.080 | Lepton Polarimetry in ESR - Calorimeter - Monitoring System
6.06.03.01 | Machine and Detector Protection System | B.081 | Low Q2 - Engineering Test Article - Hardware Components
6.06.03.01.01 | Machine Protection System Design | B.082 | ZDC - Cooling System Shipment
6.06.03.01.02 | Detector Protection System Design | B.083 | ZDC - Cooling System
6.06.03.02 | Collimation System Design and Integration | B.084 | ZDC - Mechanical Support / Table
6.06.03.02.01 | Collimation Physics Design | B.085 | B0 - Shipping
6.06.03.02.02 | Collimation HSR Design | B.086 | B0 - Interlock
6.06.03.02.03 | Collimation ESR Design | B.087 | B0 - EMCAL / Pre-Shower - Mechanical Frame
6.06.04 | IR #2 Development | B.088 | RP/OMD - Cooling Pipes
6.07 | Accelerator Support Systems | B.089 | RP/OMD - Support Frame
6.07.01 | Accelerator Support Systems Management and Infrastructure | B.090 | OMD - Mechanical Frame Engineering Test Article
6.07.01.01 | Accelerator Support Systems Management | B.091 | RP/OMD - Cooling System - Engineering Test Article
6.07.01.02 | Accelerator Support Systems Hardware and Software Infrastructure | B.092 | RP - Sensors - Engineering Test Article
6.07.02 | Control System | B.093 | RP - Cooling System - Engineering Test Article
6.07.02.01 | Controls - Global Design & Development | B.094 | Hadron Endcap Tracking - MPGD SALSA FEB Engineering Article
6.07.02.02 | Controls - High Level Applications | B.095 | Electron Endcap Tracking - MPGD SALSA FEB Engineering Article
6.07.02.03 | Controls - Diagnostics | B.096 | Outer Gas Barrel Tracking - MPGD SALSA FEB Engineering Article
6.07.02.04 | Controls - RF and LLRF | B.097 | Inner Gas Barrel Tracking - MPGD SALSA FEB Engineering Article
6.07.02.05 | Controls - Power Supplies | B.098 | B0 Detector - Engineering Test Article - Fabrication and Assembly
6.07.02.06 | Controls - Vacuum | B.099 | Calorimeter Digitizers - Engineering Test Article - Fabrication and Assembly
6.07.02.07 | Controls - Water and Cryo Cooling | B.100 | Backward nHCAL - Fibers, FEB-RDO Cables Procurement
6.07.02.08 | Controls - Facility and Temperature Monitoring | B.101 | Backward nHCAL - Electronics and Readout Assembly HW
6.07.02.09 | Controls - Safety | B.102 | Backward nHCAL - Long Power Patch Panel
6.07.02.10 | Controls - Network | B.103 | Backward nHCAL - BIAS Power Patch Panel
6.07.02.11 | Controls - Hardware Procurements | B.104 | Backward nHCAL - LV Power Supply Cables
6.07.03 | EIC Accelerator/Storage Ring Systems Installations | B.105 | Backward nHCAL - LV Circuit Board Power Supply
6.07.03.01 | EIC Accelerator/Storage Ring Systems Installations in AS01 | B.106 | Backward nHCAL - Bias Power Supply for Sensors
6.07.03.02 | EIC Accelerator/Storage Ring Systems Installations in IR02 | B.107 | Backward nHCAL - Bias Power Supply Cables
6.07.03.03 | EIC Accelerator/Storage Ring Systems Installations in AS03 | B.108 | Backward nHCAL - Engineering Test Article H2GCROC FEB
6.07.03.04 | EIC Accelerator/Storage Ring Systems Installations in IR04 | B.109 | Forward LFHCAL - Fibers, FEB-RDO Cables
6.07.03.05 | EIC Accelerator/Storage Ring Systems Installations in AS05 | B.110 | Forward LFHCAL - Electronics and Readout Assembly HW
6.07.03.06 | EIC Accelerator/Storage Ring Systems Installations in IR06 | B.111 | Forward LFHCAL - LV Power Patch Panel
6.07.03.07 | EIC Accelerator/Storage Ring Systems Installations in AS07 | B.112 | Forward LFHCAL - BIAS Power Patch Panel
6.07.03.08 | EIC Accelerator/Storage Ring Systems Installations in IR08 | B.113 | Forward LFHCAL - LV Power Supply Cables
6.07.03.09 | EIC Accelerator/Storage Ring Systems Installations in AS09 | B.114 | Forward LFHCAL - Bias Power Supply Cables
6.07.03.10 | EIC Accelerator/Storage Ring Systems Installations in IR10 | B.115 | Forward LFHCAL - Engineering Test Article H2GCROC FEB
6.07.03.11 | EIC Accelerator/Storage Ring Systems Installations in AS11 | B.116 | OUTER Barrel HCAL - Fibers, FEB-RDO Cables
6.07.03.12 | EIC Accelerator/Storage Ring Systems Installations in IR12 | B.117 | OUTER Barrel HCAL - Electronics and Readout Assembly HW
6.07.03.13 | EIC RCS Pre-Injector (LINAC Systems) Installations in IR12 | B.118 | OUTER Barrel HCAL - LV Power Patch Panel
6.07.03.14 | EIC SHC Systems Installations in IR02 | B.119 | OUTER Barrel HCAL - BIAS Power Patch Panel
6.08 | RF Systems | B.120 | OUTER Barrel HCAL - LV Power Supply Cables
6.08.01 | RF Systems Management and Integration | B.121 | OUTER Barrel HCAL - LV Circuit Board Power Supply
6.08.01.01 | RF Systems Management - BNL | B.122 | OUTER Barrel HCAL - Bias Power Supply Cables
6.08.01.02 | RF Systems Management - TJ | B.123 | OUTER Barrel HCAL -Engineering Test Article H2GCROC FEB
6.08.02 | SRF R&D | B.124 | Forward pECAL - Fibers
6.08.02.01 | 197 MHz Crab Cavity R&D | B.125 | Forward pECAL - LV Supply Cable Patch to Detector
6.08.02.02 | ESR 1-Cell Cavity R&D | B.126 | Forward pECAL - LV Supply to Patch
6.08.02.03 | High Power FPC and HOM Absorber R&D | B.127 | Forward pECAL - Power Supply Crate
6.08.02.03.01 | HP FPC Prototype | B.128 | Forward pECAL - LV Patch Panel
6.08.02.03.02 | HP HOM Absorber Prototype | B.129 | Forward pECAL - Detector - Bias Cable and Connectors
6.08.03 | SRF First Article Cryomodules | B.130 | Backward ECAL - Fibers
6.08.03.01 | 197 MHz Crab Cryomodule First Article | B.131 | Backward ECAL - LV Supply Cable Patch to Detector
6.08.03.01.01 | CS: 197 MHz Crab FA String Components | B.132 | Backward ECAL - Power Supply
6.08.03.01.01.01 | CS: 197 MHz Crab FA Design | B.133 | Backward ECAL - LV Supply to Patch
6.08.03.01.01.02 | CS: 197 MHz Crab FA Procurement | B.134 | Backward ECAL - Power Supply Crate
6.08.03.01.01.03 | CS: 197 MHz Crab FA Acceptance | B.135 | Backward ECAL - LV Patch Panel
6.08.03.01.02 | CM: 197 MHz Crab FA Cryostat Components | B.136 | Backward ECAL - Detector - HV Cable and Connectors
6.08.03.01.02.01 | CM: 197 MHz Crab FA Design | B.137 | Backward ECAL - Signal Cable and Connectors
6.08.03.01.02.02 | CM: 197 MHz Crab FA Procurement | B.138 | Barrel ECAL - FBD-RDO - Fiber Cables
6.08.03.01.02.03 | CM: 197 MHz Crab FA Acceptance | B.139 | Barrel ECAL - Electronics and Readout Assembly HW
6.08.03.01.03 | AS: 197 MHz Crab FA Cryomodule Assembly and Test | B.140 | Barrel ECAL - LV Power Patch Panel
6.08.03.01.03.01 | AS: 197 MHz Crab FA Design | B.141 | Barrel ECAL - BIAS Power Patch Panel
6.08.03.01.03.02 | AS: 197 MHz Crab FA Procurement | B.142 | Barrel ECAL - LV Power Supply - Cables
6.08.03.01.03.03 | AS: 197 MHz Crab FA Acceptance | B.143 | Barrel ECAL - LV Circuit Board - Power Supply
6.08.03.01.03.04 | AS: 197 MHz Crab FA Assembly | B.144 | Barrel ECAL - Sensors - BIAS - Power Supply Cable
6.08.03.01.03.05 | AS: 197 MHz Crab FA Acceptance Test | B.145 | Barrel ECAL - BIAS - Power Supply Cable
6.08.03.01.03.06 | AS: 197 MHz Crab FA Shipment | B.146 | Barrel ECAL - Engineering Test Article H2GCROC FEB
6.08.03.01.04 | HP: 197 MHz Crab FA High Power Test | B.147 | dRICH - Fibers
6.08.03.02 | 591 MHz 1-Cell Cryomodule First Article | B.148 | dRICH - ALCOR - Engineering Test Article
6.08.03.02.01 | CS: 591 MHz FA Cavity String Components | B.149 | pfRICH - EICROC - Power Supply and Cables
6.08.03.02.01.01 | CS: 591 MHz FA Design | B.150 | pfRICH - LV Circuit Board Power Supplies
6.08.03.02.01.02 | CS: 591 MHz FA Procurement | B.151 | pfRICH - EICROC - Engineering Test Article
6.08.03.02.01.03 | CS: 591 MHz FA Acceptance | B.152 | hpDIRC - LV Circuit Board Power Supplies
6.08.03.02.02 | CM: 591 MHz FA Cryostat Components | B.153 | hpDIRC - Fibers
6.08.03.02.02.01 | CM: 591 MHz FA Design | B.154 | hpDIRC - MCPMT/LAPPD EICROC FEB - Engineering Test Article
6.08.03.02.02.02 | CM: 591 MHz FA Procurement | B.155 | Hadron Endcap Tracking - Rack, LV, HV, Crates, Cable
6.08.03.02.02.03 | CM: 591 MHz FA Acceptance | B.156 | Hadron Endcap Tracking - Fibers
6.08.03.02.03 | AS: 591 MHz FA Cryomodule Assembly and Test | B.157 | Electron Endcap Tracking - Rack, LV, HV, Crates, Cable
6.08.03.02.03.01 | AS: 591 MHz FA Design | B.158 | Electron Endcap Tracking - Fibers
6.08.03.02.03.02 | AS: 591 MHz FA Procurement | B.159 | Outer Gas Barrel Tracking - Fibers
6.08.03.02.03.03 | AS: 591 MHz FA Acceptance | B.160 | Si Tracker - Barrel and Endcaps - Fibers
6.08.03.02.03.04 | AS: 591 MHz FA Assembly | B.161 | Inner Gas Barrel Tracking - Rack, LV, HV, Crates, Cable
6.08.03.02.03.05 | AS: 591 MHz FA Acceptance Testing | B.162 | Inner Gas Barrel Tracking - Fibers
6.08.03.02.03.06 | AS: 591 MHz FA Shipment | B.163 | pfRICH - HRPPD QA Test Station - LED Switcher Box
6.08.03.02.04 | HP: 591 MHz FA High Power Test | B.164 | pfRICH - HRPPD QA Test Station - Optics Head
6.08.04 | SRF Cryomodules | B.165 | pfRICH - HRPPD QA Test Station - Dark Box with HRPPD Mount
6.08.04.01 | 591 MHz 1-Cell Cryomodule | B.166 | pfRICH - Mirrors - Mirror Support Inside the Vessel
6.08.04.01.01 | CS: 591 MHz 1-Cell Cavity String Components | B.167 | pfRICH - Gas System
6.08.04.01.01.01 | CS: 591 MHz 1-Cell Design | B.168 | hpDIRC - Mirrors
6.08.04.01.01.02 | CS: 591 MHz 1-Cell Procurement | B.169 | Roman Pots - AC-LGAD - Service Hybrid & Module - Pack & Ship
6.08.04.01.01.03 | CS: 591 MHz 1-Cell Acceptance | B.170 | Off-Momentum Detector - AC-LGAD - Service Hybrid & Module - Readout PCB - Final
6.08.04.01.02 | CM: 591 MHz 1-Cell Cryostat Components | B.171 | Off-Momentum Detector - AC-LGAD - Service Hybrid & Module - Module PCB - Final
6.08.04.01.02.01 | CM: 591 MHz 1-Cell Design | B.172 | Off-Momentum Detector - AC-LGAD - Service Hybrid & Module - Power PCB - Final
6.08.04.01.02.02 | CM: 591 MHz 1-Cell Procurement | B.173 | Off-Momentum Detector - AC-LGAD - Service Hybrid & Module - Engineering Article - Components
6.08.04.01.02.03 | CM: 591 MHz 1-Cell Acceptance | B.174 | Off-Momentum Detector - AC-LGAD - Service Hybrid & Module - Engineering Article - Fab & Asy
6.08.04.01.03 | AS: 591 MHz 1-Cell Cryomodule Assembly and Test | B.175 | Off-Momentum Detector - AC-LGAD - Service Hybrid & Module - Production - Fab & Asy
6.08.04.01.03.01 | AS: 591 MHz 1-Cell Design | B.176 | Off-Momentum Detector - AC-LGAD - Service Hybrid & Module - Pack & Ship
6.08.04.01.03.02 | AS: 591 MHz 1-Cell Procurement | B.177 | Roman Pots - AC-LGAD - Service Hybrid & Module - Production - Fab and Asy
6.08.04.01.03.03 | AS: 591 MHz 1-Cell Acceptance | B.178 | B0 Tracker - AC-LGAD - Service Hybrid & Module - Readout PCB - Final
6.08.04.01.03.04 | AS: 591 MHz 1-Cell Assembly | B.179 | B0 Tracker - AC-LGAD - Service Hybrid & Module - Module PCB - Final
6.08.04.01.03.05 | AS: 591 MHz 1-Cell Acceptance Test | B.180 | B0 Tracker - AC-LGAD - Service Hybrid & Module - Power PCB - Final
6.08.04.01.03.06 | AS: 591 MHz 1-Cell Shipment | B.181 | B0 Tracker - AC-LGAD - Service Hybrid & Module - Engineering Article - Fab & Asy
6.08.04.01.04 | HP: 591 MHz 1-Cell High Power Test | B.182 | B0 Tracker - AC-LGAD - Service Hybrid & Module - Pack & Ship
6.08.04.02 | 591 MHz 5-Cell Cryomodule | B.183 | B0 Calorimeter - PCB - HV/Anode/LED - Interface Components
6.08.04.02.01 | CS: 591 MHz 5-Cell Cavity String Components | B.184 | Rack Layout with Cable & Buswork - Manufacturing
6.08.04.02.01.01 | CS: 591 MHz 5-Cell Design | B.185 | DCCT PS & Interface Chassis - Manufacturing
6.08.04.02.01.02 | CS: 591 MHz 5-Cell Procurement | B.186 | Rack Temp Controller - Manufacturing
6.08.04.02.01.03 | CS: 591 MHz 5-Cell Acceptance | B.187 | B0 Calorimeter - PCB - Assembly
6.08.04.02.02 | CM: 591 MHz 5-Cell Cryostat Components | B.188 | APS Sextupole Refurbishment Consumables
6.08.04.02.02.01 | CM: 591 MHz 5-Cell Design | B.189 | APS Sextupole Hazardous Waste Disposal Containers
6.08.04.02.02.02 | CM: 591 MHz 5-Cell Procurement | B.190 | APS Sextupole Machine Parts for Testing Fixtures
6.08.04.02.02.03 | CM: 591 MHz 5-Cell Acceptance | B.191 | Magnet Measurement Consumables for APS Sextupoles
6.08.04.02.03 | AS: 591 MHz 5-Cell Cryomodule Assembly and Test | D | DOE Approval - Advanced Procurement Plan (APP) =>$5M<$25M
6.08.04.02.03.01 | AS: 591 MHz 5-Cell Design | D.APP01 | Corrector and Injection Bump Supplies
6.08.04.02.03.02 | AS: 591 MHz 5-Cell Procurement | D.APP02 | Rest of RCS Supplies
6.08.04.02.03.03 | AS: 591 MHz 5-Cell Acceptance | D.APP03 | DC, AC Power Cables Controls and Magnet Interlock Cable
6.08.04.02.03.04 | AS: 591 MHz 5-Cell Assembly | D.APP04 | ESR Vacuum Bellows and Chamber Stands
6.08.04.02.03.05 | AS: 591 MHz 5-Cell Acceptance Test | D.APP05 | Lambda Power Supplies
6.08.04.02.03.06 | AS: 591 MHz 5-Cell Shipment | D.APP05.A | Lambda PS 2025
6.08.04.02.04 | HP: 591 MHz 5-Cell High Power Test | D.APP05.B | Lambda PS 2027
6.08.04.03 | 1773 MHz 5-Cell Elliptical Cavity Cryomodule | D.APP06 | ESR Vacuum Chambers
6.08.04.03.01 | CS: 1773 MHz 5-Cell Cavity String Components | D.APP07 | Detector Infrastructure
6.08.04.03.01.01 | CS: 1773 MHz 5-Cell Design | D.APP09 | RCS Dipole - Magnet I Manufacturing
6.08.04.03.01.02 | CS: 1773 MHz 5-Cell Procurement | D.APP10 | RCS Dipole - Magnet II Manufacturing
6.08.04.03.01.03 | CS: 1773 MHz 5-Cell Acceptance | D.APP11 | ESR Vacuum Pumps
6.08.04.03.02 | CM: 1773 MHz 5-Cell Cryostat Components | D.APP12 | Detector Electronics Construction Material
6.08.04.03.02.01 | CM: 1773 MHz 5-Cell Design | D.APP15 | Overhead 13.8 kV lines - switch stations and duct bank
6.08.04.03.02.02 | CM: 1773 MHz 5-Cell Procurement | D.APP16 | 138kW Substation
6.08.04.03.02.03 | CM: 1773 MHz 5-Cell Acceptance | D.APP17 | Main Dipole supply and the 2 Arc Quad supplies
6.08.04.03.03 | AS: 1773 MHz 5-Cell Cryomodule Assembly and Test | D.APP18 | Cable/ Buss
6.08.04.03.03.01 | AS: 1773 MHz 5-Cell Design | D.APP19 | A/E Service Contract
6.08.04.03.03.02 | AS: 1773 MHz 5-Cell Procurement | D.APP19.A | Design Contract
6.08.04.03.03.03 | AS: 1773 MHz 5-Cell Acceptance | D.APP19.B | Construction Contract
6.08.04.03.03.04 | AS: 1773 MHz 5-Cell Assembly | D.APP19.CD1 | A/E Service Contract Pre CD1
6.08.04.03.03.05 | AS: 1773 MHz 5-Cell Acceptance Test | D.APP19.CD1FY21 | A/E Service Contract Post CD1 - FY21
6.08.04.03.03.06 | AS: 1773 MHz 5-Cell Shipment | D.APP19.CD1FY22 | A/E Service Contract Post CD1 - FY22
6.08.04.03.04 | HP: 1773 MHz 5-Cell High Power Test | D.APP19.CD2 | A/E Service Contract Post CD2
6.08.04.04 | 197 MHz Crab Cavity Cryomodule | D.APP20 | eSR Girder Fabrication
6.08.04.04.01 | CS: 197 MHz Crab String Components | D.APP21 | RCS Girder Fabrication
6.08.04.04.01.01 | CS: 197 MHz Crab Design | D.APP22 | 591 MHz FPC Couplers
6.08.04.04.01.02 | CS: 197 MHz Crab Procurement | D.APP23 | ESR 1 Test Power Amplifiers
6.08.04.04.01.03 | CS: 197 MHz Crab Acceptance | D.APP23.A | ESR 1 Test Power Amplifiers - Option 1
6.08.04.04.02 | CM: 197 MHz Crab Cryostat Components | D.APP23.B | ESR 1 Test Power Amplifiers - Option 2
6.08.04.04.02.01 | CM: 197 MHz Crab Design | D.APP23.C | ESR 1 Test Power Amplifiers - Option 3
6.08.04.04.02.02 | CM: 197 MHz Crab Procurement | D.APP23.D | ESR 1 Test Power Amplifiers - Option 4
6.08.04.04.02.03 | CM: 197 MHz Crab Acceptance | D.APP24 | ERL 3 Power Amplifiers
6.08.04.04.03 | AS: 197 MHz Crab Cryomodule Assembly and Test | D.APP24.A | ERL 3 Power Amplifiers - First Article
6.08.04.04.03.01 | AS: 197 MHz Crab Design | D.APP24.B | ERL 3 Power Amplifiers - Production
6.08.04.04.03.02 | AS: 197 MHz Crab Procurement | D.APP25 | APS
6.08.04.04.03.03 | AS: 197 MHz Crab Acceptance | D.APP25.A | Phase A
6.08.04.04.03.04 | AS: 197 MHz Crab Assembly | D.APP25.B | Phase B
6.08.04.04.03.05 | AS: 197 MHz Crab Acceptance Test | D.APP26 | SHC Beam Transport Magnets
6.08.04.04.03.06 | AS: 197 MHz Crab Shipment | D.APP27 | Cryogenics System Installation Contract
6.08.04.04.04 | HP: 197 MHz Crab High Power Test | D.APP27.A | Cryogenics System Installation Contract - IR10
6.08.04.05 | 394 MHz Crab Cryomodule | D.APP27.B | Cryogenics System Installation Contract - IR06
6.08.04.05.01 | CS: 394 MHz Crab Cavity String Components | D.APP27.C | Cryogenics System Installation Contract - IR02
6.08.04.05.01.01 | CS: 394 MHz Crab Design | D.APP31 | Detector Magnets
6.08.04.05.01.02 | CS: 394 MHz Crab Procurement | D.APP32 | Unit Substation Xfmrs for Buildings - Initial Award
6.08.04.05.01.03 | CS: 394 MHz Crab Acceptance | D.APP33 | Barrel EMCal - SciGlass Material
6.08.04.05.02 | CM: 394 MHz Crab Cryostat Components | D.APP34 | 138kV Substation - PSEG
6.08.04.05.02.01 | CM: 394 MHz Crab Design | D.APP35 | oHCAL Steel Sectors
6.08.04.05.02.02 | CM: 394 MHz Crab Procurement | D.APP36 | 2K Cryo Distribution & 4K HSR Connection - IR02
6.08.04.05.02.03 | CM: 394 MHz Crab Acceptance | D.APP37 | RCS-Dipoles
6.08.04.05.03 | AS: 394 MHz Crab Cryomodule Assembly and Test | D.APP37.A | First Article Magnet Vendor A
6.08.04.05.03.01 | AS: 394 MHz Crab Design | D.APP37.B | First Article Magnet Vendor B
6.08.04.05.03.02 | AS: 394 MHz Crab Procurement | D.APP37.C | Production Magnets Material Vendor A
6.08.04.05.03.03 | AS: 394 MHz Crab Acceptance | D.APP37.D | Production Magnets Material Vendor B
6.08.04.05.03.04 | AS: 394 MHz Crab Assembly | D.APP37.E | Production Magnets Vendor A Second Award
6.08.04.05.03.05 | AS: 394 MHz Crab Acceptance Test | D.APP37.F | Production Magnets Vendor B Second Award
6.08.04.05.03.06 | AS: 394 MHz Crab Shipment | D.APP37.G | Production Magnets Vendor A
6.08.04.05.04 | HP: 394 MHz Crab High Power Test | D.APP37.H | Production Magnets Vendor B
6.08.04.06 | ERL Injector Cryomodule | D.APP38 | ESR-APS Quad
6.08.04.06.01 | CS: ERL Inj Cavity String Components | D.APP38.A | Refurbished
6.08.04.06.01.01 | CS: ERL Inj Design | D.APP38.B | Rebuilt
6.08.04.06.01.02 | CS: ERL Inj Procurement | D.APP39 | Collared Dipoles - Matching Magnets
6.08.04.06.01.03 | CS: ERL Inj Acceptance | D.APP40 | Scintillators
6.08.04.06.02 | CM: ERL Inj Cryostat Components | D.APP40.A | Scintillators
6.08.04.06.02.01 | CM: ERL Inj Design | D.APP40.B | Scintillators
6.08.04.06.02.02 | CM: ERL Inj Procurement | D.APP40.C | Scintillators
6.08.04.06.02.03 | CM: ERL Inj Acceptance | D.APP41 | Unit Substation - LLP
6.08.04.06.03 | AS: ERL Inj Cryomodule Assembly and Test | D.APP42 | RCS Quad Magnets
6.08.04.06.03.01 | AS: ERL Inj MHz Design | D.APP42.A | RCS Quad - First Article - Vendor I
6.08.04.06.03.02 | AS: ERL Inj MHz Procurement | D.APP42.B | RCS Quad - Production - Vendor I
6.08.04.06.03.03 | AS: ERL Inj MHz Acceptance | D.APP42.C | RCS Quad - First Article - Vendor II
6.08.04.06.03.04 | AS: ERL Inj MHz Assembly | D.APP42.D | RCS Quad - Production - Vendor II
6.08.04.06.03.05 | AS: ERL Inj MHz Acceptance Test | D.APP44 | RCS Sextupole Magnets
6.08.04.06.03.06 | AS: ERL Inj MHz Shipment | D.APP44.A | RCS Sextupole - Vendor I - First Article
6.08.04.06.04 | HP: ERL Inj High Power Test | D.APP44.B | RCS Sextupole - Vendor I - Production
6.08.05 | NCRF Cavities | D.APP44.C | RCS Sextupole - Vendor II - First Article
6.08.05.01 | 295 MHz Cavity: RCS Bunch Merge 1 (New) | D.APP44.D | RCS Sextupole - Vendor II - Production
6.08.05.02 | 148 MHz Cavity: RCS Bunch Merge 2 | D.APP45 | sPHENIX barrel HCal acquisition
6.08.05.03 | FPC Production | D.APP46 | Barrel EMCal Scintillation Fibers
6.08.05.04 | 24.6 MHz Cavity: HSR Capture and Acceleration (Mod) | D.APP47 | Backward EMCal Crystals
6.08.05.05 | 49.2 MHz Cavity: HSR Bunch Split 1 | D.APP47.A | Backward EMCal Crystals - Initial Award
6.08.05.06 | 98.4 MHz Cavity: HSR Bunch Split 2 | D.APP47.B | Backward EMCal Crystals - Option 1
6.08.05.07 | 197 MHz Cavity: HSR Store 1 (Mod) | D.APP47.C | Backward EMCal Crystals - Option 2
6.08.05.08 | 197 MHz Cavity: ERL Injector Buncher (Mod) | D.APP47.D | Backward EMCal Crystals - Option 3
6.08.05.08.01 | 197 MHz Cavity (ERL Inj) Components | D.APP48 | ESR Straight Section Chambers
6.08.05.08.02 | 197 MHz Cavity (ERL Inj) Assembly and Test | D.APP50 | ESR ARC Vacuum Chambers
6.08.05.09 | RCS Harmonic Injection Kicker | D.APP51 | not used
6.08.05.09.01 | RCS Harmonic Injection Kicker Management and Integration | D.APP51.A | not used
6.08.05.09.02 | RCS Harmonic Injection Kicker R&D | D.APP51.B | not used
6.08.05.09.03 | RCS Harmonic Injection Kicker Design | D.APP51.C | not used
6.08.05.09.04 | RCS Harmonic Injection Kicker Fabricate | D.APP53 | not used
6.08.05.09.05 | RCS Harmonic Injection Kicker Test | D.APP54 | 2K Cryogenic Distribution and 4K HSR Connections - IR02
6.08.05.09.06 | RCS Harmonic Injection Kicker Ship | D.APP55 | 2K Cryogenic Distribution and 4K HSR Connections - IR06
6.08.06 | High Power RF Systems | D.APP56 | 2K Cryogenic Distribution and 4K HSR Connections - IR10
6.08.06.01 | SSA: 591 MHz, 400 kW with 200 kW Variant | D.APP57 | Tracking FY 26 Procurements
6.08.06.02 | SSA: 591 MHz, Other Variants | D.APP58 | Tracking FY 27 Procurements
6.08.06.03 | SSA: Low to Mid Frequency, Small Production | D.APP59 | BTOF - Sensor
6.08.06.04 | SSA: High Frequency, Small Production | D.APP60 | 2K Cryo Distribution & 4K HSR Connection - IR06
6.08.06.05 | Tetrode Amplifiers | D.APP61 | not used
6.08.06.06 | Circulators/Loads and Transmission Components | D.APP62 | ESR Dipole Magnets - D1/D3
6.08.06.07 | HOM Absorbers | D.APP62.A | ESR Dipole Magnets - D1/D3 - Vendor I - CD-3B
6.08.07 | RF Controls | D.APP62.B | ESR Dipole Magnets - D1/D3 - Vendor II - CD-3B
6.08.07.01 | RF Controls Common Architecture | D.APP62.C | ESR Dipole Magnets - D1/D3 - Vendor I - Option for Remaining Production
6.08.07.02 | RF Controls Sub-System Components | D.APP62.D | ESR Dipole Magnets - D1/D3 - Vendor II - Option for Remaining Production
6.08.07.02.01 | Global Reference Clock | D.APP63 | ESR Dipole Magnets - D2
6.08.07.02.02 | System Controller | D.APP63.A | ESR Dipole Magnets - D2 - Vendor I - CD-3B
6.08.07.02.03 | Cavity Controller | D.APP63.B | ESR Dipole Magnets - D2 - Vendor II - CD-3B
6.08.07.02.04 | Resonance Control | D.APP63.C | ESR Dipole Magnets - D2 - Vendor I - Option for Remaining Production
6.08.07.02.05 | Up/Down Converter | D.APP63.D | ESR Dipole Magnets - D2 - Vendor II - Option for Remaining Production
6.08.07.02.06 | Interlocks | D.APP64 | ESR Dipole Iron Material - D1/D2/D3
6.08.07.02.07 | HPRF Control (PLC based?) | D.APP64.A | ESR Dipole Iron Material for D1/D3
6.08.07.03 | RCS: System Customization and Delivery | D.APP64.B | ESR Dipole Iron Material for D2
6.08.07.03.01 | RCS: Hardware Customizations | D25 | DOE Approval - Advanced Procurement Plan (APP) =>$25M<$50M
6.08.07.03.02 | RCS: Firmware/Software Customizations | D25.(New) | (New Code Value)
6.08.07.03.03 | RCS: Production Procurement, Assembly, Test | D25.APP01 | IR Spin Rotator Magnets
6.08.07.03.04 | RCS: Rack and System Integration | D25.APP02 | Unit Substation
6.08.07.04 | ESR: System Customization and Delivery | D25.APP02.A | Unit Substation - CD3A Funding
6.08.07.04.01 | ESR: Hardware Customizations | D25.APP02.B | Unit Substation - CD3 Funding
6.08.07.04.02 | ESR: Firmware/Software Customizations | D25.APP04
6.08.07.04.03 | ESR: Production Procurement, Assembly, Test | D25.APP04.A
6.08.07.04.04 | ESR: Rack and System Integration | D25.APP04.B
6.08.07.05 | HSR: System Customization and Delivery | D25.APP05 | not used
6.08.07.05.01 | HSR: Hardware Customizations | D25.APP05.A | not used
6.08.07.05.02 | HSR: Firmware/Software Customizations | D25.APP05.B | not used
6.08.07.05.03 | HSR: Production Procurement, Assembly, Test | D25.APP05.C | not used
6.08.07.05.04 | HSR: Rack and System Integration | D25.APP06 | Satellite Plant (IR02) - Not used
6.08.07.06 | SHC ERL: System Customization and Delivery | D25.APP06.A | Satellite Plant (Phase 1) (IR02)
6.08.07.06.01 | ERL: Hardware Customizations | D25.APP06.B | Satellite Plant (Phase 2) (IR02)
6.08.07.06.02 | ERL: Firmware/Software Customizations | D25.APP06.C | Satellite Plant (Phase 3) (IR02)
6.08.07.06.03 | ERL: Production Procurement, Assembly, Test | D25.APP07
6.08.07.06.04 | ERL: Rack and System Integration | D25.APP08 | 400 MeV Injector RF System
6.08.07.07 | Crab: System Customization and Delivery | D25.APP08.A | 400 MeV Injector RF System (Design)
6.08.07.07.01 | Crab: Hardware Customizations | D25.APP08.B | 400 MeV Injector RF System (Long Lead Materials)
6.08.07.07.02 | Crab: Firmware/Software Customizations | D25.APP08.C | 400 MeV Injector RF System (Fabrication/Installation/Commissioning)
6.08.07.07.03 | Crab: Production Procurement, Assembly, Test | D25.APP09 | eSR Dipole Magnets
6.08.07.07.04 | Crab: Rack and System Integration | D25.APP09.A | eSR Dipole Magnets - First Article - Vendor I
6.08.08 | Facilities Modifications | D25.APP09.B | eSR Dipole Magnets - Production - Vendor I
6.08.08.01 | Facilities Modifications - BNL | D25.APP09.C | eSR Dipole Magnets - First Article - Vendor II
6.08.08.01.01 | BNL Facilities Upgrades | D25.APP09.D | eSR Dipole Magnets - Production - Vendor II
6.08.08.01.02 | BNL Facilities Maintenance | D25.APP52 | Satellite Plants IR10, IR06, IR02
6.08.08.02 | Facilities Modifications - TJ | D25.APP52.A | Satellite Plant IR10 - Phase 1
6.08.08.02.01 | Cavity Processing Facilities | D25.APP52.B | Satellite Plant IR06 - Phase 2
6.08.08.02.01.01 | JLAB Facility Modifications and Upgrades Design | D25.APP52.C | Satellite Plant IR02 - Phase 3
6.08.08.02.01.02 | JLAB Facility Modifications and Upgrades Procurements | D50 | DOE Approval - Advanced Procurement Plan (APP) =>$50M
6.08.08.02.01.03 | JLAB Facility Modifications and Upgrades Installation | D50.APP01 | ESR H1 Power Amplifiers - 200 KW Initial & 400 KW Upgrade
6.08.08.02.02 | CM Testing Facilities | D50.APP01.A | ESR H1 Power Amplifiers - 200 KW
6.08.08.02.02.01 | CMTF Modification | D50.APP01.A.B | ESR H1 Power Upgrade - 400 KW
6.08.08.02.02.01.01 | CMTF Modification Design | D50.APP02 | Main CM/GC (General Contractor)
6.08.08.02.02.01.02 | CMTF Modification Procurements | D50.APP02.A | CM/GC - Phase I - Pre-Construction Services
6.08.08.02.02.01.03 | CMTF Modification Installation and Commissioning | D50.APP02.B | CM/GC - Phase II - Construction Site Preparation Services
6.08.08.02.02.02 | LERF Modification | D50.APP02.B1 | CM/GC - Phase II - DOE CD2/3
6.08.08.02.02.02.01 | LERF Modification Design | D50.APP02.B2 | CM/GC - Phase II - DOE CD3
6.08.08.02.02.02.02 | LERF Modification Procurements | D50.APP02.B3 | CM/GC - Phase II - NYS
6.08.08.02.02.02.03 | LERF Modification Installation and Commissioning | D50.APP02.C | CM/GC - Phase III - Construction Services - FY26
6.08.09 | RF Engineering Demonstration Units | D50.APP02.D | CM/GC - Phase II - Construction Services - FY27
6.08.09.01 | 197 MHz Crab Cavity Engineering Design Verification Component | D50.APP02.E | CM/GC - Phase II - Construction Services - FY28
6.08.09.02 | 591 MHz Cavity Engineering Design Component | D50.APP02.F | CM/GC - Phase II - Construction Services - FY29
6.09 | Cryogenics | D50.APP02.G | CM/GC - Phase II - Construction Services - FY30
6.09.01 | Cryogenics Management | D50.APP02.H | CM/GC - Phase III - Construction Services - FY31
6.09.01.01 | Cryogenics Management - BNL | D50.APP02.I | CM/GC - BNL Funded
6.09.01.02 | Cryogenics Management - TJ | D50.APP02.J | CM/GC - CD-3A LLP
6.09.02 | 2K Satellite Plants IR02, IR06, IR10 | D50.APP02.K | CM/GC - CD-3B LLP
6.09.02.01 | 2K Satellite Plants - System Design & Engineering | D50.APP03 | 2K Satellite Plants - System Design & Engineering
6.09.02.01.01 | Requirements Definition | IN | In-Kind
6.09.02.01.02 | System Definition and Design | IN.A | APP Level In-Kind Procurement
6.09.02.02 | 2K Satellite Plants - Procurements | IN.A.001 | In-Kind APP #001 - Detector Tracking - Mu Vertex
6.09.02.02.01 | Procurement - Satellite Refrigerator IR10 | IN.A.002 | In-Kind APP #002 - Detector Tracking - Hadron Endcap Low-rapidity Si
6.09.02.02.02 | Procurement - 2K Satellite Plant Auxiliary Systems | IN.A.003 | In-Kind APP #003 - Detector Tracking - Hadron Endcap GEM-TRD
6.09.02.02.03 | Procurement - Satellite Refrigerator IR02 | IN.A.004 | In-Kind APP - Obtaining Bars (In-Kind from BaBar) (hpDIRC)
6.09.02.02.04 | Procurement - Satellite Refrigerator IR06 | IN.A.005 | In-Kind APP - Production (FTOF)
6.09.02.03 | 2K Satellite Plants - Installation | IN.A.006 | In-Kind APP #006
6.09.02.03.01 | Installation - IR02 | IN.A.007 | In-Kind APP #007
6.09.02.03.02 | Installation - IR06 | IN.A.008 | In-Kind APP #008
6.09.02.03.03 | Installation - IR10 | IN.A.009 | In-Kind APP #009
6.09.02.04 | 2K Satellite Plants - Systems Test & Evaluation | IN.A.010 | In-Kind APP #010
6.09.02.04.01 | System Test & Evaluation - IR02 | IN.A.011 | In-Kind APP #011
6.09.02.04.02 | System Test & Evaluation - IR06 | IN.A.012 | In-Kind APP #012
6.09.02.04.03 | System Test & Evaluation - IR10 | IN.A.013 | In-Kind APP #013
6.09.03 | Reconfiguration of Existing and New 4K Distribution | IN.A.014 | In-Kind APP #014
6.09.03.01 | Reconfiguration Existing and New 4k Distribution - System Design & Engineering | IN.A.015 | In-Kind APP #015
6.09.03.01.01 | Requirements Definition | IN.A.016 | In-Kind APP #016 - Detector Tracking - Lepton Endcap Low-rapidity Si
6.09.03.01.02 | System Definition and Design | IN.A.017 | In-Kind APP #017 - Fibers Procurement (PID mRICH) (IN-KIND)
6.09.03.02 | Reconfiguration Existing and New 4k Distribution - Procurement | IN.A.018 | In-Kind APP #018 - Power supply and cables (PID mRICH) (IN-KIND)
6.09.03.02.01 | Procurement - Distribution Lines | IN.A.019 | In-Kind APP #019 - Slow Controls (Inner Gas Barrel Tracking) (IN-KIND)
6.09.03.02.02 | Procurement - Valvebox-Leadpots-Current leads circuit mods | IN.A.020 | In-Kind APP #020 - Assemble Peripheral Hardware In House (Inner Gas Barrel Tracking) (IN-KIND)
6.09.03.03 | Reconfiguration Existing and New 4k Distribution - Installation | IN.A.021 | In-Kind APP #021 - fications Including Firmware and Software (Inner Gas Barrel Tracking) (IN-KIND)
6.09.03.04 | Reconfiguration Existing and New 4k Distribution - System Test & Evaluation | IN.A.022 | In-Kind APP #022 - TR Effort for SALSA FEB - (Inner Gas Barrel Tracking) (IN-KIND)
6.09.04 | 2K Cryogenic Distribution & 4K HSR Connections | IN.A.023 | In-Kind APP #023 - TR Effort for Fibers - (Inner Gas Barrel Tracking) (IN-KIND)
6.09.04.01 | 2K Cryogenic Distribution & 4K HSR Connections - System Design & Engineering | IN.A.024 | In-Kind APP #024 - TR Effort for Rack, LV, HV, crates, cable - (Inner Gas Barrel Tracking) (IN-KIND)
6.09.04.01.01 | Requirements Definition | IN.A.025 | In-Kind APP #025 - Q&A / Testing (Inner Gas Barrel Tracking) (IN-KIND)
6.09.04.01.02 | System Definition and Design | IN.A.026 | In-Kind APP #026 - Board mounting on detector (Inner Gas Barrel Tracking) (IN-KIND)
6.09.04.02 | 2K Cryogenic Distribution & 4K HSR Connections - Procurement | IN.A.027 | In-Kind APP #027 - Integration Testing with DAQ and Timing systems (Inner Gas Barrel Tracking) (IN-KIND)
6.09.04.03 | 2K Cryogenic Distribution & 4K HSR Connections - Installation | IN.A.028 | In-Kind APP #028 - SubSystem performance testing and power measurements (Inner Gas Barrel Tracking) (IN-KIND)
6.09.04.04 | 2K Cryogenic Distribution & 4K HSR Connections - System Test & Evaluation | IN.A.029 | In-Kind APP #029 - Cooling Implementation and final test (Inner Gas Barrel Tracking) (IN-KIND)
6.09.05 | Cryogenic Controls | IN.A.030 | In-Kind APP #030 - Assemble Peripheral hardware In House (Outer Gas Barrel Tracking) (IN-KIND)
6.09.05.01 | Cryogenics Controls - System Engineering & Design Integration | IN.A.031 | In-Kind APP #031 - Develop Test specifications including firmware and software (Outer Gas Barrel Tracking) (IN-KIND)
6.09.05.01.01 | Requirements Definition | IN.A.032 | In-Kind APP #032 - Slow controls (Outer Gas Barrel Tracking) (IN-KIND)
6.09.05.01.02 | System Definition and Design | IN.A.033 | In-Kind APP #033 - Remaining Mirrors (dRICH)
6.09.05.02 | Cryogenics Controls - Controls & Instrumentation Hardware Procurement | IN.A.034 | In-Kind APP #034 - Light Monitoring System (dRICH)
6.09.05.03 | Cryogenics Controls - Controls Programming | IN.A.035 | In-Kind APP #035 - C2F6 Gas Recovery System (dRICH)
6.09.05.04 | Cryogenics Controls - Manufacturing/Installation | IN.A.036 | Photo Sensors (dRICH)
6.09.05.04.01 | Rack Build | IN.A.037 | In-Kind APP #037 - SiPMs Cooling System (dRICH)
6.09.05.04.02 | Rack Install and Wire Terminations | IN.A.038 | In-Kind APP #038 - Mirror Alignment System (dRICH)
6.09.05.05 | Cryogenics Controls - System Test & Evaluation | IN.A.039 | In-Kind APP #039 - Cooling System (dRICH)
6.1 | EIC Detector | IN.A.040 | In-Kind APP - Photosensor Q&A Test Setup (hpDIRC)
6.10.01 | Detector Management | IN.A.041 | In-Kind APP - Short Bar (hpDIRC)
6.10.01.01 | Detector Management - BNL | IN.A.042 | BTOF - Sensor - Design
6.10.01.02 | Detector Management - TJ | IN.A.043 | Sensor - ASIC Integration - Design
6.10.02 | Detector R&D and Physics Design | IN.A.044 | BTOF - Module Structure - Final Design
6.10.03 | Tracking | IN.A.045 | BTOF - Module Assembly - Final Design
6.10.03.01 | Silicon Trackers | IN.A.046 | FTOF - Module Structure - Final Design
6.10.03.02 | Micro Pattern Gaseous Detector (MPGD) Trackers | IN.A.047 | FTOF - Module Assembly - Final Design
6.10.04 | Particle Identification (PID) | IN.A.048 | FTOF - Module Assembly - Assemble onto Support Structure
6.10.04.01 | High Performance Direct Internally Reflecting Cherenkov Detector (hpDIRC) | IN.A.049 | TOF - Support Structure - Final Design
6.10.04.02 | Dual Ring Imaging Cherenkov Detector (dRICH) | IN.A.050 | TOF - Cooling System - Final Design
6.10.04.03 | Modular Ring Imaging Cherenkov Detector (mRICH)/Proximity Focusing Ring Imaging Cherenkov (pfRICH) | IN.A.051 | TOF - Alignment System - Final Design
6.10.04.04 | Time of Flight Detector (TOF) | IN.A.052 | dRICH - First Article Mirror
6.10.04.04.01 | Central Timing and Tracking Layer Detector (CTTL) | IN.A.053 | ZDC - EMCAL PbWO4 - Crystals
6.10.04.04.02 | Forward Timing and Tracking Layer Detector (FTTL) | IN.B | Basic Level Procurement
6.10.04.04.03 | Common Time of Flight (CTOF) | IN.P | P Level In-Kind Procurement
6.10.05 | Electromagnetic Calorimetry | IN.P.001 | In-Kind P - Barbox Assembly Tooling (hpDIRC)
6.10.05.01 | Backward Electromagnetic Calorimetry | IN.P.002 | In-Kind P - Slow Control, GUI, Software Development (dRICH)
6.10.05.01.01 | Backward EMCal Blocks | IN.P.003 | In-Kind P - Shipping dRICH (BNL)
6.10.05.01.02 | Backward Light sensors | IN.P.004 | dRICH - First Article Mirror
6.10.05.01.03 | Backward Mechanical Structure | IN.P.005 | dRICH - Light Monitoring System
6.10.05.02 | Barrel Electromagnetic Calorimetry | IN.P.006 | BTOF - Sensor - Design
6.10.05.02.01 | Barrel EMCal Sectors | IN.P.007 | FTOF - Sensor - Final Design
6.10.05.02.02 | Barrel Light sensors | IN.P.008 | FTOF - Module Structure - Final Design
6.10.05.02.03 | Barrel Imaging Planes | IN.P.009 | FTOF - Module Assembly - Final Design
6.10.05.02.04 | Barrel Mechanical Structure | IN.P.010 | TOF - Support Structure - Final Design
6.10.05.03 | Forward Electromagnetic Calorimetry | IN.P.011 | TOF - Cooling System - Final Design
6.10.05.03.01 | Forward EMCal Blocks | IN.P.012 | TOF - Alignment System - Final Design
6.10.05.03.02 | Forward Light sensors | IN.P.013 | Electron Endcap Tracking - SALSA FEB
6.10.05.03.03 | Forward Mechanical Structure | IN.P.014 | Hadron Endcap Tracking - SALSA FEB
6.10.06 | Hadronic Calorimetry | IN.P.015 | BTOF - Module Assembly
6.10.06.01 | Backward Hadronic Calorimetry | IN.P.016 | B0 - PbWO4 - 2cm x 2cm x 20cm with Readout
6.10.06.02 | Barrel Hadronic Calorimetry | IN.P.017 | B0 - AC-LGAD
6.10.06.03 | Forward Hadronic Calorimetry | IN.P.018 | FTOF - Sensor-ASIC Integration - Final Design
6.10.07 | Detector Magnets | IN.P.019 | pfRICH - Power Supply and Cables
6.10.08 | Electronics | IN.P.020 | RP/OMD - Sensors - Engineering Test Article
6.10.09 | DAQ / Computing | IN.P.021 | RP/OMD - Interlock System
6.10.09.01 | Data Acquisition (DAQ) | IN.P.022 | B0 - Mechanical Support Structure
6.10.09.02 | Slow Controls Integration | IN.P.023 | ZDC - Engineering Test Article - ZDC-HCAL
6.10.10 | Integration, Installation and Infrastructure | IN.P.024 | ZDC - EMCAL PbWO4 - Readout SiPM/APD/PMT
6.10.10.01 | Barrel Detector Structures | IN.P.025 | ZDC - HCAL Pb+Sci - Scintillators Readout
6.10.10.02 | Electron Endcap Structures | IN.P.026 | ZDC - HCAL Pb+Sci - Scintillators
6.10.10.03 | Hadron Endcap Structures | IN.P.027 | Low Q2 - Mechanical Frame Material - Both Stations
6.10.10.04 | Detector Infrastructure and Utilities Integration | IN.P.028 | Low Q2 - Cooling Sysytem
6.10.11 | IR Integration & Ancillary Detectors | IN.S | S Level In-Kind Procurement
6.10.11.01 | Roman Pots and Off-Momentum Detectors | IN.S.001 | Sensor - ASIC Integration - Design
6.10.11.02 | B0 Detectors | MGT | Management Consumables (Does not Obligate)
6.10.11.03 | Zero Degree Calorimeter | P | Standard Procurement =>$25k<$250K
6.10.11.04 | Low-Q2 Detectors | P.P.S200A | Workstations (group offices) - Prototype (Batch 1)
6.10.12 | Detector Pre-Ops & Commissioning | P.P253 | Vacuum Vessel (197 MHz Crab Production)
6.10.13 | Detector #2 Development | P.P258 | Instrumentation (394 MHz Crab Production)
6.10.14 | Polarimetry and Luminosity | P.P260 | Heat Exchangers (394 MHz Crab Production)
6.10.14.01 | e-Polarimetry | P.S001 | S #001 - Detector Tracking - Hadron Endcap GEM TRD
6.10.14.01.01 | Lepton Polarimetry in the Storage Ring | P.S002 | S #002
6.10.14.01.02 | Lepton Polarimetry in the RCS | P.S003 | S #003 - New PS - CAEN
6.10.14.02 | h-Polarimetry | P.S004 | HR Straight Sw Mag APS
6.10.14.02.01 | Hadron Polarimetry at IR-4 | P.S005 | S #005 - Test Cryostat
6.10.14.02.02 | Hadron Polarimetry at IR-6 | P.S006 | S #006 - Corr, Dipole & Qauds - CAEN
6.10.14.03 | Luminosity Monitor | P.S007 | D1 - Screen Prototype
6.11 | Infrastructure | P.S008 | Corrector & Injection Bump Supplies - Lambda PS
6.11.01 | Infrastructure Management & Engineering | P.S009 | 400MeV-RCS Quad/Dipole
6.11.01.01 | Infrastructure Management | P.S010 | S #010 - RCS-SR HV Corrector - CAEN
6.11.01.02 | Infrastructure Engineering | P.S011 | S #011 - Corrector & Injection Bump Supplies PDU for Lambda BTPs
6.11.01.03 | Infrastructure Construction Management & Inspection | P.S012 | S #012 - Corrector & Injection Bump Supplies Ext Intlk Panel BTP
6.11.01.04 | Infrastructure Services, Contracts and Permits | P.S013 | S #013 - Corrector & Injection Bump Supplies 1u PDU
6.11.02 | Civil Construction | P.S014 | S #014
6.11.02.01 | Site Preparation | P.S015 | S #015
6.11.02.02 | e Injection Support Building | P.S016 | D7 Large Screen OG & Thermal P1
6.11.02.02.01 | Energy Recovery LINAC Tunnel | P.S017 | Sensors (RP)
6.11.02.02.02 | Energy Recovery LINAC Support Building 1002H | P.S018 | S #018
6.11.02.02.03 | 400 MeV LINAC Support Building 1012D | P.S019 | D3 - SEY apparatus
6.11.02.03 | Cryogenic Buildings | P.S020 | Services - Power Cable Procurement
6.11.02.03.01 | 1002I - EIC Cryogenics Building | P.S021 | S #021
6.11.02.03.02 | 1006G - EIC 6 O'Clock Cryo Facility | P.S022 | Cooling System (pfRICH)
6.11.02.03.03 | 1010E - EIC 10 O'Clock Cryo Facility | P.S023 | D8 - Cryo Vacuum Test System/ Chamber
6.11.02.04 | RF Support Buildings | P.S024 | S #024
6.11.02.04.01 | 1010D - EIC 10 O'Clock DI Pumphouse | P.S025 | S #025
6.11.02.04.02 | 1010C - EIC RF Power Amplifier Building | P.S026 | D2 - RRR Apparatus - Cold Compressor
6.11.02.05 | Power Supply Buildings | P.S027 | D1 - Screen Prototype - Flange cutting and welding
6.11.02.05.01 | 1001A - EIC 1 O-Clock Power Supply Building | P.S028 | S #028
6.11.02.05.02 | 1003A - EIC 3 O-Clock Power Supply Building | P.S029 | S #029
6.11.02.05.03 | 1005T - EIC 5 O-Clock Power Supply Building | P.S030 | B0 - Calorimeter SiPM/APD
6.11.02.05.04 | 1007A - EIC 7 O-Clock Power Supply Building | P.S031 | S #031
6.11.02.05.05 | 1009A - EIC 9 O-Clock Power Supply Building | P.S032 | S #032
6.11.02.05.06 | 1011A - EIC 11 O-Clock Power Supply Building | P.S033 | S #033
6.11.02.06 | Kicker Buildings | P.S034 | Forward EMCal Engineering Design Verification
6.11.02.06.01 | 1004G - Kicker Power (A-103, S-103) | P.S035 | S #035
6.11.02.06.02 | 1012C - EIC Kicker Power Supply Building | P.S036 | First and Second Station Readout for Si, Cal FE, HV/LV/etc Procurement (Low Q2)
6.11.02.07 | Tunnel Modifications | P.S037 | D2 - RRR Apparatus - Pumping System
6.11.02.08 | Access Roads, Foundations, Paving and Sitework | P.S038 | S #038
6.11.02.08.01 | Access Roads, Paving and Sitework | P.S039 | S #039
6.11.02.08.02 | Concrete Foundations for Externally Mounted Equipment | P.S040 | S #040
6.11.02.09 | RHIC Tunnel HVAC System | P.S041 | Electron Endcap EMCal Engineering Design Verification
6.11.03 | Electrical Power Systems | P.S042 | S #042
6.11.03.01 | Main Substation #9 & #10 | P.S043 | S #043
6.11.03.02 | Overhead 13.8kV & Switching | P.S044 | S #044
6.11.03.03 | Unit Substations | P.S045 | S #045
6.11.03.04 | Motor Control & Load Centers | P.S046 | S #046
6.11.03.05 | Standby Power | P.S047 | S #047
6.11.03.06 | Cable Plant | P.S048 | S #048
6.11.03.07 | 138kV Substation | P.S049 | S #049
6.11.04 | Cooling Systems | P.S050 | S #050
6.11.04.01 | Chilled Water Systems | P.S051 | S #051
6.11.04.02 | Closed Cooling Water Systems | P.S052 | S #052 - PID - Barrel PID - hpDIRC
6.11.04.03 | Tower Water Systems | P.S053 | S #053 - SHC Chicane / New Busbar Cryoline
6.11.04.04 | Compressed Air System | P.S054 | S #054 - SHC Chicane / Interconnect Space
6.12 | Pre-Operations | P.S055 | D1 - Screen Prototype - Beam screen installation validation
6.12.01 | Pre-Operations Planning and Management | P.S056 | S #056 - RCS Injection Pulsed Bump - Power Supplies
6.12.01.01 | Pre-Operations Management - BNL | P.S057 | Barrel EMCal Pre-production units
6.12.01.02 | Pre-Operations Management - TJ | P.S058 | S #058 - Hadron Polarimetry at IR
6.12.02 | Systems Commissioning | P.S059 | S #059 - Hadron Polarimetry at IP12
6.12.02.01 | MCR Systems Commissioning | P.S060 | Lepton Polarimetry - Polarization Optics - RCS
6.12.02.02 | Electron Pre-Injector Systems Commissioning | P.S061 | S #061 - Luminosity Monitor
6.12.02.03 | Electron Injector (RCS) Systems Commissioning | P.S062 | Lepton Polarimetry - Calorimeter Infrastructure - ESR
6.12.02.04 | Hadron Ring (HSR) Systems Commissioning | P.S065 | S #065 Detector Interface Vacuum Development - Prototype Detector Chamber - Funding Phase 2
6.12.02.05 | Electron Storage Ring (ESR) Systems Commissioning | P.S066 | S #066 - ESR Injection Pulsed Bump Power Supplies
6.12.02.06 | SHC Systems Commissioning | P.S067 | RCS CCMs - DCCT System - Sensor Procurement
6.12.03 | Beam Commissioning | P.S068 | S #068 - FCT Material
6.12.03.01 | Electron Pre-Injector Beam Commissioning | P.S069 | S #069 - Tune Monitor - Construction - Non Labor
6.12.03.02 | Electron Injector (RCS) Beam Commissioning | P.S070 | NOT USED
6.12.03.03 | Hadron Ring (HSR) Beam Commissioning | P.S071 | S #071 - BPM Pick-up -Button & Housing Procurement - Material
6.12.03.04 | Electron Storage Ring (ESR) Beam Commissioning | P.S072 | S #072 - BPM Electronics - Vendor Fabrication
6.12.03.05 | Colliding Beam Commissioning Without and With Detector | P.S073 | S #073 - BPM System - Miscellaneous Materials
6.12.03.06 | SHC Beam Commissioning | P.S074 | S #074 - ICT Material
6.12.04 | Spares | P.S075 | S #075 - FCT Material
6.L1 | Level 1 Milestones | P.S076 | S #076 - BPM Electronics - Module procurement (Material)
6.L2 | Level 2 Milestones | P.S077 | S #077 - BPM Pick-up -Button & Housing Procurement - Material
6.L3 | Level 3 Milestones | P.S078 | S #078 - BPM System - Miscellaneous Materials
6.12.02.06 | SHC Systems Commissioning | P.S079 | S #079 - System Global - Materials
6.12.03 | Beam Commissioning | P.S080 | S #080 - Faraday Cup Electronic System - Material
6.12.03.01 | Electron Pre-Injector Beam Commissioning | P.S081 | S #081 - 400 MeV Current and Chargers - FCT Material
6.12.03.02 | Electron Injector (RCS) Beam Commissioning | P.S082 | S #082 - System Global - Construction
6.12.03.03 | Hadron Ring (HSR) Beam Commissioning | P.S083 | S #083 - Profile Monitors - Construction - Non Labo
6.12.03.04 | Electron Storage Ring (ESR) Beam Commissioning | P.S084 | S #084 - Emittance Slit - Construction - Non Labor
6.12.03.05 | Colliding Beam Commissioning Without and With Detector | P.S085 | S #085 - Wire Scanner - Construction - Non Labor
6.12.03.06 | SHC Beam Commissioning | P.S086 | S #086 - Beam Loss Monitors - Materials
6.12.04 | Spares | P.S087 | 3 MeV Mott Polarimeter - Vendor Fabrication
6.L1 | Level 1 Milestones | P.S088 | S #088 - Spin Rotator - Vendor Fabrication
6.L2 | Level 2 Milestones | P.S089 | S #089 - Wien Filter - Vendor Fabrication
6.L3 | Level 3 Milestones | P.S090 | S #090 - 20keV Mott polarimeter - Vendor Fabrication
|  | P.S091 | S# 091 - BPM System - Procure Prototype components (various
|  | P.S092 | S #092 - ESR Current and Charge Monitors - DCCT Material
|  | P.S093 | S #093 - ESR Current and Charge Monitors - FCT Material
|  | P.S094 | S #094 - Tune Monitor - Construction - Non Labor
|  | P.S095 | ESR Xray - Camera and Optics
|  | P.S096 | ESR Xray - Optical Transport
|  | P.S097 | S #097 - Beam Loss Monitors - Materials
|  | P.S098 | S #098 - Sleeve Procurement - Materia
|  | P.S099 | S #099 - BPM/Bellows assemblies - Material
|  | P.S100 | S #100 - BPM/Bellows Triplet assemblies - Material
|  | P.S1000 | 197MHz DVC - EBW Tooling
|  | P.S1001 | Detector Solenoid - Vendor Design - After Detailed 90% Design
|  | P.S1002 | HJET (TGA) Mass Spectrometer
|  | P.S1003 | pCarbon Materials - cables, connectors, installation
|  | P.S1004 | Electron Endcap EMCal - Detailed Design Mechanics and Integration - Material
|  | P.S1005 | BLA - SiC-35 Cylindrical Shell
|  | P.S1006 | BLA - Water Cooled Housing
|  | P.S1007 | hpDIRC - Photosensors - Test Article - Large Area - Engineering Run
|  | P.S1008 | ZDC - p-veto - Si Small-Pad Readout
|  | P.S1009 | eRD102 - Duke University - Research/Developement/Design
|  | P.S101 | S #101 - Electro-Optical Wall Current Monitor Material - Construction
|  | P.S1010 | eRD109 - Associacao Do Laboratorio - Research/Developement/Design
|  | P.S1011 | eRD109 - Associacao Do Laboratorio - Research/Developement/Design
|  | P.S1012 | ESR Profile
|  | P.S1013 | Design Verification Chamber
|  | P.S1014 | Design Verification Bellows
|  | P.S1015 | Cold bore inspection Mole
|  | P.S1016 | Design Verification Flange Cutting and Welding
|  | P.S1017 | Design Verification Installation Tooling
|  | P.S1018 | HSR BPM Cryo Cable Heat Sink
|  | P.S1019 | HSR BPM Electronic Design - Rack Hardware
|  | P.S102 | S #102 - IPM Upgrade - Material
|  | P.S1020 | HSR BPM Electronic Design - Filters & Attenuators
|  | P.S1021 | RF Workstations (Engineering Level Systems Computers with Accessories)
|  | P.S1022 | FTOF - Cooling - PED
|  | P.S1023 | FTOF - Integration - PED
|  | P.S1024 | FTOF - Mechanical - PED
|  | P.S1025 | BTOF - Cooling - PED
|  | P.S1026 | BTOF - Integration - PED
|  | P.S1027 | BTOF - Mechanical - PED
|  | P.S1028 | BTOF - Sensor - ASCI Clock Development
|  | P.S1029 | BPM Thermal Cycle Test Equipment
|  | P.S103 | S #103 - Head-Tail Pick-up - Material
|  | P.S1030 | EIC Instrumentation Automated Test Equipment
|  | P.S1031 | BPM 4-Port VNA Test Equipment
|  | P.S1032 | FNAL RCS Dpole Magnet Design
|  | P.S1033 | CERN - VTRX+ Optical Tranceiver Module
|  | P.S1034 | Forward LFHCAL - Detector - HV Cable and Connectors
|  | P.S1035 | Electron Endcap Tracking - SALSA FEB
|  | P.S1036 | Hadron Endcap Tracking - SALSA FEB
|  | P.S1037 | B1pF Collaring Press Parts (Material & Fabrication)
|  | P.S1038 | B1pF Coil Curing Center Posts
|  | P.S1039 | Design of LFHCal 8M module electrical components
|  | P.S104 | S #104 - ARTUS Upgrade - Material
|  | P.S1040 | ESR BPM Electronic Design - Rack Hardware
|  | P.S1041 | BTOF - Service Hybrid - Final Design
|  | P.S1042 | BTOF - Module
|  | P.S1043 | BTOF - Module Assembly
|  | P.S1044 | FTOF - Sensor-ASIC Integration - Final Design
|  | P.S1045 | RCS P&EM - Ancillary Equipment
|  | P.S1046 | RCS P&EM - Electronic System
|  | P.S1047 | RCS P&EM - Kicker Power Supply
|  | P.S1048 | Actuals Adjustment - EIPDTM - Nonlabor
|  | P.S1049 | DVU CM-01 Couplers: Waveguide/Doorknob: Fabrication Materials
|  | P.S105 | S #105 - BBQ Upgrade - Material
|  | P.S1050 | DVU CM-02 Couplers: Waveguide/Doorknob: Fabrication Materials
|  | P.S1051 | DVU CM-03 Couplers: Waveguide/Doorknob: Fabrication Materials
|  | P.S1052 | DVU CM-04 Couplers: Waveguide/Doorknob: Fabrication Materials
|  | P.S1053 | DVU CM-01 Couplers: Window Assembly: Fabrication Materials
|  | P.S1054 | DVU CM-02 Couplers: Window Assembly: Fabrication Materials
|  | P.S1055 | DVU CM-03 Couplers: Window Assembly: Fabrication Materials
|  | P.S1056 | DVU CM-04 Couplers: Window Assembly: Fabrication Materials
|  | P.S1057 | DVU CM-01 Couplers: Window Shipping Vessel: Fabrication Materials
|  | P.S1058 | DVU CM-02 Couplers: Window Shipping Vessel: Fabrication Materials
|  | P.S1059 | DVU CM-03 Couplers: Window Shipping Vessel: Fabrication Materials
|  | P.S106 | S #106 - HF Schottky Upgrade - Material
|  | P.S1060 | DVU CM-04 Couplers: Window Shipping Vessel: Fabrication Materials
|  | P.S1061 | DVU CM-01 Couplers: Waveguide Tuners
|  | P.S1062 | DVU CM-02 Couplers: Waveguide Tuners
|  | P.S1063 | DVU CM-03 Couplers: Waveguide Tuners
|  | P.S1064 | DVU CM-04 Couplers: Waveguide Tuners
|  | P.S1065 | ESR CCMs - Electronic System Procurement
|  | P.S1066 | ESR CCMs - Ancillary Equipment Procurement
|  | P.S1067 | B0 - ASIC Read Out - Engineering Test Article
|  | P.S1068 | B0 - Mechanical Support Structure - Materials
|  | P.S1069 | ZDC - EMCAL PbWO4 - Crystals
|  | P.S107 | S #107 - LF Schottky Upgrade - Material
|  | P.S1070 | RCS SLM - Transverse Cameras
|  | P.S1071 | RCS SLM - Optical Transport
|  | P.S1072 | RCS SLM - Optics and Suport Equipment
|  | P.S1073 | RCS SLM - Electronics Equipment
|  | P.S1076 | ESR SLM - Streak Camera
|  | P.S1077 | ESR SLM - Transverse Cameras
|  | P.S1078 | ESR SLM and Xray - Electronics Equipment
|  | P.S1079 | ESR SLM and Xray - Optics and Support Equipment
|  | P.S108 | NOT USED
|  | P.S1080 | Low Q2 - Cooling Sysytem
|  | P.S1081 | Low Q2 - Interlock/Alarm System
|  | P.S1082 | ESR BPM - Electronic Design - Front Panel
|  | P.S1083 | RP/OMD - Sensors - Engineering Test Article
|  | P.S1084 | RP/OMD - POT - Moving Stages and Support Frame
|  | P.S1085 | RP/OMD - Interlock System
|  | P.S1086 | ZDC - EMCAL PbWO4 - Readout SiPM/APD/PMT
|  | P.S1087 | ZDC - HCAL Pb+Sci - Scintillators Readout
|  | P.S1088 | Detector R&D - eRD107 - Yale
|  | P.S1089 | dRICH - LV Circuit Board - Power Supplies
|  | P.S109 | S #109 - Beam Loss Monitors - Materials
|  | P.S1090 | 197MHz FA HOMs & Field Antenna
|  | P.S1091 | 591 5 Cell Tuner Test Hardware
|  | P.S1092 | Forward pECAL - Power Supply
|  | P.S1093 | OUTER Barrel HCAL - FEB - Readout Electronics
|  | P.S1094 | Forward LFHCAL - LV Circuit Board Power Supply
|  | P.S1095 | RCS CCMs - Ancillary Equipment
|  | P.S1096 | BTOF - CTTL AC-LGAD - Service Hybrid - Power PCB - Engineering Article - Fab and Assembly
|  | P.S1097 | TOF LV Power Supply Production - BTOF - Supply & Bins
|  | P.S1098 | TOF LV Power Supply Production - FTOF - Supply & Bins
|  | P.S1099 | TOF LV Power Supply Production - FTOF - Power Board
|  | P.S110 | S #110 - BPM Pick-up - Prototype Components (various)
|  | P.S1100 | Low Q2 - Shipping
|  | P.S1101 | TOF HV Power Supply Production - FTOF - HV Modules
|  | P.S1102 | TOF Patch Panel & Cable Production
|  | P.S1103 | FTOF LV Cable Feed (5k)
|  | P.S1104 | FTOF - FTTL AC-LGAD - Service Hybrid & Module - Engineering Article - Components
|  | P.S1105 | FTOF - FTTL AC-LGAD - Service Hybrid & Module - Engineering Article - Fab & Asy
|  | P.S1106 | RCS Magnet Dipoles - Magnet Measurement Stand
|  | P.S1107 | HCAL Insert - FEB - Readout Electronics
|  | P.S1108 | ESR Vacuum Pump Connectors
|  | P.S1109 | ESR Vacuum Pump Cables
|  | P.S111 | S #111 - BPM Electronics - Module procurement
|  | P.S1110 | RCS Hardware and Seals
|  | P.S1111 | Movable ESR Collimators - Injection Collimator/Mask
|  | P.S1112 | RCS Vacuum Cables and Connectors
|  | P.S1113 | ESR Vacuum Racks
|  | P.S1114 | ESR Water Cooling Lines
|  | P.S1115 | Roughing Valves
|  | P.S1116 | ESR Vacuum Cables and Connectors
|  | P.S1117 | ESR Roughing Valves
|  | P.S1118 | Engineering Validation Unit Solenoids
|  | P.S1119 | Engineering Validation Unit Pumping Stations
|  | P.S112 | S #112 - Orbit Feedback - Procurement (material)
|  | P.S1120 | Engineering Validation Unit Machined Parts
|  | P.S1121 | Engineering Validation Unit Vacuum/gas injection equipment
|  | P.S1122 | Arc Beam Screen Laser Welding Test
|  | P.S1123 | Cryogenic leak test apparatus
|  | P.S1124 | Beam Dynamics Support - IEWO
|  | P.S1125 | Design Verification Installation Tooling
|  | P.S1126 | Design Verification Flange Cutting and Welding
|  | P.S1127 | ESR Pre Assembly Consumables
|  | P.S1128 | 197MHz Crab Pole Equipment
|  | P.S1129 | EIC Instr. Ancillary Test Equipment
|  | P.S113 | S #113 - BLM Material - Pin Diode Loss Monitor
|  | P.S1130 | Roman Pots - AC-LGAD - Service Hybrid & Module - Production - Fab and Asy
|  | P.S1131 | CERN - lpGBT Transceiver ASIC
|  | P.S1132 | B0 Tracker - AC-LGAD - Service Hybrid & Module - Engineering Article - Components
|  | P.S1133 | B0 Tracker - AC-LGAD - Service Hybrid & Module - Production - Fab & Asy
|  | P.S1134 | ESR Magnet Measurement Stand (ANL)
|  | P.S1135 | ESR Magnet Measurement Bench
|  | P.S1136 | Pin-Diode BLMs
|  | P.S1137 | Diamond Detector BLMs
|  | P.S1138 | ESR Dipole Transport Iron Material to Vendors
|  | P.S1139 | HJET Holding Field Modification
|  | P.S114 | S #114 - BLM Material - RHIC Loss Monitor
|  | P.S1140 | HJET Target Chamber Modification
|  | P.S115 | S #115 - Instrumentation Removal Sectors 2, 7, 8, 12 - Material
|  | P.S116 | S #116 - Detector Interface Vacuum Development - Adjustable Collimator
|  | P.S117 | S #117 - RCS Vacuum Pre-Tunnel Assembly - Procurement
|  | P.S118 | S #118 - ESR Vacuum Pre-Tunnel Assembly - Procurement
|  | P.S119 | S #119 - HR Inj-Sys Upgrade Vacuum - Valves and Pumps
|  | P.S120 | S #120 - DC-Gun LINAC Vacuum - I&C Systems
|  | P.S121 | S #121 - DC-Gun LINAC Vacuum - Valves and Pumps
|  | P.S122 | 4k Distribution B&P 1002 IR02 Lead Pots Raw Materials & Current Leads
|  | P.S123 | 4k Distribution B&P 1004 IR04 Lead Pots Raw Materials & Current Leads
|  | P.S124 | 4k Distribution B&P 1006 IR06 Lead Pots Raw Materials & Current Leads
|  | P.S125 | 4k Distribution B&P 1010 IR10 Lead Pots Raw Materials & Current Leads
|  | P.S126 | 4k Distribution B&P 1012 IR12 Lead Pots Raw Materials & Current Leads
|  | P.S127 | Heaters 480v cal rods and low voltage flexible kapton
|  | P.S128 | Cryomagnetic Level Controllers
|  | P.S129 | Acopian 28VPower Supplies, and other P.S.
|  | P.S130 | 2K Satellite Plant Aux Systems - Guard Vacuum Systems
|  | P.S131 | 2K Ambient Air Heat Exchanger
|  | P.S132 | TJ RF Facilities Bake Box
|  | P.S133 | TJ RF Facilities Fumehood
|  | P.S134 | TJ RF Facilities Ultrasonic Cleaning Station
|  | P.S135 | S #135 - RF 197 Crab Misc. Parts
|  | P.S136 | S #136 - RF 197 Crab End Cans
|  | P.S137 | S #137 - RF 197 Crab Thermal Shield
|  | P.S138 | S #138 - RF 197 Crab Beamline Gate Valves
|  | P.S139 | Crab Cavity Material (197 MHz Crab R&D)
|  | P.S140 | S #140 - Cavity Handling Tooling (197 MHz Crab R&D)
|  | P.S141 | S #141 - HOMs Material (197 MHz Crab R&D)
|  | P.S142 | S #142 - RRR Niobium (591MHz 1-Cell R&D)
|  | P.S143 | S #143 - First Article Beamline Gate Valves (197 MHz Crab 1st Article)
|  | P.S144 | S #144 - Rail Assembly Tooling (197 MHz Crab 1st Article)
|  | P.S145 | S #145 - First Article Thermal Shield (197 MHz Crab 1st Article)
|  | P.S146 | S #146 - First Article End Cans (197 MHz Crab 1st Article)
|  | P.S147 | S #147 - First Article Misc. Parts (197 MHz Crab 1st Article)
|  | P.S148 | First Article Cavities (591 1-Cell 1st Article)
|  | P.S150 | First Article Beamline Gate Valves (591 1-Cell 1st Article)
|  | P.S152 | First Article Vacuum Vessel (591 1-Cell 1st Article)
|  | P.S153 | First Article Misc. Parts (591 1-Cell 1st Article)
|  | P.S154 | S #154 - Tuner Frames and Thermal Straps (591 1-Cell Production CMs)
|  | P.S155 | S #155 - Tuner Frames and Thermal Straps (591 5-Cell Production CMs)
|  | P.S156 | S #156 - Helium Vessel (1773 5-Cell)
|  | P.S157 | S #157 - Thermal Shield (1773 5-Cell)
|  | P.S158 | S #158 - Spaceframes with Thermal Shield Assy. (1773 5-Cell)
|  | P.S159 | S #159 - Heat Exchangers (1773 5-Cell)
|  | P.S160 | S #160 - Saddles and Stands (1773 5-Cell)
|  | P.S161 | S #161 - Instrumentation (1773 5-Cell)
|  | P.S162 | S #162 - Tuner Frames and Thermal Straps (394MHz Crab Production)
|  | P.S163 | S #163 - Mag Shields (394MHz Crab Production)
|  | P.S164 | S#164 - FY25 Offsite Storage
|  | P.S165 | S#165 - FY26 Offsite Storage
|  | P.S166 | S#166 - FY27 Offsite Storage
|  | P.S167 | S#167 - FY28 Offsite Storage
|  | P.S168 | S#168 - FY29 Offsite Storage
|  | P.S169 | APS Magnet Quad Rebuild Parts and Fixtures
|  | P.S170 | S #170 - RCS Current and Charge Monitors
|  | P.S171 | Networking Optics
|  | P.S172 | Networking Fibers and Support
|  | P.S173 | Common Platform Carrier Components
|  | P.S174 | Common Platform Daughtercard Components
|  | P.S175 | Common Platform - Timing Generation and Distribution
|  | P.S176 | Common Platform - Machine Protection Distribution
|  | P.S177 | PLCs - Safety rated
|  | P.S178 | Lab Test Equipment
|  | P.S179 | Lab Tools (wiring equipment)
|  | P.S180 | Instrumentation - GigE cameras with ext trigger
|  | P.S181 | Instrumentation - Motion stages and Motion controllers
|  | P.S182 | Controls Misc Equipment
|  | P.S183 | Operations Servers
|  | P.S184 | ML Platform
|  | P.S185 | BPM Electronics - Module (Material)
|  | P.S186 | BPM Pick-up - Button & Housing (Material)
|  | P.S187 | BPM System Miscellaneous Materials
|  | P.S188 | 400 MeV Current & Chargers - FCT Material
|  | P.S189 | System Global - Materials
|  | P.S190 | Faraday Cup - Electronic System
|  | P.S191 | BLM Material - Pin Diode Loss Monitor
|  | P.S192 | BLM Material - RHIC Loss Monitor
|  | P.S193 | Head-Tail Pick-Up
|  | P.S194 | Artus Upgrade - Material
|  | P.S195 | BBQ Upgrade - Material
|  | P.S196 | HF Schottky Upgrade - Material
|  | P.S197 | LF Schottky Upgrade - Material
|  | P.S198 | Compute Servers (compile/test, project, thin client support) - Prototype
|  | P.S198.A | Compute Servers (compile/test, project, thin client support) - Prototype (Batch 1)
|  | P.S198.B | Compute Servers (compile/test, project, thin client support) - Prototype (Batch 2)
|  | P.S199 | Network Storage - Prototype
|  | P.S200 | Workstations (group offices) - Prototype
|  | P.S200.A | Workstations (group offices) - Prototype (Batch 1)
|  | P.S200.B | Workstations (group offices) - Prototype (Batch 2)
|  | P.S201 | Thin Clients (lab, field locations) - Prototype
|  | P.S202 | Networking - Switches - Prototype
|  | P.S202.A | Networking - Switches - Prototype (Batch 1)
|  | P.S202.B | Networking - Switches - Prototype (Batch 2)
|  | P.S203 | Networking - Racks - Prototype
|  | P.S203.A | Networking - Racks - Prototype (Batch 1)
|  | P.S203.B | Networking - Racks - Prototype (Batch 2)
|  | P.S204 | Common Platform - Electronics Components - Prototype
|  | P.S205 | Common Platform - Chassis and support equipment - Prototype
|  | P.S205.A | Common Platform - Chassis and support equipment - Prototype (Batch 1)
|  | P.S205.B | Common Platform - Chassis and support equipment - Prototype (Batch 2)
|  | P.S206 | Common Platform - Timing Generation & Distribution - Prototype
|  | P.S207 | PLCs - Generic Applications & Safety Rated - Prototype
|  | P.S208 | Lab Test Equipment (Scopes, DSAs, meters, precision PS, board analysis tools) - Prototype
|  | P.S209 | Workstations (group offices) - Implementation
|  | P.S210 | Thin Clients (lab, field locations) - Implementation
|  | P.S211 | Networking - Optics - Implementation
|  | P.S212 | Networking - Fibers and support equipment - Implementation
|  | P.S213 | Networking - Cables - Intra-rack - Implementation
|  | P.S214 | Common Platform - Racks (lab) - Implementation
|  | P.S215 | Common Platform - Timing Generation & Distribution - Implementation
|  | P.S216 | Common Platform - Machine Protection Distribution - Implementation
|  | P.S217 | UPSs (critical systems) - Implementation
|  | P.S218 | AC Reset modules - Implementation
|  | P.S219 | Lab Test Eqpt (Scopes, DSAs, meters, precision PS, board analysis tools) - Implementation
|  | P.S220 | Operations Servers (project) - Implementation
|  | P.S221 | ML Platform (HPC needs for project) - Implementation
|  | P.S222 | Networking - Cables - Inter-rack - Implementation
|  | P.S225 | Accelerator Developemet and Support
|  | P.S226 | Harmonic Injection Kicker - First Article RF Source
|  | P.S227 | Harmonic Injection Kicker - 148MHz Cavity Fabrication
|  | P.S228 | Harmonic Injection Kicker - RF Power Distribution Network Hardware
|  | P.S229 | Harmonic Injection Kicker - 148 MHz Cavity Material and Parts
|  | P.S230 | Harmonic Injection Kicker - 296MHz Cavity Fabrication
|  | P.S231 | Harmonic Injection Kicker - 296MHz Cavity Material and Parts
|  | P.S232 | Harmonic Injection Kicker - LLRF First Article Chasis Components
|  | P.S233 | Harmonic Injection Kicker - Tuner
|  | P.S234 | Harmonic Injection Kicker - Power Coupler
|  | P.S235 | Harmonic Injection Kicker - Beamline Hardware
|  | P.S236 | Transfer Lines Magnets
|  | P.S237 | Magnet Measurement Stand (ESR-APS Quad)
|  | P.S238 | Forward EMCal Epoxy
|  | P.S239 | Forward EMCal Meshes
|  | P.S240 | Forward EMCal Block Pack&Ship
|  | P.S241 | Backward EMCal Photosensor Mounting Boards
|  | P.S242 | Backward (Electron Endcap) EMCal Scintillator Wrapping Material (VM2000)
|  | P.S243 | Forward (Hadronic Endcap) EMCal Photosensor Mounting Boards
|  | P.S244 | Detector Mechanical Components, Machining, Fabrication: Cooling plates
|  | P.S245 | Detector Mechanical Components, Machining, Fabrication: Temperature control system (chiller and fans, etc.)
|  | P.S246 | Detector Mechanical Components, Machining, Fabrication: Light Monitoring system
|  | P.S247 | Barrel EMCal - Barrel Pb/SciFi absorber - Material Pack and Ship
|  | P.S248 | Barrel EMCal - Scintillator wrapping material (VM2000)
|  | P.S249 | Barrel EMCal - Light Guides
|  | P.S250 | Forward EMCal - Cooling system
|  | P.S251 | Forward EMCal - Light Guide Blocks
|  | P.S252 | Forward EMCal - Assembly Equipment
|  | P.S253 | Detector Infrastructure - Barrel HCal
|  | P.S254 | Detector Infrastructure - Cradle
|  | P.S255 | Detector Infrastructure - Outer MGPD
|  | P.S256 | Detector Infrastructure - AC LGAD
|  | P.S257 | Detector Infrastructure - FE AC LGAD
|  | P.S258 | Detector Infrastructure - Inner MGPD
|  | P.S259 | Detector Infrastructure - Si Disks
|  | P.S260 | Detector Infrastructure - Silicon Sagita
|  | P.S261 | Detector Infrastructure - Silicon Vertex
|  | P.S262 | Detector Infrastructure - DIRC
|  | P.S263 | UPS for IR02,IR10, IR06 Satellite Locations
|  | P.S264 | Software Licenses (FPGA, Database, Verison Control, Application/ Analysis Tools)
|  | P.S265 | HSR Collimators - Vacuum Mods for Momentum Collimator
|  | P.S266 | Common Platform - PS Controller - Prototype
|  | P.S267 | Emittance Slit
|  | P.S268 | Beam Loss Monitors
|  | P.S269 | ESR Current and Charge Monitors - FCT
|  | P.S270 | Instrumentation Removal Sectors 2, 7, 8,12
|  | P.S271 | BPM System - Misc Materials
|  | P.S272 | TL Current and Charge Monitors - ICT
|  | P.S273 | TL Current and Charge Monitors - FCT
|  | P.S274 | Gun Electrodes and Feedthru - Atals
|  | P.S275 | Gun Electrodes and Feedthru - MPF
|  | P.S276 | Hadron Injection Pulse Generator
|  | P.S277 | IR PS - PDU+DCCT Chassis+PSC/PSI/REG BTPs
|  | P.S278 | Quench Detection QD
|  | P.S279 | AC, Control & Interlock cables & Cable trays
|  | P.S280 | ATR Quad/Dipole Lambda - PDU+DCCT Chassis+PSC/PSI/REG BTPs
|  | P.S281 | Quench Detection
|  | P.S282 | AC & Control Cable
|  | P.S283 | Instrument Air Systems
|  | P.S300 | HSR Vacuum Beam Screen Profile
|  | P.S301 | HR Straight Sw Mag APS
|  | P.S302 | Cooler R&D Miscellaneous Materials
|  | P.S303 | Quench Protection
|  | P.S304 | Vacuum - chamber spools
|  | P.S305 | Corrector &Injection Bump Supplies - Lambda PS
|  | P.S306 | ATR Dipole
|  | P.S307 | Electron Endcap HCal Cradles
P.S308
|  | P.S309 | Electron Endcap HCal SiPMs
|  | P.S310 | Electron Endcap HCal Return Flux Steel
|  | P.S311 | Corrector & Injection Bump Supplies Internal Rack Wire
|  | P.S312 | Barrel HCal SiPMs
|  | P.S313 | Barrel HCal SiPM boards
|  | P.S314 | Corrector & Injection Bump Supplies Rack
|  | P.S315 | Shipping Support (591 1-Cell 1st Art)
|  | P.S316 | First Article Helium Vessel (591 1-Cell 1st Art)
|  | P.S317 | Cavity String Support Tooling (591 1-Cell 1st Art)
|  | P.S318 | First Article Mag Shields (591 1-Cell 1st Art)
|  | P.S319 | First Article Thermal Shield (591 1-Cell 1st Art)
|  | P.S320 | First Article Spaceframe with Thermal Shield Assembly (591 1-Cell 1st Art)
|  | P.S321 | First Article Heat Exchangers (591 1-Cell 1st Art)
|  | P.S322 | First Article Saddles and Stands (591 1-Cell 1st Art)
|  | P.S323 | First Article Instrumentation (591 1-Cell 1st Art)
|  | P.S324 | (New Code Value)
|  | P.S325 | (New Code Value)
|  | P.S326 | PLC chassis for IR02, IR10, IR6 satellites locations
|  | P.S327 | PLC chassis for SRF cryomodules
|  | P.S328 | PLC Software
|  | P.S329 | 4K Distribution B&P - Materials 1002 IR02 Current leads circuits
|  | P.S330 | 4K Distribution B&P - Materials 1004 IR04 Current leads circuits
|  | P.S331 | 4K Distribution B&P - Materials 1006 IR06 Current leads circuits
|  | P.S332 | 4K Distribution B&P - Materials 1010 IR10 Current leads circuits
|  | P.S333 | 4K Distribution B&P - Materials 1012 IR12 Current leads circuits
|  | P.S334 | Cryo Installation -1006
|  | P.S335 | Cryo Installation -1004
|  | P.S336 | Cryo Installation -1002
|  | P.S337 | Cryo Installation -1010
|  | P.S338 | Cryo Installation -1012
|  | P.S339 | Cryo temperature sensors for new cryo distribution and for HSR(RHIC VJR) mod
|  | P.S340 | Alicat low DP flow controllers
|  | P.S341 | Wika (Tecsis) pressure transducers
|  | P.S342 | Solenoid Valves and valve positioners
|  | P.S343 | Thermal Specific Heat (MKS) flow controllers
|  | P.S344 | Vacuum controllers and gauges & high voltage
|  | P.S345 | Cable Trays & Conduits & associated mounting hardware
|  | P.S346 | Lakeshore Cryogenic Sensor Controllers
|  | P.S347 | Rack Parts Active Beam Screen
|  | P.S348 | Cable Trays/Supports/ Share Active Beam Screen
|  | P.S349 | Cable and Cable Tray
|  | P.S350 | Path Length Variation Magnets
|  | P.S351 | Girder Hardware Fabrication
|  | P.S352 | RF-HR-1-PWR
|  | P.S352.A | First Article - RF-HR-1-PWR
|  | P.S352.B | Production - RF-HR-1-PWR
|  | P.S353 | RF-RCS-2-CTRL
|  | P.S353.A | First Article - RF-RCS-2-CTRL
|  | P.S353.B | Production - RF-RCS-2-CTRL
|  | P.S354 | RF-RCS-3-CTRL
|  | P.S354.A | First Article - RF-RCS-3-CTRL
|  | P.S354.B | Production - RF-RCS-3-CTRL
|  | P.S355 | DW Magnet - Q2eF - Coil Assembly Material
|  | P.S356 | DW Magnet - Q2eF - Cold Mass Assembly Material
|  | P.S357 | DW Magnet - Q2eF - Vertical Cold Test Material
|  | P.S358 | DW Magnet - Q1eR - Coil Assembly Material
|  | P.S359 | DW Magnet - Q1eR - Cold Mass Assembly Material
|  | P.S360 | DW Magnet - Q1eR - Vertical Cold Test Material
|  | P.S361 | DW Magnet - Q2eR - Coil Assembly Material
|  | P.S362 | DW Magnet - Q2eR - Cold Mass Assembly Material
|  | P.S363 | DW Magnet - Q2eR - Vertical Cold Test Material
|  | P.S364 | DW Magnet - B0ApF - Coil Assembly Material
|  | P.S365 | DW Magnet - B0ApF - Cold Mass Assembly Material
|  | P.S366 | DW Magnet - B0ApF - Vertical Cold Test Material
|  | P.S367 | DW Magnet - B0pF - Dipole - Coil Assembly Material
|  | P.S368 | DW Magnet - B0pF - Dipole - Cold Mass Assembly Material
|  | P.S369 | DW Magnet - B0pF - Dipole - Vertical Cold Test Material
|  | P.S370 | DW Magnet - B0pF - Quad - Coil Assembly Material
|  | P.S371 | DW Magnet - B0pF - Quad - Cold Mass Assembly Material
|  | P.S372 | DW Magnet - B0pF - Quad - Vertical Cold Test Material
|  | P.S373 | DW Magnet - Q0eF - Coil Assembly Material
|  | P.S374 | DW Magnet - Q0eF - Cold Mass Assembly Material
|  | P.S375 | DW Magnet - Q0eF - Vertical Cold Test Material
|  | P.S376 | DW Magnet - Q1ApR - Coil Assembly Material
|  | P.S377 | DW Magnet - Q1ApR - Cold Mass Assembly Material
|  | P.S378 | DW Magnet - Q1ApR - Vertical Cold Test Material
|  | P.S379 | DW Magnet - Q1BpR - Coil Assembly Material
|  | P.S380 | DW Magnet - Q1BpR - Cold Mass Assembly Material
|  | P.S381 | DW Magnet - Q1BpR - Vertical Cold Test Material
|  | P.S382 | DW Magnet - Q2BpR - Vertical Cold Test Material
|  | P.S383 | DW Magnet - Hadron SQ1 - Coil Assembly Material
|  | P.S384 | DW Magnet - Hadron SQ1 - Cold Mass Assembly Material
|  | P.S385 | DW Magnet - Hadron SQ1 - Vertical Cold Test Material
|  | P.S386 | DW Magnet - Hadron SQ2 - Coil Assembly Material
|  | P.S387 | DW Magnet - Hadron SQ2 - Cold Mass Assembly Material
|  | P.S388 | DW Magnet - Hadron SQ2 - Vertical Cold Test Material
|  | P.S389 | DW Magnet - Hadron SQ3 - Coil Assembly Material
|  | P.S390 | DW Magnet - Hadron SQ3 - Cold Mass Assembly Material
|  | P.S391 | DW Magnet - Hadron SQ3 - Vertical Cold Test Material
|  | P.S392 | DW Magnet - Hadron SQ4 - Coil Assembly Material
|  | P.S393 | DW Magnet - Hadron SQ4 - Cold Mass Assembly Material
|  | P.S394 | DW Magnet - Hadron SQ4 - Vertical Cold Test Material
|  | P.S395 | DW Magnet - Vertical Corrector - Coil Assembly Material
|  | P.S396 | DW Magnet - Vertical Corrector - Cold Mass Assembly Material
|  | P.S397 | DW Magnet - Vertical Corrector - Vertical Cold Test Material
|  | P.S398 | DW Magnet - Electron SQ1 - Coil Assembly Material
|  | P.S399 | DW Magnet - Electron SQ1 - Cold Mass Assembly Material
|  | P.S400 | DW Magnet - Electron SQ1 - Vertical Cold Test Material
|  | P.S401 | DW Magnet - Electron SQ2 - Coil Assembly Material
|  | P.S402 | DW Magnet - Electron SQ2 - Cold Mass Assembly Material
|  | P.S403 | DW Magnet - Electron SQ2 - Vertical Cold Test Material
|  | P.S404 | RF-HR-2-CTRL
|  | P.S404.A | First Article - RF-HR-2-CTRL
|  | P.S404.B | Production - RF-HR-2-CTRL
|  | P.S405 | RF-HR-3-CTRL
|  | P.S405.A | First Article - RF-HR-3-CTRL
|  | P.S405.B | Production - RF-HR-3-CTRL
|  | P.S406 | RF-HR-5-CTRL
|  | P.S406.A | First Article - RF-HR-5-CTRL
|  | P.S406.B | Production - RF-HR-5-CTRL
|  | P.S407 | RF-ERL-2-CTRL
|  | P.S407.A | First Article - RF-ERL-2-CTRL
|  | P.S407.B | Production - RF-ERL-2-CTRL
|  | P.S408 | RF-ERL-4-CTRL
|  | P.S408.A | First Article - RF-ERL-4-CTRL
|  | P.S408.B | Production - RF-ERL-4-CTRL
|  | P.S409 | Q1ABpF Prototype - Superconducting Wire
|  | P.S410 | Q1ABpF Prototype - Superconducting Cable/Coating
|  | P.S411 | B1pF Prototype - Strand Testing Material
|  | P.S412 | B1pF Prototype - Cabling Test Material
|  | P.S413 | Tooling Fabrication
|  | P.S414 | Collared Magnet - Q1ApF - Coil Curing
|  | P.S415 | Collared Magnet - Q1ApF - Coil Winding
|  | P.S416 | Collared Magnet - Q1BpF - Coil Curing
|  | P.S417 | Collared Magnet - Q1BpF - Coil Winding
|  | P.S418 | Collared Magnet - Q2pF - Coil Curing
|  | P.S419 | Collared Magnet - Q2pF - Coil Winding
|  | P.S420 | Collared Magnet - B1pF - Coil Curing
|  | P.S421 | Collared Magnet - B1pF - Coil Winding
|  | P.S422 | Collared Magnet - B1ApF - Coil Curing
|  | P.S423 | Collared Magnet - B1ApF - Coil Winding
|  | P.S424 | Q1ABpF Prototype - Superconducting Strand
|  | P.S425 | B1pF Prototype - Superconducting Cable
|  | P.S426 | Material Analysis (197 MHz Crab R&D)
|  | P.S427 | Dies and Fixture Raw Material (591MHz 1-Cell R&D)
|  | P.S428 | Dies and fixtures procurement package (591MHz 1-Cell R&D)
|  | P.S429 | Additional Cavity Materials (591MHz 1-Cell R&D)
|  | P.S430 | First Article Tuner Frames and Thermal Straps (197 MHz Crab 1st Art)
|  | P.S431 | First Article Mag Shields (197 MHz Crab 1st Art)
|  | P.S432 | First Article Spaceframes with Thermal Shield Assy. (197 MHz Crab 1st Art)
|  | P.S433 | Final Assembly Tooling (197 MHz Crab 1st Art)
|  | P.S434 | First Article Saddles and Stands (197 MHz Crab 1st Art)
|  | P.S435 | First Article Instrumentation (197 MHz Crab 1st Art)
|  | P.S436 | Tuner Stepper Motors (591 1-Cell Production CMs)
|  | P.S437 | Tuner Harmonic Drives (591 1-Cell Production CMs)
|  | P.S438 | Tuner Piezos (591 1-Cell Production CMs)
|  | P.S439 | Tuner Stepper Motors (591 5-Cell Production CMs)
|  | P.S440 | Tuner Harmonic Drives (591 5-Cell Production CMs)
|  | P.S441 | Tuner Piezos (591 5-Cell Production CMs)
|  | P.S442 | Cavity String Support Tooling (1773 5-Cell)
|  | P.S443 | Tuner Frames and Thermal Straps (1773 5-Cell)
|  | P.S444 | Mag Shields (1773 5-Cell)
|  | P.S445 | Tuner Frames and Thermal Straps (197 MHz Crab Production)
|  | P.S446 | Mag Shields (197 MHz Crab Production)
|  | P.S447 | Spaceframes with Thermal Shield Assy. (197 MHz Crab Production)
|  | P.S448 | Heat Exchangers (197 MHz Crab Production)
|  | P.S449 | Saddles and Stands (197 MHz Crab Production)
|  | P.S450 | Instrumentation (197 MHz Crab Production)
|  | P.S451 | Tuner Harmonic Drives (394 MHz Crab Production)
|  | P.S452 | Tuner Piezos (394 MHz Crab Production)
|  | P.S453 | Saddles and Stands (394 MHz Crab Production)
|  | P.S454 | Fumehood (TJ-Facilities)
|  | P.S455 | Magnet Measurement Stand - ESR Magnet Correctors
|  | P.S456 | First Article Magnet - ESR Magnet Correctors
|  | P.S457 | hpDIRC Quartz Bar Refurbishment
|  | P.S458 | hpDIRC Slow Control, GUI, Software Dev.
|  | P.S459 | mRICH Prototyping
|  | P.S460 | mRICH First Article
|  | P.S461 | mRICH Mirrors
|  | P.S462 | mRICH Gas System
|  | P.S463 | mRICH Carbon Support Structure
|  | P.S464 | mRICH Slow Control, GUI, Software Dev.
|  | P.S465 | mRICH Light Monitoring System
|  | P.S466 | mRICH Testing Materials-Mirrors
|  | P.S467 | Q3pF Q4pR Cryostat
|  | P.S468 | Detector Solenoid Sample Conductor
|  | P.S469 | Detector Solenoid Sample Conductor Testing
|  | P.S470 | Vacuum Side Outer Conductor
|  | P.S471 | Air Side Outer Conductor
|  | P.S472 | Air Side Inner Conductor
|  | P.S473 | Braze Test
|  | P.S474 | Window Assembly Prototypes
|  | P.S475 | Waveguide Tuner
|  | P.S476 | 295 MHz Cavity - Tuner
|  | P.S477 | 295 MHz Cavity - Window
|  | P.S478 | 295 MHz Cavity - Damper
|  | P.S479 | 148 MHz Cavity - Tuner
|  | P.S480 | 148 MHz Cavity - Window
|  | P.S481 | 148 MHz Cavity - Damper
|  | P.S482 | 24.6 MHz Cavity - Tuner
|  | P.S483 | 24.6 MHz Cavity - Window
|  | P.S484 | 24.6 MHz Cavity - Damper
|  | P.S485 | 24.6 MHz Cavity - Manufacturing / Modifications Materials
|  | P.S486 | 24.6 MHz Cavity - Power Amplifier
|  | P.S487 | 49.2 MHz Cavity - Tuner
|  | P.S488 | 49.2 MHz Cavity - Window
|  | P.S489 | 49.2 MHz Cavity - Damper
|  | P.S490 | 98.4 MHz Cavity - Tuner
|  | P.S491 | 98.4 MHz Cavity - Window
|  | P.S492 | 98.4 MHz Cavity - Damper
|  | P.S493 | 197 MHz Cavity (HSR Store 1) - Manufacturing / Modifications
|  | P.S494 | 197 MHz Cavity (HSR Store 1) - Power Amplifier
|  | P.S495 | 197 MHz Cavity (HSR Store 1) - Stand Manufacturing
|  | P.S496 | 197 MHz Cavity (HSR Store 1) - Testing
|  | P.S497 | 197 MHz Cavity (ERL Inj) - Manufacturing Material
|  | P.S498 | 197 MHz Cavity (ERL Inj) - FPC / Window
|  | P.S499 | 197 MHz Cavity (ERL Inj) - Tuner
|  | P.S500 | 197 MHz Cavity (ERL Inj) - Damper
|  | P.S501 | Vacuum Tooling and Equipment - Measurement and Data Logging Equipment
|  | P.S502 | Vacuum Tooling and Equipment - Software
|  | P.S503 | Vacuum Tooling and Equipment - Portable Cleanroom Tents
|  | P.S504 | BPM Electronics - Pre- Production Engineering Design Component Material
|  | P.S505 | B1pF Prototype - Yoke/Shell Assembly
|  | P.S506 | B1pF Prototype - End Plate Assembly
|  | P.S507 | Inverted High Voltage DC Gun
|  | P.S508 | Polarized Electron Source Laser
|  | P.S509 | Polarized Source Magnet
|  | P.S510 | Transport Line to Diagnostic Section
|  | P.S511 | Diagnostic Section Materials
|  | P.S512 | Cathode Preparation Chamber
|  | P.S513 | Cathode Storage Chamber
|  | P.S514 | Automation & Controls
|  | P.S515 | FPC Control & Interlock
|  | P.S516 | 591 MHz FPC - Conditioning Fixture
|  | P.S517 | 591 MHz FPC - Vacuum System
|  | P.S518 | 197 / 394 MHz FPC - Conditioning Fixture
|  | P.S519 | 197 / 394 MHz FPC - Vacuum System
|  | P.S520 | RCS Injection Pulsed Bump - Corrector Magnet
|  | P.S521 | Septum Electrical Components
|  | P.S522 | Septum Mechanical Components
|  | P.S523 | RCS Extraction Pulsed Bump - Corrector Magnets
|  | P.S524 | RCS Extraction Pulsed Bump - Power Supplies
|  | P.S525 | ESR Injection Pulsed Bump Corrector Magnets
|  | P.S526 | Software License
|  | P.S527 | HSR Beam Screens Cooling Tube
|  | P.S528 | HSR Beam Screen Guides
|  | P.S529 | HSR Beam screens miscellaneous parts
|  | P.S530 | Laser welding equipment for guides and skate brackets
|  | P.S531 | HSR Cutting Equipment
|  | P.S532 | HSR Part Marking Equipment
|  | P.S533 | Beam screens fixturing and tooling
|  | P.S534 | Amorphous Carbon Coating System (ACCS) - Controls
|  | P.S535 | Bake out Equipment
|  | P.S536 | Pumping Stations
|  | P.S537 | aC Carbon Coating System Power Supplies
|  | P.S538 | Vacuum/gas injection equipment
|  | P.S539 | Utilities Integration - Pulling Mechanisms for EPIC
|  | P.S540 | Electron Endcap HCal - Megatiles PCB 6 Degrees
|  | P.S543 | Forward HCal - test production for Module
|  | P.S544 | Forward HCal - Engineering Design Verification production
|  | P.S545 | Forward HCal - testing setups for readout Engineering Design Verification
|  | P.S546 | Forward HCal - Transfer Board
|  | P.S547 | Forward HCal - FPGA and Board
|  | P.S548 | Forward HCal - Tooling
|  | P.S549 | Forward HCal - lab equipment assembly
|  | P.S550 | Forward HCal - support structure cradle and slides
|  | P.S551 | Forward HCal - Test equipment and final test electronics
|  | P.S552 | Forward HCal - Signal Cable and Connectors
|  | P.S553 | Forward HCal - Long Signal Cables
|  | P.S554 | Forward HCal - Tile Wrapping
|  | P.S555 | Forward HCal - Scintillator Plate assembly
|  | P.S556 | Forward HCal - Installation Material
|  | P.S557 | Fibers Procurement (Inner Gas Barrel Tracking)
|  | P.S558 | Rack, LV, HV, crates, cable (Inner Gas Barrel Tracking)
|  | P.S559 | Fibers (Si Tracker for Barrel and Endcaps)
|  | P.S560 | Fibers (Outer Gas Barrel Tracking)
|  | P.S561 | Rack, LV, HV, crates, cable (Outer Gas Barrel Tracking)
|  | P.S562 | Power supply and cables (PID hpDIRC)
|  | P.S563 | Fibers Procurement (PID hpDIRC)
|  | P.S564 | HV Power supplies for Sensors Procurement (PID hpDIRC)
|  | P.S565 | Low and High Voltage System Procurement (TOF CTTL AC-LGAD)
|  | P.S566 | Peripheral Electronic Boards Procurement (TOF CTTL AC-LGAD)
|  | P.S567 | Fibers/Optical Connectors Procurement (TOF CTTL AC-LGAD)
|  | P.S568 | HV Power Supplies for Sensors (PID pfRICH)
|  | P.S569 | Power supply and cables - EICROC (PID pfRICH)
|  | P.S570 | Readout electronics - dRICH ALCOR FEB Procurement (PID dRICH)
|  | P.S571 | Power supply and cables (PID dRICH) (IN-KIND)
|  | P.S572 | Fibers Procurement (PID dRICH)
|  | P.S573 | Power supply and cables - ALCOR ASIC Procurement (PID dRICH)
|  | P.S574 | Low and High Voltage System Procurement (TOF FTTL AC-LGAD)
|  | P.S575 | Peripheral Electronic Boards Procurement (TOF FTTL AC-LGAD)
|  | P.S576 | Fibers/Optical Connectors Procurement (TOF FTTL AC-LGAD)
|  | P.S577 | PCB assembly (Barrel ECAL)
|  | P.S578 | Signal cable and connectors (Barrel ECAL)
|  | P.S579 | Long signal cables Procurement (Barrel ECAL)
|  | P.S580 | Power supply Procurement (Barrel ECAL)
|  | P.S581 | Fibers Procurement (Barrel ECAL)
|  | P.S582 | Interface PCB and components (HV, anode, LED) (Backward ECAL)
|  | P.S583 | PCB assembly (Backward ECAL)
|  | P.S584 | Signal cable and connectors (Backward ECAL)
|  | P.S585 | HV cable and connectors at detector (Backward ECAL)
|  | P.S586 | Fibers Procurement (Backward ECAL)
|  | P.S590 | Detector Optimization, Silicon detectors and readout
|  | P.S591 | HJET detector and electronics
|  | P.S592 | HJET DAQ system VME infrastructure
|  | P.S593 | pCarbon detector and electronics
|  | P.S594 | pCarbon calibration and controllers
|  | P.S595 | pCarbon DAQ system (VME infrastructure)
|  | P.S596 | Luminosity Monitor - First Articles
|  | P.S597 | Detector R&D Contracts Procurement - FY26
|  | P.S598 | HJET Target Gas Analyzer
|  | P.S599 | HSR Vacuum Controls and I/O
|  | P.S600 | Low Q2 Tagger
|  | P.S601 | Felix Boards for Evaluation (Timing Studies)
|  | P.S602 | Interface PCB & Components (HV, Anode, LED) Fabrication
|  | P.S603 | PCB Assembly Fabrication - Hadronic Calorimetry
|  | P.S604 | Interface PCB and components (HV, anode, LED) (OUTER Barrel HCAL)
|  | P.S605 | PCB assembly (OUTER Barrel HCAL)
|  | P.S606 | Signal cable and connectors (OUTER Barrel HCAL)
|  | P.S607 | HV cable and connectors at detector (OUTER Barrel HCAL)
|  | P.S608 | Fibers Procurement (OUTER Barrel HCAL)
|  | P.S609 | Long Signal Cables (Forward LFHCAL)
|  | P.S610 | Power Supply (Forward LFHCAL)
|  | P.S611 | Interface PCB and Components (HV, Anode, LED) (Backward nHCAL)
|  | P.S612 | RQN: PCB Assembly (Backward nHCAL)
|  | P.S613 | Signal Cables and Connectors (Backward nHCAL)
|  | P.S614 | HV Cable and Connectors at Detector (Backward nHCAL)
|  | P.S615 | Peripheral Electronic Boards AC-LGAD/EICROC (Roman Pots)
|  | P.S616 | Low Voltage System (Roman Pots)
|  | P.S617 | Cables Electrical Connectors (Roman Pots)
|  | P.S618 | Fibers and Optical Connectors (Roman Pots)
|  | P.S619 | Peripheral Electronic Boards AC-LGAD/EICROC (Off-Momentum Detector (OMD))
|  | P.S620 | RQN: Low & HV Voltage System (Off-Momentum Detector (OMD))
|  | P.S621 | Cables (Off-Momentum Detector (OMD))
|  | P.S622 | Fibers and Optical Connectors (Off-Momentum Detector (OMD))
|  | P.S623 | Peripheral Electronic Boards AC-LGAD/EICROC (B0 Detector)
|  | P.S624 | Low & HV Voltage System (B0 Detector)
|  | P.S625 | Cables and Electrical Connectors (B0 Detector)
|  | P.S626 | Fibers and Optical Connectors (B0 Detector)
|  | P.S627 | Module Assembly including Hybridization (B0 Detector)
|  | P.S628 | First Site 40x40cm Readout Electronics Si-Tracking (Low Q2 Tagger)
|  | P.S629 | Second Site 30x20cm Readout Electronics Si-Tracking (Low Q2 Tagger)
|  | P.S630 | Cables (for both sites) (Low Q2 Tagger)
|  | P.S631 | Move e-Source From SBU to BNL
|  | P.S632 | ERL 591-5 Cell RF 50kW PWR - Circulator Load
|  | P.S633 | ERL 591-5 Cell RF 50kW PWR - Waveguide
|  | P.S634 | HSR 591 5-Cell RF 70kW PWR - Circulator
|  | P.S635 | RCS 591 5-Cell RF 75kW PWR - Circulator
|  | P.S636 | RCS 591 5-Cell RF 75kW PWR - Circulator Load
|  | P.S637 | RCS 591 5-Cell RF 75kW PWR - Waveguide
|  | P.S638 | p-veto - Si small-Pad sensor (ZDC)
|  | P.S639 | First Article Bar Box & Photosensors (hpDIRC)
|  | P.S640 | Imaging W+Si - Si high gr Pad sensor (ZDC)
|  | P.S641 | Imaging W+Si - Si high gr Pad readout (ZDC)
|  | P.S642 | Imaging Pb+Si - Pb Plates (ZDC)
|  | P.S643 | HCAL Pb+Sci - Pb Plates (ZDC)
|  | P.S644 | HCAL Pb+Sci - Scintillators (ZDC)
|  | P.S645 | Fibers Procurement (PID mRICH) (IN-KIND)
|  | P.S646 | Slow Controls (Inner Gas Barrel Tracking) (IN-KIND)
|  | P.S647 | Slow controls (Outer Gas Barrel Tracking) (IN-KIND)
|  | P.S648 | B1pF Tooling Material - Curing Press Mods
|  | P.S649 | B1pF Tooling Material - Coil Rollover Fixture
|  | P.S650 | B1pF Tooling Material - Collaring Press Mods
|  | P.S651 | B1pF Tooling Material - Shell / End Plate Welding Fixtures
|  | P.S652 | B1pF Tooling Material - Solder Fixtures
|  | P.S653 | B1pF Tooling Material - Top Hat / Dewar Mods
|  | P.S654 | B1pF Tooling Material - 12" Press Mods
|  | P.S655 | B1pF Tooling Material - Insulating Line Mods
|  | P.S656 | B1pF Tooling Material - Winding Machine
|  | P.S657 | Forward HCal - LEDs
|  | P.S658 | Forward HCal - Shipping
|  | P.S659 | Forward HCal - Insert - Absorber Plates Tungsten
|  | P.S660 | Forward HCal - Insert - Absorber Plates Steel
|  | P.S661 | Forward HCal - Insert - Scintillator Rough Material
|  | P.S662 | Forward HCal - Insert - SiPM Carrier Board
|  | P.S663 | Forward HCal - Insert - FPGA and Board
|  | P.S664 | MPGD Trackers
|  | P.S665 | Detector Electronics
|  | P.S666 | Barrel EMCal Photosensor mounting boards
|  | P.S667 | Electron Endcap HCal - Sc. cassette Assembly Parts
|  | P.S668 | Electron Endcap HCal - Shipping
|  | P.S669 | Beam Screens for Triplets
|  | P.S670 | Warm to Cold Transition for Arc Screens
|  | P.S671 | Warm to Cold Transition for Triplets Screens
|  | P.S672 | Laser System - Misc Materials
|  | P.S673 | Laser System - Oscillator
|  | P.S674 | Laser System - Regenerative Amplifiers
|  | P.S675 | Laser System - Booster Amplifier
|  | P.S676 | Laser System - SHG & OPA
|  | P.S677 | Laser System - Pocket Cells
|  | P.S678 | Super Strained Lattice Cathode Lifetime w Polarized Beams
|  | P.S679 | HSR Injection Kicker - Vacuum Equipment and Adapters
|  | P.S680 | ESR Pulse Generator
|  | P.S681 | ASCIS (RP)
|  | P.S682 | Sensors (OMD)
|  | P.S683 | ASCIS (OMD)
|  | P.S684 | POT: Mechanical Vacuum Stations (OMD) (RP)
|  | P.S685 | RCS-SR Large Dipole
|  | P.S686 | POT: RF Shielding (OMD) (RP)
|  | P.S687 | Mechanical - Carbon Fiber Procurement
|  | P.S688 | Power - Multiplexing Boards Procurement
|  | P.S689 | Power - Readout Procurement
|  | P.S690 | Slow Control Procurement
|  | P.S691 | Vertexing Layers Procurement
|  | P.S692 | Additional Tooling for Probe Testing Procurement
|  | P.S693 | Mechanical - Vertexing Layers Procurement
|  | P.S694 | Mechcanical - Middle Layers Procurement
|  | P.S695 | Readout Procurement
|  | P.S696 | Half Disks 1 Procurement
|  | P.S697 | Half Disks 2 Procurement
|  | P.S698 | Cooling - Vertexing Layers Procurement
|  | P.S699 | Lepton Polarimetry - Calorimeter DAQ - ESR
|  | P.S699 | Lepton Polarimetry - Calorimeter DAQ - ESR
|  | P.S700 | Lepton Polarimetry - Calorimeter Modules - ESR
|  | P.S701 | Lepton Polarimetry - Calorimeter Readout - ESR
|  | P.S702 | Lepton Polarimetry - Laser - Diode, Driver, Controller, and Fiber - ESR
|  | P.S703 | Lepton Polarimetry - Fiber Amplifier - ESR
|  | P.S704 | Lepton Polarimetry - Laser Interaction Vacuum Chamber - ESR
|  | P.S705 | Lepton Polarimetry - Polarization Optics - ESR
|  | P.S706 | Lepton Polarimetry - Position Detectors - ESR
|  | P.S707 | Lepton Polarimetry - Calorimeter DAQ - RCS
|  | P.S708 | Lepton Polarimetry - Calorimeter Infrastructure - RCS
|  | P.S709 | Lepton Polarimetry - Calorimeter Modules - RCS
|  | P.S710 | Lepton Polarimetry - Calorimeter Readout - RCS
|  | P.S711 | Lepton Polarimetry - Position Detectors - RCS
|  | P.S712 | Lepton Polarimetry - Pulsed Laser - RCS
|  | P.S713 | Lepton Polarimetry - Vacuum Chamber - RCS
|  | P.S714 | Supply and Cables (PID pfRICH) (IN-KIND)
|  | P.S715 | SC Cable - Collared Magnets
|  | P.S716 | eRD108 - NOT YET AWARDED - Varioius
|  | P.S717 | Light Monitoring System (hpDIRC)
|  | P.S800 | Services - Signal Cable Procurement
|  | P.S801 | Probe Testing - Staves and Disks Procurement
|  | P.S802 | Probe Testing - Vertex Procurement
|  | P.S803 | Additional Tooling for Module Fabrication - Procurement
|  | P.S804 | Cooling - Stave and Disk Procurement
|  | P.S805 | Mechanical - Global Procurement
|  | P.S806 | Detector Shipment Procurement
|  | P.S807 | Detector Assembly Procurement
|  | P.S808 | First and Second Station HV/LV/FE readout boards (Low Q2)
|  | P.S809 | First and Second Station Silcon (Low Q2)
|  | P.S810 | Mechanical frame material (for both Stations) (Low Q2)
|  | P.S811 | Cooling sysytem (Low Q2)
|  | P.S812 | Vacuum/exit window Procurement (Low Q2)
|  | P.S813 | Mechanical Support Structure Fabrication & Assembly
|  | P.S814 | Rack, LV, HV, Crates, Cable Purchase Ready for Installation
|  | P.S815 | Detector Component Purchase: uRwell Foils - Make 1
|  | P.S816 | Detector Component Purchase: Detector Frames
|  | P.S817 | Detector Component Purchase: Other Components
|  | P.S818 | Design and Prototyping - Prototype Component Purchase - uRwell Foils
|  | P.S819 | Design and Prototyping - Prototype Module Assembly
|  | P.S820 | Mechanical Support Structure Fabrication and Assembly
|  | P.S821 | Rack, LV, HV, Crates, Cable Purchase Ready for Installation
|  | P.S822 | Detector Component Purchase - uRwell Foils
|  | P.S823 | Detector Component Purchase - Detector Frames
|  | P.S824 | Detector Component Purchase - Other Components
|  | P.S825 | Install, Integration & Testing - Slow Controls Integration
|  | P.S826 | Install, Integration & Testing - Detector Assembly
|  | P.S827 | Install, Integration & Testing - Mechanical Integration
|  | P.S828 | Install, Integration & Testing - System Testing & Qualification
|  | P.S829 | Install, Integration & Testing - Detector Assembly
|  | P.S830 | Install, Integration & Testing - Mechanical Integration
|  | P.S831 | Install, Integration & Testing - System Testing & Qualification
|  | P.S832 | CRT (Cosmic Ray Test-Setup) (hpDIRC)
|  | P.S833 | Assemble Full Bar Boxes Infrastructure & Materials (hpDIRC)
|  | P.S834 | Fabrication Bars & Barboxes (hpDIRC)
|  | P.S835 | Remaining Tooling (591MHz 1-Cell R&D)
|  | P.S836 | Barrel EMCal - Barrel Pb/SciFi absorber - Epoxy
|  | P.S837 | Barrel EMCal - Production Procurements - Material Pack and Ship
|  | P.S838 | Barrel EMCal Preproduction - Stave/Tray tooling
|  | P.S839 | Barrel EMCal Preproduction - Module PCB QC
|  | P.S840 | HV cable and connectors at detector (Barrel ECAL)
|  | P.S841 | ZDC - Engineering Test Article - ZDC-HCAL
|  | P.S842 | Barrel EMCal Preproduction - Wire Bonder
|  | P.S843 | Barrel EMCal Preproduction - Parylene Coater
|  | P.S844 | Barrel EMCal Preproduction - Stave/Tray test system
|  | P.S845 | Barrel EMCal Preproduction - Supplies
|  | P.S846 | Barrel EMCal Production - Stave
|  | P.S847 | Barrel EMCal Production - Tray
|  | P.S848 | Barrel EMCal Production - Dicing
|  | P.S849 | Barrel EMCal Production - Cable Harness
|  | P.S850 | Barrel EMCal Production - Consumables
|  | P.S851 | Barrel EMCal Production - Consumables
|  | P.S852 | Barrel EMCal Production - End of Stave Card
|  | P.S853 | Barrel EMCal - Mechanical Structure - Carbon Support Structure
|  | P.S854 | Barrel EMCal - Mechanical Structure - Light Guides
|  | P.S855 | Barrel EMCal - Mechanical Structure - Light Monitoring System
|  | P.S856 | Barrel EMCal - Mechanical Structure - Cooling System for SiPM
|  | P.S857 | Barrel EMCal - Mechanical Structure - Supplies and assembly tooling
|  | P.S858 | Light Pulser System (pfRICH)
|  | P.S859 | Vessel (pfRICH)
|  | P.S860 | Aerogel (pfRICH)
|  | P.S861 | HRPPD QA Test Station (pfRICH) - Test Equipment
|  | P.S862 | (pfRICH) - Transportation Cart
|  | P.S863 | Interface PCB and components (HV, anode, LED) (Barrel ECAL)
|  | P.S864 | CEA, Sacaly for Radiation Studies
|  | P.S866 | Quench Analysis for Collared Magnets (FNL)
|  | P.S867 | Epstein Frame (Magnet Measurement)
|  | P.S868 | B1pF Production - Yoke / End Plate / Splice Assembly
|  | P.S869 | B1ApF Production - Yoke / End Plate / Splice Assembly
|  | P.S870 | Q2pF Production - Yoke / End Plate / Splice Assembly
|  | P.S871 | Q1ApF Production - Yoke / End Plate / Splice Assembly
|  | P.S872 | Q1BpF Production - Yoke / End Plate / Splice Assembly
|  | P.S873 | B1ApF Production - Coil Assembly
|  | P.S874 | Q2pF Production - Coil Assembly
|  | P.S875 | Q1ApF Production - Coil Assembly
|  | P.S876 | Q1BpF Production - Coil Assembly
|  | P.S877 | B1pF Production - Cryo Assembly
|  | P.S878 | B1ApF Production - Cryo Assembly
|  | P.S879 | Q2pF Production - Cryo Assembly
|  | P.S880 | Q1ApF Production - Cryo Assembly
|  | P.S881 | Q1BpF Production - Cryo Assembly
|  | P.S882 | APS Magnet Storage Tents
|  | P.S883 | PED Contract for Barrel Imaging Calorimeter
|  | P.S884 | PED Contract - Forward Mechanical Structure
|  | P.S885 | eRD103 - hpDIRC
|  | P.S886 | eRD104 - Service Reduction
|  | P.S887 | eRD107 - Forward HCal
|  | P.S888 | eRD110 - Photosensors
|  | P.S889 | eRD110 - Photosensors
|  | P.S890 | eRD112 - AC-LGAD
|  | P.S891 | eRD112 - AC-LGAD
|  | P.S892 | eRD112 - AC-LGAD
|  | P.S893 | eRD112 - AC-LGAD
|  | P.S894 | eRD113 - MAPS sensors ITS3
|  | P.S895 | eRD113 - MAPS sensors ITS3
|  | P.S896 | eRD113 - MAPS sensors ITS3
|  | P.S897 | eRD113 - MAPS sensors ITS3
|  | P.S898 | eRD115 - Imaging Calorimeter
|  | P.S899 | R&D contract - Spectrometer with Fiber Splitter
|  | P.S900 | Detector Computing - DAQ Server - Computing Infrastructure - Phase 2
|  | P.S901 | Detector Computing - Analysis Server - Computing Infrastructure - Phase 2
|  | P.S902 | Detector Computing - File Servers - Computing Infrastructure - Phase 2
|  | P.S903 | Detector Computing - DAQ Server - Computing Infrastructure - Phase 3
|  | P.S904 | Detector Computing - Analysis Server - Computing Infrastructure - Phase 3
|  | P.S905 | Detector Computing - Readout Server - Computing Infrastructure - Phase 3
|  | P.S906 | Detector Computing - File Servers - Computing Infrastructure - Phase 3
|  | P.S907 | Detector Computing - DAQ Room Fiber
|  | P.S908 | Detector Computing - Trunk Fiber
|  | P.S909 | Detector Computing - Wide Angle Hall Fiber
|  | P.S910 | Quench Protection
|  | P.S911 | Detector Computing - Fabrication Engineering Article (DAM Board)
|  | P.S912 | Detector Computing - Racks - Computing Infrastructure - Phase 1
|  | P.S913 | Detector Computing - Network Switches - Computing Infrastructure - Phase 1
|  | P.S914 | Detector Computing - Development Server - Computing Infrastructure - Phase 1
|  | P.S915 | Detector Computing - Readout Server First Article - Computing Infrastructure - Phase 1
|  | P.S916 | Detector Computing - Fabrication Engineering Article - GTU Board
|  | P.S917 | Detector Computing - Fabrication Final Design - GTU Board
|  | P.S918 | Detector Computing - Felix Boards (Timing Studies)
|  | P.S919 | Detector Computing - Server Type 1, 2 (Slow Controls)
|  | P.S920 | Detector Computing - Network Switch (Slow Controls)
|  | P.S921 | Detector Computing - Chassis Type 2 (Slow Controls)
|  | P.S922 | Electron Endcap HCal - HGCROC
|  | P.S923 | Forward HCal - HV cables and connector at detector
|  | P.S924 | e-beamlines Baked Vacuum
|  | P.S925 | Bellows helper spring assembly
|  | P.S926 | Cryostat Mechanical Components
|  | P.S927 | Vacuum Measurement & Data Logging Equipment
|  | P.S928 | ESR Portable Clean Room Tents
|  | P.S951 | ESR APS Magnets - Rebuild Parts
|  | P.S951.A | ESR APS Magnets - Rebuild Parts Batch 1
|  | P.S951.B | ESR APS Magnets - Rebuild Parts Batch 2
|  | P.S952 | ESR APS Magnets - Magnet Measurment Stand
|  | P.S952.A | ESR APS Magnets - Magnet Measurement Stand 1
|  | P.S952.B | ESR APS Magnets - Magnet Measurement Stand 2
|  | P.S953 | INFN - Final - PROJECT ENGINEERING AND DESIGN: SIPM
|  | P.S954 | Detailed (90%) Design - Vendor Contract
|  | P.S955 | Tracking FY 30 Procurements
|  | P.S956 | (MPGD) Trackers FY 28 Procurements
|  | P.S957 | Construction of Full Chain Test Assembly (pfRICH) (Non-Labor)
|  | P.S958 | INFN PED for Design of ePIC µRWELL Trackers and Cap Discs for EIC
|  | P.S959 | Large Diameter BLA: 2 Silicon Carbide Cylinders and Tooling
|  | P.S960 | Small Diameter BLA: 2 Silicon Carbide Cylinders and Tooling
|  | P.S961 | DW Magnet - B2eR - Coil Assembly Material
|  | P.S962 | DW Magnet - B2eR - Cold Mass Assembly Material
|  | P.S970 | eRD103 - hpDIRC
|  | P.S971 | eRD112 - AC-LGAD
|  | P.S972 | eRD106 - Forward EMCal
|  | P.S973 | eRD107 - Forward HCal
|  | P.S974 | APS Magnet Storage Tents and Facilities
|  | P.S975 | B1pF Prototype Material - Coil Parts - Wedges/Wedge Tips
|  | P.S976 | B1pF Prototype Material - Coil Parts - End Spacers
|  | P.S977 | Superconducting Strand - Direct Wind Magnets (0.47mm)
|  | P.S978 | Superconducting Strand - Direct Wind Magnets (0.33mm)
|  | P.S979 | Silicon Trackers - PED Contract
|  | P.S980 | 591MHz FA - Tuner Testing
|  | P.S981 | HRPPD First Article - Setup QA Test Stand
|  | P.S982 | BTOF - Module Structure
|  | P.S983 | BTOF - Module Assembly - Onto Support Structure
|  | P.S984 | BTOF - Module Assembly/Support Structure - Install into ePIC
|  | P.S985 | FTOF - Sensor
|  | P.S986 | FTOF - Sensor-ASIC Integration
|  | P.S987 | FTOF - Module Mechanics
|  | P.S988 | FTOF - Module Assembly
|  | P.S989 | FTOF - Module Assembly/Support Structure - Install into ePIC
|  | P.S990 | TOF - Support Structure
|  | P.S991 | TOF - Cooling System
|  | P.S992 | TOF - Alignment System
|  | P.S993 | ASICS/Electronics - eRD109 - Indiana University - Develop Calorimeter Readout
|  | P.S994 | Micro Patter Gaseous Detectors - eRD108 - Saclay, France - Research/Developement/Design
|  | P.S995 | ASICS/Electronics - eRD109 - Saclay France - Production of the Salsa 1 Prototype
|  | P.S996 | Oxford PED - Procurement
|  | P.S997 | RDO Readout Board - Engineering Test Article - Fabrication and Assembly
|  | P.S998 | B1pF Prototype Inner Yoke
|  | P.S999 | 197MHz DVC - VTA Equipment
|  | S | Significant Procurement (APP)=>$250K<$2M
|  | S.1000 | (New Code Value)
|  | S.P001 | SP #001 - BPM Electronics
|  | S.P002 | SP #002
|  | S.P003 | SP #003 - 49.2 MHz Cavity
|  | S.P004 | SP #004 - XHV pumping systems
|  | S.P005 | SP #005 - Linac to RCS Transfer Line Magnets
|  | S.P006 | SP #006 - HR Inj Warm Line Septum APS
|  | S.P007 | SP #007
|  | S.P008 | SP #008 - HV Pulsed Generator
|  | S.P009 | SP #009 - Corrector & Injection Bump Supplies DCCT Chassis BTPs
|  | S.P010 | SP #010 - RCS Correctors
|  | S.P011 | SP #011 - C/M Construction Mgt Services
|  | S.P011.A | SP #011 - Phase A
|  | S.P011.B | SP #011 - Phase B
|  | S.P012 | SP #012 - Spin Rotator Quad
|  | S.P013 | SP #013 - AtR to Blue Transfer Line Magnet
|  | S.P013.A | SP #013 - Phase A
|  | S.P013.B | SP #013 - Phase B
|  | S.P014 | SP #014 - OCEM
|  | S.P015 | SP #015 - Detector Tracking - GEM foils for MPGDs
|  | S.P016 | SP #016 - RF-CRAB-2-CTRL
|  | S.P016.A | SP #016 - Phase A RF-CRAB-2-CTRL
|  | S.P016.B | SP #016 - Phase B RF-CRAB-2-CTRL
|  | S.P017 | 197 MHz Cavity (HSR Store 1) - Window
|  | S.P018 | SP #018 - HR Straight DC Cables
|  | S.P019 | SP #019 - Corrector & Injection Bump Supplies PSC BTP
|  | S.P020 | SP #020 - Staff Augmentation - Electrical Contractor
|  | S.P021 | SP #021 - Lepton Polarimetry - Position Detectors - ESR
|  | S.P022 | SP #022 - RCS Injection Pulsed Bump - Kicker Magnet
|  | S.P023 | SP #023 - Coil Assembly
|  | S.P024 | SP #024 - SBU Hydronic Cooling System Installation
|  | S.P025 | SP #025 - Magnet Measuring Station Material
|  | S.P026 | SP #026 - RCS to ESR Transfer Line Magnets
|  | S.P027 | SP #027 - Bellows Upgrade - Shield Inserts
|  | S.P028 | SP #028 - HR SS Mod Vacuum - I&C systems
|  | S.P029 | SP #029 - Chilled Water System Installation
|  | S.P030 | SP #030 - Motor Controls Center
|  | S.P031 | SP #031 - Corrector & Injection Bump Supplies DCCT Chassis BTPs
|  | S.P032 | SP #032 - ESR Stripline Kickers Electrical Components
|  | S.P033 | SP #033 - 591 MHz FPC Conditioning Box
|  | S.P034 | SP #034
|  | S.P035 | SP #035 - Zero Degree Calorimeter
|  | S.P036 | Superconducting Strand - Direct Wind Magnets
|  | S.P037 | SP #037 - Correctors PS - CAEN
|  | S.P038 | SP #038 - Stripline Kickers Mechanical Components
|  | S.P039 | SP #039 - 98.4 MHz Cavity
|  | S.P040 | SP #040 - New HR PS - CAEN
|  | S.P041 | SP #041 - 394 MHz FPC Couplers
|  | S.P042 | SP #042 - Small PS - CAEN
|  | S.P043 | SP #043 - Racks
|  | S.P044 | SP #044 - Bunch Length Monitors
|  | S.P045 | SP #045 - HR TL Material
|  | S.P046 | RCS SLM Optical Transport
|  | S.P047 | SP #047
|  | S.P048 | SP #048 - ESR Injection Septum Electrical Components
|  | S.P049 | e-beamlines Baked Vacuum - valves and pumps
|  | S.P050 | HSR Vacuum Interconnect Hardware
|  | S.P050.A | HSR Vacuum Interconnect Hardware - Option 1
|  | S.P050.B | HSR Vacuum Interconnect Hardware - Option 2
|  | S.P051 | SP #051 - Helical Magnets in Snakes
|  | S.P052 | SP #052 - RF Power Supply & Components
|  | S.P053 | SP #053 - Module - PCB Assembly
|  | S.P054 | SP #054 - EMCal - Hadron
|  | S.P055 | SP #055 - Movable ESR Collimators
|  | S.P056 | SP #056
|  | S.P057 | SP #057 - Dc, AC, Control Interlock Cable
|  | S.P058 | SP #058 - 1.773 GHz FPC Couplers
|  | S.P059 | SP #059 - Carbon Coating System
|  | S.P060 | SP #060 - RF-RCS-1-CTRL
|  | S.P060.A | SP #060 - Phase A - RF-RCS-1-CTRL
|  | S.P060.B | SP #060 - Phase B - RF-RCS-1-CTRL
|  | S.P061 | Polarized Atomic HJET and Readout Electronics
|  | S.P062 | SP #062 - Transfer Lines Vacuum - Hardware
|  | S.P063 | SP #063 - Lepton Endcap Construction
|  | S.P064 | SP #064 - 591 MHz - 600 kW Circulator with Load
|  | S.P065 | SP #065
|  | S.P065.A | SP #065 - Phase A
|  | S.P065.B | SP #065 - Phase B
|  | S.P066 | SP #066
|  | S.P067 | RCS Vacuum Gauges and Controllers
|  | S.P068 | SP #068 - RF-ERL-3-CTRL
|  | S.P068.A | SP #068 - Phase A - RF-ERL-3-CTRL
|  | S.P068.B | SP #068 - Phase B - RF-ERL-3-CTRL
|  | S.P069 | SP #069
|  | S.P070 | SP #070 - RF-HR-1-CTRL
|  | S.P070.A | SP #070 - Phase A - RF-HR-1-CTRL
|  | S.P070.B | SP #070 - Phase B - RF-HR-1-CTRL
|  | S.P071 | SP #071
|  | S.P071.A | SP #071 - Phase A
|  | S.P071.B | SP #071 - Phase B
|  | S.P072 | SP #072
|  | S.P072.A | SP #072 - Phase A
|  | S.P072.B | SP #072 - Phase B
|  | S.P073 | SP #073
|  | S.P074 | SP #074 - Tooling Material
|  | S.P075 | ESR Water Flow Monitoring
|  | S.P076 | SiPMT & SiPMT PCBoard
|  | S.P077 | SP #077
|  | S.P078 | RF Shielded Valves
|  | S.P079 | B1pF Prototype Material - Coil Parts
|  | S.P080 | SP #080 - ESR Injection Mechanical Components
|  | S.P081 | SP #081 - Variable Frequency Drives
|  | S.P082 | SP #082 - Commissioning Contract
|  | S.P082.A | Design Phase
|  | S.P082.B | Construction Phase
|  | S.P083 | SP #083 - Field Office Trailer Rental
|  | S.P084 | SP #084 - Testing Contract
|  | S.P086 | SP #086 - SC Stand NbTi IR Magnets
|  | S.P087 | SP #087 - HV DC Gun PS - Excelitas
|  | S.P088 | SP #088 - Injection System - RCS Vacuum - Installation Material
|  | S.P089 | SP #089 - ESR - Installation of Vacuum System - Material
|  | S.P090 | SP #090
|  | S.P091 | SP #091 - Cable Tray
|  | S.P092 | SP #092 - B0pF Cryostat
|  | S.P093 | SP #093
|  | S.P094 | SP #094
|  | S.P095 | SP #095 - AC & Interlock Cable
|  | S.P096 | SP #096
|  | S.P097 | SP #097 - 295 MHz Cavity
|  | S.P097.A | SP #097 - Phase A
|  | S.P097.B | SP #097 - Phase B
|  | S.P098 | SP #098 - 148 MHz Cavity
|  | S.P098.A | SP #098 - Phase A
|  | S.P098.B | SP #098 - Phase B
|  | S.P099 | SP #099
|  | S.P099.A | SP #099 - Phase A
|  | S.P099.B | SP #099 - Phase B
|  | S.P100 | SP #100 - RF-RCS-2-PWR
|  | S.P100.A | SP #100 - First Article - RF-RCS-2-PWR
|  | S.P100.B | SP #100 - Production - RF-RCS-2-PWR
|  | S.P101 | SP #101 - RF-RCS-3-PWR
|  | S.P101.A | SP #101 - First Article - RF-RCS-3-PWR
|  | S.P101.B | SP #101 - Production - RF-RCS-3-PWR
|  | S.P102 | SP #102
|  | S.P102.A | SP #102 - Phase A
|  | S.P102.B | SP #102 - Phase B
|  | S.P103 | SP #103
|  | S.P103.A | SP #103 - Phase A
|  | S.P103.B | SP #103 - Phase B
|  | S.P104 | SP #104 - RF-ERL-4-PWR
|  | S.P104.A | SP #104 - First Article - RF-ERL-4-PWR
|  | S.P104.B | SP #104 - Production - RF-ERL-4-PWR
|  | S.P105 | SP #105 - 400 MeV Linac - Installation Support - Material
|  | S.P105.A | SP #105 - 400 MeV Linac - Installation Support - Material Phase A
|  | S.P105.B | SP #105 - 400 MeV Linac - Installation Support - Material Phase B
|  | S.P106 | SP #106
|  | S.P106.A | SP #106 - Phase A
|  | S.P106.B | SP #106 - Phase B
|  | S.P107 | SP #107 - ESR Vacuum Monitoring & Control
|  | S.P107.A | SP #107 - Phase A
|  | S.P107.B | SP #107 - Phase B
|  | S.P108 | SP #108
|  | S.P108.A | SP #108 - Phase A
|  | S.P108.B | SP #108 - Phase B
|  | S.P109 | First and Second Station Procurement (Low Q2)
|  | S.P110 | pCarbon target loading station (vacuum pumps,shutters and control system)
|  | S.P111 | ESR RF Shielded Valves
|  | S.P112 | SP #112 - Laser System - Procurements
|  | S.P113 | SP #113 - Position Detectors
|  | S.P114 | SP #114 - Hadron Ring Straight Sections Mods Vacuum - Chambers, Bellows, Supports
|  | S.P115 | SP #115 - Hadron Ring Inj-Sys Upgrade Vacuum - Chambers, Bellows, Supports
|  | S.P116 | SP #116 - e-Beamlines Baked Vacuum - Chambers, Bellows, Supports
|  | S.P117 | SP #117 - e-loop Return Vacuum - Chambers, Bellows, Supports
|  | S.P118 | SP #118 - DC-Gun LINAC Vacuum - Chambers, Bellows, Supports
|  | S.P119 | SP #119
|  | S.P120 | SP #120 - e-loop Return Vacuum - Valves and Pumps
|  | S.P121 | SP #121 - e-Beamlines Baked Vacuum - Valves and Pumps
|  | S.P122 | SP #122 - Detector-Electronics
|  | S.P123 | SP #123 - BPM Electronics - Module
|  | S.P124 | SP #124 - Profile Monitors - Construction
|  | S.P125 | SP #125 - BPM Electronics - Construction
|  | S.P126 | SP #126 - Profile Monitors - Construction
|  | S.P127 | SP #127 - ICT, Material
|  | S.P128 | SP #128 - Collimators - Material
|  | S.P129 | SP #129 - BPM System - Materials
|  | S.P130 | HSR BPM Cryo Cables
|  | S.P131 | SP #131 - Charge and Current Monitors - Materials
|  | S.P132 | ESR SLM - Optical Transport
|  | S.P133 | SP #133 - ESR BPM Assembly Materials
|  | S.P133.A | ESR BPM - Design Verification Units
|  | S.P133.B | ESR BPM - Production Quantity
|  | S.P134 | SP #134 - BPM System - Signal cables, rack hardware, system connectors
|  | S.P135 | SP #135 - BPM Pick-up - Materials
|  | S.P136 | BPM Pick-up -Button
|  | S.P136.A | RCS BPM Buttons Design Verification Units
|  | S.P136.B | RCS BPM Buttons Production
|  | S.P137 | SP #137 - Longitudinal Feedback System
|  | S.P138 | SP #138 - BPM System - Miscellaneous materials
|  | S.P139 | SP #139 - Synchrotron Radiation Monitors - Synchrotron Radiation Monitors - Materials
|  | S.P140 | SP #140 - BPM Electronics - Module Procurement (material)
|  | S.P141 | SP #141 - Profile Monitors - Materials
|  | S.P142 | HSR BPM Buttons
|  | S.P142.A | HSR BPM Buttons - Design Verification Units - Initial Award
|  | S.P142.B | HSR BPM Buttons - Production - Option
|  | S.P143 | SP #143 - Tracking - Hadron Endcap Low-rapidity Si - Material - Construction
|  | S.P144 | SP #144 - Tracking - Lepton Endcap Low-rapidity Si - Material - Construction
|  | S.P145 | SP #145 - PID: Hadron Endcap Construction - Materials
|  | S.P146 | SP #146 - Detector Tracking - Lepton Endcap
|  | S.P146.A | SP #146 - Phase A
|  | S.P146.B | SP #146 - Phase B
|  | S.P147 | SP #147
|  | S.P147.A | SP #147 - Phase A
|  | S.P147.B | SP #147 - Phase B
|  | S.P148 | SP #148 - RF-ESR-1-CTRL
|  | S.P148.A | SP #148 - First Article - RF-ESR-1-CTRL
|  | S.P148.B | SP #148 - Production - RF-ESR-1-CTRL
|  | S.P149 | SP #149 - RF-HR-3-PWR
|  | S.P149.A | SP #149 - First Article - RF-HR-3-PWR
|  | S.P149.B | SP #149 - Production - RF-HR-3-PWR
|  | S.P150 | SP #150 - RF-ERL-2-PWR
|  | S.P150.A | SP #150 - First Article - RF-ERL-2-PWR
|  | S.P150.B | SP #150 - Production - RF-ERL-2-PWR
|  | S.P151 | SP #151 - RF-HR-4-CTRL
|  | S.P151.A | SP #151 - RF-HR-4-CTRL Phase A
|  | S.P151.B | SP #151 - RF-HR-4-CTRL Phase B
|  | S.P152 | Electron Endcap HCal Absorber Structure
|  | S.P153 | Forward HCal Module Casing Steel
|  | S.P154 | Detector DAQ
|  | S.P155 | 197 MHz Cavity (HSR Store 1) - Tuner
|  | S.P156 | SC Cable - Direct Wind Magnets
|  | S.P157 | RF-HR-2-PWR
|  | S.P157.A | RF-HR-2-PWR - First Article
|  | S.P157.B | RF-HR-2-PWR - Production
|  | S.P158 | ERL-1-CTRL
|  | S.P158.A | ERL-1-CTRL - First Article
|  | S.P158.B | ERL-1-CTRL - Production
|  | S.P159 | HR-5-CM: High Power Test (Production)
|  | S.P159.A | HR-5-CM: High Power Test (Production) - A
|  | S.P159.B | HR-5-CM: High Power Test (Production) - B
|  | S.P160 | Backward EMCal PbWO4 Crystals (Possible In-Kind Procurement 1)
|  | S.P161 | 197 MHz Cavity (HSR Store 1) - Damper
|  | S.P162 | Backward EMCal PbWO4 Crystals (Possible In-Kind Procurement 2)
|  | S.P163 | Detector Interface Vacuum Development - Prototype Detector Chamber
|  | S.P164 | Cooler R&D Miscellaneous Materials
|  | S.P165 | Backward EMCal Silicon Photomultipliers
|  | S.P166 | Barrel EMCal Silicon Photomultipliers
|  | S.P167 | Forward EMCal Tungsten Powder
|  | S.P168 | Vacuum - Main chamber vessel
|  | S.P169 | Laser procurement
|  | S.P170 | DW Magnet - B2eR - Coil Assembly Material
|  | S.P171 | DW Magnet - B2eR - Cold Mass Assembly Material
|  | S.P172 | DW Magnet - B2eR - Vertical Cold Test Material
|  | S.P173 | DW Magnet - Q2BpR - Coil Assembly Material
|  | S.P174 | DW Magnet - Q2BpR - Cold Mass Assembly Material
|  | S.P175 | Forward EMCal Scinillation Fibers
|  | S.P175.A | Forward EMCal Scinillation Fibers - Initial Award
|  | S.P175.B | Forward EMCal Scinillation Fibers - Option 1
|  | S.P175.C | Forward EMCal Scinillation Fibers - Option 2
|  | S.P175.D | Forward EMCal Scinillation Fibers - Option 3
|  | S.P176 | Lenses (hpDIRC)
|  | S.P177 | Forward EMCal SiPMs
|  | S.P178 | ESR APS Magnets - Refurbishment Parts
|  | S.P178.A | ESR APS Magnets - Refurbishment Parts Batch 1
|  | S.P178.B | ESR APS Magnets - Refurbishment Parts Batch 2
|  | S.P179 | ESR APS Magnets - Measurement Facilities
|  | S.P179.A | ESR APS Magnets - Measurement Facilities Batch 1
|  | S.P179.B | ESR APS Magnets - Measurement Facilities Batch 2
|  | S.P180 | U-Tubes
S.P181
|  | S.P182 | Transfer Line Magnets - Girders
|  | S.P183 | IR #2 Development (Planning Package)
|  | S.P184 | 2K Satellite Plant Aux Systems - Guard Vacuum Systems
|  | S.P185 | IR Magnet Cryostats - Rear
|  | S.P186 | PED, Quench Protection
|  | S.P187 | 4K Distribution B&P - Procurement IR02 Distribution
|  | S.P188 | 4K Distribution B&P - Procurement IR04 Distribution
|  | S.P189 | 4K Distribution B&P - Procurement IR06 Detector Solenoid Distribution
|  | S.P190 | 4K Distribution B&P - Procurement IR06 IR Magnets Tie-in & Crab Bypasses Distribution
|  | S.P191 | 4K Distribution B&P - Procurement IR06 eSR Solenoids Distribution
|  | S.P192 | 4K Distribution B&P - Procurement IR06 Blue Injection Distribution
|  | S.P193 | 4K Distribution B&P - Procurement IR10 Distribution
|  | S.P194 | 4K Distribution B&P - Procurement IR12 Distribution
|  | S.P195 | Cryo Installation - IR06
|  | S.P196 | Cryo Installation - IR04
|  | S.P197 | Cryo Installation - IR12
|  | S.P198 | Cryo Installation - IR02
|  | S.P199 | Cryo Installation - IR10
|  | S.P200 | 2K Distribution System Installation Contract - IR02
|  | S.P201 | not used
|  | S.P203 | Lakeshore Temperature Controllers
|  | S.P204 | PLC Hardware Cards
|  | S.P205 | Heater Controllers Chromalox
|  | S.P206 | Multiconductor Cables
|  | S.P207 | 2K Satellite Plant Aux Systems - Starters
|  | S.P208 | 2K Satellite Plant Aux Systems - Service Building Cooling Water Piping Systems
|  | S.P209 | 2K Satellite Plant Aux Systems - Deliver U-Tubes
|  | S.P210 | 2K Satellite Plant Aux Systems - Instrumentation Panel
|  | S.P211 | 2K Satellite Plant Aux Systems - LN2 Distribution Systems
|  | S.P212 | 2K Satellite Plant Aux Systems - Forward Magnet
|  | S.P213 | Cavity Tooling and Dies (197 MHz Crab R&D)
|  | S.P214 | First Article Helium Vessel (197MHz Crab 1st Art)
|  | S.P215 | String Assembly Toolings (197MHz Crab 1st Art)
|  | S.P216 | First Article Cavities (197MHz Crab 1st Art)
|  | S.P217 | First Article Vacuum Vessel (197 MHz Crab 1st Art)
|  | S.P218 | Cavities (591 1-Cell Production)
|  | S.P219 | Helium Vessel (591 1-Cell Production CMs)
|  | S.P220 | Misc. Parts (591 1-Cell Production CMs)
|  | S.P221 | Instrumentation (591 1-Cell Production CMs)
|  | S.P222 | Saddles and Stands (591 1 Cell Productions CMs)
|  | S.P223 | Vacuum Vessel (591 1-Cell Production CMs)
|  | S.P224 | Heat Exchangers (591 1-Cell Production CMs)
|  | S.P225 | Spaceframes with Thermal Sheild Assy. (591 1-Cell Production CMs)
|  | S.P226 | Thermal Shield (591 1-Cell Production CMs)
|  | S.P227 | Mag Shields (591 1-Cell Production CMs)
|  | S.P228 | Helium Vessel (591 5-Cell Production CMs)
|  | S.P229 | Misc. Parts (591 5-Cell Production CMs)
|  | S.P230 | Instrumentation (591 5-Cell Production CMs)
|  | S.P231 | Saddles and Stands (591 5-Cell Production CMs)
|  | S.P232 | Vacuum Vessel (591 5-Cell Production CMs)
|  | S.P233 | Heat Exchangers (591 5-Cell Production CMs)
|  | S.P234 | Spaceframes with Thermal Shield Assy. (591 5-Cell Production CMs)
|  | S.P235 | Thermal Shield (591 5-Cell Production CMs)
|  | S.P236 | Mag Shields (591 5-Cell Production CMs)
|  | S.P237 | Beamline Gate Valves (1773 5-Cell)
|  | S.P238 | Beamline Components (1773 5-Cell)
|  | S.P239 | Cavities (1773 5-Cell)
|  | S.P240 | Misc. Parts (1773 5-Cell)
|  | S.P241 | Vacuum Vessel (1773 5-Cell)
|  | S.P242 | End Cans (1773 5-Cell)
|  | S.P243 | Misc Tooling (TJ-Facilities)
|  | S.P244 | Dewar #9 (TJ-Facilities)
|  | S.P245 | Horizontal Electro Polish Station (TJ-Facilities)
|  | S.P246 | High Pressure Rinse Station (TJ-Facilities) (Includes Removal)
|  | S.P247 | Buffered Chemical Polishing Station (TJ-Facilities)
|  | S.P248 | Heat Treatment Furnace (TJ-Facilities)
|  | S.P249 | CMM (TJ-Facilities)
|  | S.P250 | Electron Beam Welder Chamber Extension (TJ-Facilities)
|  | S.P251 | Production Beamline Components (197 MHz Crab Production)
|  | S.P252 | Production Helium Vessel (197 MHz Crab Production)
|  | S.P254 | Production Beamline Gate Valves (394 MHz Crab Production)
|  | S.P255 | Production Beamline Components (394 MHz Crab Production)
|  | S.P256 | Production Helium Vessel (394 MHz Crab Production)
|  | S.P257 | Misc. Parts (394 MHz Crab Production)
|  | S.P259 | Vacuum Vessel (394 MHz Crab Production)
|  | S.P261 | End Cans (394 MHz Crab Production)
|  | S.P262 | Spaceframes with Thermal Shield Assy. (394 MHz Crab Production)
|  | S.P263 | Thermal Shield (394 MHz Crab Production)
|  | S.P264 | Satellite Refrigerators - FDR
|  | S.P265 | Satellite Refrigerators - PDR
|  | S.P266 | Diagnostic Instruments Procurement - Bergoz
|  | S.P266 | Diagnostic Instruments Procurement - Bergoz
|  | S.P266.A | ICT Material - Bergoz
|  | S.P266.A | ICT Material - Bergoz
|  | S.P266.B | FCT Material - Bergoz
|  | S.P266.C | DCCT Material - Bergoz
|  | S.P266.C | DCCT Material - Bergoz
|  | S.P266.D | Profile Monitor Material - Bergoz
|  | S.P266.D | Profile Monitor Material - Bergoz
|  | S.P266.E | Emittance Slit Material - Bergoz
|  | S.P266.E | Emittance Slit Material - Bergoz
|  | S.P266.F | Beam Loss Monitors Materials - Bergoz
|  | S.P266.F | Beam Loss Monitors Materials - Bergoz
|  | S.P267 | Magnet Measurement Power Supply (RCS-Dipoles)
|  | S.P271 | ESR-Quad 2
|  | S.P271.A | ESR-Quad 2 First Article
|  | S.P271.B | ESR-Quad 2 Production Magnets
|  | S.P272 | ESR-Correctors
|  | S.P272.A | First Article Magnet
|  | S.P272.B | Production Magnets and Material
|  | S.P273 | 20keV Mott Polarimeter
|  | S.P274 | Networking Switches
|  | S.P275 | PLCs - Implementation
|  | S.P275.A | PLCs - Generic applications - Implementation - Design
|  | S.P275.B | PLCs - Generic applications - Implementation - Construction
|  | S.P276 | Compute Servers (compile/test, project, thin client support) - Implementation
|  | S.P277 | Network Storage - Implementation
|  | S.P278 | Networking - Switches - Implementation
|  | S.P279 | Networking - Racks - Implementation
|  | S.P280 | Common Platform - Implementation
|  | S.P280.A | Common Platform - Electronics - Implementation
|  | S.P280.B | Common Platform - Carrier Components - Implementation
|  | S.P281 | Common Platform - Daughtercard Components - Implementation
|  | S.P282 | Spin Rotator Design - Saclay
|  | S.P283 | Common Platform - Chassis and support equipment - Implementation
|  | S.P284 | PLCs - Generic Applications & Safety Rated - Implementation
|  | S.P285 | Accelerator Physics Computer Cluster
|  | S.P286 | Cryo Controls - Active Beam Screen Cable
|  | S.P287 | Backward EMCal SiPMs
|  | S.P288 | Barrel EMCal SiPMs
|  | S.P289 | Barrel EMCal Detector Mechanical Components, Machining, Fabrication
|  | S.P290 | Detector Infrastructure - Solenoid
|  | S.P291 | Detector Infrastructure - Barrel EMCal Imaging
|  | S.P292 | Detector Infrastructure - Flux Return Bars
|  | S.P293 | Detector Infrastructure - pfRICH
|  | S.P294 | Detector Infrastructure - Barrel EMCal
|  | S.P295 | Production (FTOF)
|  | S.P296 | RF Shielded Bellows
|  | S.P297 | RHIC Y Main Dipole and Y Main Quad PS
|  | S.P298 | IR 4, 10 & 12 Warm D0 PS
|  | S.P299 | Fermi Lab Resource - Electron Polarization Calculation in the ESR [FY23/FY24]
|  | S.P300 | Detector Infrastructure - dRICH
|  | S.P301 | Fermi Lab Resource - Electron Polarization Calculation in the ESR [FY24]
|  | S.P302 | SP #302 - HSR Collimators - Cryo Mods for Momentum Collimator
|  | S.P303 | Direct Wind Magnets - IR Magnet Yokes
|  | S.P304 | Collared Magnets - IR Magnet Yokes
|  | S.P305 | Forward HCal SiPMs
|  | S.P306 | Barrel HCal SiPMs
|  | S.P307 | ESR Modification to building power and distribution
|  | S.P308 | (New Code Value)
|  | S.P309 | (New Code Value)
|  | S.P310 | (New Code Value)
|  | S.P311 | Detailed (90%) Design - Vendor Contract
|  | S.P312 | Coil Assembly and Yoke Material
|  | S.P313 | Install Cable and Cable Tray
|  | S.P313.A | Install Cable and Cable Tray: 1004B
|  | S.P313.B | Install Cable and Cable Tray: 1012B
|  | S.P313.C | Install Cable and Cable Tray: 1008B
|  | S.P313.D | Install Cable and Cable Tray: IR02
|  | S.P313.E | Install Cable and Cable Tray: IR06
|  | S.P313.F | Install Cable and Cable Tray: AS011
|  | S.P313.G | Install Cable and Cable Tray: AS01
|  | S.P313.H | Install Cable and Cable Tray: AS03
|  | S.P313.I | Install Cable and Cable Tray: AS05
|  | S.P313.J | Install Cable and Cable Tray: AS07
|  | S.P313.K | Install Cable and Cable Tray: AS09
|  | S.P313.L | Install Cable and Cable Tray: IR10
|  | S.P314 | RF-CRAB-1-CTRL
|  | S.P314.A | First Article - RF-CRAB-1-CTRL
|  | S.P314.B | Production - RF-CRAB-1-CTRL
|  | S.P315 | ATR Qaud/Dipole Medium PS Straight Quads/ Setupole
|  | S.P316 | HSR 591-5 Cell RF 70KW PWR - Amplifier
|  | S.P317 | RCS 591-5 Cell RF 75kW PWR - Amplifier
|  | S.P317.A | First Article - RCS 591-5 Cell RF 75kW PWR - Amplifier
|  | S.P317.B | Production - RCS 591-5 Cell RF 75kW PWR - Amplifier
|  | S.P318 | IR Magnet Cryostats - Forward
|  | S.P319 | Tunnel Feedbox for Matching Section
|  | S.P320 | B2pF B3pF Cryostat
|  | S.P321 | SHC Chicane Feedbox
|  | S.P322 | Solenoid Detector Cryocan and Flex line
|  | S.P323 | Solenoid Conductor
|  | S.P324 | Vacuum Tooling and Equipment - Clean Assembly Area
|  | S.P325 | Vacuum Tooling and Equipment - Material Handling and Storage
|  | S.P326 | Vacuum Tooling and Equipment - Support Equipment for Girder Integration
|  | S.P327 | Vacuum Tooling and Equipment - Bakeout Equipment
|  | S.P328 | RF-ESR-1 Test Power: Circulators & Loads
|  | S.P329 | B1pF Prototype Material - Collaring Parts
|  | S.P330 | RCS Girder Fabrication - Type 1
|  | S.P331 | RCS Girder Fabrication - Type 2
|  | S.P332 | RCS Girder Fabrication - Type 3
|  | S.P333 | RCS Girder Fabrication - Type 4
|  | S.P334 | RCS Girder Fabrication - Type 5
|  | S.P335 | ESR Girder Fabrication - Type 1
|  | S.P336 | ESR Girder Fabrication - Type 2
|  | S.P337 | ESR Girder Fabrication - Type 3
|  | S.P338 | ESR Girder Fabrication - Type 4
|  | S.P339 | ESR Girder Fabrication - Type 5
|  | S.P340 | Collared Dipole - Design (LBNL)
|  | S.P340.A | Collared Dipole - Preliminary Design (LBNL)
|  | S.P340.B | Collared Dipole - Final Design (LBNL)
|  | S.P341 | RCS Extraction Kicker
|  | S.P342 | RCS Extraction Septum - Electrical Components
|  | S.P343 | RCS Extraction Septum - Mechanical Components
|  | S.P344 | HSR Laser welding equipment for cooling tube
|  | S.P345 | Bellows Helper Spring assembly
|  | S.P346 | RF Fingers
|  | S.P347 | Bellows Components
|  | S.P348 | Solenoids
|  | S.P349 | Machined Parts
|  | S.P350 | Control Valves
|  | S.P351 | Coating Tubes
|  | S.P352 | ESR Vacuum RF Bellows
|  | S.P353 | ESR Vacuum Hardware and Seals
|  | S.P354 | Detector Infrastructure - Cradle and Fabrication
|  | S.P355 | Detector Infrastructure - Electron Endcap EMCal
|  | S.P356 | Detector Infrastructure - Hadron Endcap EMCal
|  | S.P357 | Utilities Integration - Rails for End Caps
|  | S.P358 | Utilities Integration - Guide Beams for End Caps
|  | S.P359 | Utilities Integration - Pulling Mechanisms for End Caps
|  | S.P360 | Detector R&D Contracts Procurement - FY24
|  | S.P361 | Electron Endcap HCal - HGCROC
|  | S.P362 | Electron Endcap HCal - Scintillator Tiles - Inner Part
|  | S.P363 | Electron Endcap HCal - Reflective and Capton Foil
|  | S.P364 | Power Supplies
|  | S.P365 | Forward HCal - HV cables and connector at detector
|  | S.P366 | SALSA FEB (Outer Gas Barrel Tracking)
|  | S.P367 | Readout electronics hpDIRC EICROC FEB - (PID hpDIRC)
|  | S.P368 | Readout Electronics - pfRICH EICROC FEB (PID pfRICH)
|  | S.P369 | Interface PCB and components (HV, anode, LED) (Barrel ECAL)
|  | S.P370 | HV cable and connectors at detector (Barrel ECAL)
|  | S.P371 | Interface PCB and components (HV, anode, LED) (Forward pECAL)
|  | S.P372 | PCB assembly (Forward pECAL)
|  | S.P373 | Signal cable and connectors (Forward pECAL)
|  | S.P374 | HV cable and connectors at detector (Forward pECAL)
|  | S.P375 | Fibers (Forward pECAL)
|  | S.P376 | Detector Computing - Readout Server - Phase 2
|  | S.P377 | Not in Use
|  | S.P378 | Detector Computing - Fiber Connectors
|  | S.P379 | HJET Target Gas Analyzer (TGA)
|  | S.P380 | Luminosity Monitor
|  | S.P380.A | Engineering Design Verification
|  | S.P380.B | PreProduction Units
|  | S.P380.C | Procurement and Fabrication
|  | S.P381 | Forward HCal - SiPM Flex
|  | S.P382 | Barrel EMCal Engineering Design Verification
|  | S.P383 | HSR Vacuum Mechanical Components
|  | S.P384 | Interface PCB & Components (HV, Anode, LED) Fabrication
|  | S.P385 | PCB Assembly Fabrication (In Kind) - Electromagnetic Calorimetry
|  | S.P386 | PCB Assembly Fabrication - Hadronic Calorimetry - Hadron Endcap HCal
|  | S.P387 | Interface PCB and Components (HV, Anode, LED) (Forward LFHCAL)
|  | S.P388 | PCB Assembly (Forward LFHCAL)
|  | S.P389 | Signal Cables and Connectors (Forward LFHCAL)
|  | S.P390 | HV Cable and Connectors at Detector (Forward LFHCAL)
|  | S.P391 | RDO - Production (RDO Readout Board)
|  | S.P392 | HRPPD Sensors (pfRICH)
|  | S.P393 | Detector R&D Contracts - FY23
|  | S.P394 | ERL 591-5 Cell RF 50kW PWR - Circulators
|  | S.P395 | Construction - Materials (FTTL)
|  | S.P396 | Aerogel (dRICH)
|  | S.P397 | Power - Silicon Procurement
|  | S.P398 | Electron Endcap HCal Absorber Structure
|  | S.P399 | Inner Barrel Gas Tracking
|  | S.P400 | Outer Barrel Gas Tracking
|  | S.P401 | Engineering Test Article Hardware (ZDC)
|  | S.P402 | EMCAL PbWO4 - Crystals (ZDC)
|  | S.P403 | EMCAL PbWO4- readout SiPM/APD/PMT (ZDC)
|  | S.P404 | Imaging W+Si - Procure W Plates (ZDC)
|  | S.P405 | Imaging W+Si - Si small Pad sensors (ZDC)
|  | S.P406 | Imaging Pb+Si - Si small Pad sensor (ZDC)
|  | S.P407 | Imaging Pb+Si - Si small Pad readout (ZDC)
|  | S.P408 | HCAL Pb+Sci - Scintillators readout (ZDC)
|  | S.P409 | Wafer - Vertex Procurement
|  | S.P410 | Middle Layers Procurement
|  | S.P411 | Additional Tooling for Staves - CMM Procurement
|  | S.P412 | Additional Tooling for Disks - CMM Procurement
|  | S.P413 | Half Disks 3,4,5 Procurement
|  | S.P414 | Bonding Machine Procurement
|  | S.P415 | Pick and Place Procurement
|  | S.P416 | Module Fabrication Procurement
|  | S.P417 | Fibers Procurement (PID mRICH) (IN-KIND)
|  | S.P418 | Power supply and cables (PID mRICH) (IN-KIND)
|  | S.P419 | B1pF Tooling Material - Curing Fixture Assembly
|  | S.P420 | B1pF Tooling Material - Winding Mandrel Assembly
|  | S.P421 | Forward HCal - scintillator tiles machined
|  | S.P422 | Forward HCal - scintillator tiles molded
|  | S.P423 | Forward HCal - Connectors
|  | S.P424 | Temperature Monitoring
|  | S.P425 | Bellows Fixturing & Tooling
|  | S.P426 | Arc Beam Screens profile
|  | S.P427 | Beam Screens Insertion Tooling
|  | S.P428 | Clean Assembly Area
|  | S.P429 | Material Handeling & CHamber Storage
|  | S.P430 | Support for Grider Integration
|  | S.P431 | Bakeout Equipment
|  | S.P432 | Measurement and Data Logging Equipment
|  | S.P433 | Portable Clean Room Tents
|  | S.P434 | RCS Arc Chambers - Arc 9,11
|  | S.P435 | RCS Bellows
|  | S.P436 | RCS Arc Chambers - Arc 5, 3, 1, 7
|  | S.P437 | RCS Straight Section Chambers
|  | S.P438 | RCS Support, Seals & Hardware
|  | S.P439 | RCS to ESR Vacuum
|  | S.P440 | Lepton Polarimetry - Position Detectors - RCS
|  | S.P441 | Electron Endcap HCal - Scintillating Megatiles
|  | S.P442 | Forward HCal Absorber Plates Steel
|  | S.P442.A | Forward HCal Absorber Plates Steel - Initial Award
|  | S.P442.B | Forward HCal Absorber Plates Steel - Option 1
|  | S.P442.C | Forward HCal Absorber Plates Steel - Option 2
|  | S.P443 | Detector R&D BNL Procurements FY25
|  | S.P444 | Arc Beam Screens guides
|  | S.P445 | Beam Screens miscelleaneous parts
|  | S.P446 | Prisms (hpDIRC)
|  | S.P447 | ASCIS (RP)
|  | S.P448 | Bellows Helper Spring Assembly
|  | S.P449 | First and Second Station Silcon (Low Q2)
|  | S.P450 | Barrel EMCal - Pb/SciFi absorber - Lead and Al Sheet
|  | S.P451 | Barrel EMCal Preproduction - Wafer Prober
|  | S.P452 | Barrel EMCal Preproduction - Pick and Place Machine
|  | S.P453 | Barrel EMCal Preproduction - Module QC Test Stand
|  | S.P454 | Barrel EMCal Production - Module PCB
|  | S.P455 | Barrel EMCal Production Development
|  | S.P456 | ESR Sextupole Magnets
|  | S.P456.A | ESR Sextupole Magnets - First Article
|  | S.P456.B | ESR Sextupole Magnets - Production
|  | S.P457 | ESR Magnets - APS Sextupole
|  | S.P458 | Construction/Assemble of Prism Box (hpDIRC)
|  | S.P459 | First Article Beamline Components (591 1-Cell 1st Art)
|  | S.P460 | First Article End Cans (591 1-Cell 1st Art)
|  | S.P461 | Mirrors (pfRICH) - Inner and Outer Conical Mirror Set
|  | S.P462 | Arc Beam Screen Material
|  | S.P463 | Magnet Processing, Storage, and Supplies-ESR APS Magnets
|  | S.P464 | Tracking FY 29 Procurements
|  | S.P465 | (MPGD) Trackers FY 24 Procurements
|  | S.P466 | (MPGD) Trackers FY 25 Procurements
|  | S.P467 | (MPGD) Trackers FY 27 Procurements
|  | S.P468 | Solenoid Conductor
|  | S.P469 | UK Design 1773 5-Cell
|  | S.P470 | Available
|  | S.P471 | Mechanical Assembly Full System Detector (dRICH)
|  | S.P472 | B1pF Production - Collar Assembly
|  | S.P473 | B1ApF Production - Collar Assembly
|  | S.P474 | Q2pF Production - Collar Assembly
|  | S.P475 | Q1ApF Production - Collar Assembly
|  | S.P476 | Q1BpF Production - Collar Assembly
|  | S.P477 | 197MHz First Article Cavities Raw Niobium
|  | S.P478 | PED contract for Barrel EMCal Imaging Calorimeter
|  | S.P479 | PED contract for Barrel EMCal Imaging Calorimeter
|  | S.P480 | PED contract for Barrel EMCal Imaging Calorimeter
|  | S.P481 | PED contract for Barrel EMCal Imaging Calorimeter
|  | S.P482 | Detector R&D Contracts Procurement - FY26
|  | S.P483 | PED contract for Barrel EMCal Imaging Calorimeter
|  | S.P484 | First Article Cavities (591 1-Cell 1st Article)
|  | S.P485 | eRD113 - MAPS Sensors ITS3
|  | S.P486 | Detector R&D - Procurements - JLAB - FY25
|  | S.P487 | ESR Machine Protection Beam Abort Kicker Mechanical Components
|  | S.P488 | Replacement Coils for APS Sextupole Magnets (PED)
|  | S.P489 | Cold bore inspection Mole
|  | S.P490 | ESR Profile
|  | S.P491 | Prototype Chamber
|  | S.P492 | ESR Bellows
|  | S.P493 | BTOF - Module Assembly
|  | S.P494 | FTOF - Sensor-ASIC Integration - Final Design
|  | S.P495 | Detector Solenoid - Cryocan and CryoFlex Line
|  | S.P496 | Detector R&D - Procurements - Final Acceptance - JLAB - FY27
|  | S.P497 | B1pF Prototype - Superconducting Strand (1.065mm)
|  | S.P498 | 197MHz DVC - ANL Cavity Support
|  | S.P499 | 197MHz DVC - Scientist Supprt
|  | S.P500 | HSR BPM Signal Cables and Connectors
|  | S.P501 | HSR BPM Cryo Feedthrough
|  | S.P502 | Calorimeter Digitizers - Discrete/HGCROC 64-Channel ADC PCB - Supporting PCB and Hardware
|  | S.P503 | ESR BPM - Common Platform System
|  | S.P504 | BTOF - Sensor - ASIC Integration
|  | S.P505 | BTOF - Flex Module - PCB
|  | S.P506 | BTOF - Service Hybrid
|  | S.P507 | FTOF - Service Hybrid Module PCB
|  | S.P508 | FTOF - Sensor
|  | S.P509 | FTOF - Sensor-ASIC Integration
|  | S.P510 | CMTF Procurement
|  | S.P511 | ZDC - EMCAL PbWO4 - Crystals
|  | S.P512 | RP - Sensors
|  | S.P513 | RCS PTM - Profile Monitor Station
|  | S.P514 | Magnet Measurement Stand (RCS-Dipole)
|  | S.P515 | BTOF - CTTL AC-LGAD - Service Hybrid - Production
|  | S.P516 | FTOF - FTTL AC-LGAD - Service Hybrid & Module - Production - Fab & Asy
|  | S.P517 | RCS Vacuum Pump Controllers
|  | S.P518 | RCS Vacuum Pump Connectors
|  | S.P519 | RCS Vacuum Pump Cables
|  | S.P520 | RCS Vacuum Pumps
|  | S.P521 | ESR Vacuum Pumps
|  | S.P522 | ESR Vacuum Pump Controllers
|  | S.P523 | RCS Chambers Stands
|  | S.P524 | Mobile Pump Stations
|  | S.P525 | Leak Detectors
|  | S.P526 | Misc Support Hardware
|  | S.P527 | RCS Vacuum PLC Hardware
|  | S.P528 | ESR Vacuum Monitoring and Controls
|  | S.P529 | ESR Vacuum PLC hardware
|  | S.P530 | Vacuum RGAs
|  | S.P531 | Bellows Thermal Strap
|  | S.P532 | Arc Beam Screens Engineering Validation Unit
|  | S.P533 | PLCs - Safety Rated - Implementation
|  | S.P533.01 | PLCs - Safety Rated - Implementation - PSS: Safety I/O
|  | S.P533.02 | PLCs - Safety Rated - Implementation - PSS: Communications Hardware
|  | S.P533.03 | PLCs - Safety Rated - Implementation - PSS: Power Supplies and UPS
|  | S.P533.04 | PLCs - Safety Rated - Implementation - PSS: Enclosures
|  | S.P533.05 | PLCs - Safety Rated - Implementation - PSS: Other Hardware
|  | S.P533.06 | PLCs - Safety Rated - Implementation - PSS: Software Licensing
|  | S.P533.07 | PLCs - Safety Rated - Implementation - PSS: Door Switches and Locksets
|  | S.P533.08 | PLCs - Safety Rated - Implementation - PSS: Doors
|  | S.P533.09 | PLCs - Safety Rated - Implementation - PSS: Other Door Hardware
|  | S.P533.10 | PLCs - Safety Rated - Implementation - PSS: Electrical Safety Rated Contractors
|  | S.P533.11 | PLCs - Safety Rated - Implementation - PSS: E-Stop Actuators
|  | S.P533.12 | PLCs - Safety Rated - Implementation - PSS: Ratiation Monitors Interfacing Hardware
|  | S.P533.13 | PLCs - Safety Rated - Implementation - PSS: Sweep Check Stations
|  | S.P533.14 | PLCs - Safety Rated - Implementation - PSS: Audible/Visual Warning Alarms
|  | S.P533.15 | PLCs - Safety Rated - Implementation - PSS: Laser Shutter Safety Switches
|  | S.P533.16 | PLCs - Safety Rated - Implementation - PSS: HMI Displays
|  | S.P533.17 | PLCs - Safety Rated - Implementation - PSS: Safety Relays
|  | S.P533.18 | PLCs - Safety Rated - Implementation - PSS: Cable & Wires
|  | S.P533.19 | PLCs - Safety Rated - Implementation - PSS: Cameras
|  | S.P533.20 | PLCs - Safety Rated - Implementation - ODH: Safety I/O
|  | S.P533.21 | PLCs - Safety Rated - Implementation - ODH: Communications Hardware
|  | S.P533.22 | PLCs - Safety Rated - Implementation - ODH: Power Supplies and UPS
|  | S.P533.23 | PLCs - Safety Rated - Implementation - ODH: Enclosures
|  | S.P533.24 | PLCs - Safety Rated - Implementation - ODH: Other Hardware
|  | S.P533.25 | PLCs - Safety Rated - Implementation - ODH: Software Licensing
|  | S.P533.26 | PLCs - Safety Rated - Implementation - ODH: O2 sensors
|  | S.P533.27 | PLCs - Safety Rated - Implementation - ODH: Audible/Visual Warning Alarms
|  | S.P533.28 | PLCs - Safety Rated - Implementation - ODH: Safety Relays
|  | S.P533.29 | PLCs - Safety Rated - Implementation - ODH: Cable & Wires
|  | S.P534 | Silicon Trackers - Wafer Probing for Vertex Sensors
|  | S.P534.A | Silicon Trackers - Wafer Probing for Vertex Sensors - RCV - Vendor Delivery - 1
|  | S.P534.B | Silicon Trackers - Wafer Probing for Vertex Sensors - RCV - Vendor Delivery - 2
|  | S.P534.C | Silicon Trackers - Wafer Probing for Vertex Sensors - RCV - Vendor Delivery - 3
|  | S.P534.D | Silicon Trackers - Wafer Probing for Vertex Sensors - RCV - Vendor Delivery - 4
|  | S.P534.E | Silicon Trackers - Wafer Probing for Vertex Sensors - RCV - Vendor Delivery - 5
|  | S.P534.F | Silicon Trackers - Wafer Probing for Vertex Sensors - RCV - Vendor Delivery - 6
|  | S.P534.G | Silicon Trackers - Wafer Probing for Vertex Sensors - RCV - Vendor Delivery - 7
|  | S.P534.H | Silicon Trackers - Wafer Probing for Vertex Sensors - RCV - Vendor Delivery - 8
|  | S.P535 | RCS Pre Assembly Consumables
|  | S.P536 | Silicon Trackers - CERN - ALICE ITS3 - Pixel Sensor Chip - NRE - Annex 1
|  | S.P537 | Tracking FY 25 Procurements
|  | S.P538 | Inner Gas Barrel Tracking - SALSA FEB
|  | S.P539 | RHIC-Style Ion Chamber BLMs
|  | S.P540 | Replacement Coils for APS Sextupole Magnets (CD-3B)
|  | S.PP059 | End Cans (591 5-Cell Production CMs)
|  | T | Travel (Does not Obligate)
|  | T.LLP010 | HSR BPM Cryo Cables - Travel
|  | T.LLP010.A | HSR BPM Cryo Cables Pre-Production - Travel
|  | T.LLP010.B | HSR BPM Cryo Cables Production - Travel
|  | T.LLP011 | HSR BPM Buttons - Travel
|  | T.LLP011.A | HSR BPM Buttons Design Verification Units - Travel
|  | T.LLP011.B | HSR BPM Buttons Production - Travel
|  | T.LLP014 | 591 MHz 1-Cell FA Cryomodule - Travel
|  | T.LLP015 | Satellite Plant IR10 - Travel
|  | T.LLP016 | Satellite Plant IR02 - Travel
|  | T.LLP017 | Satellite Plant IR06 - Travel
|  | T.LLP019 | Installation IR06 - Travel
|  | T.LLP020 | Installation IR10 - Travel
|  | T.LLP022 | Installation IR02 - Travel
|  | T.LLP023 | Unit Substation Transformers for Bldgs - Travel
|  | T.LLP024 | First Article Magnet Vendor - Travel
|  | T.LLP025 | Production Magnets and Material Vendor - Travel
|  | T.LLP026 | Magnet Measurement Power Supply (RCS-Dipoles) - Travel
|  | T.LLP027 | APS Quad Refurbishment Parts - Travel
|  | T.LLP028 | APS Quad Rebuilt Parts - Travel
|  | T.LLP029 | RCS BPM Buttons - Travel
|  | T.LLP030 | Inspect Incoming Equipment - IR06
|  | T.LLP031 | Inspect Incoming Equipment - IR10
|  | T.LLP032 | Inspect Incoming Equipment - IR02
|  | T.T.LLP18 | Aux System LN2 Distribution Systems
|  | T.T.LLP30 | Aux System Ambient Air Heat Exchanger
|  | TOOL | Tooling / Consumables (Does not Obligate)
|  | U | Utilities (Does not Obligate)

## Instructions (hidden)
STEP 1 | Run BABO_LLP List from P6 Reports
STEP 2 | Once above report is run delete row 1 and delete column Z. Data is now ready to be pasted into Tab 1.A. Refresh formulas.
STEP 3 | Open the following P6 Layout and paste into the dated, uncolored Tab 1.B. Update the date in the Tab name and refresh formulas.
STEP 4 | FOR CD-3B ONLY
If there are blanks under BNL_Procurement Designation, input "Labor Only" for those cells. The LLP Item should be ITEM92.
Update tab 1.B with "Labor Only" for No BNL_Procurement Designation
STEP 5 | Similar to the BABO, copy and paste all the Procurement Designations from Tab 1.A. Paste into tab 2.A, remove duplicates, sort A-Z, and update Column C.
STEP 6 | Update the BNL_Procurement Designation list on tabs 2.B, 2.C, 3, and 4.
STEP 7 | Paste the data appropriately.
2.B and 2.C Data
Paste the tables from those two tabs and update formulas.
2.C and 4 Data
Paste the tables from those two tabs and update formulas.
Make sure to delete the "TOTAL" column from the data you pasted.
STEP 8 | Change Data Source on the Obligation Pivot and Cost Pivot.
From here, paste the contents of each pivot to the LLP Summary tabs.
The rest is formatting and formulas.
You'll use lookup formulas for CAM, Estimator, and PMC Rep.
Award Dates, Direct Material Cost, and Labor Hours will be formulas.
The time-phased data is a direct paste from the Obligation/Cost Pivot.

## PVT (FY) MGMT&OS_Sample (hidden)
BNL_Fund_Source | (Multiple Items)
Row Labels | Sum of FY2020 | Sum of FY2021 | Sum of FY2022 | Sum of FY2023 | Sum of FY2024 | Sum of FY2025 | Sum of FY2026 | Sum of FY2027 | Sum of FY2028 | Sum of FY2029 | Sum of FY2030 | Sum of FY2031 | Sum of FY2032 | Sum of FY2033 | Sum of FY2034
Accel Physics | 853144.44 | 5031352.77 | 5506872.43 | 3809977.56 | 4270247.72 | 3379166.01 | 2759608.81 | 1942865.29 | 1397946.4 | 345946.34 | 296209.94 | 746187.87
Construction.Assemble |  |  |  | 56414.69 | 157091.24 | 559195.83 | 3787277.2 | 8173428.6 | 13259102.53 | 18306884.31 | 11600226.15 | 1633958.95 | 25972.02 | 23938.35
Construction.Fabricate | 0.01 |  |  | 968973.76 | 30835592.95 | 60112468.45 | 73135569.01 | 56400285.51 | 24243844.12 | 17680685.5 | 2312818.12 | 393928.6
Construction.Installation
Construction.Procure | 123657.31 |  | 39877.2 | 876395.93 | 4399544.22 | 9682831.69 | 18140449.9 | 7426833.38 | 3040495.13 | 989734.35 | 150899.56 | 121189.65 | 6291.06
Construction.Removals |  |  |  | 27267.92 | 77069.17 | 791549.17 | 11215679.33 | 24190704.88 | 34707920.12 | 30360281.63 | 24697919.82 | 11064096.64 | 4409078.26 | 2633471.74
Construction.Test & Accept |  |  |  | 65810.54 | 348408.06 | 3526758.26 | 6658416.35 | 22244315.93 | 25301105.08 | 17746531.8 | 10590664.74 | 3252371.66 | 326330.68
Mgmt & Oversight | 2633919.66 | 13207115.12 | 15553003.88 | 28507382.79 | 32223886.91 | 36203126.19 | 39016515.38 | 40266556.42 | 36622572.66 | 29502395.44 | 18155353.65 | 14766501.32 | 4800653.8 | 398427.37
PED.Conceptual.Act | 2511095.44 | 4861340.67 | 4246949.56
PED.Conceptual.Des | 21664.49 |  |  | 15765.1 | 379.47
PED.Final | 127455.11 | 22757.59 | 160486.75 | 6917884.53 | 28650402.43 | 30693864.4 | 12021632.92 | 6586729.75 | 1540949.92 | 521194.02 | 89880.33
PED.Preliminary.Act |  | 370588.19 | 4380814.03
PED.Preliminary.Des | 59776.45 | 34937.91 | 244125.86 | 17104910.03 | 25511654.6 | 9208642.64 | 1575864.58 | 283428.08 | 46881.26
Pre-Ops and Comm |  |  |  | 32343.1 | 49569.91 | 331509.17 | 950218.25 | 5361106.25 | 6171212.27 | 5385458.24 | 5727809.8 | 5739715.59 | 17008229.77 | 9551566.65 | 1007921.09
R&D | 109078.32 | 3955066.28 | 6547696.58 | 21097047.74 | 19355259.28 | 6113223.43 | 1127122.79 | 1159842.18 | 181696
(blank)
Grand Total | 6439791.23 | 27483158.53 | 36679826.29 | 79480173.69 | 145879105.96 | 160602335.24 | 170388354.52 | 174036096.27 | 146513725.49 | 120839111.63 | 73621782.11 | 37717950.28 | 26576555.59 | 12607404.11 | 1007921.09
| 2633919.66 | 13207115.12 | 15553003.88 | 28544745.39 | 32370138.51 | 36751264.19 | 39654718.58 | 40635550.52 | 36893564.36 | 29502395.44 | 18155353.65 | 14766501.32 | 4800653.8 | 398427.37
DOE/IRA | 2633919.66 | 13207115.12 | 15553003.88 | 28507382.79 | 32223886.91 | 36203126.19 | 39016515.38 | 40266556.42 | 36622572.66 | 29502395.44 | 18155353.65 | 14766501.32 | 4800653.8 | 398427.37
| 0 | 0 | 0 | 37362.6 | 146251.6 | 548138 | 638203.2 | 368994.1 | 270991.7 | 0 | 0 | 0 | 0 | 0