## CD-3A Documentation
CD-3A Review Documentation
Topic | Title | Owner | Status
Documentation
| Project Execution Plan | L. Lari | check for docs referenced
| Project Management Plan | L. Lari
| Updated Acquisition Strategy | C. Lavelle
| Assumptions Document | C. Lavelle
| Technical Design Maturity Plan | K. Smith
| Technical Design Review Schedule | K. Smith
| Technical Design Report | F. Willeke
| Requirements Document | K. Smith
| EVM System Description | K. Krug | Complete
| WBS Dictionary | C. Lavelle
| Cost Estimating Plan | K. Krug | Cathy - EU, Kelly - Cost Basis update
| Update Hazard Analysis Plan | C. Schaeffer
| Risk Management Plan | I Sourikova
| Risk Register | I Sourikova
| LLP Risks | I Sourikova
| Integrated Safety Management Plan | C. Schaeffer
| Quality Assurance Plan | C. Porretto
| Project Organization Chart | J. Yeck
| NEPA determination | C. Schaeffer
| Security Vulnerability Plan | L. Lari
| Long Lead Procurement List | C. Lavelle | Complete
| Long Lead Procurement Justification Form | L.Lari
| Acquisition Plans for LLPs (if applicable) | S. Alexander
| IMOU - BNL | C. Lavelle | Complete
| IMOU - JLAB | J. Fast
| Updated Procurement Plan | S. Alexander
| Configuration Management Plan | C. Porretto
| Recommendation Tracker Update | C. Porretto
Cost and Schedule
| Cartoon schedule | K. Krug | Complete
| WBS Structure | K. Krug | Complete
| RAM | K. Krug
| Escalation Analysis | H. Turbush
| Reference Profile v4 plusv5 Scenarios | C. Lavelle | Complete
| Cost Summary L2 and L3 | K. Krug
| BABO CD-3A and full project | K. Krug | Complete 3A , Full Project needs leveling procurement
| Project Schedule from P6 | K. Krug
| P6 XER file | K. Krug
| Critical Path | K. Krug
| Near Critical Items | K. Krug
| Procurement Schedule - P6 | K. Krug
| L1 and L2 Milestone Table | K. Krug | P6 PDF and Table
| L1-L4 Milestone Schedule | K. Krug
| Procurement Status | S. Alexander
| Funding Status | H. Turbush
| Project Status Chart | K. Krug
| LLP Items Basis of Estimate (BOE) | CAMs
Monthly Reports | Acumen Fuse | K. Krug
| June Monthly Report | C. Lavelle | Complete
| July Monthly Report | C. Lavelle | Complete
| August Monthly Report | C. Lavelle
| EVMS Practice Data - CPR , Variance Analysis, | K. Krug
| Work Authorization Documents | K. Krug
Close out Reports
| Accelerator Design Review | F. Willeke
| Detector Design Review | R. Ent/E. Aschenauer