## Sheet1
Updated 10/1/2010 | Jefferson Lab Order; JSA-10-C0674
Milestone Event; | Start Date | Completion Date/Comments
Order Entry | January 18,2010 | Completed 1/18/2010
Formal Design Review | May 10,2010 | Completed 5/31/2010
Final Definition of voltage/current |  | Completed 8/22/2010
Advanced Materials; All units | March 15,2010 | Complete
Receipt of long lead materials | July 15,2010 | Kanban deliveries to support production
Manufacturing;
First Article Unit; # 1 | June 20,2010 | November 30/2010
Unit one final released for Eng. |  | Complete
Kitting Sub Assemblies | August ,2010 | November 30/2010
First Article Testing Unit #1 | December 1,2010 | January 11,2011
J Lab witness test | January 18,2010 | January 18,2011
Ship First Article Unit |  | January 28,2011
Production Unit # 2 | January 14,2011 | March 31,2011
Production Unit # 3 |  | April 26,2011
Production Unit # 4 |  | May 31,2011
Production Unit # 5 |  | June 30,2011
Production Unit # 6 |  | July 29,2011
Production Unit # 7 |  | August 31,2011
Production Unit # 8 |  | September 30,2011
Production Unit #9 |  | October 28,2011
Production Unit # 10 |  | November 30,2011
Service Manuals 10 copies | To be shipped with units | Completed with unit # 10
Instruction Manuals and Dwgs |  | March 21,2011
Billing Unique Materials | September 3,2010 | September 3,2010 $10k
Billing Unique Materials | October 1,2010 | October 1 invoice; $90,000.00 #41575
Remaining Billing |  | Balance $70,000.00 will invoice 11/15