## Form
JSA / Jefferson Lab - DOE
PO Percent Complete Form
Appendix A
Vendor Name | RI - Research Instruments | [5 empty] | PO with Peg Points? (Yes or No) | No
PO Number | 15-C0587 |  |  | Buyer | FITZPATRICK | Complete through | 2016-01-31
(Date)
PO Line # | Percent Complete | Completed Peg Point (X) |  | Summary of Work (only if less than 100%)
1 | 100% |  |  | Proof of equipment order furnace uprade
2 | 100% |  |  | Proof of completed furnace uprade
3 | 100% |  |  | JLab Acceptance of nitrogen doping process - Cavity 1 (of 2)
4 |  |  |  | JLab Acceptance of nitrogen doping process - Cavity 2 (of 2)
5 | 75% |  |  | Phase II: Manufacturing Drawings released and accepted by JLab
6 |  |  |  | Phase II: First Article Cavities Mechanical Pre-fab (Deep Draw)
7 |  |  |  | Phase III: Production Cavities (9-72) Mechanical Pre-Fab
8 |  |  |  | Phase III: Production Cavities (73-133) Mechanical Pre-Fab
9 |  |  |  | Phase II: First Articles (1-8) Delivered and Accepted by JLab
10 |  |  |  | Phase III: Delivery & Acceptance of Cavities (9-12)
11 |  |  |  | Phase III: Delivery & Acceptance of Cavities (13-16)
12 |  |  |  | Phase III: Delivery & Acceptance of Cavities (17-20)
13 |  |  |  | Phase III: Delivery & Acceptance of Cavities (21-24)
14 |  |  |  | Phase III: Delivery & Acceptance of Cavities (25-28)
15 |  |  |  | Phase III: Delivery & Acceptance of Cavities (29-32)
16 |  |  |  | Phase III: Delivery & Acceptance of Cavities (33-36)
17 |  |  |  | Phase III: Delivery & Acceptance of Cavities (37-40)
18 |  |  |  | Phase III: Delivery & Acceptance of Cavities (41-44)
19 |  |  |  | Phase III: Delivery & Acceptance of Cavities (45-48)
20 |  |  |  | Phase III: Delivery & Acceptance of Cavities (49-52)
21 |  |  |  | Phase III: Delivery & Acceptance of Cavities (53-56)
22 |  |  |  | Phase III: Delivery & Acceptance of Cavities (57-60)
23 |  |  |  | Phase III: Delivery & Acceptance of Cavities (61-64)
24 |  |  |  | Phase III: Delivery & Acceptance of Cavities (65-68)
25 |  |  |  | Phase III: Delivery & Acceptance of Cavities (69-72)
26 |  |  |  | Phase III: Delivery & Acceptance of Cavities (73-76)
27 |  |  |  | Phase III: Delivery & Acceptance of Cavities (77-80)
28 |  |  |  | Phase III: Delivery & Acceptance of Cavities (81-84)
29 |  |  |  | Phase III: Delivery & Acceptance of Cavities (85-88)
30 |  |  |  | Phase III: Delivery & Acceptance of Cavities (89-92)
31 |  |  |  | Phase III: Delivery & Acceptance of Cavities (93-96)
32 |  |  |  | Phase III: Delivery & Acceptance of Cavities (97-100)
33 |  |  |  | Phase III: Delivery & Acceptance of Cavities (101-104)
34 |  |  |  | Phase III: Delivery & Acceptance of Cavities (105-108)
35 |  |  |  | Phase III: Delivery & Acceptance of Cavities (109-112)
36 |  |  |  | Phase III: Delivery & Acceptance of Cavities (113-116)
37 |  |  |  | Phase III: Delivery & Acceptance of Cavities (117-120)
38 |  |  |  | Phase III: Delivery & Acceptance of Cavities (121-124)
39 |  |  |  | Phase III: Delivery & Acceptance of Cavities (125-128)
40 |  |  |  | Phase III: Delivery & Acceptance of Cavities (129-133)
Vendor Technical Representative Contacted:
|  |  | Name |  |  |  |  | Date
Jlab Control Account Manager (CAM): |  |  |  |  | Ed Daly |  |  | 2016-01-31
[6 empty] | Name |  | Date
Below for use by Accounting/Shipping & Receiving Only
Accounting or Shipping & Receiving Entered By:
Date
Data Entry Verified By:
Date

## Process
JSA / Jefferson Lab - DOE
PO Percent Complete Form
Procedure
A Subcontract Purchase Order (PO) is a service type PO with loosely defined scheduled deliverables and variable amounts. A Peg Point PO has specified scheduled deliverable dates for a specified amount.
This form is to be used if NO invoice has been approved by the SOTR or CAM for work completed.
SOTR or CAM contacts a vendor technical representative for an evaluation of the percent of work completed. This can be done either verbally or via email.
Required information - Vendor Name, indicate if PO is a Peg Point type PO or not, PO #, Buyer, Complete through date (usually the end of the month), PO Line #, Percent complete, a short Summary of Work performed provided by the Vendor Technical Representative that supports the percent complete if less than 100%, the name of the Vendor Technical Representative contacted, and the CAM name.
The SOTR or CAM will submit a PO Percent Complete form by the 2nd working day following the end of the month affected for work that has been completed. This allows time for Accounting to process an accrual for the month end closing. Reminder if PO is for Peg Points, the peg point must be fully complete before claiming it.
Submit the completed form with all the information via email to evpo@jlab.org. The file name of the spreadsheet attached to the email should always include the PO# and the letters 'S&R' if it is a Peg Point type PO. File name examples: Peg Point Type PO 08-C5413 S&R, Subcontract Type PO 08-A2659. This email will forward the form automatically to personnel in Procurement, Shipping & Receiving, CFO, and PMI.
If the PO is a Subcontract type PO, the SOTR or CAM will still be required to sign all invoices received at JLab from the vendor up since this was an estimate. An approved invoice by the SOTR or CAM can also be used as basis for the percent of work complete.
If the PO is a Peg Point type PO, Shipping & Receiving will use this form to enter that Peg Point into the Costpoint Financial System. No additional invoice approvals will be required since the SOTR or CAM already indicated the work was complete. An approved invoice by the SOTR or CAM can also be used as basis for the percent of work complete without having to complete this form.
If a previous percent complete was submitted and subsequently determined to be in error, adjust the percent complete to correct the error. Add an explanatory note to support the adjustment.

## Accting USE Data Entry Form
JSA / Jefferson Lab - DOE
Data Entry Update Subcontract PO Percent Complete
Appendix B
Vendor Name |  | RI - Research Instruments | [5 empty] | Percent complete thru |  |  | 2016-01-31
(Date)
PO Number |  | 15-C0587 | [6 empty] | OR
Invoice Number
PO Line # | Description | Percent Complete |  | PO Line Total | = | Completed Work Amt | Completed Work Amt | - | Eligible for Voucher Amt | - | Prev Vouchered Amount | = | Completed Work Retention Amt
1 | Proof of equipment order furnace uprade | 100% | X | 157470 | = | 157470 | 157470 | - | 0 | - | 157470 | = | 0
2 | Proof of completed furnace uprade | 100% | X | 157470 | = | 157470 | 157470 | - | 0 | - | 157470 | = | 0
3 | JLab Acceptance of nitrogen doping process - Cavity 1 (of 2) | 100% | X | 104980 | = | 104980 | 104980 | - | 104980 | - | 0 | = | 0
4 | JLab Acceptance of nitrogen doping process - Cavity 2 (of 2) | 0% | X | 104980 | = | 0 | 0 | - | 0 | - | 0 | = | 0
5 | Phase II: Manufacturing Drawings released and accepted by JLab | 75% | X | 317520 | = | 238140 | 238140 | - | 238140 | - |  | = | 0
6 | Phase II: First Article Cavities Mechanical Pre-fab (Deep Draw) | 0% | X | 423360 | = | 0 | 0 | - | 0 | - |  | = | 0
7 | Phase III: Production Cavities (9-72) Mechanical Pre-Fab | 0% | X | 1607500 | = | 0 | 0 | - | 0 | - |  | = | 0
8 | Phase III: Production Cavities (73-133) Mechanical Pre-Fab | 0% | X | 1446750 | = | 0 | 0 | - | 0 | - |  | = | 0
9 | Phase II: First Articles (1-8) Delivered and Accepted by JLab | 0% | X | 317520 | = | 0 | 0 |  | 0 |  |  | = | 0
10 | Phase III: Delivery & Acceptance of Cavities (9-12) | 0% | X | 160750 | = | 0 | 0 | - | 0 | - |  | = | 0
11 | Phase III: Delivery & Acceptance of Cavities (13-16) | 0% | X | 160750 | = | 0 | 0 | - | 0 | - |  | = | 0
12 | Phase III: Delivery & Acceptance of Cavities (17-20) | 0% | X | 160750 | = | 0 | 0 | - | 0 | - |  | = | 0
13 | Phase III: Delivery & Acceptance of Cavities (21-24) | 0% | X | 160750 | = | 0 | 0 | - | 0 | - |  | = | 0
14 | Phase III: Delivery & Acceptance of Cavities (25-28) | 0% | X | 160750 | = | 0 | 0 | - | 0 | - |  | = | 0
15 | Phase III: Delivery & Acceptance of Cavities (29-32) | 0% | X | 160750 | = | 0 | 0 | - | 0 | - |  | = | 0
16 | Phase III: Delivery & Acceptance of Cavities (33-36) | 0% | X | 160750 | = | 0 | 0 | - | 0 | - |  | = | 0
17 | Phase III: Delivery & Acceptance of Cavities (37-40) | 0% | X | 160750 | = | 0 | 0 | - | 0 | - |  | = | 0
18 | Phase III: Delivery & Acceptance of Cavities (41-44) | 0% | X | 160750 | = | 0 | 0 | - | 0 | - |  | = | 0
19 | Phase III: Delivery & Acceptance of Cavities (45-48) | 0% | X | 160750 | = | 0 | 0 | - | 0 | - |  | = | 0
20 | Phase III: Delivery & Acceptance of Cavities (49-52) | 0% | X | 160750 | = | 0 | 0 | - | 0 | - |  | = | 0
21 | Phase III: Delivery & Acceptance of Cavities (53-56) | 0% | X | 160750 | = | 0 | 0 | - | 0 | - |  | = | 0
22 | Phase III: Delivery & Acceptance of Cavities (57-60) | 0% | X | 160750 | = | 0 | 0 | - | 0 | - |  | = | 0
23 | Phase III: Delivery & Acceptance of Cavities (61-64) | 0% | X | 160750 | = | 0 | 0 | - | 0 | - |  | = | 0
24 | Phase III: Delivery & Acceptance of Cavities (65-68) | 0% | X | 160750 | = | 0 | 0 | - | 0 | - |  | = | 0
25 | Phase III: Delivery & Acceptance of Cavities (69-72) | 0% | X | 160750 | = | 0 | 0 | - | 0 | - |  | = | 0
26 | Phase III: Delivery & Acceptance of Cavities (73-76) | 0% | X | 160750 | = | 0 | 0 | - | 0 | - |  | = | 0
27 | Phase III: Delivery & Acceptance of Cavities (77-80) | 0% | X | 160750 | = | 0 | 0 | - | 0 | - |  | = | 0
28 | Phase III: Delivery & Acceptance of Cavities (81-84) | 0% | X | 160750 | = | 0 | 0 | - | 0 | - |  | = | 0
29 | Phase III: Delivery & Acceptance of Cavities (85-88) | 0% | X | 160750 | = | 0 | 0 | - | 0 | - |  | = | 0
30 | Phase III: Delivery & Acceptance of Cavities (89-92) | 0% | X | 160750 | = | 0 | 0 | - | 0 | - |  | = | 0
31 | Phase III: Delivery & Acceptance of Cavities (93-96) | 0% | X | 160750 | = | 0 | 0 | - | 0 | - |  | = | 0
32 | Phase III: Delivery & Acceptance of Cavities (97-100) | 0% | X | 160750 | = | 0 | 0 | - | 0 | - |  | = | 0
33 | Phase III: Delivery & Acceptance of Cavities (101-104) | 0% | X | 160750 | = | 0 | 0 | - | 0 | - |  | = | 0
34 | Phase III: Delivery & Acceptance of Cavities (105-108) | 0% | X | 160750 | = | 0 | 0 | - | 0 | - |  | = | 0
35 | Phase III: Delivery & Acceptance of Cavities (109-112) | 0% | X | 160750 | = | 0 | 0 | - | 0 | - |  | = | 0
36 | Phase III: Delivery & Acceptance of Cavities (113-116) | 0% | X | 160750 | = | 0 | 0 | - | 0 | - |  | = | 0
37 | Phase III: Delivery & Acceptance of Cavities (117-120) | 0% | X | 160750 | = | 0 | 0 | - | 0 | - |  | = | 0
38 | Phase III: Delivery & Acceptance of Cavities (121-124) | 0% | X | 160750 | = | 0 | 0 | - | 0 | - |  | = | 0
39 | Phase III: Delivery & Acceptance of Cavities (125-128) | 0% | X | 160750 | = | 0 | 0 | - | 0 | - |  | = | 0
40 |  | 0% | X | 160750 | = | 0 | 0 | - | 0 | - |  | = | 0
|  | 6.84% |  | 9620800 |  | 658060 | 658060 |  | 658060 |  |  |  | 0
Procurement Entered By: ________________________________________________________________ |  |  |  | Jarrod Fitzpatrick | [6 empty] | 2016-01-31
Date
Procurement Data Entry Verified By: _______________________________________________________
Date