## Form
JSA / Jefferson Lab - DOE
PO Percent Complete Form
Appendix A
Vendor Name | RI Research Instruments | [5 empty] | PO with Peg Points? (Yes or No)
PO Number | 15-C0587 |  |  | Buyer | Fitzpatrick | Complete through | 2017-02-28
(Date)
PO Line # | Percent Complete | Completed Peg Point (X) |  | Summary of Work (only if less than 100%)
1 | 100% |  |  | Proof of equipment order furnace uprade
2 | 100% |  |  | Proof of completed furnace uprade
3 | 100% |  |  | Acceptance of Ni doping process - Cav 1 (of 2)
4 | 100% |  |  | Acceptance of Ni doping process - Cav 2 (of 2)
5 | 100% |  |  | PH II: Mfg Drawings Accepted by JLab
6 | 100% |  |  | PH II: FAs Mech Pre-fab (Deep Draw)
7 | 100% |  |  | PH III: Mech Pre-Fab Cavities (9-72)
8 | 100% |  |  | PH III: Mech Pre-Fab Cavities (73-133)
9 | 100% |  |  | PH II: First Articles Deliver & Accept (1-8)
10 | 100% |  |  | PH III: Deliver & Accept Cavities (9-12)
11 | 100% |  |  | PH III: Deliver & Accept Cavities (13-16)
12 | 100% |  |  | PH III: Deliver & Accept Cavities (17-20)
13 | 100% |  |  | PH III: Deliver & Accept Cavities (21-24)
14 | 100% |  |  | PH III: Deliver & Accept Cavities (25-28)
15 | 100% |  |  | PH III: Deliver & Accept Cavities (29-32)
16 | 100% |  |  | PH III: Deliver & Accept Cavities (33-36)
17 | 100% |  |  | PH III: Deliver & Accept Cavities (37-40)
18 | 100% |  |  | PH III: Deliver & Accept Cavities (41-44)
19 | 100% |  |  | PH III: Deliver & Accept Cavities (45-48)
20 | 100% |  |  | PH III: Deliver & Accept Cavities (49-52)
21 | 100% |  |  | MOD 002: DESY Equip Refurbishment
22 | 15.2% |  |  | MOD 002: DESY Equip Service & Support Costs
23 | 97.73% |  |  | MOD 003: Accel Shipment (1-16) Incentives (Max of $323,136)
24 | 67.11% |  |  | MOD 004: Incentives for Accelerated Production Deliveries
25 | 56.25% |  |  | MOD 005: DESY Equipment Lease ($9,200/ month)
26 | 75% |  |  | PH III: Deliver & Accept Cavities (53-56)
27 | 50% |  |  | PH III: Deliver & Accept Cavities (57-60)
28 | 25% |  |  | PH III: Deliver & Accept Cavities (61-64)
29 | 0% |  |  | PH III: Deliver & Accept Cavities (65-68)
30 | 0% |  |  | PH III: Deliver & Accept Cavities (69-72)
31 | 0% |  |  | PH III: Deliver & Accept Cavities (73-76)
32 | 0% |  |  | PH III: Deliver & Accept Cavities (77-80)
33 | 0% |  |  | PH III: Deliver & Accept Cavities (81-84)
34 | 0% |  |  | PH III: Deliver & Accept Cavities (85-88)
35 | 0% |  |  | PH III: Deliver & Accept Cavities (89-92)
36 | 0% |  |  | PH III: Deliver & Accept Cavities (93-96)
37 | 0% |  |  | PH III: Deliver & Accept Cavities (97-100)
38 | 0% |  |  | PH III: Deliver & Accept Cavities (101-104)
39 | 0% |  |  | PH III: Deliver & Accept Cavities (105-108)
40 | 0% |  |  | PH III: Deliver & Accept Cavities (109-112)
41 | 0% |  |  | PH III: Deliver & Accept Cavities (113-116)
42 | 0% |  |  | PH III: Deliver & Accept Cavities (117-120)
43 | 0% |  |  | PH III: Deliver & Accept Cavities (121-124)
44 | 0% |  |  | PH III: Deliver & Accept Cavities (125-128)
45 | 0% |  |  | PH III: Deliver & Accept Cavities (129-133)
46 | 100% |  |  | MOD 007: LCLS-II R&D Cavities (4)
47 | 100% |  |  | MOD 008: CTM Spare Parts
48 | 38.94% |  |  | MOD 009: Recipe Modification (21-133) ($4283.18/cavity)
49 | 37.61% |  |  | MOD 010: Niobium Caps $494.02/ea (Cavs 17-133)
50 | 0% |  |  | MOD 010: Ningxia Material Sorting
51 | 0% |  |  | MOD 011: Optional Cavities 1-8
52 | 0%
53 | 0%
54 | 0%
55 | 0%
56 | 0%
57 | 0%
58 | 0%
59 | 0%
60 | 0%
Vendor Technical Representative Contacted:
|  |  | Name |  |  |  |  | Date
Jlab Control Account Manager (CAM): |  |  |  |  | Eden Evans for Ed Daly |  |  | 2017-02-28
[6 empty] | Name |  | Date
Below for use by Accounting/Shipping & Receiving Only
Accounting or Shipping & Receiving Entered By:
Date
Data Entry Verified By:
Date

## Process
JSA / Jefferson Lab - DOE
PO Percent Complete Form
Procedure
A Subcontract Purchase Order (PO) is a service type PO with loosely defined scheduled deliverables and variable amounts. A Peg Point PO has specified scheduled deliverable dates for a specified amount.
This form is to be used if NO invoice has been approved by the SOTR or CAM for work completed.
SOTR or CAM contacts a vendor technical representative for an evaluation of the percent of work completed. This can be done either verbally or via email.
Required information - Vendor Name, indicate if PO is a Peg Point type PO or not, PO #, Buyer, Complete through date (usually the end of the month), PO Line #, Percent complete, a short Summary of Work performed provided by the Vendor Technical Representative that supports the percent complete if less than 100%, the name of the Vendor Technical Representative contacted, and the CAM name.
The SOTR or CAM will submit a PO Percent Complete form by the 2nd working day following the end of the month affected for work that has been completed. This allows time for Accounting to process an accrual for the month end closing. Reminder if PO is for Peg Points, the peg point must be fully complete before claiming it.
Submit the completed form with all the information via email to evpo@jlab.org. The file name of the spreadsheet attached to the email should always include the PO# and the letters 'S&R' if it is a Peg Point type PO. File name examples: Peg Point Type PO 08-C5413 S&R, Subcontract Type PO 08-A2659. This email will forward the form automatically to personnel in Procurement, Shipping & Receiving, CFO, and PMI.
If the PO is a Subcontract type PO, the SOTR or CAM will still be required to sign all invoices received at JLab from the vendor up since this was an estimate. An approved invoice by the SOTR or CAM can also be used as basis for the percent of work complete.
If the PO is a Peg Point type PO, Shipping & Receiving will use this form to enter that Peg Point into the Costpoint Financial System. No additional invoice approvals will be required since the SOTR or CAM already indicated the work was complete. An approved invoice by the SOTR or CAM can also be used as basis for the percent of work complete without having to complete this form.
If a previous percent complete was submitted and subsequently determined to be in error, adjust the percent complete to correct the error. Add an explanatory note to support the adjustment.

## Accting USE Data Entry Form
JSA / Jefferson Lab - DOE
Data Entry Update Subcontract PO Percent Complete
Appendix B
| Vendor Name | [17 empty] | RI Research Instruments | [6 empty] | Percent complete thru |  |  | 2017-02-28
(Date)
| PO Number | [17 empty] | 15-C0587 | [7 empty] | OR
| Buyer | [17 empty] | Fitzpatrick | [6 empty] | Invoice Number
[5 empty] | 2016-11-01 | 2016-12-01 | 2017-01-01 | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01
PO Line # | Description |  | PO Line Total | Prior % Complete | Monthly Accrual $ | Monthly Accrual $3 | Monthly Accrual $5 | Monthly Accrual $7 | Monthly Accrual $9 | Monthly Accrual $11 | Monthly Accrual $12 | Monthly Accrual $13 | Monthly Accrual $14 | Monthly Accrual $15 | Monthly Accrual $16 | Monthly Accrual $17 | Monthly Accrual $2 | Est Date | Percent Complete | # | PO Line Total2 | = | Completed Work Amt | c | Completed Work Amt2 | - | Eligible for Voucher Amt | -3 | Prev Vouchered Amount | =4 | Completed Work Retention Amt | Note | Column1
1 | Proof of equipment order furnace uprade | 1 | 157470 | 100% | [13 empty] | 2015-09-01 | 100% | X | 157470 | = | 157470 |  | 157470 | - | 0 | - | 157470 | = | 0 |  | 0.0625
2 | Proof of completed furnace uprade | 2 | 157470 | 100% | [13 empty] | 2015-11-01 | 100% | X | 157470 | = | 157470 |  | 157470 | - | 0 | - | 157470 | = | 0 |  | 0.0625
3 | Acceptance of Ni doping process - Cav 1 (of 2) | 3 | 104980 | 100% | [13 empty] | 2015-12-01 | 100% | X | 104980 | = | 104980 |  | 104980 | - | 0 | - | 104980 | = | 0 |  | 0.0625
4 | Acceptance of Ni doping process - Cav 2 (of 2) | 4 | 104980 | 100% | [13 empty] | 2016-02-28 | 100% | X | 104980 | = | 104980 |  | 104980 | - | 0 | - | 104980 | = | 0 |  | 0.0625
5 | PH II: Mfg Drawings Accepted by JLab | 5 | 317520 | 100% | [13 empty] | 2015-12-04 | 100% | X | 317520 | = | 317520 |  | 317520 | - | 0 | - | 317520 | = | 0 |  | 0.0625
6 | PH II: FAs Mech Pre-fab (Deep Draw) | 6 | 423360 | 100% | [13 empty] | 2015-12-11 | 100% | X | 423360 | = | 423360 |  | 423360 | - | 0 | - | 423360 | = | 0 |  | 0.0625
7 | PH III: Mech Pre-Fab Cavities (9-72) | 7 | 1607500 | 100% | [13 empty] | 2015-12-18 | 100% | X | 1607500 | = | 1607500 |  | 1607500 | - | 0 | - | 1607500 | = | 0 |  | 0.0625
8 | PH III: Mech Pre-Fab Cavities (73-133) | 8 | 1446750 | 100% | [13 empty] | 2016-03-31 | 100% | X | 1446750 | = | 1446750 |  | 1446750 | - | 0 | - | 1446750 | = | 0 |  | 0.0625
9 | PH II: First Articles Deliver & Accept (1-8) | 9 | 317520 | 100% | [13 empty] | 2016-08-25 | 100% | X | 317520 | = | 317520 |  | 317520 |  | 0 | - | 317520 | = | 0 |  | 0.0625
10 | PH III: Deliver & Accept Cavities (9-12) | 10 | 160750 | 100% | [13 empty] | 2016-12-15 | 100% | X | 160750 | = | 160750 |  | 160750 | - | 0 | - | 160750 | = | 0 |  | 0.0625
11 | PH III: Deliver & Accept Cavities (13-16) | 11 | 160750 | 100% | [13 empty] | 2017-01-03 | 100% | X | 160750 | = | 160750 |  | 160750 | - | 0 | - | 160750 | = | 0 |  | 0.0625
12 | PH III: Deliver & Accept Cavities (17-20) | 12 | 160750 | 100% | [13 empty] | 2017-01-11 | 100% | X | 160750 | = | 160750 |  | 160750 | - | 0 | - | 160750 | = | 0 |  | 0.0625
13 | PH III: Deliver & Accept Cavities (21-24) | 13 | 160750 |  | 2016-11-01: 160750 | 2017-01-19 | 100% | X | 160750 | = | 160750 |  | 160750 | - | 0 | - | 160750 | = | 0 |  | 0.0625
14 | PH III: Deliver & Accept Cavities (25-28) | 14 | 160750 |  | 2016-12-01: 160750 | 2017-01-27 | 100% | X | 160750 | = | 160750 |  | 160750 | - | 0 | - | 160750 | = | 0 |  | 0.0625
15 | PH III: Deliver & Accept Cavities (29-32) | 15 | 160750 |  | 2016-12-01: 160750 | 2017-02-06 | 100% | X | 160750 | = | 160750 |  | 160750 | - | 0 | - | 160750 | = | 0 |  | 0.0625
16 | PH III: Deliver & Accept Cavities (33-36) | 16 | 160750 |  | 2016-12-01: 160750 | 2017-02-14 | 100% | X | 160750 | = | 160750 |  | 160750 | - | 0 | - | 160750 | = | 0 |  | 0.0625
17 | PH III: Deliver & Accept Cavities (37-40) | 17 | 160750 |  | 2016-12-01: 160750 | 2017-02-22 | 100% | X | 160750 | = | 160750 |  | 160750 | - | 0 | - | 160750 | = | 0 |  | 0.0625
18 | PH III: Deliver & Accept Cavities (41-44) | 18 | 160750 |  | 2016-12-01: 160750 | 2017-03-02 | 100% | X | 160750 | = | 160750 |  | 160750 | - | 0 | - | 160750 | = | 0 |  | 0.0625
19 | PH III: Deliver & Accept Cavities (45-48) | 19 | 160750 |  | 2017-02-01: 160750 | 2017-03-10 | 100% | X | 160750 | = | 160750 |  | 160750 | - | 160750 | - | 0 | = | 0 |  | 0.0625
20 | PH III: Deliver & Accept Cavities (49-52) | 20 | 160750 |  | 2017-02-01: 160750 | 2017-03-20 | 100% | X | 160750 | = | 160750 |  | 160750 | - | 160750 | - | 0 | = | 0 |  | 0.0625
21 | MOD 002: DESY Equip Refurbishment | 21 | 90800 | 100% | [13 empty] | 2016-04-18 | 100% | X | 90800 | = | 90800 |  | 90800 | - | 0 | - | 90800 | = | 0 |  | 0.0625
22 | MOD 002: DESY Equip Service & Support Costs | 22 | 49696 |  | 2016-12-01: 7554.66 | 2017-06-19 | 15.2% | X | 49696 | = | 7554.66 |  | 7554.66 | - | 0 | - | 7554.66 | = | 0 |  | 0.0625
23 | MOD 003: Accel Shipment (1-16) Incentives (Max of $323,136) | 23 | 323136 | 97.73% | [13 empty] | 2016-10-10 | 97.73% | X | 323136 | = | 315792 |  | 315792 | - | -8.8476e-09 | - | 315792 | = | 0 | Remaining $7,344 to be de-obligated. | 0.0625
24 | MOD 004: Incentives for Accelerated Production Deliveries | 24 | 246240 | 9.34% | 2016-11-01: 23000; 2016-12-01: 101080; 2017-02-01: 18160 | 2017-07-17 | 67.11% | X | 246240 | = | 165239.9999 |  | 165239.9999 | - | 18159.9999 | - | 147080 | = | 0 | Cavities 17-20. | 0.0625
25 | MOD 005: DESY Equipment Lease ($9,200/ month) | 25 | 147200 | 31.25% | 2016-11-01: 9200; 2016-12-01: 9200; 2017-01-01: 9200; 2017-02-01: 9200 | 2017-07-17 | 56.25% | X | 147200 | = | 82800 |  | 82800 | - | 18400 | - | 64400 | = | 0 | 6.25% for October | 0.0625
26 | PH III: Deliver & Accept Cavities (53-56) | 26 | 160750 |  | 2017-02-01: 80375 | 2017-03-28 | 75% | X | 160750 | = | 120562.5 |  | 120562.5 | - | 120562.5 | - | 0 | = | 0 |  | 0.0625
27 | PH III: Deliver & Accept Cavities (57-60) | 27 | 160750 |  | 2017-02-01: 80375 | 2017-04-05 | 50% | X | 160750 | = | 80375 |  | 80375 | - | 80375 | - | 0 | = | 0 |  | 0.0625
28 | PH III: Deliver & Accept Cavities (61-64) | 28 | 160750 |  | 2017-02-01: 40187.5 | 2017-04-13 | 25% | X | 160750 | = | 40187.5 |  | 40187.5 | - | 40187.5 | - | 0 | = | 0 |  | 0.0625
29 | PH III: Deliver & Accept Cavities (65-68) | 29 | 160750 | [14 empty] | 2017-04-21 | 0% | X | 160750 | = | 0 |  | 0 | - | 0 | - | 0 | = | 0 |  | 0.0625
30 | PH III: Deliver & Accept Cavities (69-72) | 30 | 160750 | [14 empty] | 2017-05-01 | 0% | X | 160750 | = | 0 |  | 0 | - | 0 | - | 0 | = | 0 |  | 0.0625
31 | PH III: Deliver & Accept Cavities (73-76) | 31 | 160750 | [14 empty] | 2017-05-09 | 0% | X | 160750 | = | 0 |  | 0 | - | 0 | - | 0 | = | 0 |  | 0.0625
32 | PH III: Deliver & Accept Cavities (77-80) | 32 | 160750 | [14 empty] | 2017-05-17 | 0% | X | 160750 | = | 0 |  | 0 | - | 0 | - | 0 | = | 0 |  | 0.0625
33 | PH III: Deliver & Accept Cavities (81-84) | 33 | 160750 | [14 empty] | 2017-05-25 | 0% | X | 160750 | = | 0 |  | 0 | - | 0 | - | 0 | = | 0 |  | 0.0625
34 | PH III: Deliver & Accept Cavities (85-88) | 34 | 160750 | [14 empty] | 2017-06-02 | 0% | X | 160750 | = | 0 |  | 0 | - | 0 | - | 0 | = | 0 |  | 0.0625
35 | PH III: Deliver & Accept Cavities (89-92) | 35 | 160750 | [14 empty] | 2017-06-12 | 0% | X | 160750 | = | 0 |  | 0 | - | 0 | - | 0 | = | 0 |  | 0.0625
36 | PH III: Deliver & Accept Cavities (93-96) | 36 | 160750 | [14 empty] | 2017-06-20 | 0% | X | 160750 | = | 0 |  | 0 | - | 0 | - | 0 | = | 0 |  | 0.0625
37 | PH III: Deliver & Accept Cavities (97-100) | 37 | 160750 | [14 empty] | 2017-06-28 | 0% | X | 160750 | = | 0 |  | 0 | - | 0 | - | 0 | = | 0 |  | 0.0625
38 | PH III: Deliver & Accept Cavities (101-104) | 38 | 160750 | [14 empty] | 2017-07-06 | 0% | X | 160750 | = | 0 |  | 0 | - | 0 | - | 0 | = | 0 |  | 0.0625
39 | PH III: Deliver & Accept Cavities (105-108) | 39 | 160750 | [14 empty] | 2017-07-14 | 0% | X | 160750 | = | 0 |  | 0 | - | 0 | - | 0 | = | 0 |  | 0.0625
40 | PH III: Deliver & Accept Cavities (109-112) | 40 | 160750 | [14 empty] | 2017-07-24 | 0% | X | 160750 | = | 0 |  | 0 | - | 0 | - | 0 | = | 0 |  | 0.0625
41 | PH III: Deliver & Accept Cavities (113-116) | 41 | 160750 | [14 empty] | 2017-08-01 | 0% | X | 160750 | = | 0 |  | 0 | - | 0 | - | 0 | = | 0 |  | 0.0625
42 | PH III: Deliver & Accept Cavities (117-120) | 42 | 160750 | [14 empty] | 2017-08-09 | 0% | X | 160750 | = | 0 |  | 0 | - | 0 | - | 0 | = | 0 |  | 0.0625
43 | PH III: Deliver & Accept Cavities (121-124) | 43 | 160750 | [14 empty] | 2017-08-17 | 0% | X | 160750 | = | 0 |  | 0 | - | 0 | - | 0 | = | 0 |  | 0.0625
44 | PH III: Deliver & Accept Cavities (125-128) | 44 | 160750 | [14 empty] | 2017-08-25 | 0% | X | 160750 | = | 0 |  | 0 | - | 0 | - | 0 | = | 0 |  | 0.0625
45 | PH III: Deliver & Accept Cavities (129-133) | 45 | 160750 | [14 empty] | 2017-09-19 | 0% | X | 160750 | = | 0 |  | 0 | - | 0 | - | 0 | = | 0 |  | 0.0625
46 | MOD 007: LCLS-II R&D Cavities (4) | 46 | 38000 | 100% | [13 empty] | 2016-09-01 | 100% | X | 38000 | = | 38000 |  | 38000 | - | 0 | - | 38000 | = | 0 |  | 0.0625
47 | MOD 008: CTM Spare Parts | 47 | 71500 | 100% | [13 empty] | 2016-09-30 | 100% | X | 71500 | = | 71500 |  | 71500 | - | 0 | - | 71500 | = | 0 |  | 0.0625
48 | MOD 009: Recipe Modification (21-133) ($4283.18/cavity) | 48 | 484000 |  | 2016-11-01: 17132.76; 2016-12-01: 102796.56; 2017-02-01: 68530.88 | 2017-09-09 | 38.94% | X | 484000 | = | 188460.2 |  | 188460.2 | - | 85663.88 | - | 102796.32 | = | 0 |  | 0.0625
49 | MOD 010: Niobium Caps $494.02/ea (Cavs 17-133) | 49 | 57800 |  | 2016-12-01: 13720; 2017-01-01: 112.56; 2017-02-01: 7904.32 |  | 37.61% |  | 57800 |  | 21736.88 |  | 21736.88 |  | 7904.32 |  | 13832.56 |  | 0 |  | 0.0625
50 | MOD 010: Ningxia Material Sorting | 50 | 21335 |  | 2017-01-01: 21335 |  | 100% |  | 21335 |  | 21335 |  | 21335 |  | 0 |  | 21335 |  | 0
51 | MOD 011: Optional Cavities 1-8 | 51 | 499817.6 | [15 empty] | 0% | X | 499817.6 | = | 0 |  | 0 | - | 0 | - | 0 | = | 0 |  | 0.0625
Total |  |  | 11650324.6 |  | 2017-01-01: 30647.56 |  |  |  | 11650324.6 |  | 7650143.7399 |  | 7650143.7399 |  | 692753.1999 |  | 6957390.54 |  | 0 | 3
Procurement Entered By: ________________________________________________________________ | [28 empty] | 2017-02-28
Date
Procurement Data Entry Verified By: _______________________________________________________
Date

## Accrual Details (hidden)
JSA / Jefferson Lab - DOE
Data Entry Update Subcontract PO Percent Complete
Appendix B
| Vendor Name | [16 empty] | RI Research Instruments | [6 empty] | Percent complete thru |  |  | 2016-12-31
(Date)
| PO Number | [16 empty] | 15-C0587 | [7 empty] | OR
| Buyer | [16 empty] | Fitzpatrick | [6 empty] | Invoice Number
PO Line # | Description | PO Line Total | Prior % Complete | 2016-11-01 | 2016-12-01 | 2017-01-01 | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | Est Date | Percent Complete | # | PO Line Total2 | = | Completed Work Amt | c | Completed Work Amt2 | - | Eligible for Voucher Amt | -3 | Prev Vouchered Amount | =4 | Completed Work Retention Amt | Note
1 | Proof of equipment order furnace uprade | 157470 | 100% | [13 empty] | 2015-09-01 | 100% | X | 157470 | = | 157470 |  | 157470 | - | 0 | - | 157470 | = | 0
2 | Proof of completed furnace uprade | 157470 | 100% | [13 empty] | 2015-11-01 | 100% | X | 157470 | = | 157470 |  | 157470 | - | 0 | - | 157470 | = | 0
3 | Acceptance of Ni doping process - Cav 1 (of 2) | 104980 | 100% | [13 empty] | 2015-12-01 | 100% | X | 104980 | = | 104980 |  | 104980 | - | 0 | - | 104980 | = | 0
4 | Acceptance of Ni doping process - Cav 2 (of 2) | 104980 | 100% | [13 empty] | 2016-02-28 | 100% | X | 104980 | = | 104980 |  | 104980 | - | 0 | - | 104980 | = | 0
5 | PH II: Mfg Drawings Accepted by JLab | 317520 | 100% | [13 empty] | 2015-12-04 | 100% | X | 317520 | = | 317520 |  | 317520 | - | 0 | - | 317520 | = | 0
6 | PH II: FAs Mech Pre-fab (Deep Draw) | 423360 | 100% | [13 empty] | 2015-12-11 | 100% | X | 423360 | = | 423360 |  | 423360 | - | 0 | - | 423360 | = | 0
7 | PH III: Mech Pre-Fab Cavities (9-72) | 1607500 | 100% | [13 empty] | 2015-12-18 | 100% | X | 1607500 | = | 1607500 |  | 1607500 | - | 0 | - | 1607500 | = | 0
8 | PH III: Mech Pre-Fab Cavities (73-133) | 1446750 | 100% | [13 empty] | 2016-03-31 | 100% | X | 1446750 | = | 1446750 |  | 1446750 | - | 0 | - | 1446750 | = | 0
9 | PH II: First Articles Deliver & Accept (1-8) | 317520 | 100% | [13 empty] | 2016-08-25 | 100% | X | 317520 | = | 317520 |  | 317520 |  | 0 | - | 317520 | = | 0
10 | PH III: Deliver & Accept Cavities (9-12) | 160750 | 100% | [13 empty] | 2016-12-15 | 100% | X | 160750 | = | 160750 |  | 160750 | - | 0 | - | 160750 | = | 0
11 | PH III: Deliver & Accept Cavities (13-16) | 160750 | 100% | [13 empty] | 2017-01-03 | 100% | X | 160750 | = | 160750 |  | 160750 | - | 0 | - | 160750 | = | 0
12 | PH III: Deliver & Accept Cavities (17-20) | 160750 | 100% | [13 empty] | 2017-01-11 | 100% | X | 160750 | = | 160750 |  | 160750 | - | 0 | - | 160750 | = | 0
13 | PH III: Deliver & Accept Cavities (21-24) | 160750 | -3.192e-14% | 2016-11-01: 160750 | 2017-01-19 | 100% | X | 160750 | = | 160750 |  | 160750 | - | 0 | - | 160750 | = | 0
14 | PH III: Deliver & Accept Cavities (25-28) | 160750 |  | 2016-12-01: 160750 | 2017-01-27 | 100% | X | 160750 | = | 160750 |  | 160750 | - | 0 | - | 160750 | = | 0
15 | PH III: Deliver & Accept Cavities (29-32) | 160750 |  | 2016-12-01: 160750 | 2017-02-06 | 100% | X | 160750 | = | 160750 |  | 160750 | - | 0 | - | 160750 | = | 0
16 | PH III: Deliver & Accept Cavities (33-36) | 160750 |  | 2016-12-01: 160750 | 2017-02-14 | 100% | X | 160750 | = | 160750 |  | 160750 | - | 0 | - | 160750 | = | 0
17 | PH III: Deliver & Accept Cavities (37-40) | 160750 |  | 2016-12-01: 160750 | 2017-02-22 | 100% | X | 160750 | = | 160750 |  | 160750 | - | 0 | - | 160750 | = | 0
18 | PH III: Deliver & Accept Cavities (41-44) | 160750 |  | 2016-12-01: 160750 | 2017-03-02 | 100% | X | 160750 | = | 160750 |  | 160750 | - | 0 | - | 160750 | = | 0
19 | PH III: Deliver & Accept Cavities (45-48) | 160750 | [14 empty] | 2017-03-10 | 0% | X | 160750 | = | 0 |  | 0 | - | 0 | - | 0 | = | 0
20 | PH III: Deliver & Accept Cavities (49-52) | 160750 | [14 empty] | 2017-03-20 | 0% | X | 160750 | = | 0 |  | 0 | - | 0 | - | 0 | = | 0
21 | MOD 002: DESY Equip Refurbishment | 90800 | 100% | [13 empty] | 2016-04-18 | 100% | X | 90800 | = | 90800 |  | 90800 | - | 0 | - | 90800 | = | 0
22 | MOD 002: DESY Equip Service & Support Costs | 49696 | [14 empty] | 2017-06-19 | 0% | X | 49696 | = | 0 |  | 0 | - | -7554.66 | - | 7554.66 | = | 0
23 | MOD 003: Accel Shipment (1-16) Incentives (Max of $323,136) | 323136 | 97.73% | [13 empty] | 2016-10-10 | 97.73% | X | 323136 | = | 315792 |  | 315792 | - | -8.8476e-09 | - | 315792 | = | 0 | Remaining $7,344 to be de-obligated.
24 | MOD 004: Incentives for Accelerated Production Deliveries | 246240 | 9.34% | 2016-11-01: 23000; 2016-12-01: 101080 | 2017-07-17 | 59.73% | X | 246240 | = | 147079.9999 |  | 147079.9999 | - | -7.808e-05 | - | 147080 | = | 0 | Cavities 17-20.
25 | MOD 005: DESY Equipment Lease ($9,200/ month) | 147200 | 31.25% | 2016-11-01: 9200; 2016-12-01: 9200 | 2017-07-17 | 43.75% | X | 147200 | = | 64400 |  | 64400 | - | 0 | - | 64400 | = | 0 | 6.25% for October
26 | PH III: Deliver & Accept Cavities (53-56) | 160750 | [14 empty] | 2017-03-28 | 0% | X | 160750 | = | 0 |  | 0 | - | 0 | - | 0 | = | 0
27 | PH III: Deliver & Accept Cavities (57-60) | 160750 | [14 empty] | 2017-04-05 | 0% | X | 160750 | = | 0 |  | 0 | - | 0 | - | 0 | = | 0
28 | PH III: Deliver & Accept Cavities (61-64) | 160750 | [14 empty] | 2017-04-13 | 0% | X | 160750 | = | 0 |  | 0 | - | 0 | - | 0 | = | 0
29 | PH III: Deliver & Accept Cavities (65-68) | 160750 | [14 empty] | 2017-04-21 | 0% | X | 160750 | = | 0 |  | 0 | - | 0 | - | 0 | = | 0
30 | PH III: Deliver & Accept Cavities (69-72) | 160750 | [14 empty] | 2017-05-01 | 0% | X | 160750 | = | 0 |  | 0 | - | 0 | - | 0 | = | 0
31 | PH III: Deliver & Accept Cavities (73-76) | 160750 | [14 empty] | 2017-05-09 | 0% | X | 160750 | = | 0 |  | 0 | - | 0 | - | 0 | = | 0
32 | PH III: Deliver & Accept Cavities (77-80) | 160750 | [14 empty] | 2017-05-17 | 0% | X | 160750 | = | 0 |  | 0 | - | 0 | - | 0 | = | 0
33 | PH III: Deliver & Accept Cavities (81-84) | 160750 | [14 empty] | 2017-05-25 | 0% | X | 160750 | = | 0 |  | 0 | - | 0 | - | 0 | = | 0
34 | PH III: Deliver & Accept Cavities (85-88) | 160750 | [14 empty] | 2017-06-02 | 0% | X | 160750 | = | 0 |  | 0 | - | 0 | - | 0 | = | 0
35 | PH III: Deliver & Accept Cavities (89-92) | 160750 | [14 empty] | 2017-06-12 | 0% | X | 160750 | = | 0 |  | 0 | - | 0 | - | 0 | = | 0
36 | PH III: Deliver & Accept Cavities (93-96) | 160750 | [14 empty] | 2017-06-20 | 0% | X | 160750 | = | 0 |  | 0 | - | 0 | - | 0 | = | 0
37 | PH III: Deliver & Accept Cavities (97-100) | 160750 | [14 empty] | 2017-06-28 | 0% | X | 160750 | = | 0 |  | 0 | - | 0 | - | 0 | = | 0
38 | PH III: Deliver & Accept Cavities (101-104) | 160750 | [14 empty] | 2017-07-06 | 0% | X | 160750 | = | 0 |  | 0 | - | 0 | - | 0 | = | 0
39 | PH III: Deliver & Accept Cavities (105-108) | 160750 | [14 empty] | 2017-07-14 | 0% | X | 160750 | = | 0 |  | 0 | - | 0 | - | 0 | = | 0
40 | PH III: Deliver & Accept Cavities (109-112) | 160750 | [14 empty] | 2017-07-24 | 0% | X | 160750 | = | 0 |  | 0 | - | 0 | - | 0 | = | 0
41 | PH III: Deliver & Accept Cavities (113-116) | 160750 | [14 empty] | 2017-08-01 | 0% | X | 160750 | = | 0 |  | 0 | - | 0 | - | 0 | = | 0
42 | PH III: Deliver & Accept Cavities (117-120) | 160750 | [14 empty] | 2017-08-09 | 0% | X | 160750 | = | 0 |  | 0 | - | 0 | - | 0 | = | 0
43 | PH III: Deliver & Accept Cavities (121-124) | 160750 | [14 empty] | 2017-08-17 | 0% | X | 160750 | = | 0 |  | 0 | - | 0 | - | 0 | = | 0
44 | PH III: Deliver & Accept Cavities (125-128) | 160750 | [14 empty] | 2017-08-25 | 0% | X | 160750 | = | 0 |  | 0 | - | 0 | - | 0 | = | 0
45 | PH III: Deliver & Accept Cavities (129-133) | 160750 | [14 empty] | 2017-09-19 | 0% | X | 160750 | = | 0 |  | 0 | - | 0 | - | 0 | = | 0
46 | MOD 007: LCLS-II R&D Cavities (4) | 38000 | 100% | [13 empty] | 2016-09-01 | 100% | X | 38000 | = | 38000 |  | 38000 | - | 0 | - | 38000 | = | 0
47 | MOD 008: CTM Spare Parts | 71500 | 100% | [13 empty] | 2016-09-30 | 100% | X | 71500 | = | 71500 |  | 71500 | - | 0 | - | 71500 | = | 0
48 | MOD 009: Recipe Modification (21-133) ($4283.19/cavity) | 484000 |  | 2016-11-01: 17132.76; 2016-12-01: 102796.56 | 2017-09-09 | 24.78% | X | 484000 | = | 119929.32 |  | 119929.32 | - | 17133 | - | 102796.32 | = | 0
49 | MOD 010: Niobium Caps (Cavs 21-133) $511.504/cavity | 57800 |  | 2016-12-01: 12276.1062 |  | 21.24% |  | 57800 |  |  |  | 0 |  | 0 |  |  |  | 0
50 | MOD 010: Ningxia Material Sorting | 21335 | [15 empty] | 0% |  | 21335
51 | MOD 011: Optional Cavities 1-8 | 499817.6 | [15 empty] | 0% | X | 499817.6 | = | 0 |  | 0 | - | 0 | - | 0 | = | 0
Total |  | 11650324.6 |  | 2016-12-01: 1029102.6662 |  |  |  | 11650324.6 |  | 7650143.7399 |  | 7650143.7399 |  | 692753.1999 |  | 6957390.54 |  | 0 | 3
Procurement Entered By: ________________________________________________________________ | [27 empty] | 2017-02-28
Date
Procurement Data Entry Verified By: _______________________________________________________
Date

## Invoices
# | Invoice # | Date | Milestone/ Line | Invoice Amount | Approval Date | Line
1 | 3456.01 | 2015-08-11 | Proof of equipment order furnace uprade | 157470
2 | 3456.02 | 2015-11-12 | Proof of completed furnace uprade | 157470
3 | 3456.03 | 2016-05-25 | PH II: FAs Mech Pre-fab (Deep Draw) | 423360
4 | 3456.04 | 2016-05-25 | PH III: Mech Pre-Fab Cavities (9-72) | 1607500
5 | 3456.05 | 2016-08-19 | PH II: Mfg Drawings Accepted by JLab | 317520
6 | 3456.06 | 2016-09-20 | PH III: Mech Pre-Fab Cavities (73-133) | 1446750
7 | 51222 | 2016-02-17 | Acceptance of Ni doping process - Cav 1 (of 2) | 104980
8 | 51222 | 2016-02-17 | Acceptance of Ni doping process - Cav 2 (of 2) | 104980
9 | 51315 | 2016-05-25 | MOD 002: DESY Equip Refurbishment | 90800
10 | 51419 | 2016-08-29 | MOD 003: Accel Shipment (1-16) Incentives (Max of $323,136) | 80784
11 | 51419 | 2016-08-29 | PH II: First Articles Deliver & Accept (1-8) | 158760
12 | 51428 | 2016-08-30 | MOD 008: CTM Spare Parts | 71500
13 | 51448 | 2016-09-23 | MOD 003: Accel Shipment (1-16) Incentives (Max of $323,136) | 73440
14 | 51448 | 2016-09-23 | PH II: First Articles Deliver & Accept (1-8) | 158760
15 | 51450 | 2016-09-26 | MOD 003: Accel Shipment (1-16) Incentives (Max of $323,136) | 161568
16 | 51450 | 2016-09-26 | PH III: Deliver & Accept Cavities (9-12) | 160750
17 | 51450 | 2016-09-26 | PH III: Deliver & Accept Cavities (13-16) | 160750
18 | 51451 | 2016-09-26 | MOD 005: DESY Equipment Lease ($9,200/ month) | 36800
19 | 51452 | 2016-09-26 | MOD 007: LCLS-II R&D Cavities (4) | 38000
20 | 51511 | 2016-11-24 | MOD 002: DESY Equip Service & Support Costs | 7554.66 | 2017-01-18
21 | 51533 | 2016-11-30 | PH III: Deliver & Accept Cavities (17-20) | 160750 | 2016-12-02
22 | 51533 | 2016-11-30 | MOD 004: Incentives for Accelerated Production Deliveries | 23000 | 2016-12-02
23 | 51554 | 2016-12-19 | MOD 005: DESY Equipment Lease ($9,200/ month) | 27600 | 2017-01-18
24 | 51589 | 2016-12-23 | MOD 004: Incentives for Accelerated Production Deliveries | 101080 | 2017-02-15 | 24
25 | 51589 | 2016-12-23 | PH III: Deliver & Accept Cavities (21-24) | 160750 | 2017-02-15 | 13
26 | 51589 | 2016-12-23 | PH III: Deliver & Accept Cavities (25-28) | 160750 | 2017-02-15 | 14
27 | 51589 | 2016-12-23 | PH III: Deliver & Accept Cavities (29-32) | 160750 | 2017-02-15 | 15
28 | 51589 | 2016-12-23 | PH III: Deliver & Accept Cavities (33-36) | 160750 | 2017-02-15 | 16 | 257200
29 | 51589 | 2016-12-23 | PH III: Deliver & Accept Cavities (37-40) | 160750 | 2017-02-15 | 17
30 | 51589 | 2016-12-23 | PH III: Deliver & Accept Cavities (41-44) | 160750 | 2017-02-15 | 18
31 | 51589 | 2016-12-23 | MOD 009: Recipe Modification (21-133) ($4283.18/cavity) | 102796.32 | 2017-02-15 | 48
32 | 51595 | 2016-12-31 | MOD 010: Ningxia Material Sorting | 21335 | 2017-01-18 | 50
33 | 51595 | 2016-12-31 | MOD 010: Niobium Caps $494.02/ea (Cavs 17-133) | 11856.48 | 2017-01-18 | 49
34 | 51599 | 2017-01-20 | MOD 004: Incentives for Accelerated Production Deliveries | 23000 | 2017-02-15 | 24
35 | 51600 | 2017-01-23 | MOD 010: Niobium Caps $494.02/ea (Cavs 17-133) | 1976.08 | 2017-02-17 | 49
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
Total |  |  |  | 6957390.54

## Sheet1 (hidden)
Amount | PO Line
101080 | 24
160750 | 13
160750 | 14
160750 | 15
160750 | 16
160750 | 17
160750 | 18
102796.32 | 48

## Cavity Status
Unit # | Serial # | Material | EP | Heat | Caps | Hold Point 1 | Hold Point 2 | Hold Point 3 | NCRs | NCR Comments | Dest | Ship # | Incentivized Ship Date | Actual Ship Date | Wks +/- Incentive Date | Incentive Available | Incentive Earned | Receipt Date | Milestone # | Milestone Value | Status | Recipe Modification (Mod 9) | Caps (Mod 10) | Milestone | Total | Accept Date | Notes
1 | CAV0001 | TD | 140 | 800 | No | OK | OK | OK | NCR 8, 17 |  | JLab | 1 | 2016-07-01 |  | 0 |  | 0 |  | 14 | 40187.5 | Complete |  |  | 40187.5 | 40187.5 |  | JLAB CM02
2 | CAV0002 | TD | 140 | 800 | No | OK | OK | OK |  |  | JLab | 1 | 2016-07-01 |  | 0 |  | 0 |  | 14 | 40187.5 | Complete |  |  | 40187.5 | 40187.5 |  | JLAB CM02
3 | CAV0004 | TD | 140 | 800 | No | OK | OK | OK | NCR 10 |  | JLab | 1 | 2016-07-01 |  | 0 |  | 0 |  | 14 | 40187.5 | Complete |  |  | 40187.5 | 40187.5 |  | JLAB CM02
4 | CAV0005 | TD | 140 | 800 | No | OK | OK | OK | NCR 11 |  | JLab | 1 | 2016-07-01 |  | 0 |  | 0 |  | 14 | 40187.5 | Complete |  |  | 40187.5 | 40187.5 |  | JLAB CM02
5 | CAV0003 | TD | 140 | 800 | No | OK | OK | OK | NCR 9 |  | FNAL | 2 | 2016-07-01 |  | 0 |  | 0 |  | 15 | 40187.5 | Complete |  |  | 40187.5 | 40187.5 |  | JLAB CM02
6 | CAV0006 | TD | 140 | 800 | No | OK | OK | OK | NCR 18 |  | FNAL | 2 | 2016-07-01 |  | 0 |  | 0 |  | 15 | 40187.5 | Complete |  |  | 40187.5 | 40187.5 |  | JLAB CM02
7 | CAV0007 | TD | 140 | 800 | No | OK | OK | OK | NCR 20 |  | FNAL | 2 | 2016-07-01 |  | 0 |  | 0 |  | 15 | 40187.5 | Complete |  |  | 40187.5 | 40187.5 |  | JLAB CM02
8 | CAV0008 | TD | 140 | 800 | No | OK | OK | OK | NCR 19, 22 | NCR discussed (split ring repositioning by FNAL, 1.4 deg. off) | FNAL | 2 | 2016-07-01 |  | 0 |  | 0 |  | 15 | 40187.5 | Complete |  |  | 40187.5 | 40187.5 |  | JLAB CM02
9 | CAV0009 | TD | 140 | 800 | No | OK | OK | OK |  |  | JLab | 3 | 2016-08-01 |  | 0 |  | 0 |  | 16 | 40187.5 | Complete |  |  | 40187.5 | 40187.5 |  | FNAL CM02
10 | CAV0010 | TD | 140 | 800 | No | OK | OK | OK | NCR 21, 23 |  | JLab | 3 | 2016-08-01 |  | 0 |  | 0 |  | 16 | 40187.5 | Complete |  |  | 40187.5 | 40187.5 |  | FNAL CM02
11 | CAV0012 | TD | 140 | 800 | No | OK | OK | OK | NCR 7, 24 |  | JLab | 3 | 2016-08-01 |  | 0 |  | 0 |  | 16 | 40187.5 | Complete |  |  | 40187.5 | 40187.5 |  | FNAL CM02
12 | CAV0014 | TD | 140 | 800 | No | OK | OK | OK | NCR 25 |  | JLab | 3 | 2016-08-01 |  | 0 |  | 0 |  | 16 | 40187.5 | Complete |  |  | 40187.5 | 40187.5 |  | FNAL CM02
13 | CAV0011 | TD | 140 | 800 | No | OK | OK | OK |  |  | FNAL | 4 | 2016-08-01 |  | 0 |  | 0 |  | 17 | 40187.5 | Complete |  |  | 40187.5 | 40187.5 |  | FNAL CM02
14 | CAV0013 | TD | 140 | 800 | No | OK | OK | OK | NCR 26 |  | FNAL | 4 | 2016-08-01 |  | 0 |  | 0 |  | 17 | 40187.5 | Complete |  |  | 40187.5 | 40187.5 |  | FNAL CM02
15 | CAV0015 | TD | 140 | 800 | No | OK | OK | OK | NCR 27 |  | FNAL | 4 | 2016-08-01 |  | 0 |  | 0 |  | 17 | 40187.5 | Complete |  |  | 40187.5 | 40187.5 |  | FNAL CM02
16 | CAV0016 | TD | 140 | 800 | No | OK | OK | OK | NCR 28, 29 |  | FNAL | 4 | 2016-08-01 |  | 0 |  | 0 |  | 17 | 40187.5 | Complete |  |  | 40187.5 | 40187.5 |  | FNAL CM02
17 | CAV0017 | TD | 200 | 900 | Yes | OK | 2016-09-16 | 2016-10-04 | NCR 47 |  | FNAL | 5 | 2016-11-02 | 2016-10-07 | -3.7143 | 5750 | 5750 | 2016-10-26 | 13 | 40187.5 | Accepted |  | 490 | 40187.5 | 46427.5 | 2016-12-01 | bare cavity |  | 490
18 | CAV0018 | TD | 240 | 900 | Yes | OK | 2016-09-16 | 2016-10-04 | NCR 46, 48 |  | FNAL | 5 | 2016-11-02 | 2016-10-07 | -3.7143 | 5750 | 5750 | 2016-10-26 | 13 | 40187.5 | Accepted |  | 490 | 40187.5 | 46427.5 | 2016-11-01 | bare cavity |  | 490
19 | CAV0019 | TD | 240 | 900 | Yes | OK | 2016-09-21 | 2016-10-12 | NCR 51 | NCR 51 - minor mechanical | FNAL | 6 | 2016-11-02 | 2016-10-19 | -2 | 5750 | 5750 | 2016-10-26 | 13 | 40187.5 | Accepted |  | 490 | 40187.5 | 46427.5 | 2016-11-01 | dressed cavity |  | 490
20 | CAV0020 | TD | 200 | 900 | Yes | OK | 2016-09-21 | 2016-10-12 | NCR 52 | NCR 52 - minor mechanical | FNAL | 6 | 2016-11-02 | 2016-10-19 | -2 | 5750 | 5750 | 2016-10-26 | 13 | 40187.5 | Accepted |  | 490 | 40187.5 | 46427.5 | 2016-11-01 | dressed cavity |  | 490
21 | CAV0021 | TD | 200 | 900 | Yes | OK | 2016-09-21 | 2016-10-18 | NCR 39, 54 | NCR 54 - minor mechanical | JLab | 7 | 2016-11-02 | 2016-11-02 | 0 | 5750 | 5750 | 2016-11-11 | 13 | 40187.5 | Received | 4283.18 | 490 | 40187.5 | 50710.68 | 2016-11-01 |  |  | 490
22 | CAV0023 | TD | 200 | 900 | Yes | OK | 2016-09-22 | 2016-10-20 | NCR 1, 59 | NCR 59 - minor mechanical | JLab | 7 | 2016-11-02 | 2016-11-02 | 0 | 5750 | 5750 | 2016-11-11 | 13 | 40187.5 | Received | 4283.18 | 490 | 40187.5 | 50710.68 | 2016-11-01 |  |  | 490
23 | CAV0024 | TD | 200 | 900 | Yes | OK | 2016-09-23 | 2016-10-20 | NCR 60 | NCR 60 - minor mechanical | JLab | 7 | 2016-11-02 | 2016-11-02 | 0 | 5750 | 5750 | 2016-11-11 | 13 | 40187.5 | Received | 4283.18 | 490 | 40187.5 | 50710.68 | 2016-11-01 |  |  | 490
24 | CAV0028 | TD | 200 | 900 | Yes | OK | 2016-10-10 | 2016-10-20 | NCR 61 | NCR 61 - minor mechanical | JLab | 7 | 2016-11-02 | 2016-11-02 | 0 | 5750 | 5750 | 2016-11-11 | 13 | 40187.5 | Received | 4283.18 | 490 | 40187.5 | 50710.68 | 2016-11-01 |  |  | 490
25 | CAV0026 | TD | 200 | 900 | Yes | OK | 2016-09-27 |  | NCR 57 | NCR 57 - minor mechanical | FNAL | 8 | 2016-11-02 | 2016-11-14 | 1.7143 | 5750 | 5407.1429 | 2016-11-21 | 14 | 40187.5 | Received | 4283.18 | 490 | 40187.5 | 50367.8229 | 2016-12-01 | 2 wk - recipe investigation. |  | 490
26 | CAV0027 | TD | 200 | 900 | Yes | 2016-09-19 | 2016-10-10 |  |  |  | FNAL | 8 | 2016-11-02 | 2016-11-14 | 1.7143 | 5750 | 5407.1429 | 2016-11-21 | 14 | 40187.5 | Received | 4283.18 | 490 | 40187.5 | 50367.8229 | 2016-12-01 | 2 wk - recipe investigation. |  | 490
27 | CAV0029 | TD | 200 | 900 | Yes | 2016-09-19 | 2016-10-10 |  |  |  | FNAL | 8 | 2016-11-02 | 2016-11-14 | 1.7143 | 5750 | 5407.1429 | 2016-11-21 | 14 | 40187.5 | Received | 4283.18 | 490 | 40187.5 | 50367.8229 | 2016-12-01 | 2 wk - recipe investigation. |  | 490
28 | CAV0032 | TD | 200 | 900 | Yes | 2016-09-29 | 2016-10-28 | 2016-10-28 |  |  | FNAL | 8 | 2016-11-02 | 2016-11-14 | 1.7143 | 5750 | 5407.1429 | 2016-11-21 | 14 | 40187.5 | Received | 4283.18 | 490 | 40187.5 | 50367.8229 | 2016-12-01 | 2 wk - recipe investigation. |  | 490
29 | CAV0022 | TD | 200 | 900 | Yes | OK | 2016-09-22 | 2016-11-04 | NCR 53 | NCR 53 - minor mechanical | JLab | 9 | 2016-11-30 | 2016-11-16 | -2 | 5750 | 5750 | 2016-11-28 | 15 | 40187.5 | Received | 4283.18 | 490 | 40187.5 | 50710.68 | 2016-12-01 |  |  | 490
30 | CAV0031 | TD | 200 | 900 | Yes | 2016-09-27 | 2016-10-26 |  |  | 4 cavities in oven | JLab | 9 | 2016-11-30 | 2016-11-16 | -2 | 5750 | 5750 | 2016-11-28 | 15 | 40187.5 | Received | 4283.18 | 490 | 40187.5 | 50710.68 | 2016-12-01 |  |  | 490
31 | CAV0033 | TD | 200 | 900 | Yes | 2016-10-05 | 2016-11-02 |  |  |  | JLab | 9 | 2016-11-30 | 2016-11-16 | -2 | 5750 | 5750 | 2016-11-28 | 15 | 40187.5 | Received | 4283.18 | 490 | 40187.5 | 50710.68 | 2016-12-01 |  |  | 490
32 | CAV0035 | TD | 200 | 900 | Yes | 2016-09-27 | 2016-10-26 |  |  |  | JLab | 9 | 2016-11-30 | 2016-11-16 | -2 | 5750 | 5750 | 2016-11-28 | 15 | 40187.5 | Received | 4283.18 | 490 | 40187.5 | 50710.68 | 2016-12-01 |  |  | 490
33 | CAV0025 | TD | 200 | 900 | Yes | OK | 2016-10-07 |  | NCR 50, 56 | NCR 56 - minor mechanical | FNAL | 10 | 2016-11-30 | 2016-11-24 | -0.85714 | 5750 | 5750 | 2016-12-01 | 16 | 40187.5 | Received | 4283.18 | 490 | 40187.5 | 50710.68 | 2016-12-01 |  |  | 490
34 | CAV0030 | TD | 200 | 900 | Yes | OK | 2016-10-10 | 2016-11-04 | NCR 58 | NCR 58 - minor mechanical | FNAL | 10 | 2016-11-30 | 2016-11-24 | -0.85714 | 5750 | 5750 | 2016-12-01 | 16 | 40187.5 | Received | 4283.18 | 490 | 40187.5 | 50710.68 | 2016-12-01 |  |  | 490
35 | CAV0034 | TD | 200 | 900 | Yes | 2016-10-05 | 2016-11-02 |  |  |  | FNAL | 10 | 2016-11-30 | 2016-11-24 | -0.85714 | 5750 | 5750 | 2016-12-01 | 16 | 40187.5 | Received | 4283.18 | 490 | 40187.5 | 50710.68 | 2016-12-01 |  |  | 490
36 | CAV0036 | TD | 200 | 900 | Yes | 2016-10-05 | 2016-11-04 |  |  |  | FNAL | 10 | 2016-11-30 | 2016-11-24 | -0.85714 | 5750 | 5750 | 2016-12-01 | 16 | 40187.5 | Received | 4283.18 | 490 | 40187.5 | 50710.68 | 2016-12-01 |  |  | 490
37 | CAV0037 | TD | 200 | 900 | Yes | 2016-10-17 |  |  |  |  | JLab | 11 | 2016-11-30 | 2016-11-28 | -0.28571 | 5750 | 5750 | 2016-12-05 | 17 | 40187.5 | Received | 4283.18 | 490 | 40187.5 | 50710.68 | 2016-12-01 |  |  | 490
38 | CAV0038 | TD | 200 | 900 | Yes | 2016-10-05 |  |  |  |  | JLab | 11 | 2016-11-30 | 2016-11-28 | -0.28571 | 5750 | 5750 | 2016-12-05 | 17 | 40187.5 | Received | 4283.18 | 490 | 40187.5 | 50710.68 | 2016-12-01 |  |  | 490
39 | CAV0045 | TD | 200 | 900 | Yes | 2016-10-21 |  |  |  |  | JLab | 11 | 2016-11-30 | 2016-11-28 | -0.28571 | 5750 | 5750 | 2016-12-05 | 17 | 40187.5 | Received | 4283.18 | 490 | 40187.5 | 50710.68 | 2016-12-01 |  |  | 490
40 | CAV0049 | TD | 200 | 900 | Yes | 2016-11-04 |  |  |  |  | JLab | 11 | 2016-11-30 | 2016-11-28 | -0.28571 | 5750 | 5750 | 2016-12-05 | 17 | 40187.5 | Received | 4283.18 | 490 | 40187.5 | 50710.68 | 2016-12-01 |  |  | 490
41 | CAV0039 | TD | 200 | 900 | Yes | 2016-10-21 |  |  |  |  | FNAL | 12 | 2016-12-28 | 2016-11-30 | -4 | 2270 | 2270 | 2016-12-07 | 18 | 40187.5 | Received | 4283.18 | 490 | 40187.5 | 47230.68 | 2016-12-01 |  |  | 490
42 | CAV0040 | TD | 200 | 900 | Yes | 2016-11-04 |  |  |  |  | FNAL | 12 | 2016-12-28 | 2016-11-30 | -4 | 2270 | 2270 | 2016-12-07 | 18 | 40187.5 | Received | 4283.18 | 490 | 40187.5 | 47230.68 | 2016-12-01 |  |  | 490
43 | CAV0041 | TD | 200 | 900 | Yes | 2016-11-02 |  |  |  |  | FNAL | 12 | 2016-12-28 | 2016-11-30 | -4 | 2270 | 2270 | 2016-12-07 | 18 | 40187.5 | Received | 4283.18 | 490 | 40187.5 | 47230.68 | 2016-12-01 |  |  | 490
44 | CAV0042 | TD | 200 | 900 | Yes | 2016-10-21 |  |  |  |  | FNAL | 12 | 2016-12-28 | 2016-11-30 | -4 | 2270 | 2270 | 2016-12-07 | 18 | 40187.5 | Received | 4283.18 | 490 | 40187.5 | 47230.68 | 2016-12-01 |  |  | 490
45 | CAV0043 | TD |  |  |  | 2016-11-02 |  |  |  |  | FNAL | 13 | 2016-12-28 | 2016-12-16 | -1.7143 | 2270 | 2270 | 2017-01-11 | 18 | 40187.5 | HP1 | 4283.18 | 490 | 40187.5 | 47230.68 | 2017-02-22 |  |  | 490
46 | CAV0044 | TD |  |  |  | 2016-11-04 |  |  |  |  | FNAL | 13 | 2016-12-28 | 2016-12-16 | -1.7143 | 2270 | 2270 | 2017-01-11 | 18 | 40187.5 | HP1 | 4283.18 | 490 | 40187.5 | 47230.68 | 2017-02-22 |  |  | 490
47 | CAV0047 | TD | [8 empty] | FNAL | 13 | 2016-12-28 | 2016-12-16 | -1.7143 | 2270 | 2270 | 2017-01-11 |  | 40187.5 | Pre-Fab | 4283.18 | 490 | 40187.5 | 47230.68 | 2017-02-22 |  |  | 490
48 | CAV0048 | TD |  |  |  | 2016-11-04 |  |  |  |  | FNAL | 14 | 2016-12-28 | 2016-12-16 | -1.7143 | 2270 | 2270 | 2017-01-11 | 18 | 40187.5 | HP1 | 4283.18 | 490 | 40187.5 | 47230.68 | 2017-02-22 |  |  | 490
49 | CAV0046 | TD | [8 empty] | FNAL | 13 | 2016-12-28 | 2017-01-11 | 2 | 2270 | 2270 | 2017-01-19 | 18 | 40187.5 | Pre-Fab | 4283.18 | 490 | 40187.5 | 47230.68 | 2017-02-22 |  |  | 490
50 | CAV0050 | TD | [8 empty] | FNAL | 14 | 2016-12-28 | 2017-01-11 | 2 | 2270 | 2270 | 2017-01-19 |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 47230.68 | 2017-02-22 |  |  | 490
51 | CAV0051 | TD | [8 empty] | FNAL | 14 | 2016-12-28 | 2017-01-11 | 2 | 2270 | 2270 | 2017-01-19 |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 47230.68 | 2017-02-22 |  |  | 490
52 | CAV0052 | TD | [8 empty] | FNAL | 14 | 2016-12-28 | 2017-01-11 | 2 | 2270 | 2270 | 2017-01-19 |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 47230.68 | 2017-02-22 |  |  | 490
| CAV0053 | TD | [10 empty] | 2017-01-25 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0054 | TD | [10 empty] | 2017-01-25 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0055 | TD | [10 empty] | 2017-01-25 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0056 | TD | [10 empty] | 2017-01-25 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0057 | TD | [10 empty] | 2017-01-25 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0058 | TD | [10 empty] | 2017-01-25 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0059 | TD | [10 empty] | 2017-01-25 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0060 | TD | [10 empty] | 2017-01-25 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0061 | TD | [10 empty] | 2017-01-25 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0062 | TD | [10 empty] | 2017-01-25 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0063 | TD | [10 empty] | 2017-01-25 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0064 | TD | [10 empty] | 2017-01-25 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0065 | TD | [10 empty] | 2017-02-22 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0066 | TD | [10 empty] | 2017-02-22 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0067 | NX | [10 empty] | 2017-02-22 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0068 | NX | [10 empty] | 2017-02-22 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0069 | NX | [10 empty] | 2017-02-22 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0070 | NX | [10 empty] | 2017-02-22 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0071 | NX | [10 empty] | 2017-02-22 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0072 | NX | [10 empty] | 2017-02-22 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0073 | NX | [10 empty] | 2017-02-22 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0074 | NX | [10 empty] | 2017-02-22 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0075 | NX | [10 empty] | 2017-02-22 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0076 | NX | [10 empty] | 2017-02-22 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0077 | NX | [10 empty] | 2017-03-22 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0078 | NX | [10 empty] | 2017-03-22 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0079 | NX | [10 empty] | 2017-03-22 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0080 | NX | [10 empty] | 2017-03-22 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0081 | NX | [10 empty] | 2017-03-22 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0082 | NX | [10 empty] | 2017-03-22 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0083 | NX | [10 empty] | 2017-03-22 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0084 | NX | [10 empty] | 2017-03-22 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0085 | NX | [10 empty] | 2017-03-22 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0086 | NX | [10 empty] | 2017-03-22 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0087 | NX | [10 empty] | 2017-03-22 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0088 | NX | [10 empty] | 2017-03-22 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0089 | NX | [10 empty] | 2017-04-19 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0090 | NX | [10 empty] | 2017-04-19 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0091 | NX | [10 empty] | 2017-04-19 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0092 | [11 empty] | 2017-04-19 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0093 | [11 empty] | 2017-04-19 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0094 | [11 empty] | 2017-04-19 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0095 | [11 empty] | 2017-04-19 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0096 | [11 empty] | 2017-04-19 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0097 | [11 empty] | 2017-04-19 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0098 | [11 empty] | 2017-04-19 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0099 | [11 empty] | 2017-04-19 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0100 | [11 empty] | 2017-04-19 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0101 | [11 empty] | 2017-05-17 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0102 | [11 empty] | 2017-05-17 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0103 | [11 empty] | 2017-05-17 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0104 | [11 empty] | 2017-05-17 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0105 | [11 empty] | 2017-05-17 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0106 | [11 empty] | 2017-05-17 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0107 | [11 empty] | 2017-05-17 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0108 | [11 empty] | 2017-05-17 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0109 | [11 empty] | 2017-05-17 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0110 | [11 empty] | 2017-05-17 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0111 | [11 empty] | 2017-05-17 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0112 | [11 empty] | 2017-05-17 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0113 | [11 empty] | 2017-06-14 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0114 | [11 empty] | 2017-06-14 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0115 | [11 empty] | 2017-06-14 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0116 | [11 empty] | 2017-06-14 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0117 | [11 empty] | 2017-06-14 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0118 | [11 empty] | 2017-06-14 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0119 | [11 empty] | 2017-06-14 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0120 | [11 empty] | 2017-06-14 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0121 | [11 empty] | 2017-06-14 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0122 | [11 empty] | 2017-06-14 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0123 | [11 empty] | 2017-06-14 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0124 | [11 empty] | 2017-06-14 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0125 | [11 empty] | 2017-07-12 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0126 | [11 empty] | 2017-07-12 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0127 | [11 empty] | 2017-07-12 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0128 | [11 empty] | 2017-07-12 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0129 | [11 empty] | 2017-07-12 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0130 | [11 empty] | 2017-07-12 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0131 | [11 empty] | 2017-07-12 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0132 | [11 empty] | 2017-07-12 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.18 | 490 | 40187.5 | 45960.68 |  |  |  | 490
| CAV0133 | [11 empty] | 2017-07-12 |  | 0 | 1000 | 1000 |  |  |  | Pre-Fab | 4283.84 | 470 | 40187.5 | 45941.34 |  |  |  | 490
[15 empty] | 0 |  | 0 |  | 18 | 40187.5 |  |  |  | 40187.5 | 40187.5 |  |  | 57800 | 57330
[15 empty] | 0 |  | 0 |  |  | 964500 |  |  |  | 40187.5 | 40187.5 |  |  |  | 470
[15 empty] | 0 |  | 0 | [6 empty] | 40187.5 | 40187.5
[15 empty] | 0 |  | 0 | [6 empty] | 40187.5 | 40187.5
[15 empty] | 0 |  | 0 | [6 empty] | 40187.5 | 40187.5
[15 empty] | 0 |  | 0 | [6 empty] | 40187.5 | 40187.5
[15 empty] | 0 |  | 0 | [6 empty] | 40187.5 | 40187.5
[15 empty] | 0 |  | 0 | [6 empty] | 40187.5 | 40187.5
[15 empty] | 0 |  | 0 | [6 empty] | 40187.5 | 40187.5
[15 empty] | 0 |  | 0 | [6 empty] | 40187.5 | 40187.5
[15 empty] | 0 |  | 0 | [6 empty] | 40187.5 | 40187.5
[15 empty] | 0 |  | 0 | [6 empty] | 40187.5 | 40187.5
[15 empty] | 0 |  | 0 | [6 empty] | 40187.5 | 40187.5
[15 empty] | 0 |  | 0 | [6 empty] | 40187.5 | 40187.5
[15 empty] | 0 |  | 0 | [6 empty] | 40187.5 | 40187.5
[15 empty] | 0 |  | 0 | [6 empty] | 40187.5 | 40187.5
Total | [16 empty] | 244868.5714 |  |  | 2973875 |  | 484000 | 57310 | 5987937.5 | 6774116.0714
484000
0
40187.5
Formulas:
Wks +/- Incentive Date = IF(CavityStatus[[#This Row],[Actual Ship Date]]<>0,([Actual Ship Date]-[Incentivized Ship Date])/7,0)

## List
| Description | PO# | RI |  | EZ |  | Ship Date | Ship Loc | Material | Status | % Complete | 2016-11-01 | CavityMilestone
% Complete | Proof of equipment order furnace uprade | 1 | 1-4 | JLab 02 | 1-4 | FNAL 03 | 2017-02-22 | JLab | TD | Pre-Fab | 0% | 2016-12-01 | 40187.5
100% | Proof of completed furnace uprade | 2 | 5-8 | FNAL 02 | 5-8 | FNAL 03 | 2017-02-23 | FNAL | NX | HP1 | 2.5% | 2017-01-01
95% | Acceptance of Ni doping process - Cav 1 (of 2) | 3 | 9-12 | FNAL 02 | 9-12 | FNAL 05 | 2017-02-24 |  |  | HP2 | 5% | 2017-02-01
90% | Acceptance of Ni doping process - Cav 2 (of 2) | 4 | 13-16 | JLab 02 | 13-16 | FNAL 05 | 2017-02-27 |  |  | HP3 | 7.5% | 2017-03-01
85% | PH II: Mfg Drawings Accepted by JLab | 5 | 17-20 | FNAL 04 | 17-20 | JLab 04 | 2017-02-28 |  |  | Shipped | 10% | 2017-04-01
80% | PH II: FAs Mech Pre-fab (Deep Draw) | 6 | 21-24 | FNAL 04 | 21-24 | JLab 04 | 2017-03-01 |  |  | Received | 12.5% | 2017-05-01
75% | PH III: Mech Pre-Fab Cavities (9-72) | 7 | 25-28 | JLab 03 | 25-28 | JLab 06 | 2017-03-02 |  |  | Accepted | 15% | 2017-06-01
70% | PH III: Mech Pre-Fab Cavities (73-133) | 8 | 29-32 | JLab 03 | 29-32 | JLab 06 | 2017-03-03 |  |  | Complete | 17.5% | 2017-07-01
65% | PH II: First Articles Deliver & Accept (1-8) | 9 | 33-36 | JLab 05 | 33-36 | FNAL 06 | 2017-03-06 |  |  |  | 20% | 2017-08-01
60% | PH III: Deliver & Accept Cavities (9-12) | 10 | 37-40 | JLab 05 | 37-40 | FNAL 06 | 2017-03-07 |  |  |  | 22.5% | 2017-09-01
55% | PH III: Deliver & Accept Cavities (13-16) | 11 | 41-44 | JLab 07 | 41-44 | FNAL 07 | 2017-03-08 |  |  |  | 25% | 2017-10-01
50% | PH III: Deliver & Accept Cavities (17-20) | 12 | 45-48 | JLab 07 | 45-48 | FNAL 07 | 2017-03-09 |  |  |  | 27.5% | 2017-11-01
45% | PH III: Deliver & Accept Cavities (21-24) | 13 | 49-52 | FNAL 08 | 49-52 | FNAL 09 | 2017-03-10 |  |  |  | 30% | 2017-12-01
40% | PH III: Deliver & Accept Cavities (25-28) | 14 | 53-56 | FNAL 08 | 53-56 | FNAL 09 | 2017-03-13 |  |  |  | 32.5% | 2018-01-01
35% | PH III: Deliver & Accept Cavities (29-32) | 15 | 57-60 | FNAL 11 | 57-60 | FNAL 10 | 2017-03-14 |  |  |  | 35% | 2018-02-01
30% | PH III: Deliver & Accept Cavities (33-36) | 16 | 61-64 | FNAL 11 | 61-64 | FNAL 10 | 2017-03-15 |  |  |  | 37.5% | 2018-03-01
25% | PH III: Deliver & Accept Cavities (37-40) | 17 | 65-68 | JLab 09 | 65-68 | JLab 08 | 2017-03-16 |  |  |  | 40% | 2018-04-01
20% | PH III: Deliver & Accept Cavities (41-44) | 18 | 69-72 | JLab 09 | 69-72 | JLab 08 | 2017-03-17 |  |  |  | 42.5% | 2018-05-01
15% | PH III: Deliver & Accept Cavities (45-48) | 19 | 73-76 | JLab 11 | 73-76 | JLab 10 | 2017-03-20 |  |  |  | 45% | 2018-06-01
10% | PH III: Deliver & Accept Cavities (49-52) | 20 | 77-80 | JLab 11 | 77-80 | Jlab 10 | 2017-03-21 |  |  |  | 47.5% | 2018-07-01
5% | MOD 002: DESY Equip Refurbishment | 21 | 81-84 | JLab 14 | 81-84 | JLab 12 | 2017-03-22 |  |  |  | 50% | 2018-08-01
-3.192e-14% | MOD 002: DESY Equip Service & Support Costs | 22 | 85-88 | JLab 14 | 85-88 | JLab 12 |  |  |  |  | 52.5% | 2018-09-01
| MOD 003: Accel Shipment (1-16) Incentives (Max of $323,136) | 23 | 89-92 | JLab 15 | 89-92 | JLab 13 |  |  |  |  | 55%
| MOD 004: Incentives for Accelerated Production Deliveries | 24 | 93-96 | JLab 15 | 93-96 | JLab 13 |  |  |  |  | 57.5%
| MOD 005: DESY Equipment Lease ($9,200/ month) | 25 | 97-100 | FNAL 13 | 97-100 | FNAL 12 |  |  |  |  | 60%
| PH III: Deliver & Accept Cavities (53-56) | 26 | 101-104 | FNAL 13 | 101-104 | FNAL 12 |  |  |  |  | 62.5%
| PH III: Deliver & Accept Cavities (57-60) | 27 | 105-108 | FNAL 14 | 105-108 | JLab 16 |  |  |  |  | 65%
| PH III: Deliver & Accept Cavities (61-64) | 28 | 109-112 | FNAL 14 | 109-112 | JLab 16 |  |  |  |  | 67.5%
| PH III: Deliver & Accept Cavities (65-68) | 29 | 113-116 | FNAL 16 | 113-116 | JLab 17 |  |  |  |  | 70%
| PH III: Deliver & Accept Cavities (69-72) | 30 | 117-120 | FNAL 16 | 117-120 | JLab 17 |  |  |  |  | 72.5%
| PH III: Deliver & Accept Cavities (73-76) | 31 | 121-124 | FNAL 17 | 121-124 | FNAL 15 |  |  |  |  | 75%
| PH III: Deliver & Accept Cavities (77-80) | 32 | 125-128 | FNAL 17 | 125-128 | FNAL 15 |  |  |  |  | 77.5%
| PH III: Deliver & Accept Cavities (81-84) | 33 | 129-130 | Jlab 18 | 129-133 | Jlab 18 |  |  |  |  | 80%
| PH III: Deliver & Accept Cavities (85-88) | 34 | 131-133 | Jlab 18 | [6 empty] | 82.5%
| PH III: Deliver & Accept Cavities (89-92) | 35 | [8 empty] | 85%
| PH III: Deliver & Accept Cavities (93-96) | 36 | [8 empty] | 87.5%
| PH III: Deliver & Accept Cavities (97-100) | 37 | [8 empty] | 90%
| PH III: Deliver & Accept Cavities (101-104) | 38 | [8 empty] | 92.5%
| PH III: Deliver & Accept Cavities (105-108) | 39 | [8 empty] | 95%
| PH III: Deliver & Accept Cavities (109-112) | 40 | [8 empty] | 97.5%
| PH III: Deliver & Accept Cavities (113-116) | 41 | [8 empty] | 100%
| PH III: Deliver & Accept Cavities (117-120) | 42
| PH III: Deliver & Accept Cavities (121-124) | 43
| PH III: Deliver & Accept Cavities (125-128) | 44
| PH III: Deliver & Accept Cavities (129-133) | 45
| MOD 007: LCLS-II R&D Cavities (4) | 46
| MOD 008: CTM Spare Parts | 51
| MOD 009: Recipe Modification (21-133) ($4283.18/cavity) | Total
| MOD 010: Niobium Caps $494.02/ea (Cavs 17-133) | 0
| MOD 011: Optional Cavities 1-8 | Procurement Entered By: ________________________________________________________________
0
0
Procurement Data Entry Verified By: _______________________________________________________
0
0
0
0
0
0
0
0
Formulas:
Ship Date = WORKDAY([Ship Date, row above],1)