## Form
JSA / Jefferson Lab - DOE
PO Percent Complete Form
Appendix A
Vendor Name | Air Liquide Advanced Technologies, US Inc. (ALATUS) | [5 empty] | PO with Peg Points? (Yes or No)
PO Number | 15-C1196 |  |  | Buyer | Fitzpatrick | Complete through | 2017-02-28
(Date)
PO Line # | Percent Complete | Completed Peg Point (X) |  | Summary of Work (only if less than 100%)
1 | 100% |  |  | Completion of Kick Off Meeting (KOM)
2 | 100% |  |  | Preliminary Design Review (PDR)
3 | 100% |  |  | Mod 002: Issue order for Long Lead Items, add engineering*
4 | 90.11% |  |  | Complete final design review (FDR)
5 | 100% |  |  | Delivery of main material to start CB manufacturing at factory
6 | 0% |  |  | Cold Box 1 Manufacturing Complete
7 | 0% |  |  | MOD 005: Customs & Duties for Line 5
8 | 0% |  |  | MOD 005: UL Stamp for ELE Boxes
9 | 0% |  |  | Factory acceptance of completed turbines
10 | 0% |  |  | Cold Box 1 Received at SLAC
11 | 0% |  |  | Cold Box 1 Assembled at SLAC
12 | 0% |  |  | Cold Box 2 Manufacturing Complete
13 | 0% |  |  | Cold Box 2 Received at SLAC
14 | 0% |  |  | Cold Box 2 Assembled at SLAC
15 | 0% |  |  | Commissioning, Training, & Acceptance - CB1
16 | 0% |  |  | Delivery of operating and maintenance manuals
17 | 0% |  |  | Commissioning, Training, & Acceptance - CB2
18 | 0%
19 | 0%
20 | 0%
21 | 0%
22 | 0%
23 | 0%
24 | 0%
25 | 0%
26 | 0%
27 | 0%
28 | 0%
29 | 0%
30 | 0%
31 | 0%
32 | 0%
33 | 0%
34 | 0%
35 | 0%
36 | 0%
37 | 0%
38 | 0%
39 | 0%
40 | 0%
41 | 0%
42 | 0%
0%
0%
Vendor Technical Representative Contacted:
|  |  | Name |  |  |  |  | Date
Jlab Control Account Manager (CAM): |  |  |  |  | Dana Arenius |  |  | 2017-02-28
[6 empty] | Name |  | Date
Below for use by Accounting/Shipping & Receiving Only
Accounting or Shipping & Receiving Entered By:
Date
Data Entry Verified By:
Date

## Process
JSA / Jefferson Lab - DOE
PO Percent Complete Form
Procedure
A Subcontract Purchase Order (PO) is a service type PO with loosely defined scheduled deliverables and variable amounts. A Peg Point PO has specified scheduled deliverable dates for a specified amount.
This form is to be used if NO invoice has been approved by the SOTR or CAM for work completed.
SOTR or CAM contacts a vendor technical representative for an evaluation of the percent of work completed. This can be done either verbally or via email.
Required information - Vendor Name, indicate if PO is a Peg Point type PO or not, PO #, Buyer, Complete through date (usually the end of the month), PO Line #, Percent complete, a short Summary of Work performed provided by the Vendor Technical Representative that supports the percent complete if less than 100%, the name of the Vendor Technical Representative contacted, and the CAM name.
The SOTR or CAM will submit a PO Percent Complete form by the 2nd working day following the end of the month affected for work that has been completed. This allows time for Accounting to process an accrual for the month end closing. Reminder if PO is for Peg Points, the peg point must be fully complete before claiming it.
Submit the completed form with all the information via email to evpo@jlab.org. The file name of the spreadsheet attached to the email should always include the PO# and the letters 'S&R' if it is a Peg Point type PO. File name examples: Peg Point Type PO 08-C5413 S&R, Subcontract Type PO 08-A2659. This email will forward the form automatically to personnel in Procurement, Shipping & Receiving, CFO, and PMI.
If the PO is a Subcontract type PO, the SOTR or CAM will still be required to sign all invoices received at JLab from the vendor up since this was an estimate. An approved invoice by the SOTR or CAM can also be used as basis for the percent of work complete.
If the PO is a Peg Point type PO, Shipping & Receiving will use this form to enter that Peg Point into the Costpoint Financial System. No additional invoice approvals will be required since the SOTR or CAM already indicated the work was complete. An approved invoice by the SOTR or CAM can also be used as basis for the percent of work complete without having to complete this form.
If a previous percent complete was submitted and subsequently determined to be in error, adjust the percent complete to correct the error. Add an explanatory note to support the adjustment.

## Accting USE Data Entry Form
JSA / Jefferson Lab - DOE
Data Entry Update Subcontract PO Percent Complete
Vendor Name |  | Air Liquide Advanced Technologies, US Inc. (ALATUS) | [14 empty] | Percent complete thru |  |  | 2017-02-28
(Date)
PO Number |  | 15-C1196 | [15 empty] | OR
Buyer |  | Fitzpatrick |  |  | 2016-11-01 | 2016-12-01 | 2017-01-01 | 2017-02-01 | 2017-03-01 | 2017-04-01 | [6 empty] | Invoice Number
PO Line # | Milestone # | Description | Est Date | Beg % Complete | Monthly Accrual ($) | Monthly Accrual ($) | Monthly Accrual ($) | Monthly Accrual ($) | Monthly Accrual ($) | Monthly Accrual ($) | Tot % Complete |  | PO Line Total | = | Completed Work Amt | Completed Work Amt | - | Eligible for Voucher Amt | - | Prev Vouchered Amount | = | Completed Work Retention Amt
1 | 1 | Completion of Kick Off Meeting (KOM) | 2015-10-08 | 100% | [6 empty] | 100% | X | 502100 | = | 502100 | 502100 | - | 0 | - | 502100 | = | 0
2 | 2 | Preliminary Design Review (PDR) | 2016-03-10 | 100% | [6 empty] | 100% | X | 502100 | = | 502100 | 502100 | - | 0 | - | 502100 | = | 0
3 | 3 | Mod 002: Issue order for Long Lead Items, add engineering* | 2016-04-08 | 82.25% |  |  | 936680 |  |  |  | 100% | X | 5277520 | = | 5277519.9095 | 5277519.9095 | - | -0.090477 | - | 5277520 | = | 0
4 | 4 | Complete final design review (FDR) | 2016-07-11 | 90.11% | [6 empty] | 90.11% | X | 1861900 | = | 1677756.044 | 1677756.044 | - | 0.043956 | - | 1677756 | = | 0
5 | 5 | Delivery of main material to start CB manufacturing at factory | 2016-11-11 | 0% |  |  | 910806.018 | 1515207.982 |  |  | 100% | X | 2426014 | = | 2426014 | 2426014 | - | 0 | - | 2426014 | = | 0
6 | 6 | Cold Box 1 Manufacturing Complete | 2017-08-11 | 0% | [6 empty] | 0% | X | 1483976 | = | 0 | 0 | - | 0 | - | 0 | = | 0
7 | 5 | MOD 005: Customs & Duties for Line 5 | 2019-02-11 | 0% | [6 empty] | 0% | X | 278066 | = | 0 | 0 | - | 0 | - | 0 | = | 0
8 | 5 | MOD 005: UL Stamp for ELE Boxes | 2019-02-11 | 0% | [6 empty] | 0% | X | 5544 | = | 0 | 0 | - | 0 | - | 0 | = | 0
9 | 7 | Factory acceptance of completed turbines | 2017-08-25 | 0% | [6 empty] | 0% | X | 930950 | = | 0 | 0 |  | 0 |  | 0 | = | 0
10 | 8 | Cold Box 1 Received at SLAC | 2017-09-11 | 0% | [6 empty] | 0% | X | 465475 | = | 0 | 0 | - | 0 | - | 0 | = | 0
11 | 9 | Cold Box 1 Assembled at SLAC | 2017-12-11 | 0% | [6 empty] | 0% | X | 465475 | = | 0 | 0 | - | 0 | - | 0 | = | 0
12 | 10 | Cold Box 2 Manufacturing Complete | 2018-02-12 | 0% | [6 empty] | 0% | X | 1489519.9883 | = | 0 | 0 | - | 0 | - | 0 | = | 0
13 | 11 | Cold Box 2 Received at SLAC | 2018-03-12 | 0% | [6 empty] | 0% | X | 465475 | = | 0 | 0 | - | 0 | - | 0 | = | 0
14 | 12 | Cold Box 2 Assembled at SLAC | 2018-06-11 | 0% | [6 empty] | 0% | X | 465475 | = | 0 | 0 | - | 0 | - | 0 | = | 0
15 | 13 | Commissioning, Training, & Acceptance - CB1 | 2018-10-11 | 0% | [6 empty] | 0% | X | 930950.4 | = | 0 | 0 | - | 0 | - | 0 | = | 0
16 | 14 | Delivery of operating and maintenance manuals | 2019-01-11 | 0% | [6 empty] | 0% | X | 485319.2 | = | 0 | 0 | - | 0 | - | 0 | = | 0
17 | 15 | Commissioning, Training, & Acceptance - CB2 | 2019-02-11 | 0% | [6 empty] | 0% | X | 930950.4 | = | 0 | 0 | - | 0 | - | 0 | = | 0
18 |  |  |  | 0% | [6 empty] | 0% | X |  | = | 0 | 0 | - | 0 | - | 0 | = | 0
19 |  |  |  | 0% | [6 empty] | 0% | X |  | = | 0 | 0 | - | 0 | - | 0 | = | 0
20 |  |  |  | 0% | [6 empty] | 0% | X |  | = | 0 | 0 | - | 0 | - | 0 | = | 0
21 |  |  |  | 0% | [6 empty] | 0% | X |  | = | 0 | 0 | - | 0 | - | 0 | = | 0
22 |  |  |  | 0% | [6 empty] | 0% | X |  | = | 0 | 0 | - | 0 | - | 0 | = | 0
23 |  |  |  | 0% | [6 empty] | 0% | X |  | = | 0 | 0 | - | 0 | - | 0 | = | 0
24 |  |  |  | 0% | [6 empty] | 0% | X |  | = | 0 | 0 | - | 0 | - | 0 | = | 0
25 |  |  |  | 0% | [6 empty] | 0% | X |  | = | 0 | 0 | - | 0 | - | 0 | = | 0
26 |  |  |  | 0% | [6 empty] | 0% | X |  | = | 0 | 0 | - | 0 | - | 0 | = | 0
27 |  |  |  | 0% | [6 empty] | 0% | X |  | = | 0 | 0 | - | 0 | - | 0 | = | 0
28 |  |  |  | 0% | [6 empty] | 0% | X |  | = | 0 | 0 | - | 0 | - | 0 | = | 0
29 |  |  |  | 0% | [6 empty] | 0% | X |  | = | 0 | 0 | - | 0 | - | 0 | = | 0
30 |  |  |  | 0% | [6 empty] | 0% | X |  | = | 0 | 0 | - | 0 | - | 0 | = | 0
31 |  |  |  | 0% | [6 empty] | 0% | X |  | = | 0 | 0 | - | 0 | - | 0 | = | 0
32 |  |  |  | 0% | [6 empty] | 0% | X |  | = | 0 | 0 | - | 0 | - | 0 | = | 0
33 |  |  |  | 0% | [6 empty] | 0% | X |  | = | 0 | 0 | - | 0 | - | 0 | = | 0
34 |  |  |  | 0% | [6 empty] | 0% | X |  | = | 0 | 0 | - | 0 | - | 0 | = | 0
35 |  |  |  | 0% | [6 empty] | 0% | X |  | = | 0 | 0 | - | 0 | - | 0 | = | 0
36 |  |  |  | 0% | [6 empty] | 0% | X |  | = | 0 | 0 | - | 0 | - | 0 | = | 0
37 |  |  |  | 0% | [6 empty] | 0% | X |  | = | 0 | 0 | - | 0 | - | 0 | = | 0
38 |  |  |  | 0% | [6 empty] | 0% |  |  |  | 0 |  |  |  |  | 0
39 |  |  |  | 0% | [6 empty] | 0% |  |  |  | 0 |  |  |  |  | 0
40 |  |  |  | 0% | [6 empty] | 0% |  |  |  | 0 |  |  |  |  | 0
41 |  |  |  | 0% | [6 empty] | 0% |  |  |  | 0 |  |  |  |  | 0
42 |  |  |  | 0% | [6 empty] | 0% | X |  | = | 0 | 0 | - | 0 | - | 0 | = | 0
|  |  |  | 54.76% | [8 empty] | 18966809.9883 |  | 10385489.9535 | 10385489.9535 |  | 10385489.9535 |  |  |  | 0
Procurement Entered By: ________________________________________________________________ | [19 empty] | 2017-02-28
Date
Procurement Data Entry Verified By: _______________________________________________________ | [12 empty] | 1232842.6492
[13 empty] | 924631.9869 |  | 1232842.6492 |  |  |  |  | Date
[13 empty] | 616421.3246 |  | 308210.6623

## Invoices
Invoice # | Invoice Date | Description | Invoice Amount | Approval Date | PO line
64737390 | 2016-05-18 | Preliminary Design Review (PDR) | 502100
64678952 | 2016-05-06 | Mod 002: Issue order for Long Lead Items, add engineering* | 4340840
63449614 | 2015-12-18 | Completion of Kick Off Meeting (KOM) | 502100
65699321 | 2016-10-01 | Complete final design review (FDR) | 1677756 | 2016-10-26
66002927 | 2016-12-05 | Mod 002: Issue order for Long Lead Items, add engineering* | 936680 | 2017-01-27
66311061 | 2017-02-08 | Delivery of main material to start CB manufacturing at factory | 2426014 | 2017-03-01 | 5

## Mods
C | Mod# | Award Sched Line | Description | Unit | Unit Amount | Total
| 1 | N/A | Administrative Mod | 0 | 0 | 0
| 2 | 5 | CP2 Fabrication | 1 | 7719000 | 7719000
| 2 | 6 | CP2 Seismic Option 2 | 1 | 90000 | 90000
| 2 | 7 | CP2 Delivery | 1 | 228000 | 228000
| 2 | 8 | Dual Core HX-1 Design | 2 | 270000 | 540000
| 2 | 9 | Delay Costs for HX-1 Design | 4 | 16050 | 64200
| 3 | N/A | Funding Modification | 0 | 0 | 0
| 4 | N/A | Funding Modification | 0 | 0 | 0
2017-01-24 | 5 | 10 | Heat Exchangers Shipment - CP1 | 1 | 114453 | 0
2017-01-24 | 5 | 10 | Turbine Casing Shipment - CP1 | 1 | 19420 | 0
2017-01-24 | 5 | 10 | Turbine Cartridges and Spare Parts Shipment - CP1 | 1 | 19846 | 0
2017-01-24 | 5 | 10 | Heat Exchangers Shipment - CP2 | 1 | 91648 | 0
2017-01-24 | 5 | 10 | Turbine Casing Shipment - CP2 | 1 | 17218 | 0
2017-01-24 | 5 | 10 | Turbine Cartridges and Spare Parts Shipment - CP2 | 1 | 15481 | 0
Total | [5 empty] | 8641200

## Change Request
Change Requests
CRN# | Description | Date Issued | Issued By | Review Date | Approved? | Resulting Mod | Notes
CRNAL_001
CRNAL_002
CRNAL_003
CRNAL_004
CRNAL_005
CRNAL_006 | Anchor Design Change | 2017-02-09 | ALATUS
CRNAL_007
CRNAL_008
CRNAL_009

## Weekly Update
| 4.5K CB Milestones | Award Value |  | $18.7 M
# | Milestone Description | Subcontract Complete Date | Status |  | Comments
1 | Completion of Kick Off Meeting | 2015-10-08 | 2015-10-08 | 100%
2 | Preliminary Design Review (PDR) | 2016-03-10 | 2016-03-10 | 100%
3 | Order LLPs (Heat Exchangers, Cryovalves, Cold Box Shell) | 2016-04-08 | In Progress | 100% | 11/1/16 - All LLPs orderd. Jlab approval is pending FDR (Seismic Design Report) acceptance.
4 | Final Design Review (FDR) | 2016-07-11 | In Progress | 83% | 2/24/17 - Revised Hopper Report expected on March 6th. 2/9/17 - Conference call with all parties scheduled for Monday morning. 1/26/17 - Approval pending resolution of FDR/ Seismic Report comments. 1/13/17 - All Seismic Report comments submitted to AL for response.
5 | Main Material Delivery (to PHPK) | 2016-11-11 | Complete | 100% | 2/23/17 - Main materials delivered. Manufacturing has begun.
6 | Cold Box 1 Manufacturing | 2017-08-11 | Started | 1% | 2/1/17 - AL internal manufacturing readiness review conducted at PHPK.
7 | Factory acceptance of completed turbines | 2017-08-25 |  | 0%
8 | Cold Box 1 Received at SLAC | 2017-09-11
9 | Cold Box 1 Assembled at SLAC | 2017-12-11
10 | Cold Box 2 Manufacturing Complete | 2018-02-12
11 | Cold Box 2 Received at SLAC | 2018-03-12
12 | Cold Box 2 Assembled at SLAC | 2018-06-11
13 | Commissioning, Train, & Accept (CB1) | 2018-10-11
14 | Deliver Ops & Main Manuals | 2019-01-11
15 | Commissioning, Train, & Accept (CB2) | 2019-02-11

## List
% Complete | Date
100% | 2017-02-22
95% | 2017-02-23
90% | 2017-02-24
85% | 2017-02-27
80% | 2017-02-28
75% | 2017-03-01
70% | 2017-03-02
65% | 2017-03-03
60% | 2017-03-06
55% | 2017-03-07
50% | 2017-03-08
45% | 2017-03-09
40% | 2017-03-10
35% | 2017-03-13
30% | 2017-03-14
25% | 2017-03-15
20% | 2017-03-16
15% | 2017-03-17
10% | 2017-03-20
5% | 2017-03-21
-3.192e-14% | 2017-03-22

## Tableau
Activity ID | TaskID | Activity | System | Activity Type | Description | Abbrev Name | MS # | Duration | Start | Complete (Subcontract Required) | Actual Complete | Status/ % Complete | Column1 | Comments
1 | 1.1 | Preliminary Design | CB1 | Task | Subonctract Execution | Award | N/A | 1 | 2015-10-08 | 2015-10-08 | 2015-10-08 | 2015-10-08 | 100%
1 | 1.2 | Preliminary Design | CB1 | Milestone | Completion of Kick Off Meeting | Kickoff Meeting | 1 | 1 | 2015-10-09 | 2015-10-08 | 2015-10-08 | 2015-10-08 | 100%
1 | 1.3 | Preliminary Design | CB1 | Milestone | Preliminary Design Review (PDR) | PDR | 2 | 110 | 2015-10-09 | 2016-03-10 | 2016-03-10 | 2016-03-10 | 100%
2 | 2 | Procurement | CB1 | Task | Order LLPs (Heat Exchangers, Cryovalves, Cold Box Shell) | Order LLPs | N/A | 100 | 2016-03-11 | 2016-04-08 | 2017-01-27 | In Progress | 100% | 11/1/16 - All LLPs orderd. Jlab approval is pending FDR (Seismic Design Report) acceptance.
2 | 2.1 | Procurement | CB1 | Milestone | Order LLPs (Heat Exchangers, Cryovalves, Cold Box Shell) | Order LLPs | 3 | 1 | 2016-04-11 | 2016-04-08
3 | 3 | Final Design | CB1 | Task | Final Design Review (FDR) | Final Design | 4 | 66 | 2016-04-11 | 2016-07-11 |  | In Progress | 83% | 2/9/17 - Conference call with all parties scheduled for Monday morning. 1/26/17 - Approval pending resolution of FDR/ Seismic Report comments. 1/13/17 - All Seismic Report comments submitted to AL for response.
3 | 3.1 | Final Design | CB1 | Milestone | Final Design Review (FDR) | FDR | 4 | 1 | 2016-07-11 | 2016-07-11
2 | 2.2 | Procurement | CB1 | Milestone | Main Material Delivery (to PHPK) | Main Mat'l Delivery | 5 | 89 | 2016-07-12 | 2016-11-11 |  | In Progress | 40% | 2/9/17 - 4th Heat exchanger shipment expected at the end of March. 1/19/17 - Inspection of 3rd (of 4) heat exchanger shipments conducted at PHPK.
2 | 2.3 | Procurement | CB2 | Milestone | Main Material Delivery (to PHPK) | Main Mat'l Delivery | 5 | -2 | 2016-11-14 | 2016-11-11
4 | 4 | Manufacturing | CB1 | Task | Cold Box 1 Manufacturing | Manufacturing | 6 | 1 | 2016-11-14 | 2017-08-11 |  | Started | 1% | 2/1/17 - AL internal manufacturing readiness review conducted at PHPK.
4 | 4.2 | Manufacturing | CB1 | Witness Point | WP1 HX-4 Leak Check | HX-4 Leak Check | 2 | 1 | 2017-01-31 | 2017-04-21
4 | 4.5 | Manufacturing | CB1 | Milestone | Factory acceptance of completed turbines | Factory Acceptance (turbines) | 7 | 1 | 2017-03-02 | 2017-08-25 |  |  | 0%
4 | 4.3 | Manufacturing | CB1 | Witness Point | WP3 Test Cryo Control Valves | Test Cryo Control Valves | 3 | 1 | 2017-04-24 | 2017-03-01
4 | 4.4 | Manufacturing | CB1 | Milestone | Manufacturing Acceptance Test | Mfg Acceptance Test | 6 | 1 | 2017-08-11 | 2017-08-11
5 | 5 | Shipment | CB1 | Task | Ship Cold Box | Ship Cold Box | N/A | 30 | 2017-08-26 | 2017-09-11
5 | 5.1 | Shipment | CB1 | Milestone | Received at SLAC | Received at SLAC | 8 | 1 | 2017-08-28 | 2017-09-11
6 | 6 | Assembly | CB1 | Task | Assemble Cold Box | Assemble Cold Box | N/A | 65 | 2017-09-12 | 2017-12-11
6 | 6.1 | Assembly | CB1 | Milestone | Cold Box assembly complete | Cold Box assembly complete | 9 | 1 | 2017-09-12 | 2017-12-11
4 | 4.1 | Manufacturing | CB1 | Witness Point | WP1 HX-3 Leak Check | HX-3 Leak Check | 1 | 1 | 2017-11-11 | 2017-01-30 |  | Complete | 100%
4 | 4.6 | Manufacturing | CB2 | Milestone | Cold Box 2 Manufacturing Complete | Manufacturing | 10 | 1 | 2017-12-12 | 2018-02-12
5 | 5.2 | Shipment | CB2 | Milestone | Cold Box 2 Received at SLAC | Received at SLAC | 11 | 1 | 2018-02-13 | 2018-03-12
6 | 6.2 | Assembly | CB2 | Milestone | Cold Box 2 Assembled at SLAC | Assembled at SLAC | 12 | 1 | 2018-03-13 | 2018-06-11
7 | 7 | Commissioning | CB1 | Milestone | Commissioning, Train, & Accept (CB1) | Comm, Train, & Accept Test | 13 | 1 | 2018-06-12 | 2018-10-11
7 | 7.1 | Commissioning | CB2 | Milestone | Deliver Ops & Main Manuals | Deliver Ops & Maint Manuals | 14 | 1 | 2018-10-12 | 2019-01-11
7 | 7.2 | Commissioning | CB2 | Milestone | Commissioning, Train, & Accept (CB2) | Comm, Train, & Accept Test | 15 | 1 | 2019-01-14 | 2019-02-11
Formulas:
Duration = NETWORKDAYS([Start],[Complete (Subcontract Required)])