## Form
JSA / Jefferson Lab - DOE
PO Percent Complete Form
Appendix A
Vendor Name | PHPKTE Kendall Holdings Ltd | [5 empty] | PO with Peg Points? (Yes or No) | NO
PO Number | JSA-15-C1402 |  |  | Buyer | Ted Peshehonoff | Complete through | 2017-04-30
(Date)
PO Line # | Percent Complete | Completed Peg Point (X) |  | Summary of Work (only if less than 100%)
1 | 100% |  |  | Complete Kick-Off Meeting (Completed)
2 | 100% |  |  | Complete Preliminary Design Review (PDR)
3 | 100% |  |  | Order Frames (First Set) *
4 | 100% |  |  | Order Heat Exchangers (Coolers) (First Set) *
5 | 100% |  |  | Order Compressors (First Set) *
6 | 100% |  |  | Order Motors (First Set) *
7 | 100% |  |  | Order Frames (Second Set) *
8 | 100% |  |  | Order Compressors (Second Set) *
9 | 100% |  |  | Order Heat Exchangers (Coolers) (Second Set) *
10 | 100% |  |  | Order Motors (Second Set) *
11 | 100% |  |  | Complete CDR (Both Sets) *
12 | 100% |  |  | Receive Compressors (First Set)
13 | 100% |  |  | Receive Motors (First Set)
14 | 100% |  |  | Receive Heat Exchangers (Coolers) (First Set)
15 | 100% |  |  | Receive Compressors (Second Set)
16 | 100% |  |  | Receive Heat Exchangers (Coolers) (Second Set)
17 | 100% |  |  | Receive Motors (Second Set)
18 | 90% |  |  | Complete Installation of Compressors, Motors, Coolers, & Bulk Oil Separators (First Set)
19 | 50% |  |  | Complete Installation of Compressors, Motors, Coolers, & Bulk Oil Separators (Second Set)
20 | 90% |  |  | Complete Installation of Electrical Panels, Instruments, & Devices (First Set)
21 | 40% |  |  | Complete Installation of Electrical Panels, Instruments, & Devices (Second Set)
22 | 85% |  |  | Complete skid system pressure, leak test, and instrumentation and controls check at PHPK (First Set) *
23 | 0% |  |  | Complete skid system pressure, leak test, and instrumentation and controls check at PHPK (Second Set) *
24 | 90% |  |  | Mod 004: Reference Line 20 - Additional Funding for Line 20
25 | 0% |  |  | Mod 005: Delivery of Spares Parts
26 | 0% |  |  | Mod 005: User Readiness Review
27 | 0% |  |  | Mod 005: CP1 Compressor Set Commissioning
28 | 0% |  |  | Mod 005: CP1 Set System Acceptance
29 | 0% |  |  | Mod 005: CP2 Compressor Set Commissioning
30 | 0% |  |  | Mod 005: CP2 Set System Acceptance
31 | 100% |  |  | Mod 005: Expansion Joints as per ARA 15-5071-004
32 | 100% |  |  | Mod 005: UL Certification Assessment
33 | 100% |  |  | Mod 006: Contract Scope Increase - Changes due to UL and siesmic analysis
34 | 100% |  |  | Mod 007: Initial Anchor Hole Survey
35 | 100% |  |  | Mod 008: Lifting Fixture Purchase and Shipment
36 | 0% |  |  | Mod 009: Seismic Braces as per ARA-012
37 | 100% |  |  | Mod 009: Provide additional truck for Delivery #1
38 | 0% |  |  | Mod 009: Complete Anchor Hole Surveys
Vendor Technical Representative Contacted: |  |  |  |  | Mike Agosta |  |  | 2017-04-20
|  |  | Name |  |  |  |  | Date
Jlab Control Account Manager (CAM): |  |  |  |  | Dana Arenius |  |  | 2017-05-01
[6 empty] | Name |  | Date
Below for use by Accounting/Shipping & Receiving Only
Accounting or Shipping & Receiving Entered By:
Date
Data Entry Verified By:
Date
Enter Data

## Process
JSA / Jefferson Lab - DOE
PO Percent Complete Form
Procedure
A Subcontract Purchase Order (PO) is a service type PO with loosely defined scheduled deliverables and variable amounts. A Peg Point PO has specified scheduled deliverable dates for a specified amount.
This form is to be used if NO invoice has been approved by the SOTR or CAM for work completed.
SOTR or CAM contacts a vendor technical representative for an evaluation of the percent of work completed. This can be done either verbally or via email.
Required information - Vendor Name, indicate if PO is a Peg Point type PO or not, PO #, Buyer, Complete through date (usually the end of the month), PO Line #, Percent complete, a short Summary of Work performed provided by the Vendor Technical Representative that supports the percent complete if less than 100%, the name of the Vendor Technical Representative contacted, and the CAM name.
The SOTR or CAM will submit a PO Percent Complete form by the 2nd working day following the end of the month affected for work that has been completed. This allows time for Accounting to process an accrual for the month end closing. Reminder if PO is for Peg Points, the peg point must be fully complete before claiming it.
Submit the completed form with all the information via email to evpo@jlab.org. The file name of the spreadsheet attached to the email should always include the PO# and the letters 'S&R' if it is a Peg Point type PO. File name examples: Peg Point Type PO 08-C5413 S&R, Subcontract Type PO 08-A2659. This email will forward the form automatically to personnel in Procurement, Shipping & Receiving, CFO, and PMI.
If the PO is a Subcontract type PO, the SOTR or CAM will still be required to sign all invoices received at JLab from the vendor up since this was an estimate. An approved invoice by the SOTR or CAM can also be used as basis for the percent of work complete.
If the PO is a Peg Point type PO, Shipping & Receiving will use this form to enter that Peg Point into the Costpoint Financial System. No additional invoice approvals will be required since the SOTR or CAM already indicated the work was complete. An approved invoice by the SOTR or CAM can also be used as basis for the percent of work complete without having to complete this form.
If a previous percent complete was submitted and subsequently determined to be in error, adjust the percent complete to correct the error. Add an explanatory note to support the adjustment.

## Accting USE Data Entry Form
JSA / Jefferson Lab - DOE
Data Entry Update Subcontract PO Percent Complete
Appendix B
Vendor Name |  |  | PHPKTE Kendall Holdings Ltd | [5 empty] | Percent complete thru |  |  | 2017-04-30
(Date)
PO Number |  |  | JSA-15-C1402 | [6 empty] | OR
Buyer |  |  | Ted Peshehonoff | [5 empty] | Invoice Number
PO Line # | Description | Est Date | Percent Complete |  | PO Line Total | = | Completed Work Amt | Completed Work Amt | - | Eligible for Voucher Amt | - | Prev Vouchered Amount | = | Completed Work Retention Amt
1 | Complete Kick-Off Meeting (Completed) | 2015-10-15 | 100% | X | 140157 | = | 140157 | 140157 | - | 140157 | - | 0 | = | 0
2 | Complete Preliminary Design Review (PDR) | 2015-11-10 | 100% | X | 611537.5 | = | 611537.5 | 611537.5 | - | 611537.5 | - | 0 | = | 0
3 | Order Frames (First Set) * | 2015-12-15 | 100% | X | 318496.13 | = | 318496.13 | 318496.13 | - | 318496.13 | - | 0 | = | 0
4 | Order Heat Exchangers (Coolers) (First Set) * | 2016-01-25 | 100% | X | 642114.37 | = | 642114.37 | 642114.37 | - | 642114.37 | - | 0 | = | 0
5 | Order Compressors (First Set) * | 2015-12-28 | 100% | X | 550383.75 | = | 550383.75 | 550383.75 | - | 550383.75 | - | 0 | = | 0
6 | Order Motors (First Set) * | 2015-12-28 | 100% | X | 489230 | = | 489230 | 489230 | - | 489230 | - | 0 | = | 0
7 | Order Frames (Second Set) * | 2015-12-07 | 100% | X | 622064 | = | 622064 | 622064 | - | 622064 | - | 0 | = | 0
8 | Order Compressors (Second Set) * | 2015-12-15 | 100% | X | 622064 | = | 622064 | 622064 | - | 622064 | - | 0 | = | 0
9 | Order Heat Exchangers (Coolers) (Second Set) * | 2015-12-20 | 100% | X | 622064 | = | 622064 | 622064 |  | 622064 |  | 0 | = | 0
10 | Order Motors (Second Set) * | 2015-12-22 | 100% | X | 622064 | = | 622064 | 622064 | - | 622064 | - | 0 | = | 0
11 | Complete CDR (Both Sets) * | 2016-04-25 | 100% | X | 1237814.5 | = | 1237814.5 | 1237814.5 | - | 1237814.5 | - | 0 | = | 0
12 | Receive Compressors (First Set) | 2016-07-27 | 100% | X | 495143 | = | 495143 | 495143 | - | 495143 | - | 0 | = | 0
13 | Receive Motors (First Set) | 2016-08-24 | 100% | X | 501392.65 | = | 501392.65 | 501392.65 | - | 501392.65 | - | 0 | = | 0
14 | Receive Heat Exchangers (Coolers) (First Set) | 2016-07-15 | 100% | X | 489230 | = | 489230 | 489230 | - | 489230 | - | 0 | = | 0
15 | Receive Compressors (Second Set) | 2016-08-26 | 100% | X | 503564.2 | = | 503564.2 | 503564.2 | - | 503564.2 | - | 0 | = | 0
16 | Receive Heat Exchangers (Coolers) (Second Set) | 2016-08-01 | 100% | X | 559857.6 | = | 559857.6 | 559857.6 | - | 559857.6 | - | 0 | = | 0
17 | Receive Motors (Second Set) | 2016-10-05 | 100% | X | 570967.6 | = | 570967.6 | 570967.6 | - | 570967.6 | - | 0 | = | 0
18 | Complete Installation of Compressors, Motors, Coolers, & Bulk Oil Separators (First Set) | 2016-11-30 | 90% | X | 366922.5 | = | 330230.25 | 330230.25 | - | 330230.25 | - | 0 | = | 0 | 330230.25 | 0
19 | Complete Installation of Compressors, Motors, Coolers, & Bulk Oil Separators (Second Set) | 2017-02-13 | 50% | X | 404341.6 | = | 202170.8 | 202170.8 | - | 202170.8 | - | 0 | = | 0 | 202170.8 | 0
20 | Complete Installation of Electrical Panels, Instruments, & Devices (First Set) | 2016-12-29 | 90% | X | 305768.75 | = | 275191.875 | 275191.875 | - | 275191.875 | - | 0 | = | 0 | 229326.5625 | -45865.3125
21 | Complete Installation of Electrical Panels, Instruments, & Devices (Second Set) | 2017-03-13 | 40% | X | 372924.09 | = | 149169.636 | 149169.636 | - | 149169.636 | - | 0 | = | 0 | 0 | -149169.636
22 | Complete skid system pressure, leak test, and instrumentation and controls check at PHPK (First Set) * | 2017-01-15 | 85% | X | 397499.6 | = | 337874.66 | 337874.66 | - | 337874.66 | - | 0 | = | 0 | 198749.8 | -139124.86
23 | Complete skid system pressure, leak test, and instrumentation and controls check at PHPK (Second Set) * | 2017-04-15 | 0% | X | 397498.91 | = | 0 | 0 | - | 0 | - | 0 | = | 0 | 0 | 0
24 | Mod 004: Reference Line 20 - Additional Funding for Line 20 | 2017-11-29 | 90% | X | 12637 | = | 11373.3 | 11373.3 | - | 11373.3 | - | 0 | = | 0 | 9477.75 | -1895.55
25 | Mod 005: Delivery of Spares Parts | 2017-07-31 | 0% | X | 95270 | = | 0 | 0 | - | 0 | - | 0 | = | 0
26 | Mod 005: User Readiness Review | 2017-08-10 | 0% | X | 55268.45 | = | 0 | 0 | - | 0 | - | 0 | = | 0
27 | Mod 005: CP1 Compressor Set Commissioning | 2018-04-16 | 0% | X | 61154 | = | 0 | 0 | - | 0 | - | 0 | = | 0
28 | Mod 005: CP1 Set System Acceptance | 2018-04-24 | 0% | X | 81335.9 | = | 0 | 0 | - | 0 | - | 0 | = | 0
29 | Mod 005: CP2 Compressor Set Commissioning | 2019-05-14 | 0% | X | 61154 | = | 0 | 0 | - | 0 | - | 0 | = | 0
30 | Mod 005: CP2 Set System Acceptance | 2019-05-22 | 0% | X | 81335.9 | = | 0 | 0 | - | 0 | - | 0 | = | 0
31 | Mod 005: Expansion Joints as per ARA 15-5071-004 | 2017-08-15 | 100% | X | 19250 | = | 19250 | 19250 | - | 19250 | - | 0 | = | 0
32 | Mod 005: UL Certification Assessment | 2017-09-01 | 100% | X | 1745.24 | = | 1745.24 | 1745.24 | - | 1745.24 | - | 0 | = | 0
33 | Mod 006: Contract Scope Increase - Changes due to UL and siesmic analysis | 2017-02-28 | 100% | X | 71831.05 | = | 71831.05 | 71831.05 | - | 71831.05 | - | 0 | = | 0
34 | Mod 007: Initial Anchor Hole Survey | 2017-02-28 | 100% | X | 2500 | = | 2500 | 2500 | - | 2500 | - | 0 | = | 0
35 | Mod 008: Lifting Fixture Purchase and Shipment | 2007-01-31 | 100% | X | 4666.18 | = | 4666.18 | 4666.18 | - | 4666.18 | - | 0 | = | 0
36 | Mod 009: Seismic Braces as per ARA-012 |  | 0% | X | 16462 | = | 0 | 0 | - | 0 | - | 0 | = | 0
37 | Mod 009: Provide additional truck for Delivery #1 |  | 100% | X | 7000 | = | 7000 | 7000 | - | 7000 | - | 0 | = | 0
38 | Mod 009: Complete Anchor Hole Surveys |  | 0% | X | 17500 | = | 0 | 0 | - | 0 | - | 0 | = | 0
|  |  | 0% | X |  | = | 0 | 0 | - | 0 | - | 0 | = | 0
|  |  |  | X |  | = | 0 | 0 | - | 0 | - | 0 | = | 0
|  |  | 88.57% |  | 12432209.47 |  | 11011147.291 | 11011147.291 |  | 11011147.291 |  | 0 |  | 0
Procurement Entered By: ________________________________________________________________ |  |  |  |  | Ted Peshehonoff | [6 empty] | 2017-04-30
Date
Procurement Data Entry Verified By: _______________________________________________________
Date
Back to Summary

## Invoices
Invoice # | Invoice Date | Description | Invoice Amount

## List
% Complete | Date
100% | 2016-01-31
95% | 2016-02-29
90% | 2016-03-31
85% | 2016-04-30
80% | 2016-05-31
75% | 2016-06-30
70% | 2016-07-31
65% | 2016-08-31
60% | 2016-09-30
55% | 2016-10-31
50% | 2016-11-30
45% | 2016-12-31
40% | 2017-01-31
35% | 2017-02-28
30% | 2017-03-31
25% | 2017-04-30
20% | 2017-05-31
15% | 2017-06-30
10% | 2017-07-31
5% | 2017-08-31
-3.192e-14% | 2017-09-30
2017-10-31
2017-11-30
2017-12-31
2018-01-31
2018-02-28
2018-03-31
2018-04-30
2018-05-31
2018-06-30
2018-07-31
2018-08-31
2018-09-30
2018-10-31
2018-11-30
2018-12-31
2019-01-31
2019-02-28
2019-03-31
2019-04-30
2019-05-31
2019-06-30
2019-07-31
2019-08-31
2019-09-30
2019-10-31
2019-11-30
2019-12-31
2020-01-31
2020-02-29
2020-03-31
2020-04-30
2020-05-31
2020-06-30
2020-07-31
2020-08-31
2020-09-30
2020-10-31
2020-11-30
2020-12-31