## Form
JSA / Jefferson Lab - DOE
PO Percent Complete Form
Appendix A
Vendor Name | Etorre Zanon | [5 empty] | PO with Peg Points? (Yes or No) | NO
PO Number | 15-C0753 |  |  | Buyer | Fitzpatrick | Complete through | 2017-04-30
(Date)
PO Line # | Percent Complete | Completed Peg Point (X) |  | Summary of Work (only if less than 100%)
1 | 100% |  |  | Proof of completed furnace uprade
2 | 100% |  |  | JLab Acceptance of nitrogen doping process - Cavity 1 (of 2)
3 | 100% |  |  | JLab Acceptance of nitrogen doping process - Cavity 2 (of 2)
4 | 100% |  |  | Manufacturing Drawings released and accepted by JLab
5 | 100% |  |  | First Article Cavities Mechanical Pre-fab
6 | 100% |  |  | First Articles (1-8) Delivered and Accepted by JLab
7 | 100% |  |  | Production Cavities (9-72) Mechanical Pre-Fabrication
8 | 100% |  |  | Production Cavities (73-133) Mechanical Pre-Fabrication
9 | 100% |  |  | Delivery & Acceptance of Cavities (9-12)
10 | 100% |  |  | Delivery & Acceptance of Cavities (13-16)
11 | 100% |  |  | Delivery & Acceptance of Cavities (17-20)
12 | 100% |  |  | Delivery & Acceptance of Cavities (21-24)
13 | 100% |  |  | Delivery & Acceptance of Cavities (25-28)
14 | 100% |  |  | Delivery & Acceptance of Cavities (29-32)
15 | 0% |  |  | Delivery & Acceptance of Cavities (33-36)
16 | 0% |  |  | Delivery & Acceptance of Cavities (37-40)
17 | 0% |  |  | Delivery & Acceptance of Cavities (41-44)
18 | 0% |  |  | Delivery & Acceptance of Cavities (45-48)
19 | 0% |  |  | Delivery & Acceptance of Cavities (49-52)
20 | 0% |  |  | Delivery & Acceptance of Cavities (53-56)
21 | 0% |  |  | Delivery & Acceptance of Cavities (57-60)
22 | 0% |  |  | Delivery & Acceptance of Cavities (61-64)
23 | 44.62% |  |  | MOD 002: Support of DESY EQUIPMENT (7,621/mo)
24 | 16.67% |  |  | MOD 003: First Article Incentives
25 | 100% |  |  | MOD 004: Right Angle Valves
26 | 100% |  |  | MOD 005: CTM Spare Parts
27 | 0% |  |  | Delivery & Acceptance of Cavities (65-68)
28 | 0% |  |  | Delivery & Acceptance of Cavities (69-72)
29 | 100% |  |  | MOD 006: Recipe Modification (Cavities 9-16)
30 | 100% |  |  | MOD 007: Recipe Mod (Cavs 17-133) $3547.1/ea
31 | 0% |  |  | MOD 008: Right Angle Valves
32 | 0% |  |  | Delivery & Acceptance of Cavities (73-76)
33 | 0% |  |  | Delivery & Acceptance of Cavities (77-80)
34 | 0% |  |  | Delivery & Acceptance of Cavities (81-84)
35 | 0% |  |  | Delivery & Acceptance of Cavities (85-88)
36 | 0% |  |  | Delivery & Acceptance of Cavities (89-92)
37 | 0% |  |  | Delivery & Acceptance of Cavities (93-96)
38 | 0% |  |  | Delivery & Acceptance of Cavities (97-100)
39 | 0% |  |  | Delivery & Acceptance of Cavities (101-104)
40 | 0% |  |  | Delivery & Acceptance of Cavities (105-108)
41 | 0% |  |  | Delivery & Acceptance of Cavities (109-112)
42 | 0% |  |  | Delivery & Acceptance of Cavities (113-116)
43 | 0% |  |  | Delivery & Acceptance of Cavities (117-120)
44 | 0% |  |  | Delivery & Acceptance of Cavities (121-124)
45 | 0% |  |  | Delivery & Acceptance of Cavities (125-128)
46 | 0% |  |  | Delivery & Acceptance of Cavities (129-133)
47 | 0%
48 | 0%
49 | 0%
50 | 0%
Vendor Technical Representative Contacted:
|  |  | Name |  |  |  |  | Date
Jlab Control Account Manager (CAM):
[6 empty] | Name |  | Date
Below for use by Accounting/Shipping & Receiving Only
Accounting or Shipping & Receiving Entered By:
Date
Data Entry Verified By:
Date

## Process
JSA / Jefferson Lab - DOE
PO Percent Complete Form
Procedure
A Subcontract Purchase Order (PO) is a service type PO with loosely defined scheduled deliverables and variable amounts. A Peg Point PO has specified scheduled deliverable dates for a specified amount.
This form is to be used if NO invoice has been approved by the SOTR or CAM for work completed.
SOTR or CAM contacts a vendor technical representative for an evaluation of the percent of work completed. This can be done either verbally or via email.
Required information - Vendor Name, indicate if PO is a Peg Point type PO or not, PO #, Buyer, Complete through date (usually the end of the month), PO Line #, Percent complete, a short Summary of Work performed provided by the Vendor Technical Representative that supports the percent complete if less than 100%, the name of the Vendor Technical Representative contacted, and the CAM name.
The SOTR or CAM will submit a PO Percent Complete form by the 2nd working day following the end of the month affected for work that has been completed. This allows time for Accounting to process an accrual for the month end closing. Reminder if PO is for Peg Points, the peg point must be fully complete before claiming it.
Submit the completed form with all the information via email to evpo@jlab.org. The file name of the spreadsheet attached to the email should always include the PO# and the letters 'S&R' if it is a Peg Point type PO. File name examples: Peg Point Type PO 08-C5413 S&R, Subcontract Type PO 08-A2659. This email will forward the form automatically to personnel in Procurement, Shipping & Receiving, CFO, and PMI.
If the PO is a Subcontract type PO, the SOTR or CAM will still be required to sign all invoices received at JLab from the vendor up since this was an estimate. An approved invoice by the SOTR or CAM can also be used as basis for the percent of work complete.
If the PO is a Peg Point type PO, Shipping & Receiving will use this form to enter that Peg Point into the Costpoint Financial System. No additional invoice approvals will be required since the SOTR or CAM already indicated the work was complete. An approved invoice by the SOTR or CAM can also be used as basis for the percent of work complete without having to complete this form.
If a previous percent complete was submitted and subsequently determined to be in error, adjust the percent complete to correct the error. Add an explanatory note to support the adjustment.

## Accting USE Data Entry Form
JSA / Jefferson Lab - DOE
Data Entry Update Subcontract PO Percent Complete
Appendix B
Vendor Name | [15 empty] | Etorre Zanon | [5 empty] | Percent complete thru |  |  | 2017-04-30
(Date)
PO Number | [15 empty] | 15-C0753 | [6 empty] | OR
Buyer | [15 empty] | Fitzpatrick | [5 empty] | Invoice Number
PO Line # | Description | Est Date | Act Complete Date | Invoice Approval Date | Percent Complete |  | 2017-04-30 | 2017-04-30 | 2017-05-31 | 2017-06-30 | 2017-07-31 | 2017-08-31 | 2017-09-30 | 2017-10-31 | TOTAL | Percent Complete |  | PO Line Total | = | Completed Work Amt | Completed Work Amt | - | Eligible for Voucher Amt | - | Prev Vouchered Amount | = | Completed Work Retention Amt | NOTES
1 | Proof of completed furnace uprade | 2015-07-01 |  |  | 100% | 27286.996 | [8 empty] | 27286.996 | 100% | X | 27286.996 | = | 27286.996 | 27286.996 | - | -0.004 | - | 27287 | = | 0
2 | JLab Acceptance of nitrogen doping process - Cavity 1 (of 2) | 2015-10-25 |  |  | 100% | 54573.992 | [8 empty] | 54573.992 | 100% | X | 54573.992 | = | 54573.992 | 54573.992 | - | 0.002 | - | 54573.99 | = | 0
3 | JLab Acceptance of nitrogen doping process - Cavity 2 (of 2) | 2015-11-25 |  |  | 100% | 54573.992 | [8 empty] | 54573.992 | 100% | X | 54573.992 | = | 54573.992 | 54573.992 | - | 0.002 | - | 54573.99 | = | 0
4 | Manufacturing Drawings released and accepted by JLab | 2016-01-22 |  |  | 100% | 114938.04 | [8 empty] | 114938.04 | 100% | X | 114938.04 | = | 114938.04 | 114938.04 | - | 0 | - | 114938.04 | = | 0
5 | First Article Cavities Mechanical Pre-fab | 2016-03-04 |  |  | 100% | 229876.08 | [8 empty] | 229876.08 | 100% | X | 229876.08 | = | 229876.08 | 229876.08 | - | 0 | - | 229876.08 | = | 0
6 | First Articles (1-8) Delivered and Accepted by JLab | 2016-07-11 | 2016-10-21 | 2016-10-21 | 100% | 229876.08 | [8 empty] | 229876.08 | 100% | X | 229876.08 | = | 229876.08 | 229876.08 | - | 0 | - | 229876.08 | = | 0
7 | Production Cavities (9-72) Mechanical Pre-Fabrication | 2016-01-22 |  |  | 100% | 777203.75 | [8 empty] | 777203.75 | 100% | X | 777203.75 | = | 777203.75 | 777203.75 | - | 0 | - | 777203.75 | = | 0
8 | Production Cavities (73-133) Mechanical Pre-Fabrication | 2016-08-09 |  |  | 100% | 2176170.5 | [8 empty] | 2176170.5 | 100% | X | 2176170.5 | = | 2176170.5 | 2176170.5 | - | 0 | - | 2176170.5 | = | 0
9 | Delivery & Acceptance of Cavities (9-12) | 2016-10-25 |  |  | 100% | 233161.13 | [8 empty] | 233161.13 | 100% | X | 233161.13 | = | 233161.13 | 233161.13 |  | 0 |  | 233161.13 | = | 0
10 | Delivery & Acceptance of Cavities (13-16) | 2016-11-01 |  |  | 100% | 233161.13 | [8 empty] | 233161.13 | 100% | X | 233161.13 | = | 233161.13 | 233161.13 | - | 23316.113 | - | 209845.017 | = | 0
11 | Delivery & Acceptance of Cavities (17-20) | 2016-11-08 |  |  | 100% | 233161.13 | [8 empty] | 233161.13 | 100% | X | 233161.13 | = | 233161.13 | 233161.13 | - | 0.005 | - | 233161.125 | = | 0
12 | Delivery & Acceptance of Cavities (21-24) | 2016-11-15 |  |  | 50% | 116580.565 |  | 116581 | [6 empty] | 233161.565 | 100% | X | 233161.13 | = | 233161.565 | 233161.565 | - | 116581.0025 | - | 116580.5625 | = | 0
13 | Delivery & Acceptance of Cavities (25-28) | 2016-11-22 |  |  | 100% | 233161.13 | [8 empty] | 233161.13 | 100% | X | 233161.13 | = | 233161.13 | 233161.13 | - | 0.005 | - | 233161.125 | = | 0
14 | Delivery & Acceptance of Cavities (29-32) | 2016-11-29 |  |  | 100% | 233161.13 | [8 empty] | 233161.13 | 100% | X | 233161.13 | = | 233161.13 | 233161.13 | - | 0 | - | 233161.13 | = | 0
15 | Delivery & Acceptance of Cavities (33-36) | 2016-12-06 |  |  | 0% | 0 | [8 empty] | 0 | 0% | X | 233161.13 | = | 0 | 0 | - | 0 | - | 0 | = | 0
16 | Delivery & Acceptance of Cavities (37-40) | 2016-12-13 |  |  | 0% | 0 | [8 empty] | 0 | 0% | X | 233161.13 | = | 0 | 0 | - | 0 | - | 0 | = | 0
17 | Delivery & Acceptance of Cavities (41-44) | 2016-12-20 |  |  | 0% | 0 | [8 empty] | 0 | 0% | X | 233161.13 | = | 0 | 0 | - | 0 | - | 0 | = | 0
18 | Delivery & Acceptance of Cavities (45-48) | 2016-12-27 |  |  | 0% | 0 | [8 empty] | 0 | 0% | X | 233161.13 | = | 0 | 0 | - | 0 | - | 0 | = | 0
19 | Delivery & Acceptance of Cavities (49-52) | 2017-01-03 |  |  | 0% | 0 | [8 empty] | 0 | 0% | X | 155440.75 | = | 0 | 0 | - | 0 | - | 0 | = | 0
20 | Delivery & Acceptance of Cavities (53-56) | 2017-01-10 |  |  | 0% | 0 | [8 empty] | 0 | 0% | X | 155440.75 | = | 0 | 0 | - | 0 | - | 0 | = | 0
21 | Delivery & Acceptance of Cavities (57-60) | 2017-01-17 |  |  | 0% | 0 | [8 empty] | 0 | 0% | X | 155440.75 | = | 0 | 0 | - | 0 | - | 0 | = | 0
22 | Delivery & Acceptance of Cavities (61-64) | 2017-01-24 |  |  | 0% | 0 | [8 empty] | 0 | 0% | X | 155440.75 | = | 0 | 0 | - | 0 | - | 0 | = | 0
23 | MOD 002: Support of DESY EQUIPMENT (7,621/mo) | 2017-09-17 |  |  | 38.81% | 101816.7212 | 7621 | 7621 | [6 empty] | 117058.7212 | 44.62% | X | 262347.64 | = | 117058.7212 | 117058.7212 | - | 51471.8112 | - | 65586.91 | = | 0 | 9886 | 0.037683
24 | MOD 003: First Article Incentives | 2016-11-17 |  |  | 16.67% | 50000 | [8 empty] | 50000 | 16.67% | X | 300000 | = | 50000 | 50000 | - | 0 | - | 50000 | = | 0
25 | MOD 004: Right Angle Valves | 2017-09-17 |  | 2016-10-21 | 100% | 2545 | [8 empty] | 2545 | 100% | X | 2545 | = | 2545 | 2545 | - | 0 | - | 2545 | = | 0
26 | MOD 005: CTM Spare Parts | 2016-09-30 |  |  | 100% | 59400 | [8 empty] | 59400 | 100% | X | 59400 | = | 59400 | 59400 | - | 0 | - | 59400 | = | 0
27 | Delivery & Acceptance of Cavities (65-68) | 2017-01-31 |  |  | 0% | 0 | [8 empty] | 0 | 0% | X | 155440.75 | = | 0 | 0 | - | 0 | - | 0 | = | 0
28 | Delivery & Acceptance of Cavities (69-72) | 2017-02-07 |  |  | 0% | 0 | [8 empty] | 0 | 0% | X | 155440.75 | = | 0 | 0 | - | 0 | - | 0 | = | 0
29 | MOD 006: Recipe Modification (Cavities 9-16) | 2017-09-30 |  |  | 100% | 25000 | [8 empty] | 25000 | 100% | X | 25000 | = | 25000 | 25000 | - | 0 | - | 25000 | = | 0
30 | MOD 007: Recipe Mod (Cavs 17-133) $3547.1/ea | 2017-09-30 |  |  | 11.97% | 49658.14 |  | 7094.2 | [6 empty] | 56752.34 | 13.68% | X | 415000 | = | 56752.34 | 56752.34 | - | 7094.2 | - | 49658.14 | = | 0
31 | MOD 008: Right Angle Valves | 2017-02-21 |  |  | 0% | 0 |  | 11830 | [6 empty] | 11830 | 100% | X | 11830 | = | 11830 | 11830 | - | 11830 | - | 0 | = | 0
32 | Delivery & Acceptance of Cavities (73-76) | 2017-02-21 |  |  | 0% | 0 | [8 empty] | 0 | 0% | X | 155440.75 | = | 0 | 0 | - | 0 | - | 0 | = | 0
33 | Delivery & Acceptance of Cavities (77-80) | 2017-02-21 |  |  | 0% | 0 | [8 empty] | 0 | 0% | X | 155440.75 | = | 0 | 0 | - | 0 | - | 0 | = | 0
34 | Delivery & Acceptance of Cavities (81-84) | 2017-02-28 |  |  | 0% | 0 | [8 empty] | 0 | 0% | X | 155440.75 | = | 0 | 0 | - | 0 | - | 0 | = | 0
35 | Delivery & Acceptance of Cavities (85-88) | 2017-03-07 |  |  | 0% | 0 | [8 empty] | 0 | 0% | X | 155440.75 | = | 0 | 0 | - | 0 | - | 0 | = | 0
36 | Delivery & Acceptance of Cavities (89-92) | 2017-03-14 |  |  | 0% | 0 | [8 empty] | 0 | 0% | X | 155440.75 | = | 0 | 0 | - | 0 | - | 0 | = | 0
37 | Delivery & Acceptance of Cavities (93-96) | 2017-03-21 |  |  | 0% | 0 | [8 empty] | 0 | 0% | X | 77720.375 | = | 0 | 0 | - | 0 | - | 0 | = | 0
38 | Delivery & Acceptance of Cavities (97-100) | 2017-03-28 |  |  | 0% | 0 | [8 empty] | 0 | 0% | X | 77720.375 | = | 0 | 0 | - | 0 | - | 0 | = | 0
39 | Delivery & Acceptance of Cavities (101-104) | 2017-04-04 |  |  | 0% | 0 | [8 empty] | 0 | 0% | X | 77720.375 | = | 0 | 0 | - | 0 | - | 0 | = | 0
40 | Delivery & Acceptance of Cavities (105-108) | 2017-04-11 |  |  | 0% | 0 | [8 empty] | 0 | 0% | X | 77720.375 | = | 0 | 0 | - | 0 | - | 0 | = | 0
41 | Delivery & Acceptance of Cavities (109-112) | 2017-04-18 |  |  | 0% | 0 | [8 empty] | 0 | 0% | X | 77720.375 | = | 0 | 0 | - | 0 | - | 0 | = | 0
42 | Delivery & Acceptance of Cavities (113-116) | 2017-04-25 |  |  | 0% | 0 | [8 empty] | 0 | 0% | X | 77720.375 | = | 0 | 0 | - | 0 | - | 0 | = | 0
43 | Delivery & Acceptance of Cavities (117-120) | 2017-05-02 |  |  | 0% | 0 | [8 empty] | 0 | 0% | X | 77720.375 | = | 0 | 0 | - | 0 | - | 0 | = | 0
44 | Delivery & Acceptance of Cavities (121-124) | 2017-05-09 |  |  | 0% | 0 | [8 empty] | 0 | 0% | X | 77720.375 | = | 0 | 0 | - | 0 | - | 0 | = | 0
45 | Delivery & Acceptance of Cavities (125-128) | 2017-05-16 |  |  | 0% | 0 | [8 empty] | 0 | 0% | X | 77720.375 | = | 0 | 0 | - | 0 | - | 0 | = | 0
46 | Delivery & Acceptance of Cavities (129-133) | 2017-05-23 |  |  | 0% | 0 | [8 empty] | 0 | 0% | X | 77720.375 | = | 0 | 0 | - | 0 | - | 0 | = | 0
47 | [5 empty] | 0 | [8 empty] | 0 | 0% | X |  | = | 0 | 0 | - | 0 | - | 0 | = | 0
48 | [5 empty] | 0 | [8 empty] | 0 | 0% | X |  | = | 0 | 0 | - | 0 | - | 0 | = | 0
49 | [5 empty] | 0 | [8 empty] | 0 | 0% | X |  | = | 0 | 0 | - | 0 | - | 0 | = | 0
50 | [5 empty] | 0 | [8 empty] | 0 | 0% | X |  | = | 0 | 0 | - | 0 | - | 0 | = | 0
51 | [5 empty] | 0 | [8 empty] | 0 | 0% | X |  | = | 0 | 0 | - | 0 | - | 0 | = | 0
[16 empty] | 56.34% |  | 9559285.37 |  | 5386052.7062 | 5386052.7062 |  | 210293.1367 |  | 5175759.5695 |  | 0
Procurement Entered By: ________________________________________________________________ | [17 empty] | Jarrod Fitzpatrick | [6 empty] | 2017-04-30
Date
Procurement Data Entry Verified By: _______________________________________________________
Date
14188
21282

## PO Line
PO Line # | Description | Est Date | PO Line Total | Payments | Balance | NOTES
1 | Proof of completed furnace uprade | 2015-07-01 | 27286.996 | 27287 | -0.004
2 | JLab Acceptance of nitrogen doping process - Cavity 1 (of 2) | 2015-10-25 | 54573.992 | 54573.99 | 0.002
3 | JLab Acceptance of nitrogen doping process - Cavity 2 (of 2) | 2015-11-25 | 54573.992 | 54573.99 | 0.002
4 | Manufacturing Drawings released and accepted by JLab | 2016-01-22 | 114938.04 | 114938.04 | 0
5 | First Article Cavities Mechanical Pre-fab | 2016-03-04 | 229876.08 | 229876.08 | 0
6 | First Articles (1-8) Delivered and Accepted by JLab | 2016-07-11 | 229876.08 | 229876.08 | 0
7 | Production Cavities (9-72) Mechanical Pre-Fabrication | 2016-01-22 | 777203.75 | 777203.75 | 0
8 | Production Cavities (73-133) Mechanical Pre-Fabrication | 2016-08-09 | 2176170.5 | 2176170.5 | 0
9 | Delivery & Acceptance of Cavities (9-12) | 2016-10-25 | 233161.13 | 233161.13 | 0
10 | Delivery & Acceptance of Cavities (13-16) | 2016-11-01 | 233161.13 | 209845.017 | 23316.113
11 | Delivery & Acceptance of Cavities (17-20) | 2016-11-08 | 233161.13 | 233161.125 | 0.005
12 | Delivery & Acceptance of Cavities (21-24) | 2016-11-15 | 233161.13 | 116580.5625 | 116580.5675
13 | Delivery & Acceptance of Cavities (25-28) | 2016-11-22 | 233161.13 | 233161.125 | 0.005
14 | Delivery & Acceptance of Cavities (29-32) | 2016-11-29 | 233161.13 | 233161.13 | 0
15 | Delivery & Acceptance of Cavities (33-36) | 2016-12-06 | 233161.13 | 0 | 233161.13
16 | Delivery & Acceptance of Cavities (37-40) | 2016-12-13 | 233161.13 | 0 | 233161.13
17 | Delivery & Acceptance of Cavities (41-44) | 2016-12-20 | 233161.13 | 0 | 233161.13
18 | Delivery & Acceptance of Cavities (45-48) | 2016-12-27 | 233161.13 | 0 | 233161.13
19 | Delivery & Acceptance of Cavities (49-52) | 2017-01-03 | 155440.75 | 0 | 155440.75
20 | Delivery & Acceptance of Cavities (53-56) | 2017-01-10 | 155440.75 | 0 | 155440.75
21 | Delivery & Acceptance of Cavities (57-60) | 2017-01-17 | 155440.75 | 0 | 155440.75
22 | Delivery & Acceptance of Cavities (61-64) | 2017-01-24 | 155440.75 | 0 | 155440.75
23 | MOD 002: Support of DESY EQUIPMENT (7,621/mo) | 2017-09-17 | 262347.64 | 65586.91 | 196760.73
24 | MOD 003: First Article Incentives | 2016-11-17 | 300000 | 50000 | 250000
25 | MOD 004: Right Angle Valves | 2017-09-17 | 2545 | 2545 | 0
26 | MOD 005: CTM Spare Parts | 2016-09-30 | 59400 | 59400 | 0
27 | Delivery & Acceptance of Cavities (65-68) | 2017-01-31 | 155440.75 | 0 | 155440.75
28 | Delivery & Acceptance of Cavities (69-72) | 2017-02-07 | 155440.75 | 0 | 155440.75
29 | MOD 006: Recipe Modification (Cavities 9-16) | 2017-09-30 | 25000 | 25000 | 0
30 | MOD 007: Recipe Mod (Cavs 17-133) $3547.1/ea | 2017-09-30 | 415000 | 49658.14 | 365341.86
31 | MOD 008: Right Angle Valves | 2017-02-21 | 11830 | 0 | 11830
32 | Delivery & Acceptance of Cavities (73-76) | 2017-02-21 | 155440.75 | 0 | 155440.75
33 | Delivery & Acceptance of Cavities (77-80) | 2017-02-21 | 155440.75 | 0 | 155440.75
34 | Delivery & Acceptance of Cavities (81-84) | 2017-02-28 | 155440.75 | 0 | 155440.75
35 | Delivery & Acceptance of Cavities (85-88) | 2017-03-07 | 155440.75 | 0 | 155440.75
36 | Delivery & Acceptance of Cavities (89-92) | 2017-03-14 | 155440.75 | 0 | 155440.75
37 | Delivery & Acceptance of Cavities (93-96) | 2017-03-21 | 77720.375 | 0 | 77720.375
38 | Delivery & Acceptance of Cavities (97-100) | 2017-03-28 | 77720.375 | 0 | 77720.375
39 | Delivery & Acceptance of Cavities (101-104) | 2017-04-04 | 77720.375 | 0 | 77720.375
40 | Delivery & Acceptance of Cavities (105-108) | 2017-04-11 | 77720.375 | 0 | 77720.375
41 | Delivery & Acceptance of Cavities (109-112) | 2017-04-18 | 77720.375 | 0 | 77720.375
42 | Delivery & Acceptance of Cavities (113-116) | 2017-04-25 | 77720.375 | 0 | 77720.375
43 | Delivery & Acceptance of Cavities (117-120) | 2017-05-02 | 77720.375 | 0 | 77720.375
44 | Delivery & Acceptance of Cavities (121-124) | 2017-05-09 | 77720.375 | 0 | 77720.375
45 | Delivery & Acceptance of Cavities (125-128) | 2017-05-16 | 77720.375 | 0 | 77720.375
46 | Delivery & Acceptance of Cavities (129-133) | 2017-05-23 | 77720.375 | 0 | 77720.375
|  |  | 77720.375 | 0 | 77720.375
|  |  | 77720.375 | 0 | 77720.375
|  |  | 77720.375 | 0 | 77720.375
|  |  | 77720.375 | 0 | 77720.375
|  |  | 77720.375 | 0 | 77720.375
|  |  | 77720.375 | 0 | 77720.375

## Invoices
Invoice # | Invoice Date | Invoice Amount | Description | Amount Approved | Approval Date | Dollar Approved | Balance | PO Line # | Notes
15356 | 2015-10-05 | 27287 | Proof of completed furnace uprade | 100% | 2015-10-20 | 27287 | 0 | 1
15387 | 2015-11-12 | 54573.99 | JLab Acceptance of nitrogen doping process - Cavity 1 (of 2) | 100% | 2016-01-27 | 54573.99 | 0 | 2
15411 | 2015-02-12 | 54573.99 | JLab Acceptance of nitrogen doping process - Cavity 2 (of 2) | 100% | 2016-01-27 | 54573.99 | 0 | 3
16006 | 2016-01-26 | 114938.04 | Manufacturing Drawings released and accepted by JLab | 100% | 2016-07-20 | 114938.04 | 0 | 4
16112 | 2016-05-31 | 229876.08 | First Article Cavities Mechanical Pre-fab | 100% | 2016-06-03 | 229876.08 | 0 | 5
16153 | 2016-07-14 | 348187.28 | Production Cavities (9-72) Mechanical Pre-Fabrication | 100% | 2016-07-19 | 348187.28 | 0 | 7
16154 | 2016-07-14 | 65586.91 | MOD 002: Support of DESY EQUIPMENT (7,621/mo) | 100% | 2016-07-19 | 65586.91 | 0 | 23
16186 | 2016-09-16 | 429016.47 | Production Cavities (9-72) Mechanical Pre-Fabrication | 100% | 2016-09-17 | 429016.47 | 0 | 7
16187 | 2016-09-16 | 2176170.5 | Production Cavities (73-133) Mechanical Pre-Fabrication | 100% | 2016-09-19 | 2176170.5 | 0 | 8
16191 | 2016-09-23 | 114938.04 | First Articles (1-8) Delivered and Accepted by JLab | 100% | 2016-10-21 | 114938.04 | 0 | 6 | Cavities 200-203
16191 | 2016-09-23 | 2036 | MOD 004: Right Angle Valves | 100% | 2016-10-21 | 2036 | 0 | 25
16208 | 2016-10-12 | 114938.04 | First Articles (1-8) Delivered and Accepted by JLab | 100% | 2017-01-18 | 114938.04 | 0 | 6 | Cavities 204-207
16219 | 2016-10-25 | 509 | MOD 004: Right Angle Valves | 100% | 2016-12-13 | 509 | 0 | 25
16219 | 2016-10-26 | 12500 | MOD 006: Recipe Modification (Cavities 9-16) | 100% | 2016-12-13 | 12500 | 0 | 29
16219 | 2016-10-26 | 233161.13 | Delivery & Acceptance of Cavities (9-12) | 100% | 2017-01-18 | 233161.13 | 0 | 9
16220 | 2016-10-26 | 233161.13 | Delivery & Acceptance of Cavities (13-16) | 90% | 2017-01-18 | 209845.017 | 23316.113 | 10
16220 | 2016-10-26 | 12500 | MOD 006: Recipe Modification (Cavities 9-16) | 100% | 2016-12-19 | 12500 | 0 | 29
16287 | 2016-12-27 | 59400 | MOD 005: CTM Spare Parts | 100% | 2017-01-18 | 59400 | 0 | 26
16288 | 2016-12-27 | 50000 | MOD 003: First Article Incentives | 100% | 2017-01-18 | 50000 | 0 | 24
16251 | 2016-11-22 | 233161.125 | Delivery & Acceptance of Cavities (17-20) | 100% | 2017-01-18 | 233161.125 | 0 | 11
16251 | 2016-11-22 | 116580.5625 | Delivery & Acceptance of Cavities (21-24) | 100% | 2017-01-18 | 116580.5625 | 0 | 12
16251 | 2016-11-22 | 21282.06 | MOD 007: Recipe Mod (Cavs 17-133) $3547.1/ea | 100% | 2017-01-18 | 21282.06 | 0 | 30
16253 | 2016-11-22 | 14188.04 | MOD 007: Recipe Mod (Cavs 17-133) $3547.1/ea | 100% | 2017-01-18 | 14188.04 | 0 | 30
16253 | 2016-11-22 | 233161.125 | Delivery & Acceptance of Cavities (25-28) | 100% | 2017-01-18 | 233161.125 | 0 | 13
17007 | 2017-09-01 | 14188.04 | MOD 007: Recipe Mod (Cavs 17-133) $3547.1/ea | 100% | 2017-02-15 | 14188.04 | 0 | 30
17007 | 2017-09-01 | 233161.13 | Delivery & Acceptance of Cavities (29-32) | 100% | 2017-02-18 | 233161.13 | 0 | 14
17027 | 2017-02-08 | 1914 |  |  |  | 0 | 1914 |  | Shipping Costs

## List
% Complete | Date
100% | 2016-01-31
95% | 2016-02-29
90% | 2016-03-31
85% | 2016-04-30
80% | 2016-05-31
75% | 2016-06-30
70% | 2016-07-31
65% | 2016-08-31
60% | 2016-09-30
55% | 2016-10-31
50% | 2016-11-30
45% | 2016-12-31
40% | 2017-01-31
35% | 2017-02-28
30% | 2017-03-31
25% | 2017-04-30
20% | 2017-05-31
15% | 2017-06-30
10% | 2017-07-31
5% | 2017-08-31
-3.192e-14% | 2017-09-30
2017-10-31
2017-11-30
2017-12-31
2018-01-31
2018-02-28
2018-03-31
2018-04-30
2018-05-31
2018-06-30
2018-07-31
2018-08-31
2018-09-30
2018-10-31
2018-11-30
2018-12-31
2019-01-31
2019-02-28
2019-03-31
2019-04-30
2019-05-31
2019-06-30
2019-07-31
2019-08-31
2019-09-30
2019-10-31
2019-11-30
2019-12-31
2020-01-31
2020-02-29
2020-03-31
2020-04-30
2020-05-31
2020-06-30
2020-07-31
2020-08-31
2020-09-30
2020-10-31
2020-11-30
2020-12-31