## Form
JSA / Jefferson Lab - DOE
PO Percent Complete Form
Appendix A
Vendor Name | Etorre Zanon | [5 empty] | PO with Peg Points? (Yes or No) | NO
PO Number | 15-C0753 |  |  | Buyer | Fitzpatrick | Complete through | 2017-06-30
(Date)
PO Line # | Percent Complete | Completed Peg Point (X) |  | Summary of Work (only if less than 100%)
1 | 100% |  |  | Proof of completed furnace uprade
2 | 100% |  |  | JLab Acceptance of nitrogen doping process - Cavity 1 (of 2)
3 | 100% |  |  | JLab Acceptance of nitrogen doping process - Cavity 2 (of 2)
4 | 100% |  |  | Manufacturing Drawings released and accepted by JLab
5 | 100% |  |  | First Article Cavities Mechanical Pre-fab
6 | 100% |  |  | First Articles (1-8) Delivered and Accepted by JLab
7 | 100% |  |  | Production Cavities (9-72) Mechanical Pre-Fabrication
8 | 100% |  |  | Production Cavities (73-133) Mechanical Pre-Fabrication
9 | 100% |  |  | Delivery & Acceptance of Cavities (9-12)
10 | 100% |  |  | Delivery & Acceptance of Cavities (13-16)
11 | 100% |  |  | Delivery & Acceptance of Cavities (17-20)
12 | 100% |  |  | Delivery & Acceptance of Cavities (21-24)
13 | 100% |  |  | Delivery & Acceptance of Cavities (25-28)
14 | 100% |  |  | Delivery & Acceptance of Cavities (29-32)
15 | 100% |  |  | Delivery & Acceptance of Cavities (33-36)
16 | 100% |  |  | Delivery & Acceptance of Cavities (37-40)
17 | 0% |  |  | Delivery & Acceptance of Cavities (41-44)
18 | 0% |  |  | Delivery & Acceptance of Cavities (45-48)
19 | 0% |  |  | Delivery & Acceptance of Cavities (49-52)
20 | 0% |  |  | Delivery & Acceptance of Cavities (53-56)
21 | 0% |  |  | Delivery & Acceptance of Cavities (57-60)
22 | 0% |  |  | Delivery & Acceptance of Cavities (61-64)
23 | 50.43% |  |  | MOD 002: Support of DESY EQUIPMENT (7,621/mo)
24 | 16.67% |  |  | MOD 003: First Article Incentives
25 | 100% |  |  | MOD 004: Right Angle Valves
26 | 100% |  |  | MOD 005: CTM Spare Parts
27 | 0% |  |  | Delivery & Acceptance of Cavities (65-68)
28 | 0% |  |  | Delivery & Acceptance of Cavities (69-72)
29 | 100% |  |  | MOD 006: Recipe Modification (Cavities 9-16)
30 | 20.51% |  |  | MOD 007: Recipe Mod (Cavs 17-133) $3547.1/ea
31 | 100% |  |  | MOD 008: Right Angle Valves
32 | 0% |  |  | Delivery & Acceptance of Cavities (73-76)
33 | 0% |  |  | Delivery & Acceptance of Cavities (77-80)
34 | 0% |  |  | Delivery & Acceptance of Cavities (81-84)
35 | 0% |  |  | Delivery & Acceptance of Cavities (85-88)
36 | 0% |  |  | Delivery & Acceptance of Cavities (89-92)
37 | 0% |  |  | Delivery & Acceptance of Cavities (93-96)
38 | 0% |  |  | Delivery & Acceptance of Cavities (97-100)
39 | 0% |  |  | Delivery & Acceptance of Cavities (101-104)
40 | 0% |  |  | Delivery & Acceptance of Cavities (105-108)
41 | 0% |  |  | Delivery & Acceptance of Cavities (109-112)
42 | 0% |  |  | Delivery & Acceptance of Cavities (113-116)
43 | 0% |  |  | Delivery & Acceptance of Cavities (117-120)
44 | 0% |  |  | Delivery & Acceptance of Cavities (121-124)
45 | 0% |  |  | Delivery & Acceptance of Cavities (125-128)
46 | 0% |  |  | Delivery & Acceptance of Cavities (129-133)
47 | 0%
48 | 0%
49 | 0%
50 | 0%
Vendor Technical Representative Contacted:
|  |  | Name |  |  |  |  | Date
Jlab Control Account Manager (CAM):
[6 empty] | Name |  | Date
Below for use by Accounting/Shipping & Receiving Only
Accounting or Shipping & Receiving Entered By:
Date
Data Entry Verified By:
Date

## Process
JSA / Jefferson Lab - DOE
PO Percent Complete Form
Procedure
A Subcontract Purchase Order (PO) is a service type PO with loosely defined scheduled deliverables and variable amounts. A Peg Point PO has specified scheduled deliverable dates for a specified amount.
This form is to be used if NO invoice has been approved by the SOTR or CAM for work completed.
SOTR or CAM contacts a vendor technical representative for an evaluation of the percent of work completed. This can be done either verbally or via email.
Required information - Vendor Name, indicate if PO is a Peg Point type PO or not, PO #, Buyer, Complete through date (usually the end of the month), PO Line #, Percent complete, a short Summary of Work performed provided by the Vendor Technical Representative that supports the percent complete if less than 100%, the name of the Vendor Technical Representative contacted, and the CAM name.
The SOTR or CAM will submit a PO Percent Complete form by the 2nd working day following the end of the month affected for work that has been completed. This allows time for Accounting to process an accrual for the month end closing. Reminder if PO is for Peg Points, the peg point must be fully complete before claiming it.
Submit the completed form with all the information via email to evpo@jlab.org. The file name of the spreadsheet attached to the email should always include the PO# and the letters 'S&R' if it is a Peg Point type PO. File name examples: Peg Point Type PO 08-C5413 S&R, Subcontract Type PO 08-A2659. This email will forward the form automatically to personnel in Procurement, Shipping & Receiving, CFO, and PMI.
If the PO is a Subcontract type PO, the SOTR or CAM will still be required to sign all invoices received at JLab from the vendor up since this was an estimate. An approved invoice by the SOTR or CAM can also be used as basis for the percent of work complete.
If the PO is a Peg Point type PO, Shipping & Receiving will use this form to enter that Peg Point into the Costpoint Financial System. No additional invoice approvals will be required since the SOTR or CAM already indicated the work was complete. An approved invoice by the SOTR or CAM can also be used as basis for the percent of work complete without having to complete this form.
If a previous percent complete was submitted and subsequently determined to be in error, adjust the percent complete to correct the error. Add an explanatory note to support the adjustment.

## Accting USE Data Entry Form
JSA / Jefferson Lab - DOE
Data Entry Update Subcontract PO Percent Complete
Appendix B
Vendor Name | [15 empty] | Etorre Zanon |  |  |  |  | 4291600%
(Date)
PO Number | [15 empty] | 15-C0753 |  |  |  | OR
Buyer | [15 empty] | Fitzpatrick
PO Line # | Description | Est Date | Act Complete Date | Invoice Approval Date | Percent Complete | Column1 | May-17 | Apr-17 | May-172 | Jun-17 | Jul-17 | Aug-17 | Sep-17 | October-17 | TOTAL | Percent Complete3 | PO Line Total | Completed Work Amt | Completed Work Amt | Eligible for Voucher Amt | Prev Vouchered Amount | = | Completed Work Retention Amt | NOTES
1 | Proof of completed furnace uprade | 2015-07-01 |  |  | 100% | 27286.996 | [8 empty] | 27286.996 | 100% | 27286.996 | 27286.996 | 27286.996 | 27286.996 | 0 | = | 0
2 | JLab Acceptance of nitrogen doping process - Cavity 1 (of 2) | 2015-10-25 |  |  | 100% | 54573.992 | [8 empty] | 54573.992 | 100% | 54573.992 | 54573.992 | 54573.992 | 54573.992 | 0 | = | 0
3 | JLab Acceptance of nitrogen doping process - Cavity 2 (of 2) | 2015-11-25 |  |  | 100% | 54573.992 | [8 empty] | 54573.992 | 100% | 54573.992 | 54573.992 | 54573.992 | 54573.992 | 0 | = | 0
4 | Manufacturing Drawings released and accepted by JLab | 2016-01-22 |  |  | 100% | 114938.04 | [8 empty] | 114938.04 | 100% | 114938.04 | 114938.04 | 114938.04 | 114938.04 | 0 | = | 0
5 | First Article Cavities Mechanical Pre-fab | 2016-03-04 |  |  | 100% | 229876.08 | [8 empty] | 229876.08 | 100% | 229876.08 | 229876.08 | 229876.08 | 229876.08 | 0 | = | 0
6 | First Articles (1-8) Delivered and Accepted by JLab | 2016-07-11 | 2016-10-21 | 2016-10-21 | 100% | 229876.08 | [8 empty] | 229876.08 | 100% | 229876.08 | 229876.08 | 229876.08 | 229876.08 | 0 | = | 0
7 | Production Cavities (9-72) Mechanical Pre-Fabrication | 2016-01-22 |  |  | 100% | 777203.75 | [8 empty] | 777203.75 | 100% | 777203.75 | 777203.75 | 777203.75 | 777203.75 | 0 | = | 0
8 | Production Cavities (73-133) Mechanical Pre-Fabrication | 2016-08-09 |  |  | 100% | 2176170.5 | [8 empty] | 2176170.5 | 100% | 2176170.5 | 2176170.5 | 2176170.5 | 2176170.5 | 0 | = | 0
9 | Delivery & Acceptance of Cavities (9-12) | 2016-10-25 |  |  | 100% | 233161.13 | [8 empty] | 233161.13 | 100% | 233161.13 | 233161.13 | 233161.13 | 233161.13 | 0 | = | 0
10 | Delivery & Acceptance of Cavities (13-16) | 2016-11-01 |  |  | 100% | 233161.13 | [8 empty] | 233161.13 | 100% | 233161.13 | 233161.13 | 233161.13 | 233161.13 | 0 | = | 0
11 | Delivery & Acceptance of Cavities (17-20) | 2016-11-08 |  |  | 100% | 233161.13 | [8 empty] | 233161.13 | 100% | 233161.13 | 233161.13 | 233161.13 | 233161.13 | 0 | = | 0
12 | Delivery & Acceptance of Cavities (21-24) | 2016-11-15 |  |  | 50% | 116580.565 |  | 116581 | [6 empty] | 233161.565 | 100% | 233161.13 | 233161.565 | 233161.565 | 233161.565 | 0 | = | 0
13 | Delivery & Acceptance of Cavities (25-28) | 2016-11-22 |  |  | 100% | 233161.13 | [8 empty] | 233161.13 | 100% | 233161.13 | 233161.13 | 233161.13 | 233161.13 | 0 | = | 0
14 | Delivery & Acceptance of Cavities (29-32) | 2016-11-29 |  |  | 100% | 233161.13 | [8 empty] | 233161.13 | 100% | 233161.13 | 233161.13 | 233161.13 | 233161.13 | 0 | = | 0
15 | Delivery & Acceptance of Cavities (33-36) | 2016-12-06 |  |  | 0% | 0 |  |  | 233161.13 | [5 empty] | 233161.13 | 100% | 233161.13 | 233161.13 | 233161.13 | 233161.13 | 0 | = | 0
16 | Delivery & Acceptance of Cavities (37-40) | 2016-12-13 |  |  | 0% | 0 |  |  |  | 233161.13 |  |  |  |  | 233161.13 | 100% | 233161.13 | 233161.13 | 233161.13 | 233161.13 | 0 | = | 0
17 | Delivery & Acceptance of Cavities (41-44) | 2016-12-20 |  |  | 0% | 0 | [8 empty] | 0 | 0% | 233161.13 | 0 | 0 | 0 | 0 | = | 0
18 | Delivery & Acceptance of Cavities (45-48) | 2016-12-27 |  |  | 0% | 0 | [8 empty] | 0 | 0% | 233161.13 | 0 | 0 | 0 | 0 | = | 0
19 | Delivery & Acceptance of Cavities (49-52) | 2017-01-03 |  |  | 0% | 0 | [8 empty] | 0 | 0% | 155440.75 | 0 | 0 | 0 | 0 | = | 0
20 | Delivery & Acceptance of Cavities (53-56) | 2017-01-10 |  |  | 0% | 0 | [8 empty] | 0 | 0% | 155440.75 | 0 | 0 | 0 | 0 | = | 0
21 | Delivery & Acceptance of Cavities (57-60) | 2017-01-17 |  |  | 0% | 0 | [8 empty] | 0 | 0% | 155440.75 | 0 | 0 | 0 | 0 | = | 0
22 | Delivery & Acceptance of Cavities (61-64) | 2017-01-24 |  |  | 0% | 0 | [8 empty] | 0 | 0% | 155440.75 | 0 | 0 | 0 | 0 | = | 0
23 | MOD 002: Support of DESY EQUIPMENT (7,621/mo) | 2017-09-17 |  |  | 38.81% | 101816.7212 | 7621 | 7621 | 7621 | 7621 |  |  |  |  | 132300.7212 | 50.43% | 262347.64 | 132300.7212 | 132300.7212 | 132300.7212 | 0 | = | 0 | 9886 | 0.037683
24 | MOD 003: First Article Incentives | 2016-11-17 |  |  | 16.67% | 50000 | [8 empty] | 50000 | 16.67% | 300000 | 50000 | 50000 | 50000 | 0 | = | 0
25 | MOD 004: Right Angle Valves | 2017-09-17 |  | 2016-10-21 | 100% | 2545 | [8 empty] | 2545 | 100% | 2545 | 2545 | 2545 | 2545 | 0 | = | 0
26 | MOD 005: CTM Spare Parts | 2016-09-30 |  |  | 100% | 59400 | [8 empty] | 59400 | 100% | 59400 | 59400 | 59400 | 59400 | 0 | = | 0
27 | Delivery & Acceptance of Cavities (65-68) | 2017-01-31 |  |  | 0% | 0 | [8 empty] | 0 | 0% | 155440.75 | 0 | 0 | 0 | 0 | = | 0
28 | Delivery & Acceptance of Cavities (69-72) | 2017-02-07 |  |  | 0% | 0 | [8 empty] | 0 | 0% | 155440.75 | 0 | 0 | 0 | 0 | = | 0
29 | MOD 006: Recipe Modification (Cavities 9-16) | 2017-09-30 |  |  | 100% | 25000 | [8 empty] | 25000 | 100% | 25000 | 25000 | 25000 | 25000 | 0 | = | 0
30 | MOD 007: Recipe Mod (Cavs 17-133) $3547.1/ea | 2017-09-30 |  |  | 11.97% | 49658.14 |  | 7094.2 | 14188.4 | 14188.4 |  |  |  |  | 85129.14 | 20.51% | 415000 | 85129.14 | 85129.14 | 85129.14 | 0 | = | 0
31 | MOD 008: Right Angle Valves | 2017-02-21 |  |  | 0% | 0 |  | 11830 | [6 empty] | 11830 | 100% | 11830 | 11830 | 11830 | 11830 | 0 | = | 0
32 | Delivery & Acceptance of Cavities (73-76) | 2017-02-21 |  |  | 0% | 0 | [8 empty] | 0 | 0% | 155440.75 | 0 | 0 | 0 | 0 | = | 0
33 | Delivery & Acceptance of Cavities (77-80) | 2017-02-21 |  |  | 0% | 0 | [8 empty] | 0 | 0% | 155440.75 | 0 | 0 | 0 | 0 | = | 0
34 | Delivery & Acceptance of Cavities (81-84) | 2017-02-28 |  |  | 0% | 0 | [8 empty] | 0 | 0% | 155440.75 | 0 | 0 | 0 | 0 | = | 0
35 | Delivery & Acceptance of Cavities (85-88) | 2017-03-07 |  |  | 0% | 0 | [8 empty] | 0 | 0% | 155440.75 | 0 | 0 | 0 | 0 | = | 0
36 | Delivery & Acceptance of Cavities (89-92) | 2017-03-14 |  |  | 0% | 0 | [8 empty] | 0 | 0% | 155440.75 | 0 | 0 | 0 | 0 | = | 0
37 | Delivery & Acceptance of Cavities (93-96) | 2017-03-21 |  |  | 0% | 0 | [8 empty] | 0 | 0% | 77720.375 | 0 | 0 | 0 | 0 | = | 0
38 | Delivery & Acceptance of Cavities (97-100) | 2017-03-28 |  |  | 0% | 0 | [8 empty] | 0 | 0% | 77720.375 | 0 | 0 | 0 | 0 | = | 0
39 | Delivery & Acceptance of Cavities (101-104) | 2017-04-04 |  |  | 0% | 0 | [8 empty] | 0 | 0% | 77720.375 | 0 | 0 | 0 | 0 | = | 0
40 | Delivery & Acceptance of Cavities (105-108) | 2017-04-11 |  |  | 0% | 0 | [8 empty] | 0 | 0% | 77720.375 | 0 | 0 | 0 | 0 | = | 0
41 | Delivery & Acceptance of Cavities (109-112) | 2017-04-18 |  |  | 0% | 0 | [8 empty] | 0 | 0% | 77720.375 | 0 | 0 | 0 | 0 | = | 0
42 | Delivery & Acceptance of Cavities (113-116) | 2017-04-25 |  |  | 0% | 0 | [8 empty] | 0 | 0% | 77720.375 | 0 | 0 | 0 | 0 | = | 0
43 | Delivery & Acceptance of Cavities (117-120) | 2017-05-02 |  |  | 0% | 0 | [8 empty] | 0 | 0% | 77720.375 | 0 | 0 | 0 | 0 | = | 0
44 | Delivery & Acceptance of Cavities (121-124) | 2017-05-09 |  |  | 0% | 0 | [8 empty] | 0 | 0% | 77720.375 | 0 | 0 | 0 | 0 | = | 0
45 | Delivery & Acceptance of Cavities (125-128) | 2017-05-16 |  |  | 0% | 0 | [8 empty] | 0 | 0% | 77720.375 | 0 | 0 | 0 | 0 | = | 0
46 | Delivery & Acceptance of Cavities (129-133) | 2017-05-23 |  |  | 0% | 0 | [8 empty] | 0 | 0% | 77720.375 | 0 | 0 | 0 | 0 | = | 0
47 | [5 empty] | 0 | [8 empty] | 0 | 0% |  | 0 | 0 | 0 | 0 | = | 0
48 | [5 empty] | 0 | [8 empty] | 0 | 0% |  | 0 | 0 | 0 | 0 | = | 0
49 | [5 empty] | 0 | [8 empty] | 0 | 0% |  | 0 | 0 | 0 | 0 | = | 0
50 | [5 empty] | 0 | [8 empty] | 0 | 0% |  | 0 | 0 | 0 | 0 | = | 0
51 | [5 empty] | 0 | [8 empty] | 0 | 0% |  | 0 | 0 | 0 | 0 | = | 0
[8 empty] | 143126.2 | 254970.53 | 254970.53 | 0 | 0 | 0 |  |  |  | 9559285.37 | 5895993.7662
Procurement Entered By: ________________________________________________________________ | [16 empty] | Jarrod Fitzpatrick |  |  |  | 4291600%
Date
Procurement Data Entry Verified By: _______________________________________________________
Date
14188
21282

## PO Line
PO Line # | Description | Est Date | PO Line Total | Payments | Balance | NOTES
1 | Proof of completed furnace uprade | 2015-07-01 | 27286.996 | 0 | 27286.996
2 | JLab Acceptance of nitrogen doping process - Cavity 1 (of 2) | 2015-10-25 | 54573.992 | 0 | 54573.992
3 | JLab Acceptance of nitrogen doping process - Cavity 2 (of 2) | 2015-11-25 | 54573.992 | 0 | 54573.992
4 | Manufacturing Drawings released and accepted by JLab | 2016-01-22 | 114938.04 | 0 | 114938.04
5 | First Article Cavities Mechanical Pre-fab | 2016-03-04 | 229876.08 | 0 | 229876.08
6 | First Articles (1-8) Delivered and Accepted by JLab | 2016-07-11 | 229876.08 | 0 | 229876.08
7 | Production Cavities (9-72) Mechanical Pre-Fabrication | 2016-01-22 | 777203.75 | 0 | 777203.75
8 | Production Cavities (73-133) Mechanical Pre-Fabrication | 2016-08-09 | 2176170.5 | 0 | 2176170.5
9 | Delivery & Acceptance of Cavities (9-12) | 2016-10-25 | 233161.13 | 0 | 233161.13
10 | Delivery & Acceptance of Cavities (13-16) | 2016-11-01 | 233161.13 | 0 | 233161.13
11 | Delivery & Acceptance of Cavities (17-20) | 2016-11-08 | 233161.13 | 0 | 233161.13
12 | Delivery & Acceptance of Cavities (21-24) | 2016-11-15 | 233161.13 | 0 | 233161.13
13 | Delivery & Acceptance of Cavities (25-28) | 2016-11-22 | 233161.13 | 0 | 233161.13
14 | Delivery & Acceptance of Cavities (29-32) | 2016-11-29 | 233161.13 | 0 | 233161.13
15 | Delivery & Acceptance of Cavities (33-36) | 2016-12-06 | 233161.13 | 0 | 233161.13
16 | Delivery & Acceptance of Cavities (37-40) | 2016-12-13 | 233161.13 | 0 | 233161.13
17 | Delivery & Acceptance of Cavities (41-44) | 2016-12-20 | 233161.13 | 0 | 233161.13
18 | Delivery & Acceptance of Cavities (45-48) | 2016-12-27 | 233161.13 | 0 | 233161.13
19 | Delivery & Acceptance of Cavities (49-52) | 2017-01-03 | 155440.75 | 0 | 155440.75
20 | Delivery & Acceptance of Cavities (53-56) | 2017-01-10 | 155440.75 | 0 | 155440.75
21 | Delivery & Acceptance of Cavities (57-60) | 2017-01-17 | 155440.75 | 0 | 155440.75
22 | Delivery & Acceptance of Cavities (61-64) | 2017-01-24 | 155440.75 | 0 | 155440.75
23 | MOD 002: Support of DESY EQUIPMENT (7,621/mo) | 2017-09-17 | 262347.64 | 0 | 262347.64
24 | MOD 003: First Article Incentives | 2016-11-17 | 300000 | 0 | 300000
25 | MOD 004: Right Angle Valves | 2017-09-17 | 2545 | 0 | 2545
26 | MOD 005: CTM Spare Parts | 2016-09-30 | 59400 | 0 | 59400
27 | Delivery & Acceptance of Cavities (65-68) | 2017-01-31 | 155440.75 | 0 | 155440.75
28 | Delivery & Acceptance of Cavities (69-72) | 2017-02-07 | 155440.75 | 0 | 155440.75
29 | MOD 006: Recipe Modification (Cavities 9-16) | 2017-09-30 | 25000 | 0 | 25000
30 | MOD 007: Recipe Mod (Cavs 17-133) $3547.1/ea | 2017-09-30 | 415000 | 0 | 415000
31 | MOD 008: Right Angle Valves | 2017-02-21 | 11830 | 0 | 11830
32 | Delivery & Acceptance of Cavities (73-76) | 2017-02-21 | 155440.75 | 0 | 155440.75
33 | Delivery & Acceptance of Cavities (77-80) | 2017-02-21 | 155440.75 | 0 | 155440.75
34 | Delivery & Acceptance of Cavities (81-84) | 2017-02-28 | 155440.75 | 0 | 155440.75
35 | Delivery & Acceptance of Cavities (85-88) | 2017-03-07 | 155440.75 | 0 | 155440.75
36 | Delivery & Acceptance of Cavities (89-92) | 2017-03-14 | 155440.75 | 0 | 155440.75
37 | Delivery & Acceptance of Cavities (93-96) | 2017-03-21 | 77720.375 | 0 | 77720.375
38 | Delivery & Acceptance of Cavities (97-100) | 2017-03-28 | 77720.375 | 0 | 77720.375
39 | Delivery & Acceptance of Cavities (101-104) | 2017-04-04 | 77720.375 | 0 | 77720.375
40 | Delivery & Acceptance of Cavities (105-108) | 2017-04-11 | 77720.375 | 0 | 77720.375
41 | Delivery & Acceptance of Cavities (109-112) | 2017-04-18 | 77720.375 | 0 | 77720.375
42 | Delivery & Acceptance of Cavities (113-116) | 2017-04-25 | 77720.375 | 0 | 77720.375
43 | Delivery & Acceptance of Cavities (117-120) | 2017-05-02 | 77720.375 | 0 | 77720.375
44 | Delivery & Acceptance of Cavities (121-124) | 2017-05-09 | 77720.375 | 0 | 77720.375
45 | Delivery & Acceptance of Cavities (125-128) | 2017-05-16 | 77720.375 | 0 | 77720.375
46 | Delivery & Acceptance of Cavities (129-133) | 2017-05-23 | 77720.375 | 0 | 77720.375
|  |  | 77720.375 | 0 | 77720.375
|  |  | 77720.375 | 0 | 77720.375
|  |  | 77720.375 | 0 | 77720.375
|  |  | 77720.375 | 0 | 77720.375
|  |  | 77720.375 | 0 | 77720.375
|  |  | 77720.375 | 0 | 77720.375

## Invoice
InvoiceID | InvoiceDate | Vendor
15356 | 2015-10-05 | ZANON
15387 | 2015-11-12 | ZANON
15411 | 2015-02-12 | ZANON
16006 | 2016-01-26 | ZANON
16112 | 2016-05-31 | ZANON
16153 | 2016-07-14 | ZANON
16154 | 2016-07-14 | ZANON
16186 | 2016-09-16 | ZANON
16187 | 2016-09-16 | ZANON
16191 | 2016-09-23 | ZANON
16191 | 2016-09-23 | ZANON
16208 | 2016-10-12 | ZANON
16219 | 2016-10-25 | ZANON
16220 | 2016-10-26 | ZANON
16251 | 2016-11-22 | ZANON
16253 | 2016-11-22 | ZANON
16287 | 2016-12-27 | ZANON
16288 | 2016-12-27 | ZANON
17007 | 2017-01-09 | ZANON
17027 | 2017-02-08 | ZANON
17054 | 2017-03-03 | ZANON
17097 | 2017-04-17 | ZANON
17127 | 2017-05-12 | ZANON
17129 | 2017-05-12 | ZANON
17147 | 2017-05-28 | ZANON
17097 | 2017-02-12 | ZANON

## InvDetail
Invoice # | Cavity # | Qty | Unit Price | Description | Invoice Amount | POLineID | Approval Note | Amount Retained | Amount Approved | Approval Date | Dollar Approved | Balance | PO Line # | Notes
15356 |  |  |  | Proof of completed furnace uprade | 27287 | 15-C0753-01 |  |  | 100% | 4229700% | 27287 | 0 | 1
15387 |  |  |  | JLab Acceptance of nitrogen doping process - Cavity 1 (of 2) | 54573.99 |  |  |  | 100% | 4239600% | 54573.99 | 0 | 2
15411 |  |  |  | JLab Acceptance of nitrogen doping process - Cavity 2 (of 2) | 54573.99 |  |  |  | 100% | 4239600% | 54573.99 | 0 | 3
16006 |  |  |  | Manufacturing Drawings released and accepted by JLab | 114938.04 |  |  |  | 100% | 4257100% | 114938.04 | 0 | 4
16112 |  |  |  | First Article Cavities Mechanical Pre-fab | 229876.08 |  |  |  | 100% | 4252400% | 229876.08 | 0 | 5
16153 |  |  |  | Production Cavities (9-72) Mechanical Pre-Fabrication | 348187.28 |  |  |  | 100% | 4257000% | 348187.28 | 0 | 7
16154 |  |  |  | MOD 002: Support of DESY EQUIPMENT (7,621/mo) | 65586.91 |  |  |  | 100% | 4257000% | 65586.91 | 0 | 23
16186 |  |  |  | Production Cavities (9-72) Mechanical Pre-Fabrication | 429016.47 |  |  |  | 100% | 4263000% | 429016.47 | 0 | 7
16187 |  |  |  | Production Cavities (73-133) Mechanical Pre-Fabrication | 2176170.5 |  |  |  | 100% | 4263200% | 2176170.5 | 0 | 8
16191 |  |  |  | First Articles (1-8) Delivered and Accepted by JLab | 114938.04 |  |  |  | 100% | 4266400% | 114938.04 | 0 | 6 | Cavities 200-203
16191 |  |  |  | MOD 004: Right Angle Valves | 2036 |  |  |  | 100% | 4266400% | 2036 | 0 | 25
16208 |  |  |  | First Articles (1-8) Delivered and Accepted by JLab | 114938.04 |  |  |  | 100% | 4275300% | 114938.04 | 0 | 6 | Cavities 204-207
16219 |  |  |  | MOD 004: Right Angle Valves | 509 |  |  |  | 100% | 4271700% | 509 | 0 | 25
16219 |  |  |  | MOD 006: Recipe Modification (Cavities 9-16) | 12500 |  |  |  | 100% | 4271700% | 12500 | 0 | 29
16219 |  |  |  | Delivery & Acceptance of Cavities (9-12) | 233161.13 |  |  |  | 100% | 4275300% | 233161.13 | 0 | 9
16220 |  |  |  | Delivery & Acceptance of Cavities (13-16) | 233161.13 |  |  |  | 90% | 4275300% | 209845.017 | 23316.113 | 10
16220 |  |  |  | MOD 006: Recipe Modification (Cavities 9-16) | 12500 |  |  |  | 100% | 4272300% | 12500 | 0 | 29
16287 |  |  |  | MOD 005: CTM Spare Parts | 59400 |  |  |  | 100% | 4275300% | 59400 | 0 | 26
16288 |  |  |  | MOD 003: First Article Incentives | 50000 |  |  |  | 100% | 4275300% | 50000 | 0 | 24
16251 |  |  |  | Delivery & Acceptance of Cavities (17-20) | 233161.125 |  |  |  | 100% | 4275300% | 233161.125 | 0 | 11
16251 |  |  |  | Delivery & Acceptance of Cavities (21-24) | 116580.5625 |  |  |  | 100% | 4275300% | 116580.5625 | 0 | 12
16251 |  |  |  | MOD 007: Recipe Mod (Cavs 17-133) $3547.1/ea | 21282.06 |  |  |  | 100% | 4275300% | 21282.06 | 0 | 30
16253 |  |  |  | MOD 007: Recipe Mod (Cavs 17-133) $3547.1/ea | 14188.04 |  |  |  | 100% | 4275300% | 14188.04 | 0 | 30
16253 |  |  |  | Delivery & Acceptance of Cavities (25-28) | 233161.125 |  |  |  | 100% | 4275300% | 233161.125 | 0 | 13
17007 |  |  |  | MOD 007: Recipe Mod (Cavs 17-133) $3547.1/ea | 14188.04 |  |  |  | 100% | 4278100% | 14188.04 | 0 | 30
17007 |  |  |  | Delivery & Acceptance of Cavities (29-32) | 233161.13 |  |  |  | 100% | 4278400% | 233161.13 | 0 | 14
17027 |  |  |  |  | 1914 | [5 empty] | 0 | 1914 |  | Shipping Costs
17054 |  |  |  | MOD 008: Right Angle Valves | 11830 |  |  |  | 100% | 4287200% | 11830 | 0 | 31
17097 | [10 empty] | 0 | 0
17127 | 229 |  |  | Delivery & Acceptance | 58290.28 | [5 empty] | 0 | 58290.28
17127 | 234 |  |  | Delivery & Acceptance | 58290.28 | [5 empty] | 0 | 58290.28
17127 | 238 |  |  | Delivery & Acceptance | 58290.28 | [5 empty] | 0 | 58290.28
17127 | 244 |  |  | Delivery & Acceptance | 58290.28 | [5 empty] | 0 | 58290.28
17097 | 256 |  |  | Delivery & Acceptance | 58290.28 | [5 empty] | 0 | 58290.28
17097 | 257 |  |  | Delivery & Acceptance | 58290.28 | [5 empty] | 0 | 58290.28
17097 | 258 |  |  | Delivery & Acceptance | 58290.28 | [5 empty] | 0 | 58290.28
17097 | 259 |  |  | Delivery & Acceptance | 58290.28 | [5 empty] | 0 | 58290.28
17127 | 229 |  |  | Recipe Mod | 3547.01
17127 | 234 |  |  | Recipe Mod | 3547.01
17127 | 238 |  |  | Recipe Mod | 3547.01
17127 | 244 |  |  | Recipe Mod | 3547.01
17097 | 256 |  |  | Recipe Mod | 3547.01
17097 | 257 |  |  | Recipe Mod | 3547.01
17097 | 258 |  |  | Recipe Mod | 3547.01
17097 | 259 |  |  | Recipe Mod | 3547.01
17129 | 226 |  |  | Delivery & Acceptance | 58290.28 |  | Re-work Cavity. Do Not Approve | 58290.28 | 0
17129 | 230 |  |  | Delivery & Acceptance | 58290.28 |  | Re-work Cavity. Do Not Approve | 58290.28 | 0
17129 | 233 |  |  | Delivery & Acceptance | 58290.28 |  | Re-work Cavity. Do Not Approve | 58290.28 | 0
17129 | 235 |  |  | Delivery & Acceptance | 58290.28 |  | Re-work Cavity. Do Not Approve | 58290.28 | 0
17129 | 236 |  |  | Delivery & Acceptance | 58290.28 |  | Re-work Cavity. Do Not Approve | 58290.28 | 0
17129 | 237 |  |  | Delivery & Acceptance | 58290.28 |  | Re-work Cavity. Do Not Approve | 58290.28 | 0
17129 | 241 |  |  | Delivery & Acceptance | 58290.28 |  | Re-work Cavity. Do Not Approve | 58290.28 | 0
17129 | 242 |  |  | Delivery & Acceptance | 58290.28 |  | Re-work Cavity. Do Not Approve | 58290.28 | 0
17129 | 226 |  |  | Recipe Mod | 3547.01 |  | Re-work Cavity. Do Not Approve | 3547.01 | 0
17129 | 230 |  |  | Recipe Mod | 3547.01 |  | Re-work Cavity. Do Not Approve | 3547.01 | 0
17129 | 233 |  |  | Recipe Mod | 3547.01 |  | Re-work Cavity. Do Not Approve | 3547.01 | 0
17129 | 235 |  |  | Recipe Mod | 3547.01 |  | Re-work Cavity. Do Not Approve | 3547.01 | 0
17129 | 236 |  |  | Recipe Mod | 3547.01 |  | Re-work Cavity. Do Not Approve | 3547.01 | 0
17129 | 237 |  |  | Recipe Mod | 3547.01 |  | Re-work Cavity. Do Not Approve | 3547.01 | 0
17129 | 241 |  |  | Recipe Mod | 3547.01 |  | Re-work Cavity. Do Not Approve | 3547.01 | 0
17129 | 242 |  |  | Recipe Mod | 3547.01 |  | Re-work Cavity. Do Not Approve | 3547.01 | 0

## Cavities
CAV S/N | InvoiceDetail
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332

## List
% Complete | Date
100% | 4240000%
95% | 4242900%
90% | 4246000%
85% | 4249000%
80% | 4252100%
75% | 4255100%
70% | 4258200%
65% | 4261300%
60% | 4264300%
55% | 4267400%
50% | 4270400%
45% | 4273500%
40% | 4276600%
35% | 4279400%
30% | 4282500%
25% | 4285500%
20% | 4288600%
15% | 4291600%
10% | 4294700%
5% | 4297800%
-3.192e-14% | 4300800%
4303900%
4306900%
4310000%
4313100%
4315900%
4319000%
4322000%
4325100%
4328100%
4331200%
4334300%
4337300%
4340400%
4343400%
4346500%
4349600%
4352400%
4355500%
4358500%
4361600%
4364600%
4367700%
4370800%
4373800%
4376900%
4379900%
4383000%
4386100%
4389000%
4392100%
4395100%
4398200%
4401200%
4404300%
4407400%
4410400%
4413500%
4416500%
4419600%