## Form
JSA / Jefferson Lab - DOE
PO Percent Complete Form
Appendix A
Vendor Name | Etorre Zanon | [5 empty] | PO with Peg Points? (Yes or No) | NO
PO Number | 15-C0753 |  |  | Buyer | Laney | Complete through | 2017-12-31
(Date)
PO Line # | Percent Complete | Completed Peg Point (X) |  | Summary of Work (only if less than 100%)
1 | 100% |  |  | Proof of Complete Furnace Upgrade
2 | 100% |  |  | JLab Acceptance of nitrogen doping process - Cavity 1 (of 2)
3 | 100% |  |  | JLab Acceptance of nitrogen doping process - Cavity 2 (of 2)
4 | 100% |  |  | Manufacturing Drawings released and accepted by JLab
5 | 100% |  |  | First Article Cavities Mechanical Pre-fab
6 | 100% |  |  | First Articles (1-8) Delivered and Accepted by JLab
7 | 100% |  |  | Production Cavities (9-72) Mechanical Pre-Fabrication
8 | 100% |  |  | Production Cavities (73-133) Mechanical Pre-Fabrication
9 | 100% |  |  | Delivery & Acceptance of Cavities (9-12)
10 | 100% |  |  | Delivery & Acceptance of Cavities (13-16)
11 | 100% |  |  | Delivery & Acceptance of Cavities (17-20)
12 | 100% |  |  | Delivery & Acceptance of Cavities (21-24)
13 | 100% |  |  | Delivery & Acceptance of Cavities (25-28)
14 | 100% |  |  | Delivery & Acceptance of Cavities (29-32)
15 | 100% |  |  | Delivery & Acceptance of Cavities (33-36)
16 | 94.49% |  |  | Delivery & Acceptance of Cavities (37-40)
17 | 90% |  |  | Delivery & Acceptance of Cavities (41-44)
18 | 90% |  |  | Delivery & Acceptance of Cavities (45-48)
19 | 100% |  |  | Delivery & Acceptance of Cavities (49-52)
20 | 100% |  |  | Delivery & Acceptance of Cavities (53-56)
21 | 100% |  |  | Delivery & Acceptance of Cavities (57-60)
22 | 100% |  |  | Delivery & Acceptance of Cavities (61-64)
23 | 80.96% |  |  | MOD 002: Support of DESY EQUIPMENT (7,621/mo)
24 | 16.67% |  |  | MOD 003: First Article Incentives
25 | 100% |  |  | MOD 004: Right Angle Valves
26 | 100% |  |  | MOD 005: CTM Spare Parts
27 | 100% |  |  | Delivery & Acceptance of Cavities (65-68)
28 | 100% |  |  | Delivery & Acceptance of Cavities (69-72)
29 | 100% |  |  | MOD 006: Recipe Modification (Cavities 9-16)
30 | 81.25% |  |  | MOD 007: Recipe Mod (Cavs 17-133) $3547.1/ea
31 | 100% |  |  | MOD 008: Right Angle Valves
32 | 100% |  |  | MOD 009 Shipping and Customs
33 | 100% |  |  | MOD 009 Shipping and Customs
34 | 100% |  |  | MOD 011 BCP Rework
35 | 100% |  |  | Delivery & Acceptance of Cavities (73-76)
36 | 100% |  |  | Delivery & Acceptance of Cavities (77-80)
37 | 100% |  |  | Delivery & Acceptance of Cavities (81-84)
38 | 90% |  |  | Delivery & Acceptance of Cavities (85-88)
39 | 100% |  |  | Delivery & Acceptance of Cavities (89-92)
40 | 100% |  |  | Delivery & Acceptance of Cavities (93-96)
41 | 100% |  |  | Delivery & Acceptance of Cavities (97-100)
42 | 100% |  |  | Delivery & Acceptance of Cavities (101-104)
43 | 100% |  |  | Delivery & Acceptance of Cavities (105-108)
44 | 100% |  |  | Delivery & Acceptance of Cavities (109-112)
45 | 0% |  |  | Delivery & Acceptance of Cavities (113-116)
46 | 50% |  |  | Delivery & Acceptance of Cavities (117-120)
47 | 0% |  |  | Delivery & Acceptance of Cavities (121-124)
48 | 0% |  |  | Delivery & Acceptance of Cavities (125-128)
49 | 0% |  |  | Delivery & Acceptance of Cavities (129-133)
50 | 52.63% |  |  | Performance Incentives
Vendor Technical Representative Contacted:
|  |  | Name |  |  |  |  | Date
Jlab Control Account Manager (CAM): |  |  |  |  | Eden Evans for Ed Daly |  |  | 2017-12-31
[6 empty] | Name |  | Date
Below for use by Accounting/Shipping & Receiving Only
Accounting or Shipping & Receiving Entered By:
Date
Data Entry Verified By:
Date

## Process
JSA / Jefferson Lab - DOE
PO Percent Complete Form
Procedure
A Subcontract Purchase Order (PO) is a service type PO with loosely defined scheduled deliverables and variable amounts. A Peg Point PO has specified scheduled deliverable dates for a specified amount.
This form is to be used if NO invoice has been approved by the SOTR or CAM for work completed.
SOTR or CAM contacts a vendor technical representative for an evaluation of the percent of work completed. This can be done either verbally or via email.
Required information - Vendor Name, indicate if PO is a Peg Point type PO or not, PO #, Buyer, Complete through date (usually the end of the month), PO Line #, Percent complete, a short Summary of Work performed provided by the Vendor Technical Representative that supports the percent complete if less than 100%, the name of the Vendor Technical Representative contacted, and the CAM name.
The SOTR or CAM will submit a PO Percent Complete form by the 2nd working day following the end of the month affected for work that has been completed. This allows time for Accounting to process an accrual for the month end closing. Reminder if PO is for Peg Points, the peg point must be fully complete before claiming it.
Submit the completed form with all the information via email to evpo@jlab.org. The file name of the spreadsheet attached to the email should always include the PO# and the letters 'S&R' if it is a Peg Point type PO. File name examples: Peg Point Type PO 08-C5413 S&R, Subcontract Type PO 08-A2659. This email will forward the form automatically to personnel in Procurement, Shipping & Receiving, CFO, and PMI.
If the PO is a Subcontract type PO, the SOTR or CAM will still be required to sign all invoices received at JLab from the vendor up since this was an estimate. An approved invoice by the SOTR or CAM can also be used as basis for the percent of work complete.
If the PO is a Peg Point type PO, Shipping & Receiving will use this form to enter that Peg Point into the Costpoint Financial System. No additional invoice approvals will be required since the SOTR or CAM already indicated the work was complete. An approved invoice by the SOTR or CAM can also be used as basis for the percent of work complete without having to complete this form.
If a previous percent complete was submitted and subsequently determined to be in error, adjust the percent complete to correct the error. Add an explanatory note to support the adjustment.

## Accting USE Data Entry Form
JSA / Jefferson Lab - DOE
Data Entry Update Subcontract PO Percent Complete
Appendix B
Vendor Name | [21 empty] | Etorre Zanon |  |  |  |  | 4303900%
(Date)
PO Number | [21 empty] | 15-C0753 |  |  | OR
Buyer | [21 empty] | Fitzpatrick
Includes accrual + adjustments needed to balance with Costpoint
PO Line # | Description | Line | Est Date | Act Complete Date | Invoice Approval Date | Percent Complete | Column1 | May-17 | Apr-17 | May-172 | Jun-17 | Jul-17 | Aug-17 | Sep-17 | October-17 | November-17 | December-18 | January-18 | February-18 | March-18 | TOTAL | Percent Complete3 | PO Line Total | Completed Work Amt | Eligible for Voucher Amt | Prev Vouchered | Prev Voucher Approved | Completed Work Retention Amt | % Approved | NOTES | Column3
1 | Proof of Complete Furnace Upgrade | 1 | 2015-07-01 |  |  | 100% | 27286.996 | [13 empty] | 27286.996 | 100% | 27286.996 | 27286.996 | 27286.996 | #VALUE! | 0 | 0 | 0% |  | 0
2 | JLab Acceptance of nitrogen doping process - Cavity 1 (of 2) | 2 | 2015-10-25 |  |  | 100% | 54573.992 | [13 empty] | 54573.992 | 100% | 54573.992 | 54573.992 | 0.002 | #VALUE! | 54573.99 | 0 | 100% |  | 0
3 | JLab Acceptance of nitrogen doping process - Cavity 2 (of 2) | 3 | 2015-11-25 |  |  | 100% | 54573.992 | [13 empty] | 54573.992 | 100% | 54573.992 | 54573.992 | 0.002 | #VALUE! | 54573.99 | 0 | 100% |  | 0
4 | Manufacturing Drawings released and accepted by JLab | 4 | 2016-01-22 |  |  | 100% | 114938.04 | [13 empty] | 114938.04 | 100% | 114938.04 | 114938.04 | 0 | #VALUE! | 114938.04 | 0 | 100% |  | 0
5 | First Article Cavities Mechanical Pre-fab | 5 | 2016-03-04 |  |  | 100% | 229876.08 | [13 empty] | 229876.08 | 100% | 229876.08 | 229876.08 | 0 | #VALUE! | 229876.08 | 0 | 100% |  | 0
6 | First Articles (1-8) Delivered and Accepted by JLab | 6 | 2016-07-11 | 2016-10-21 | 2016-10-21 | 100% | 229876.08 | [13 empty] | 229876.08 | 100% | 229876.08 | 229876.08 | 0 | #VALUE! | 229876.08 | 0 | 100% |  | 0
7 | Production Cavities (9-72) Mechanical Pre-Fabrication | 7 | 2016-01-22 |  |  | 100% | 777203.75 | [13 empty] | 777203.75 | 100% | 777203.75 | 777203.75 | 0 | #VALUE! | 777203.75 | 0 | 100% |  | 0
8 | Production Cavities (73-133) Mechanical Pre-Fabrication | 8 | 2016-08-09 |  |  | 100% | 2176170.5 | [13 empty] | 2176170.5 | 100% | 2176170.5 | 2176170.5 | 0 | #VALUE! | 2176170.5 | 0 | 100% |  | 0
9 | Delivery & Acceptance of Cavities (9-12) | 9 | 2016-10-25 |  |  | 100% | 233161.13 | [13 empty] | 233161.13 | 100% | 233161.13 | 233161.13 | 0.01 | #VALUE! | 233161.12 | 0 | 100% |  | 0
10 | Delivery & Acceptance of Cavities (13-16) | 10 | 2016-11-01 |  |  | 100% | 233161.13 | [13 empty] | 233161.13 | 100% | 233161.13 | 233161.13 | 0.01 | #VALUE! | 233161.12 | 0 | 100% |  | 0
11 | Delivery & Acceptance of Cavities (17-20) | 11 | 2016-11-08 |  |  | 100% | 233161.13 | [13 empty] | 233161.13 | 100% | 233161.13 | 233161.13 | 0.01 | #VALUE! | 233161.12 | 0 | 100% |  | 0
12 | Delivery & Acceptance of Cavities (21-24) | 12 | 2016-11-15 |  |  | 50% | 116580.565 |  | 116580.565 | [11 empty] | 233161.13 | 100% | 233161.13 | 233161.13 | 0.0033333 | #VALUE! | 233161.1267 | 0 | 100% |  | 0
13 | Delivery & Acceptance of Cavities (25-28) | 13 | 2016-11-22 |  |  | 100% | 233161.13 | [13 empty] | 233161.13 | 100% | 233161.13 | 233161.13 | 0.01 | #VALUE! | 233161.12 | 0 | 100% |  | 0
14 | Delivery & Acceptance of Cavities (29-32) | 14 | 2016-11-29 |  |  | 100% | 233161.13 | [13 empty] | 233161.13 | 100% | 233161.13 | 233161.13 | 0.01 | #VALUE! | 233161.12 | 0 | 100% |  | 0
15 | Delivery & Acceptance of Cavities (33-36) | 15 | 2016-12-06 |  |  | 0% | 0 |  |  | 233161.13 | [10 empty] | 233161.13 | 100% | 233161.13 | 233161.13 | 0.01 | #VALUE! | 233161.12 | 0 | 100% |  | 0
16 | Delivery & Acceptance of Cavities (37-40) | 16 | 2016-12-13 |  |  | 0% | 0 |  |  |  | 0 |  | 58290.2833 |  | 162023.666 | [5 empty] | 220313.9493 | 94.49% | 233161.13 | 220313.9493 | 4639.91 | #VALUE! | 215674.0393 | 0 | 92.5% |  | 0
17 | Delivery & Acceptance of Cavities (41-44) | 17 | 2016-12-20 |  |  | 0% | 0 | [7 empty] | 209845.02 | [5 empty] | 209845.02 | 90% | 233161.13 | 209845.02 | 0.012 | #VALUE! | 209845.008 | 0 | 90% |  | 0
18 | Delivery & Acceptance of Cavities (45-48) | 18 | 2016-12-27 |  |  | 0% | 0 | [7 empty] | 209845.02 | [5 empty] | 209845.02 | 90% | 233161.13 | 209845.02 | 0.012 | #VALUE! | 209845.008 | 0 | 90% |  | 0
19 | Delivery & Acceptance of Cavities (49-52) | 19 | 2017-01-03 |  |  | 0% | 0 |  |  |  | 155440.75 | [9 empty] | 155440.75 | 100% | 155440.75 | 155440.75 | -0.01 | #VALUE! | 155440.76 | 0 | 100% |  | 0
20 | Delivery & Acceptance of Cavities (53-56) | 20 | 2017-01-10 |  |  | 0% | 0 |  |  |  |  | 155440.75 | [8 empty] | 155440.75 | 100% | 155440.75 | 155440.75 | 0 | #VALUE! | 155440.75 | 0 | 100% |  | 0
21 | Delivery & Acceptance of Cavities (57-60) | 21 | 2017-01-17 |  |  | 0% | 0 | [5 empty] | 155440.75 | [7 empty] | 155440.75 | 100% | 155440.75 | 155440.75 | 0 | #VALUE! | 155440.75 | 0 | 100% |  | 0
22 | Delivery & Acceptance of Cavities (61-64) | 22 | 2017-01-24 |  |  | 0% | 0 | [5 empty] | 155440.75 | [7 empty] | 155440.75 | 100% | 155440.75 | 155440.75 | 0 | #VALUE! | 155440.75 | 0 | 100% |  | 0
23 | MOD 002: Support of DESY EQUIPMENT (7,621/mo) | 23 | 2017-09-17 |  |  | 38.81% | 101816.7212 | 7621 | 7621 | 7621 | 7621 | 7621 | 7621 | 7621 | 7597.15 | 49635.78 |  |  |  |  | 212396.6512 | 80.96% | 262347.64 | 212396.6512 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0% | 9886 | 0.037683
24 | MOD 003: First Article Incentives | 24 | 2016-11-17 |  |  | 16.67% | 50000 | [7 empty] | 10 | [5 empty] | 50010 | 16.67% | 300000 | 50010 | 10 | #VALUE! | 50000 | 0 | 16.67% |  | 0
25 | MOD 004: Right Angle Valves | 25 | 2017-09-17 |  | 2016-10-21 | 100% | 2545 | [13 empty] | 2545 | 100% | 2545 | 2545 | 0 | #VALUE! | 2545 | 0 | 100% |  | 0
26 | MOD 005: CTM Spare Parts | 26 | 2016-09-30 |  |  | 100% | 59400 | [13 empty] | 59400 | 100% | 59400 | 59400 | 0 | #VALUE! | 59400 | 0 | 100% |  | 0
27 | Delivery & Acceptance of Cavities (65-68) | 27 | 2017-01-31 |  |  | 0% | 0 | [6 empty] | 155440.75 | [6 empty] | 155440.75 | 100% | 155440.75 | 155440.75 | 0 | #VALUE! | 155440.75 | 0 | 100% |  | 0
28 | Delivery & Acceptance of Cavities (69-72) | 28 | 2017-02-07 |  |  | 0% | 0 | [6 empty] | 155440.75 | [6 empty] | 155440.75 | 100% | 155440.75 | 155440.75 | 0 | #VALUE! | 155440.75 | 0 | 100% |  | 0
29 | MOD 006: Recipe Modification (Cavities 9-16) | 29 | 2017-09-30 |  |  | 100% | 25000 | [13 empty] | 25000 | 100% | 25000 | 25000 | 0 | #VALUE! | 25000 | 0 | 100% |  | 0
30 | MOD 007: Recipe Mod (Cavs 17-133) $3547.1/ea | 30 | 2017-09-30 |  |  | 11.97% | 49658.14 |  | 7094.2 | 14188.4 | 14188.4 | 14188.4 | 28376.8 | 42565.2 | 74507.46 | 92420.5 |  |  |  |  | 337187.5 | 81.25% | 415000 | 337187.5 | 92443.81 | #VALUE! | 244743.69 | 0 | 58.97% |  | 0
31 | MOD 008: Right Angle Valves | 31 | 2017-02-21 |  |  | 0% | 0 |  | 11830 | [11 empty] | 11830 | 100% | 11830 | 11830 | 0 | #VALUE! | 11830 | 0 | 100% |  | 0
32 | MOD 009 Shipping and Customs | 32 | 2017-09-09 |  |  | 0% | 0 | 2000 | [12 empty] | 2000 | 100% | 2000 | 2000 | 2000 | #VALUE! | 0 | 0 | 0% |  | 0
33 | MOD 009 Shipping and Customs | 33 | 2017-09-09 |  |  | 0% | 0 | 4132.13 | [12 empty] | 4132.13 | 100% | 4132.13 | 4132.13 | 4132.13 | #VALUE! | 0 | 0 | 0% |  | 0
34 | MOD 011 BCP Rework | 34 | 2017-12-31 |  |  | 0% | 0 | [5 empty] | 15840 | [7 empty] | 15840 | 100% | 15840 | 15840 | 15840 | #VALUE! | 0 | 0 | 0% |  | 0
35 | Delivery & Acceptance of Cavities (73-76) | 35 | 2017-02-21 |  |  | 0% | 0 | [6 empty] | 155440.75 | [6 empty] | 155440.75 | 100% | 155440.75 | 155440.75 | 0 | #VALUE! | 155440.75 | 0 | 100% |  | 0
36 | Delivery & Acceptance of Cavities (77-80) | 36 | 2017-02-21 |  |  | 0% | 0 | [7 empty] | 155440.75 | [5 empty] | 155440.75 | 100% | 155440.75 | 155440.75 | 0 | #VALUE! | 155440.75 | 0 | 100% |  | 0
37 | Delivery & Acceptance of Cavities (81-84) | 37 | 2017-03-14 |  |  | 0% | 0 | [7 empty] | 139896.68 | 15544.07 |  |  |  |  | 155440.75 | 100% | 155440.75 | 155440.75 | 0 | #VALUE! | 155440.75 | 0 | 100% |  | 0
38 | Delivery & Acceptance of Cavities (85-88) | 38 | 2017-03-21 |  |  | 0% | 0 | [7 empty] | 139896.6837 | [5 empty] | 139896.6837 | 90% | 155440.75 | 139896.6837 | 120466.59 | #VALUE! | 19430.0938 | 0 | 12.5% |  | 0
39 | Delivery & Acceptance of Cavities (89-92) | 39 | 2017-03-28 |  |  | 0% | 0 | [7 empty] | 155440.75 | [5 empty] | 155440.75 | 100% | 155440.75 | 155440.75 | 155440.75 | #VALUE! | 0 | 0 | 0% |  | 0
40 | Delivery & Acceptance of Cavities (93-96) | 40 | 2017-04-04 |  |  | 0% | 0 | [8 empty] | 77720.38 |  |  |  |  | 77720.38 | 100% | 77720.375 | 77720.38 | 77720.38 | #VALUE! | 0 | 0 | 0% |  | 0
41 | Delivery & Acceptance of Cavities (97-100) | 41 | 2017-04-11 |  |  | 0% | 0 | [8 empty] | 77720.38 |  |  |  |  | 77720.38 | 100% | 77720.375 | 77720.38 | 77720.38 | #VALUE! | 0 | 0 | 0% |  | 0
42 | Delivery & Acceptance of Cavities (101-104) | 42 | 2017-04-18 |  |  | 0% | 0 | [9 empty] | 77720.38 |  |  |  | 77720.38 | 100% | 77720.375 | 77720.38 | 77720.38 | #VALUE! | 0 | 0 | 0% |  | 0
43 | Delivery & Acceptance of Cavities (105-108) | 43 | 2017-04-25 |  |  | 0% | 0 | [9 empty] | 14387.05 |  |  |  | 14387.05 | 100% | 14387.05 | 14387.05 | 14387.05 | #VALUE! | 0 | 0 | 0% |  | 0
44 | Delivery & Acceptance of Cavities (109-112) | 44 | 2017-05-02 |  |  | 0% | 0 | [9 empty] | 14387.05 |  |  |  | 14387.05 | 100% | 14387.05 | 14387.05 | 14387.05 | #VALUE! | 0 | 0 | 0% |  | 0
45 | Delivery & Acceptance of Cavities (113-116) | 45 | 2017-05-09 |  |  | 0% | 0 | [13 empty] | 0 | 0% | 14387.05 | 0 | 0 | #VALUE! | 0 | 0 | 0% |  | 0
46 | Delivery & Acceptance of Cavities (117-120) | 46 | 2017-05-16 |  |  | 0% | 0 | [9 empty] | 38860.19 |  |  |  | 38860.19 | 50% | 77720.375 | 38860.19 | 38860.19 | #VALUE! | 0 | 0 | 0% |  | 0
47 | Delivery & Acceptance of Cavities (121-124) | 47 | 2017-05-23 |  |  | 0% | 0 | [13 empty] | 0 | 0% | 77720.375 | 0 | 0 | #VALUE! | 0 | 0 | 0% |  | 0
48 | Delivery & Acceptance of Cavities (125-128) | 48 |  |  |  | 0% | 0 | [13 empty] | 0 | 0% | 77720.375 | 0 | 0 | #VALUE! | 0 | 0 | 0% |  | 0
49 | Delivery & Acceptance of Cavities (129-133) | 49 |  |  |  | 0% | 0 | [13 empty] | 0 | 0% | 77720.375 | 0 | 0 | #VALUE! | 0 | 0 | 0% |  | 0
50 | Performance Incentives | 50 |  |  |  | 0% | 0 | [9 empty] | 100000 |  |  |  | 100000 | 52.63% | 190000 | 100000 | 100000 | #VALUE! |  |  | 0% |  | 0
[7 empty] | 5235305.5062 |  | 143125.765 | 254970.53 | 177250.15 | 177250.15 | 421009.5833 | 516508.45 | 1254503.1798 | 313041.11 | 245354.67 |  |  |  | 8752072.2243 |  | 9581257.525 | 8752072.2243 |  | #VALUE! |  |  | 0% |  | 0
8652072.22
-100000.0043
Procurement Entered By: ________________________________________________________________ | [22 empty] | Jarrod Fitzpatrick |  |  |  | 4303900%
Date
Procurement Data Entry Verified By: _______________________________________________________
Date
14188
21282
Delivery & Acceptance of Cavities (97-100)

## POLinePivot (hidden)
Row Labels | Beg Bal | Invoiced | Amount Approved | End Bal | %Complete
1
Proof of completed furnace uprade | 27287 | 27287 | 27287 | 0 | 100%
2
JLab Acceptance of nitrogen doping process - Cavity 1 (of 2) | 54573.99 | 54573.99 | 54573.99 | 0 | 100%
3
JLab Acceptance of nitrogen doping process - Cavity 2 (of 2) | 54573.99 | 54573.99 | 54573.99 | 0 | 100%
4
Manufacturing Drawings released and accepted by JLab | 114938.04 | 114938.04 | 114938.04 | 0 | 100%
5
First Article Cavities Mechanical Pre-fab | 229876.08 | 229876.08 | 229876.08 | 0 | 100%
6
First Articles (1-8) Delivered and Accepted by JLab | 229876.08 | 229876.08 | 229876.08 | -2.9104e-11 | 100%
7
Production Cavities (9-72) Mechanical Pre-Fabrication | 777203.75 | 777203.75 | 777203.75 | 0 | 100%
8
Production Cavities (73-133) Mechanical Pre-Fabrication | 2176170.5 | 2176170.5 | 2176170.5 | 0 | 100%
9
Delivery & Acceptance of Cavities (9-12) | 233161.13 | 233161.12 | 233161.12 | 0.01 | 100%
10
Delivery & Acceptance of Cavities (13-16) | 233161.13 | 233161.12 | 233161.12 | 0.01 | 100%
11
Delivery & Acceptance of Cavities (17-20) | 233161.13 | 233161.12 | 233161.12 | 0.01 | 100%
12
Delivery & Acceptance of Cavities (21-24) | 233161.13 | 116580.56 | 116580.56 | 116580.57 | 50%
13
Delivery & Acceptance of Cavities (25-28) | 233161.13 | 233161.12 | 233161.12 | 0.01 | 100%
14
Delivery & Acceptance of Cavities (29-32) | 233161.13 | 233161.12 | 233161.12 | 0.01 | 100%
15
Delivery & Acceptance of Cavities (33-36) | 233161.13 | 233161.12 | 233161.12 | 0.01 | 100%
16
Delivery & Acceptance of Cavities (37-40) | 233161.13 |  |  | 233161.13
17
Delivery & Acceptance of Cavities (41-44) | 233161.13 |  |  | 233161.13
18
Delivery & Acceptance of Cavities (45-48) | 233161.13 |  |  | 233161.13
19
Delivery & Acceptance of Cavities (49-52) | 155440.75 | 155440.76 | 155440.76 | -0.01 | 100%
20
Delivery & Acceptance of Cavities (53-56) | 155440.75 | 155440.75 | 155440.75 | 0 | 100%
21
Delivery & Acceptance of Cavities (57-60) | 155440.75 |  |  | 155440.75
22
Delivery & Acceptance of Cavities (61-64) | 155440.75 |  |  | 155440.75
23
MOD 002: Support of DESY EQUIPMENT (7,621/mo) | 262347.64 | 65586.91 | 65586.91 | 196760.73 | 25%
24
MOD 003: First Article Incentives | 300000 | 50000 | 50000 | 250000 | 16.67%
25
MOD 004: Right Angle Valves | 2545 | 2545 | 2545 | 0 | 100%
26
MOD 005: CTM Spare Parts | 59400 | 59400 | 59400 | 0 | 100%
27
Delivery & Acceptance of Cavities (65-68) | 155440.75 |  |  | 155440.75
28
Delivery & Acceptance of Cavities (69-72) | 155440.75 |  |  | 155440.75
29
MOD 006: Recipe Modification (Cavities 9-16) | 25000 | 25000 | 25000 | 0 | 100%
30
MOD 007: Recipe Mod (Cavs 17-133) $3547.1/ea | 415000 | 120598.34 | 78034.22 | 336965.78 | 18.8%
31
MOD 008: Right Angle Valves | 11830 | 11830 | 11830 | 0 | 100%
32
Delivery & Acceptance of Cavities (73-76) | 155440.75 |  |  | 155440.75
33
Delivery & Acceptance of Cavities (77-80) | 155440.75 |  |  | 155440.75
34
Delivery & Acceptance of Cavities (81-84) | 155440.75 |  |  | 155440.75
35
Delivery & Acceptance of Cavities (85-88) | 155440.75 |  |  | 155440.75
36
Delivery & Acceptance of Cavities (89-92) | 155440.75 |  |  | 155440.75
37
Delivery & Acceptance of Cavities (93-96) | 77720.38 |  |  | 77720.38
38
Delivery & Acceptance of Cavities (97-100) | 77720.38 |  |  | 77720.38
39
Delivery & Acceptance of Cavities (101-104) | 77720.38 |  |  | 77720.38
40
Delivery & Acceptance of Cavities (105-108) | 77720.38 |  |  | 77720.38
41
Delivery & Acceptance of Cavities (109-112) | 77720.38 |  |  | 77720.38
42
Delivery & Acceptance of Cavities (113-116) | 77720.38 |  |  | 77720.38
43
Delivery & Acceptance of Cavities (117-120) | 77720.38 |  |  | 77720.38
44
Delivery & Acceptance of Cavities (121-124) | 77720.38 |  |  | 77720.38
45
Delivery & Acceptance of Cavities (125-128) | 77720.38 |  |  | 77720.38
46
Delivery & Acceptance of Cavities (129-133) | 77720.38 |  |  | 77720.38
(blank)
(blank) |  | 699483.36 | 0 | 0 | #NUM!
Grand Total | 9559285.42 | 6525371.83 | 5783324.35 | 3775961.07 | 60.5%

## Power View1 (hidden)
Power View can only print one sheet at a time.
Please switch to the desired sheet and try again.

## PO Line (hidden)
PO Line # | Description | Phase | Category | Est Date | Beg Bal | Funding Action | Funding Date | NOTES
1 | Proof of completed furnace uprade | I | Qualification | 2015-07-01 | 27287
2 | JLab Acceptance of nitrogen doping process - Cavity 1 (of 2) | I | Qualification | 2015-10-25 | 54573.99
3 | JLab Acceptance of nitrogen doping process - Cavity 2 (of 2) | I | Qualification | 2015-11-25 | 54573.99
4 | Manufacturing Drawings released and accepted by JLab | I | Qualification | 2016-01-22 | 114938.04
5 | First Article Cavities Mechanical Pre-fab | II | First Articles | 2016-03-04 | 229876.08
6 | First Articles (1-8) Delivered and Accepted by JLab | II | First Articles | 2016-07-11 | 229876.08
7 | Production Cavities (9-72) Mechanical Pre-Fabrication | II | First Articles | 2016-01-22 | 777203.75
8 | Production Cavities (73-133) Mechanical Pre-Fabrication | II | First Articles | 2016-08-09 | 2176170.5
9 | Delivery & Acceptance of Cavities (9-12) | III | Production Cavities | 2016-10-25 | 233161.13
10 | Delivery & Acceptance of Cavities (13-16) | III | Production Cavities | 2016-11-01 | 233161.13
11 | Delivery & Acceptance of Cavities (17-20) | III | Production Cavities | 2016-11-08 | 233161.13
12 | Delivery & Acceptance of Cavities (21-24) | III | Production Cavities | 2016-11-15 | 233161.13
13 | Delivery & Acceptance of Cavities (25-28) | III | Production Cavities | 2016-11-22 | 233161.13
14 | Delivery & Acceptance of Cavities (29-32) | III | Production Cavities | 2016-11-29 | 233161.13
15 | Delivery & Acceptance of Cavities (33-36) | III | Production Cavities | 2016-12-06 | 233161.13
16 | Delivery & Acceptance of Cavities (37-40) | III | Production Cavities | 2016-12-13 | 233161.13
17 | Delivery & Acceptance of Cavities (41-44) | III | Production Cavities | 2016-12-20 | 233161.13
18 | Delivery & Acceptance of Cavities (45-48) | III | Production Cavities | 2016-12-27 | 233161.13
19 | Delivery & Acceptance of Cavities (49-52) | III | Production Cavities | 2017-01-03 | 155440.75
20 | Delivery & Acceptance of Cavities (53-56) | III | Production Cavities | 2017-01-10 | 155440.75
21 | Delivery & Acceptance of Cavities (57-60) | III | Production Cavities | 2017-01-17 | 155440.75
22 | Delivery & Acceptance of Cavities (61-64) | III | Production Cavities | 2017-01-24 | 155440.75
23 | MOD 002: Support of DESY EQUIPMENT (7,621/mo) | II | DESY Equip | 2017-09-17 | 262347.64
24 | MOD 003: First Article Incentives | II | First Articles | 2016-11-17 | 300000
25 | MOD 004: Right Angle Valves | Other | Mod | 2017-09-17 | 2545
26 | MOD 005: CTM Spare Parts | II | DESY Equip | 2016-09-30 | 59400
27 | Delivery & Acceptance of Cavities (65-68) | III | Production Cavities | 2017-01-31 | 155440.75
28 | Delivery & Acceptance of Cavities (69-72) | III | Production Cavities | 2017-02-07 | 155440.75
29 | MOD 006: Recipe Modification (Cavities 9-16) | III | Mod | 2017-09-30 | 25000
30 | MOD 007: Recipe Mod (Cavs 17-133) $3547.1/ea | III | Mod | 2017-09-30 | 415000
31 | MOD 008: Right Angle Valves | III | Mod | 2017-02-21 | 11830
32 | Delivery & Acceptance of Cavities (73-76) | III | Production Cavities | 2017-02-21 | 155440.75
33 | Delivery & Acceptance of Cavities (77-80) | III | Production Cavities | 2017-02-21 | 155440.75
34 | Delivery & Acceptance of Cavities (81-84) | III | Production Cavities | 2017-02-28 | 155440.75
35 | Delivery & Acceptance of Cavities (85-88) | III | Production Cavities | 2017-03-07 | 155440.75
36 | Delivery & Acceptance of Cavities (89-92) | III | Production Cavities | 2017-03-14 | 155440.75
37 | Delivery & Acceptance of Cavities (93-96) | III | Production Cavities | 2017-03-21 | 77720.38
38 | Delivery & Acceptance of Cavities (97-100) | III | Production Cavities | 2017-03-28 | 77720.38
39 | Delivery & Acceptance of Cavities (101-104) | III | Production Cavities | 2017-04-04 | 77720.38
40 | Delivery & Acceptance of Cavities (105-108) | III | Production Cavities | 2017-04-11 | 77720.38
41 | Delivery & Acceptance of Cavities (109-112) | III | Production Cavities | 2017-04-18 | 77720.38
42 | Delivery & Acceptance of Cavities (113-116) | III | Production Cavities | 2017-04-25 | 77720.38
43 | Delivery & Acceptance of Cavities (117-120) | III | Production Cavities | 2017-05-02 | 77720.38
44 | Delivery & Acceptance of Cavities (121-124) | III | Production Cavities | 2017-05-09 | 77720.38
45 | Delivery & Acceptance of Cavities (125-128) | III | Production Cavities | 2017-05-16 | 77720.38
46 | Delivery & Acceptance of Cavities (129-133) | III | Production Cavities | 2017-05-23 | 77720.38

## Invoice
InvoiceID | InvoiceDate | Vendor | Description | Tot Amount
15356 | 2015-10-05 | ZANON
15387 | 2015-11-12 | ZANON
15411 | 2015-02-12 | ZANON
16006 | 2016-01-26 | ZANON
16112 | 2016-05-31 | ZANON
16153 | 2016-07-14 | ZANON
16154 | 2016-07-14 | ZANON
16186 | 2016-09-16 | ZANON
16187 | 2016-09-16 | ZANON
16191 | 2016-09-23 | ZANON | Cavities 200,201,202,203
16208 | 2016-10-12 | ZANON | Cavities 204,205,206,207
16219 | 2016-10-25 | ZANON
16220 | 2016-10-26 | ZANON
16251 | 2016-11-22 | ZANON
16253 | 2016-11-22 | ZANON
16287 | 2016-12-27 | ZANON
16288 | 2016-12-27 | ZANON
17007 | 2017-01-09 | ZANON
17027 | 2017-02-08 | ZANON
17054 | 2017-03-03 | ZANON
17079 | 2017-03-30 | ZANON
17097 | 2017-04-17 | ZANON |  | 247349.17
17127 | 2017-05-12 | ZANON |  | 247349.17
17129 | 2017-05-12 | ZANON |  | 494698.34
17147 | 2017-05-28 | ZANON |  | 169628.79
17160 | 2017-06-12 | ZANON
17170 | 2017-06-21 | ZANON
17172 | 2017-06-21 | ZANON
17190 | 2017-06-21 | ZANON
17191 | 2017-07-04 | ZANON
17202 | 2017-07-19 | ZANON
17237 | 2017-08-04 | ZANON
17253 | 2017-09-03 | ZANON |  | 169628.79
17265 | 2017-09-18 | ZANON
17266 | 2017-09-18 | ZANON
17227 | 2017-07-31 | ZANON
17242 | 2017-08-31
17260 | 2017-09-07

## InvDetail
Invoice# | Description | Cavity | Receipt | Invoice Amount | Approved | Approval Date | Amount Approved | Retained | % Approved | Remaing | PO Line | Column3
15356 | Proof of completed furnace uprade | N/A | N/A | 27287 | Approved | 4229700% | 27287 | 0 | 100% | 0 | 0
15387 | JLab Acceptance of nitrogen doping process - Cavity 1 (of 2) | N/A | N/A | 54573.99 | Approved | 4239600% | 54573.99 | 0 | 100% | 0 | 2
15411 | JLab Acceptance of nitrogen doping process - Cavity 2 (of 2) | N/A | N/A | 54573.99 | Approved | 4239600% | 54573.99 | 0 | 100% | 0 | 3
16006 | Manufacturing Drawings released and accepted by JLab | N/A | N/A | 114938.04 | Approved | 4257100% | 114938.04 | 0 | 100% | 0 | 4
16112 | First Article Cavities Mechanical Pre-fab | N/A | N/A | 229876.08 | Approved | 4252400% | 229876.08 | 0 | 100% | 0 | 5
16153 | Production Cavities (9-72) Mechanical Pre-Fabrication | N/A | N/A | 348187.28 | Approved | 4257000% | 348187.28 | 0 | 100% | 0 | 7
16154 | MOD 002: Support of DESY EQUIPMENT (7,621/mo) | N/A | N/A | 65586.91 | Approved | 4257000% | 65586.91 | 0 | 100% | 0 | 23
16186 | Production Cavities (9-72) Mechanical Pre-Fabrication | N/A | N/A | 429016.47 | Approved | 4263000% | 429016.47 | 0 | 100% | 0 | 7
16187 | Production Cavities (73-133) Mechanical Pre-Fabrication | N/A | N/A | 2176170.5 | Approved | 4263200% | 2176170.5 | 0 | 100% | 0 | 8
16191 | First Articles (1-8) Delivered and Accepted by JLab | 200 | 4265300% | 28734.51 | Approved | 4266400% | 28734.51 | 0 | 100% | 0 | 6 | Cavities 200-203
16191 | First Articles (1-8) Delivered and Accepted by JLab | 201 | 4265300% | 28734.51 | Approved | 4266400% | 28734.51 | 0 | 100% | 0 | 6
16191 | First Articles (1-8) Delivered and Accepted by JLab | 202 | 4265300% | 28734.51 | Approved | 4266400% | 28734.51 | 0 | 100% | 0 | 6
16191 | First Articles (1-8) Delivered and Accepted by JLab | 203 | 4265300% | 28734.51 | Approved | 4266400% | 28734.51 | 0 | 100% | 0 | 6
16191 | MOD 004: Right Angle Valves | N/A | N/A | 2036 | Approved | 4266400% | 2036 | 0 | 100% | 0 | 25
16208 | First Articles (1-8) Delivered and Accepted by JLab | 204 | 4266100% | 28734.51 | Approved | 4275300% | 28734.51 | 0 | 100% | 0 | 6 | Cavities 204-207
16208 | First Articles (1-8) Delivered and Accepted by JLab | 205 | 4266100% | 28734.51 | Approved | 4266400% | 28734.51 | 0 | 100% | 0 | 6
16208 | First Articles (1-8) Delivered and Accepted by JLab | 206 | 4266100% | 28734.51 | Approved | 4266400% | 28734.51 | 0 | 100% | 0 | 6
16208 | First Articles (1-8) Delivered and Accepted by JLab | 207 | 4266100% | 28734.51 | Approved | 4266400% | 28734.51 | 0 | 100% | 0 | 6
16219 | Delivery & Acceptance of Cavities (9-12) | 208 | 4268500% | 58290.28 | Approved | 4275300% | 58290.28 | 0 | 100% | 0 | 9
16219 | Delivery & Acceptance of Cavities (9-12) | 209 | 4268500% | 58290.28 | Approved | 4275300% | 58290.28 | 0 | 100% | 0 | 9
16219 | Delivery & Acceptance of Cavities (9-12) | 210 | 4268500% | 58290.28 | Approved | 4275300% | 58290.28 | 0 | 100% | 0 | 9
16219 | Delivery & Acceptance of Cavities (9-12) | 211 | 4268500% | 58290.28 | Approved | 4275300% | 58290.28 | 0 | 100% | 0 | 9
16219 | MOD 004: Right Angle Valves | N/A | N/A | 509 | Approved | 4271700% | 509 | 0 | 100% | 0 | 25
16219 | MOD 006: Recipe Modification (Cavities 9-16) | N/A | N/A | 12500 | Approved | 4271700% | 12500 | 0 | 100% | 0 | 29
16220 | Delivery & Acceptance of Cavities (13-16) | 212 | 4271100% | 58290.28 | Approved | 4275300% | 58290.28 | 0 | 100% | 0 | 10
16220 | Delivery & Acceptance of Cavities (13-16) | 213 | 4271100% | 58290.28 | Approved | 4275300% | 58290.28 | 0 | 100% | 0 | 10
16220 | Delivery & Acceptance of Cavities (13-16) | 214 | 4271100% | 58290.28 | Approved | 4275300% | 58290.28 | 0 | 100% | 0 | 10
16220 | Delivery & Acceptance of Cavities (13-16) | 215 | 4271100% | 58290.28 | Approved | 4275300% | 58290.28 | 0 | 100% | 0 | 10
16220 | MOD 006: Recipe Modification (Cavities 9-16) | N/A | N/A | 12500 | Approved | 4272300% | 12500 | 0 | 100% | 0 | 29
16251 | Delivery & Acceptance of Cavities (17-20) | 216 | 4270600% | 58290.28 | Approved | 4275300% | 58290.28 | 0 | 100% | 0 | 11
16251 | Delivery & Acceptance of Cavities (17-20) | 217 | 4270600% | 58290.28 | Approved | 4275300% | 58290.28 | 0 | 100% | 0 | 11
16251 | Delivery & Acceptance of Cavities (17-20) | 218 | 4270600% | 58290.28 | Approved | 4275300% | 58290.28 | 0 | 100% | 0 | 11
16251 | Delivery & Acceptance of Cavities (17-20) | 219 | 4270600% | 58290.28 | Approved | 4275300% | 58290.28 | 0 | 100% | 0 | 11
16251 | Delivery & Acceptance of Cavities (21-24) | 224 | 4270600% | 58290.28 | Approved | 4275300% | 58290.28 | 0 | 100% | 0 | 12
16251 | Delivery & Acceptance of Cavities (21-24) | 225 | 4270600% | 58290.28 | Approved | 4275300% | 58290.28 | 0 | 100% | 0 | 12
16251 | MOD 007: Recipe Mod (Cavs 17-133) $3547.1/ea | N/A | N/A | 21282.06 | Approved | 4275300% | 21282.06 | 0 | 100% | 0 | 30
16253 | Delivery & Acceptance of Cavities (25-28) | 220 | 0% | 58290.28 | Approved | 4275300% | 58290.28 | 0 | 100% | 0 | 13
16253 | Delivery & Acceptance of Cavities (25-28) | 221 | 0% | 58290.28 | Approved | 4275300% | 58290.28 | 0 | 100% | 0 | 13
16253 | Delivery & Acceptance of Cavities (25-28) | 222 | 0% | 58290.28 | Approved | 4275300% | 58290.28 | 0 | 100% | 0 | 13
16253 | Delivery & Acceptance of Cavities (25-28) | 223 | 0% | 58290.28 | Approved | 4275300% | 58290.28 | 0 | 100% | 0 | 13
16253 | MOD 007: Recipe Mod (Cavs 17-133) $3547.1/ea | N/A | N/A | 14188.04 | Approved | 4275300% | 14188.04 | 0 | 100% | 0 | 30
16287 | MOD 005: CTM Spare Parts | N/A | N/A | 59400 | Approved | 4275300% | 59400 | 0 | 100% | 0 | 26
16288 | MOD 003: First Article Incentives | N/A | N/A | 50000 | Approved | 4275300% | 50000 | 0 | 100% | 0 | 24
17007 | Delivery & Acceptance of Cavities (29-32) | 240 | 0% | 58290.28 | Approved | 4278400% | 58290.28 | 0 | 100% | 0 | 14
17007 | Delivery & Acceptance of Cavities (29-32) | 243 | 0% | 58290.28 | Approved | 4278100% | 58290.28 | 0 | 100% | 0 | 14
17007 | Delivery & Acceptance of Cavities (29-32) | 248 | 0% | 58290.28 | Approved | 4278100% | 58290.28 | 0 | 100% | 0 | 14
17007 | Delivery & Acceptance of Cavities (29-32) | 249 | 0% | 58290.28 | Approved | 4278100% | 58290.28 | 0 | 100% | 0 | 14
17007 | MOD 007: Recipe Mod (Cavs 17-133) $3547.1/ea | N/A | N/A | 14188.04 | Approved | 4278100% | 14188.04 | 0 | 100% | 0 | 30
17054 | MOD 008: Right Angle Valves | N/A | N/A | 11830 | Approved | 4287200% | 11830 | 0 | 100% | 0 | 31
17079 | Delivery & Acceptance of Cavities (21-24) | 227 | 4284300% | 58290.2833 | Approved | 4297900% | 58290.2833 | 0 | 100% | 0 | 12
17079 | Delivery & Acceptance of Cavities (21-24) | 228 | 4284300% | 58290.2833 | Approved | 4297900% | 58290.2833 | 0 | 100% | 0 | 12
17079 | Delivery & Acceptance of Cavities (37-40) | 231 | 4284300% | 58290.2833 | Approved | 4297900% | 58290.2833 | 0 | 100% | 0 | 16
17079 | MOD 007: Recipe Mod (Cavs 17-133) $3547.1/ea | N/A | N/A | 10641.03 | Approved | 4297900% | 10641.03 | 0 | 100% | 0 | 30
17097 | Delivery & Acceptance of Cavities (33-36) | 256 | 4288700% | 58290.28 | Approved | 4291600% | 58290.28 | 0 | 100% | 0 | 15
17097 | Delivery & Acceptance of Cavities (33-36) | 257 | 4288700% | 58290.28 | Approved | 4291600% | 58290.28 | 0 | 100% | 0 | 15
17097 | Delivery & Acceptance of Cavities (33-36) | 258 | 4288700% | 58290.28 | Approved | 4291600% | 58290.28 | 0 | 100% | 0 | 15
17097 | Delivery & Acceptance of Cavities (33-36) | 259 | 4288700% | 58290.28 | Approved | 4291600% | 58290.28 | 0 | 100% | 0 | 15
17097 | MOD 007: Recipe Mod (Cavs 17-133) $3547.1/ea | N/A | N/A | 14188.04 | Approved | 4291600% | 14188.04 | 0 | 100% | 0 | 30
17127 | Delivery & Acceptance of Cavities (37-40) | 229 | 4289900% | 58290.28 | Partially Approved | 4301300% | 52461.252 | 5829.028 | 90% | 5829.028 | 16 | Re-work Cavity. Approve 90%
17127 | Delivery & Acceptance of Cavities (37-40) | 234 | 4289900% | 58290.28 | Partially Approved | 4301300% | 52461.252 | 5829.028 | 90% | 5829.028 | 16 | Re-work Cavity. Approve 90%
17127 | Delivery & Acceptance of Cavities (37-40) | 238 | 4289900% | 58290.28 | Partially Approved | 4301300% | 52461.252 | 5829.028 | 90% | 5829.028 | 16 | Re-work Cavity. Approve 90%
17127 | Delivery & Acceptance of Cavities (41-44) | 244 | 4289900% | 58290.28 | Partially Approved | 4301300% | 52461.252 | 5829.028 | 90% | 5829.028 | 17 | Re-work Cavity. Approve 90%
17127 | MOD 007: Recipe Mod (Cavs 17-133) $3547.1/ea | N/A | N/A | 14188.04 | Approved | 4301300% | 14188.04 | 0 | 100% | 0 | 30 | Re-work Cavity. Approve 90%
17129 | Delivery & Acceptance of Cavities (41-44) | 226 | 4289900% | 58290.28 | Partially Approved | 4301300% | 52461.252 | 5829.028 | 90% | 5829.028 | 17 | Re-work Cavity. Approve 90%
17129 | Delivery & Acceptance of Cavities (41-44) | 230 | 4289900% | 58290.28 | Partially Approved | 4301300% | 52461.252 | 5829.028 | 90% | 5829.028 | 17 | Re-work Cavity. Approve 90%
17129 | Delivery & Acceptance of Cavities (41-44) | 233 | 4289900% | 58290.28 | Partially Approved | 4301300% | 52461.252 | 5829.028 | 90% | 5829.028 | 17 | Re-work Cavity. Approve 90%
17129 | Delivery & Acceptance of Cavities (45-48) | 235 | 4289900% | 58290.28 | Partially Approved | 4301300% | 52461.252 | 5829.028 | 90% | 5829.028 | 18 | Re-work Cavity. Approve 90%
17129 | Delivery & Acceptance of Cavities (45-48) | 236 | 4289900% | 58290.28 | Partially Approved | 4301300% | 52461.252 | 5829.028 | 90% | 5829.028 | 18 | Re-work Cavity. Approve 90%
17129 | Delivery & Acceptance of Cavities (45-48) | 237 | 4289900% | 58290.28 | Partially Approved | 4301300% | 52461.252 | 5829.028 | 90% | 5829.028 | 18 | Re-work Cavity. Approve 90% | 248705.2
17129 | Delivery & Acceptance of Cavities (45-48) | 241 | 4289900% | 58290.28 | Partially Approved | 4301300% | 52461.252 | 5829.028 | 90% | 5829.028 | 18 | Re-work Cavity. Approve 90% | -93264.45
17129 | Delivery & Acceptance of Cavities (61-64) | 242 | 4289900% | 58290.28 | Partially Approved | 4301300% | 52461.252 | 5829.028 | 90% | 5829.028 | 22 | Re-work Cavity. Approve 90% | 155440.75
17129 | MOD 007: Recipe Mod (Cavs 17-133) $3547.1/ea | N/A | N/A | 28376.08 | Approved | 4301300% | 28376.08 | 0 | 100% | 0 | 30 |  | 38860.1875
17147 | Delivery & Acceptance of Cavities (49-52) | 262 | 4289300% | 38860.19 | Approved | 4291600% | 38860.19 | 0 | 100% | 0 | 19
17147 | Delivery & Acceptance of Cavities (49-52) | 263 | 4289300% | 38860.19 | Approved | 4291600% | 38860.19 | 0 | 100% | 0 | 19
17147 | Delivery & Acceptance of Cavities (49-52) | 264 | 4289300% | 38860.19 | Approved | 4291600% | 38860.19 | 0 | 100% | 0 | 19
17147 | Delivery & Acceptance of Cavities (49-52) | 265 | 4289300% | 38860.19 | Approved | 4291600% | 38860.19 | 0 | 100% | 0 | 19
17147 | MOD 007: Recipe Mod (Cavs 17-133) $3547.1/ea | N/A | N/A | 14188.04 | Approved | 4291600% | 14188.04 | 0 | 100% | 0 | 30
17160 | Delivery & Acceptance of Cavities (53-56) | 260 | 4290900% | 38860.1875 | Approved | 4297800% | 38860.1875 | 0 | 100% | 0 | 20
17160 | Delivery & Acceptance of Cavities (53-56) | 261 | 4290900% | 38860.1875 | Approved | 4297800% | 38860.1875 | 0 | 100% | 0 | 20
17160 | Delivery & Acceptance of Cavities (53-56) | 267 | 4290900% | 38860.1875 | Approved | 4297800% | 38860.1875 | 0 | 100% | 0 | 20
17160 | Delivery & Acceptance of Cavities (53-56) | 269 | 4290900% | 38860.1875 | Approved | 4297800% | 38860.1875 | 0 | 100% | 0 | 20
17160 | MOD 007: Recipe Mod (Cavs 17-133) $3547.1/ea | N/A | N/A | 14188.04 | Approved | 4297800% | 14188.04 | 0 | 100% | 0 | 30
17170 | Delivery & Acceptance of Cavities (57-60) | 268 | 4292100% | 38860.1875 | Approved | 4297800% | 38860.1875 | 0 | 100% | 0 | 21
17170 | Delivery & Acceptance of Cavities (57-60) | 271 | 4292100% | 38860.1875 | Approved | 4297800% | 38860.1875 | 0 | 100% | 0 | 21
17170 | Delivery & Acceptance of Cavities (57-60) | 272 | 4292100% | 38860.1875 | Approved | 4297800% | 38860.1875 | 0 | 100% | 0 | 21
17170 | Delivery & Acceptance of Cavities (57-60) | 273 | 4292100% | 38860.1875 | Approved | 4297800% | 38860.1875 | 0 | 100% | 0 | 21
17170 | MOD 007: Recipe Mod (Cavs 17-133) $3547.1/ea | N/A | N/A | 14188.04 | Approved | 4297800% | 14188.04 | 0 | 100% | 0 | 30
17172 | MOD 002: Support of DESY EQUIPMENT (7,621/mo) | N/A | N/A | 196760.73 |  |  |  | 196760.73 | 0% | 196760.73 | 23 | Need Actual cost receipts
17191 | Delivery & Acceptance of Cavities (65-68) | 266 | 4293000% | 38860.1875 | Approved | 4300700% | 38860.1875 | 0 | 100% | 0 | 27
17191 | Delivery & Acceptance of Cavities (65-68) | 274 | 4293000% | 38860.1875 | Approved | 4300700% | 38860.1875 | 0 | 100% | 0 | 27
17191 | Delivery & Acceptance of Cavities (65-68) | 275 | 4293000% | 38860.1875 | Approved | 4300700% | 38860.1875 | 0 | 100% | 0 | 27
17191 | Delivery & Acceptance of Cavities (65-68) | 277 | 4293000% | 38860.1875 | Approved | 4300700% | 38860.1875 | 0 | 100% | 0 | 27
17191 | MOD 007: Recipe Mod (Cavs 17-133) $3547.1/ea | N/A | N/A | 14188.04 | Approved | 4300700% | 14188.04 | 0 | 100% | 0 | 30
17202 | Delivery & Acceptance of Cavities (69-72) | 270 | 4294700% | 38860.1875 | Approved | 4300700% | 38860.1875 | 0 | 100% | 0 | 28
17202 | Delivery & Acceptance of Cavities (69-72) | 278 | 4294700% | 38860.1875 | Approved | 4300700% | 38860.1875 | 0 | 100% | 0 | 28
17202 | Delivery & Acceptance of Cavities (69-72) | 279 | 4294700% | 38860.1875 | Approved | 4300700% | 38860.1875 | 0 | 100% | 0 | 28
17202 | Delivery & Acceptance of Cavities (69-72) | 281 | 4294700% | 38860.1875 | Approved | 4300700% | 38860.1875 | 0 | 100% | 0 | 28
17202 | MOD 007: Recipe Mod (Cavs 17-133) $3547.1/ea | N/A | N/A | 14188.04 | Approved | 4300700% | 14188.04 | 0 | 100% | 0 | 30
17227 | Delivery & Acceptance of Cavities (81-84) | 280 | N/A | 38860.1875 | Approved | 4301400% | 38860.1875 | 0 | 100% | 0 | 37
17227 | Delivery & Acceptance of Cavities (81-84) | 282 | 4301300% | 38860.1875 | Approved | 4301400% | 38860.1875 | 0 | 100% | 0 | 37
17227 | Delivery & Acceptance of Cavities (81-84) | 283 | 4301300% | 38860.1875 | Approved | 4301400% | 38860.1875 | 0 | 100% | 0 | 37
17227 | Delivery & Acceptance of Cavities (81-84) | 287 | 4301300% | 38860.1875 | Approved | 4301400% | 38860.1875 | 0 | 100% | 0 | 37
17227 | MOD 007: Recipe Mod (Cavs 17-133) $3547.1/ea | N/A | 4301300% | 14188.04 | Approved | 4301400% | 14188.04 | 0 | 100% | 0 | 30
17237 | Delivery & Acceptance of Cavities (73-76) | 284 | 4296100% | 38860.1875 | Approved | 4300700% | 38860.1875 | 0 | 100% | 0 | 35
17237 | Delivery & Acceptance of Cavities (73-76) | 286 | 4296100% | 38860.1875 | Approved | 4300700% | 38860.1875 | 0 | 100% | 0 | 35
17237 | Delivery & Acceptance of Cavities (73-76) | 288 | 4296100% | 38860.1875 | Approved | 4300700% | 38860.1875 | 0 | 100% | 0 | 35
17237 | Delivery & Acceptance of Cavities (73-76) | 289 | 4296100% | 38860.1875 | Approved | 4300700% | 38860.1875 | 0 | 100% | 0 | 35
17237 | MOD 007: Recipe Mod (Cavs 17-133) $3547.1/ea | N/A | N/A | 14188.04 | Approved | 4300700% | 14188.04 | 0 | 100% | 0 | 30
17242 | Delivery & Acceptance of Cavities (77-80) | 290 | 4296300% | 38860.1875 | Approved | 4301300% | 38860.1875 | 0 | 100% | 0 | 36
17242 | Delivery & Acceptance of Cavities (77-80) | 294 | 4296300% | 38860.1875 | Approved | 4301300% | 38860.1875 | 0 | 100% | 0 | 36
17242 | Delivery & Acceptance of Cavities (77-80) | 291 | 4296300% | 38860.1875 | Approved | 4301300% | 38860.1875 | 0 | 100% | 0 | 36
17242 | Delivery & Acceptance of Cavities (77-80) | 296 | 4296300% | 38860.1875 | Approved | 4301300% | 38860.1875 | 0 | 100% | 0 | 36
17242 | MOD 007: Recipe Mod (Cavs 17-133) $3547.1/ea | N/A | N/A | 14188.04 | Approved | 4301300% | 14188.04 | 0 | 100% | 0 | 30
17253 | Delivery & Acceptance of Cavities (61-64) | 276 | 4299100% | 38860.1875 | Approved | 4301400% | 34326.4993 | 4533.6882 | 88.33% | 4533.6882 | 22
17253 | Delivery & Acceptance of Cavities (61-64) | 295 | 4299100% | 38860.1875 | Approved | 4301400% | 34326.4993 | 4533.6882 | 88.33% | 4533.6882 | 22
17253 | Delivery & Acceptance of Cavities (61-64) | 297 | 4299100% | 38860.1875 | Approved | 4301400% | 34326.4993 | 4533.6882 | 88.33% | 4533.6882 | 22
17253 | Delivery & Acceptance of Cavities (85-88) | 299 | 4299100% | 38860.1875 | Approved | 4301400% | 19430.0938 | 19430.0938 | 50% | 19430.0938 | 38
17253 | MOD 007: Recipe Mod (Cavs 17-133) $3547.1/ea | N/A | N/A | 14188.04 | Approved | 4301400% | 14188.04 | 0 | 100% | 0 | 30
17260 | MOD 011 BCP Rework | N/A | N/A | 15840 | Waiting for Katherine's approval |  |  | 15840 | 0% | 15840 | 34
17265 | Delivery & Acceptance of Cavities (85-88) | 292 | 4299800% | 38860.1875 |  |  |  | 38860.1875 | 0% | 38860.1875 | 38
17265 | Delivery & Acceptance of Cavities (85-88) | 301 | 4299800% | 38860.1875 |  |  |  | 38860.1875 | 0% | 38860.1875 | 38
17265 | Delivery & Acceptance of Cavities (85-88) | 302 | 4299800% | 38860.1875 |  |  |  | 38860.1875 | 0% | 38860.1875 | 38
17265 | Delivery & Acceptance of Cavities (89-92) | 303 | 4299800% | 38860.1875 |  |  |  | 38860.1875 | 0% | 38860.1875 | 39
17265 | MOD 007: Recipe Mod (Cavs 17-133) $3547.1/ea | N/A | N/A | 14188.04 |  |  |  | 14188.04 | 0% | 14188.04 | 30
Total |  |  |  | 8294702.8 |  |  | 7809493.7858 | 485209.0143 |  |  |  | 16

## Sheet1
456 | 4562 | 4563 | 4564
3 | 3 | 3 | 3
3 | 3 | 3 | 3
3 | 3 | 3 | 3
3 | 3 | 3 | 3
3 | 3 | 3 | 3
3 | 3 | 3 | 3
3 | 3 | 3 | 3
2
77720.375
19430.0938
155440.75
52461.252
|  |  |  | 102979.498 | 34326.4993

## Cavities (hidden)
CAV S/N | InvoiceDetail
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332

## List
|  |  | CAV s/n | Ship# | Receipt Date
% Complete | Date | Status | N/A | N/A
100% | 4240000% | Open | 200 | 1 | 2016-10-10
95% | 4242900% | Inprogress | 201 | 2 | 2016-10-10
90% | 4246000% | Complete | 202 | 3 | 2016-10-10
85% | 4249000% |  | 203 | 4 | 2016-10-10
80% | 4252100% |  | 204 | 5 | 2016-10-18
75% | 4255100% |  | 205 | 6 | 2016-10-18
70% | 4258200% |  | 206 | 7 | 2016-10-18
65% | 4261300% |  | 207 | 8 | 2016-10-18
60% | 4264300% |  | 208 | 9 | 2016-11-11
55% | 4267400% |  | 209 | 10 | 2016-11-11
50% | 4270400% |  | 210 | 11 | 2016-11-11
45% | 4273500% |  | 211 | 12 | 2016-11-11
40% | 4276600% |  | 212 | 13 | 2016-12-07
35% | 4279400% |  | 213 | 14 | 2016-12-07
30% | 4282500% |  | 214 | 15 | 2016-12-07
25% | 4285500% |  | 215 | 16 | 2016-12-07
20% | 4288600% |  | 216 | 17 | 2016-12-02
15% | 4291600% |  | 217 | 18 | 2016-12-02
10% | 4294700% |  | 218 | 19 | 2016-12-02
5% | 4297800% |  | 219 | 20 | 2016-12-02
-3.192e-14% | 4300800% |  | 220 | 21
| 4303900% |  | 221 | 22
| 4306900% |  | 222 | 23
| 4310000% |  | 223 | 24
| 4313100% |  | 224 | 25 | 2016-12-02
| 4315900% |  | 225 | 26 | 2016-12-02
| 4319000% |  | 226 | 27 | 2017-06-13
| 4322000% |  | 227 | 28 | 2017-04-18
| 4325100% |  | 228 | 29 | 2017-04-18
| 4328100% |  | 229 | 30 | 2017-06-13
| 4331200% |  | 230 | 31 | 2017-06-13
| 4334300% |  | 231 | 32 | 2017-04-18
| 4337300% |  | 232 | 33
| 4340400% |  | 233 | 34 | 2017-06-13
| 4343400% |  | 234 | 35 | 2017-06-13
| 4346500% |  | 235 | 36 | 2017-06-13
| 4349600% |  | 236 | 37 | 2017-06-13
| 4352400% |  | 237 | 38 | 2017-06-13
| 4355500% |  | 238 | 39 | 2017-06-13
| 4358500% |  | 239 | 40
| 4361600% |  | 240 | 41
| 4364600% |  | 241 | 42 | 2017-06-13
| 4367700% |  | 242 | 43 | 2017-06-13
| 4370800% |  | 243 | 44
| 4373800% |  | 244 | 45 | 2017-06-13
| 4376900% |  | 245 | 46
| 4379900% |  | 246 | 47
| 4383000% |  | 247 | 48
| 4386100% |  | 248 | 49
| 4389000% |  | 249 | 50
| 4392100% |  | 250 | 51
| 4395100% |  | 251 | 52
| 4398200% |  | 252 | 53
| 4401200% |  | 253 | 54
| 4404300% |  | 254 | 55
| 4407400% |  | 255 | 56
| 4410400% |  | 256 | 57 | 2017-06-01
| 4413500% |  | 257 | 58 | 2017-06-01
| 4416500% |  | 258 | 59 | 2017-06-01
| 4419600% |  | 259 | 60 | 2017-06-01
|  |  | 260 | 61 | 2017-06-23
|  |  | 261 | 62 | 2017-06-23
|  |  | 262 | 63 | 2017-06-07
|  |  | 263 | 64 | 2017-06-07
|  |  | 264 | 65 | 2017-06-07
|  |  | 265 | 66 | 2017-06-07
|  |  | 266 | 67 | 2017-07-14
|  |  | 267 | 68 | 2017-06-23
|  |  | 268 | 69 | 2017-07-05
|  |  | 269 | 70 | 2017-06-23
|  |  | 270 | 71 | 2017-07-31
|  |  | 271 | 72 | 2017-07-05
|  |  | 272 | 73 | 2017-07-05
|  |  | 273 | 74 | 2017-07-05
|  |  | 274 | 75 | 2017-07-14
|  |  | 275 | 76 | 2017-07-14
|  |  | 276 | 77 | 2017-09-20
|  |  | 277 | 78 | 2017-07-14
|  |  | 278 | 79 | 2017-07-31
|  |  | 279 | 80 | 2017-07-31
|  |  | 280 | 81 | 2017-08-14
|  |  | 281 | 82 | 2017-07-31
|  |  | 282 | 83 | 2017-08-14
|  |  | 283 | 84 | 2017-08-14
|  |  | 284 | 85 | 2017-08-16
|  |  | 285 | 86
|  |  | 286 | 87 | 2017-08-16
|  |  | 287 | 88 | 2017-08-14
|  |  | 288 | 89 | 2017-08-16
|  |  | 289 | 90 | 2017-08-16
|  |  | 290 | 91 | 2017-09-13
|  |  | 291 | 92 | 2017-09-13
|  |  | 292 | 93 | 2017-10-05
|  |  | 293 | 94
|  |  | 294 | 95 | 2017-09-13
|  |  | 295 | 96 | 2017-09-20
|  |  | 296 | 97 | 2017-09-13
|  |  | 297 | 98 | 2017-09-20
|  |  | 298 | 99
|  |  | 299 | 100 | 2017-09-20
|  |  | 300 | 101
|  |  | 301 | 102 | 2017-10-05
|  |  | 302 | 103 | 2017-10-05
|  |  | 303 | 104 | 2017-10-05
|  |  | 304 | 105
|  |  | 305 | 106
|  |  | 306 | 107
|  |  | 307 | 108
|  |  | 308 | 109
|  |  | 309 | 110
|  |  | 310 | 111
|  |  | 311 | 112
|  |  | 312 | 113
|  |  | 313 | 114
|  |  | 314 | 115
|  |  | 315 | 116
|  |  | 316 | 117
|  |  | 317 | 118
|  |  | 318 | 119
|  |  | 319 | 120
|  |  | 320 | 121
|  |  | 321 | 122
|  |  | 322 | 123
|  |  | 323 | 124
|  |  | 324 | 125
|  |  | 325 | 126
|  |  | 326 | 127
|  |  | 327 | 128
|  |  | 328 | 129
|  |  | 329 | 130
|  |  | 330 | 131
|  |  | 331 | 132
|  |  | 332 | 133