## Form
JSA / Jefferson Lab - DOE
PO Percent Complete Form
Appendix A
Vendor Name | RI Research Instruments | [5 empty] | PO with Peg Points? (Yes or No)
PO Number | 15-C0587 |  |  | Buyer | Laney | Complete through | 2018-01-31
(Date)
PO Line # | Percent Complete | Completed Peg Point (X) |  | Summary of Work (only if less than 100%)
1 | 100% |  |  | Proof of equipment order furnace uprade
2 | 100% |  |  | Proof of completed furnace uprade
3 | 100% |  |  | Acceptance of Ni doping process - Cav 1 (of 2)
4 | 100% |  |  | Acceptance of Ni doping process - Cav 2 (of 2)
5 | 100% |  |  | PH II: Mfg Drawings Accepted by JLab
6 | 100% |  |  | PH II: FAs Mech Pre-fab (Deep Draw)
7 | 100% |  |  | PH III: Mech Pre-Fab Cavities (9-72)
8 | 100% |  |  | PH III: Mech Pre-Fab Cavities (73-133)
9 | 100% |  |  | PH II: First Articles Deliver & Accept (1-8)
10 | 100% |  |  | PH III: Deliver & Accept Cavities (9-12)
11 | 100% |  |  | PH III: Deliver & Accept Cavities (13-16)
12 | 100% |  |  | PH III: Deliver & Accept Cavities (17-20)
13 | 100% |  |  | PH III: Deliver & Accept Cavities (21-24)
14 | 100% |  |  | PH III: Deliver & Accept Cavities (25-28)
15 | 100% |  |  | PH III: Deliver & Accept Cavities (29-32)
16 | 100% |  |  | PH III: Deliver & Accept Cavities (33-36)
17 | 100% |  |  | PH III: Deliver & Accept Cavities (37-40)
18 | 100% |  |  | PH III: Deliver & Accept Cavities (41-44)
19 | 100% |  |  | PH III: Deliver & Accept Cavities (45-48)
20 | 100% |  |  | PH III: Deliver & Accept Cavities (49-52)
21 | 100% |  |  | MOD 002: DESY Equip Refurbishment
22 | 55.3% |  |  | MOD 002: DESY Equip Service & Support Costs
23 | 100% |  |  | MOD 003: Accel Shipment (1-16) Incentives (Max of $323,136)
24 | 99.6% |  |  | MOD 004: Incentives for Accelerated Production Deliveries
25 | 100% |  |  | MOD 005: DESY Equipment Lease ($9,200/ month)
26 | 100% |  |  | PH III: Deliver & Accept Cavities (53-56)
27 | 100% |  |  | PH III: Deliver & Accept Cavities (57-60)
28 | 100% |  |  | PH III: Deliver & Accept Cavities (61-64)
29 | 100% |  |  | PH III: Deliver & Accept Cavities (65-68)
30 | 100% |  |  | PH III: Deliver & Accept Cavities (69-72)
31 | 100% |  |  | PH III: Deliver & Accept Cavities (73-76)
32 | 100% |  |  | PH III: Deliver & Accept Cavities (77-80)
33 | 100% |  |  | PH III: Deliver & Accept Cavities (81-84)
34 | 100% |  |  | PH III: Deliver & Accept Cavities (85-88)
35 | 100% |  |  | PH III: Deliver & Accept Cavities (89-92)
36 | 100% |  |  | PH III: Deliver & Accept Cavities (93-96)
37 | 100% |  |  | PH III: Deliver & Accept Cavities (97-100)
38 | 100% |  |  | PH III: Deliver & Accept Cavities (101-104)
39 | 100% |  |  | PH III: Deliver & Accept Cavities (105-108)
40 | 100% |  |  | PH III: Deliver & Accept Cavities (109-112)
41 | 100% |  |  | PH III: Deliver & Accept Cavities (113-116)
42 | 100% |  |  | PH III: Deliver & Accept Cavities (117-120)
43 | 100% |  |  | PH III: Deliver & Accept Cavities (121-124)
44 | 100% |  |  | PH III: Deliver & Accept Cavities (125-128)
45 | 100% |  |  | PH III: Deliver & Accept Cavities (129-133)
46 | 100% |  |  | MOD 007: LCLS-II R&D Cavities (4)
47 | 100% |  |  | MOD 008: CTM Spare Parts
48 | 99.12% |  |  | MOD 009: Recipe Modification (21-133) ($4283.18/cavity)
49 | 98.54% |  |  | MOD 010: Niobium Caps $490.00/ea (Cavs 17-133)
50 | 100% |  |  | MOD 010: Ningxia Material Sorting
51 | 0% |  |  | MOD 011: Optional Cavities 1-8
52 | 100% |  |  | MOD 012: DESY Testing 4X RF Tests
53 | 26.84% |  |  | MOD 012: Add DESY Testing Costs (Not to Exceed)
54 | 100% |  |  | MOD013-32+3: Material Supply, 1st lot
55 | 100% |  |  | MOD013-32+3: Material Supply, 2nd lot
56 | 100% |  |  | MOD013-32+3: DESY QA of 1st material lot
57 | 100% |  |  | MOD013-32+3: DESY Q of 2nd material lot
58 | 0% |  |  | MOD013-32+3: Deliver & Accept 4 Cavities
59 | 0% |  |  | MOD013-32+3: Deliver & Accept 4 Cavities
60 | 0% |  |  | MOD013-32+3: Deliver & Accept 4 Cavities
61 | 0% |  |  | MOD013-32+3: Deliver & Accept 4 Cavities
62 | 0% |  |  | MOD013-32+3: Deliver & Accept 4 Cavities
63 | 0% |  |  | MOD013-32+3: Deliver & Accept 4 Cavities
64 | 0% |  |  | MOD013-32+3: Deliver & Accept 4 Cavities
65 | 0% |  |  | MOD013-32+3: Deliver & Accept 4 Cavities
66 | 0% |  |  | MOD013-32+3: Deliver & Accept 2 Single Cell Cavities
67 | 39.89% |  |  | MOD013-32+3: Lease/Maintenance DESY Equipment
68 | 100% |  |  | MOD013-Add Mat'l: Material Supply, 1st lot
69 | 100% |  |  | MOD013-Add Mat'l: DESY QA of 1st material lot
70 | 0% |  |  | MOD013-Add Mat'l: Material Supply, 2nd lot
71 | 0% |  |  | MOD013-Add Mat'l: DESY QA of 2nd material lot
72 | 0% |  |  | MOD013-Add Mat'l: Material Supply, 3rd lot
73 | 0% |  |  | MOD013-Add Mat'l: DESY QA of 3rd material lot
74 | 0% |  |  | MOD013-Add Mat'l: Material Supply, 4th lot
75 | 0% |  |  | MOD013-Add Mat'l: DESY QA of 4th material lot
76 | 0% |  |  | MOD013-Add Mat'l: Storage of material for up to 6 months
77 | 0% |  |  | MOD013-Add Mat'l: Package and air shipment of material
78 | 0% |  |  | MOD013-Add Mat'l: Deliver & Accept 1-Cell Cavites (Lot 1)
79 | 0% |  |  | MOD013-Add Mat'l: Deliver & Accept 1-Cell Cavites (Lot 2)
80 | 0% |  |  | MOD013-Add Mat'l: Deliver & Accept 1-Cell Cavites (Lot 3)
81 | 0% |  |  | MOD013-Add Mat'l: Deliver & Accept 1-Cell Cavites (Lot 4)
82 | 100% |  |  | MOD014: Supply & QC of 320 TD Sheets
83 | 100% |  |  | MOD015: Acceptance of Optional Cavities (9-16)
84 | 0% |  |  | MOD015: Incentive- Accelerated Delivery $5K/ cavities (9-16)
85 | 100% |  |  | MOD016: Transport Excess Zanon Cavity Materials to RI
86 | 100% |  |  | MOD016: Delivery & Accept TD Cavities (Zanon Material 1-4 of 18)
87 | 100% |  |  | MOD016: Delivery & Accept 4 TD Cavities (Zanon Material 5-8 of 18)
88 | 100% |  |  | MOD016: Delivery & Accept 4 TD Cavities (Zanon Material 9-12 of 18)
89 | 50% |  |  | MOD016: Delivery & Accept 4 TD Cavities (Zanon Material 13-16 of 18)
90 | 0% |  |  | MOD016: Delivery & Accept 2 TD Cavities (Zanon Material 17-18 of 18)
91 | 0% |  |  | MOD019: Delivery & Accept Optional 3
92 | 0% |  |  | MOD020: Heat Treatment of Lot B
93 | 0% |  |  | MOD020: Bellow Tank Replacement
94 | 0%
95 | 0%
96 | 0%
97 | 0%
98 | 0%
99 | 0%
100 | 0%
101 | 0%
102 | 0%
103 | 0%
104 | 0%
105 | 0%
106 | 0%
Vendor Technical Representative Contacted:
|  |  | Name |  |  |  |  | Date
Jlab Control Account Manager (CAM): |  |  |  |  | Eden Evans for Ed Daly |  |  | 2018-01-31
[6 empty] | Name |  | Date
Below for use by Accounting/Shipping & Receiving Only
Accounting or Shipping & Receiving Entered By:
Date
Data Entry Verified By:
Date

## Process
JSA / Jefferson Lab - DOE
PO Percent Complete Form
Procedure
A Subcontract Purchase Order (PO) is a service type PO with loosely defined scheduled deliverables and variable amounts. A Peg Point PO has specified scheduled deliverable dates for a specified amount.
This form is to be used if NO invoice has been approved by the SOTR or CAM for work completed.
SOTR or CAM contacts a vendor technical representative for an evaluation of the percent of work completed. This can be done either verbally or via email.
Required information - Vendor Name, indicate if PO is a Peg Point type PO or not, PO #, Buyer, Complete through date (usually the end of the month), PO Line #, Percent complete, a short Summary of Work performed provided by the Vendor Technical Representative that supports the percent complete if less than 100%, the name of the Vendor Technical Representative contacted, and the CAM name.
The SOTR or CAM will submit a PO Percent Complete form by the 2nd working day following the end of the month affected for work that has been completed. This allows time for Accounting to process an accrual for the month end closing. Reminder if PO is for Peg Points, the peg point must be fully complete before claiming it.
Submit the completed form with all the information via email to evpo@jlab.org. The file name of the spreadsheet attached to the email should always include the PO# and the letters 'S&R' if it is a Peg Point type PO. File name examples: Peg Point Type PO 08-C5413 S&R, Subcontract Type PO 08-A2659. This email will forward the form automatically to personnel in Procurement, Shipping & Receiving, CFO, and PMI.
If the PO is a Subcontract type PO, the SOTR or CAM will still be required to sign all invoices received at JLab from the vendor up since this was an estimate. An approved invoice by the SOTR or CAM can also be used as basis for the percent of work complete.
If the PO is a Peg Point type PO, Shipping & Receiving will use this form to enter that Peg Point into the Costpoint Financial System. No additional invoice approvals will be required since the SOTR or CAM already indicated the work was complete. An approved invoice by the SOTR or CAM can also be used as basis for the percent of work complete without having to complete this form.
If a previous percent complete was submitted and subsequently determined to be in error, adjust the percent complete to correct the error. Add an explanatory note to support the adjustment.

## Accting USE Data Entry Form
Vendor | RI Research Instruments | [18 empty] | "+"Monthly Accruals
PO | 15-C0587
Buyer | Fitzpatrick
Complete thru | 4300800%
PO Line # | Description | line | PO Line Beg Bal | Prior % Complete | Nov-16 | Dec-16 | Jan-17 | Feb-17 | Mar-17 | Apr-17 | May-17 | Jun-17 | Jul-17 | Aug-17 | Sep-17 | Oct-17 | Nov-17 | Dec-17 | Jan-18 | Est Complete Date | Percent Complete | Completed Work Amt | Eligible for Voucher Amt | Prev Vouchered Amount | Completed Work Retention Amt | Note
1 | Proof of equipment order furnace uprade | 1 | 157470 | 100% | [11 empty] | 0 |  |  |  | 2015-09-01 | 100% | 157470 | 0 | 157470 | 0
2 | Proof of completed furnace uprade | 2 | 157470 | 100% | [11 empty] | 0 |  |  |  | 2015-11-01 | 100% | 157470 | 0 | 157470 | 0
3 | Acceptance of Ni doping process - Cav 1 (of 2) | 3 | 104980 | 100% | [11 empty] | 0 |  |  |  | 2015-12-01 | 100% | 104980 | 0 | 104980 | 0
4 | Acceptance of Ni doping process - Cav 2 (of 2) | 4 | 104980 | 100% | [11 empty] | 0 |  |  |  | 2016-02-28 | 100% | 104980 | 0 | 104980 | 0
5 | PH II: Mfg Drawings Accepted by JLab | 5 | 317520 | 100% | [11 empty] | 0 |  |  |  | 2015-12-04 | 100% | 317520 | 0 | 317520 | 0
6 | PH II: FAs Mech Pre-fab (Deep Draw) | 6 | 423360 | 100% | [11 empty] | 0 |  |  |  | 2015-12-11 | 100% | 423360 | 0 | 423360 | 0
7 | PH III: Mech Pre-Fab Cavities (9-72) | 7 | 1607500 | 100% | [11 empty] | 0 |  |  |  | 2015-12-18 | 100% | 1607500 | 0 | 1607500 | 0
8 | PH III: Mech Pre-Fab Cavities (73-133) | 8 | 1446750 | 100% | [11 empty] | 0 |  |  |  | 2016-03-31 | 100% | 1446750 | 0 | 1446750 | 0
9 | PH II: First Articles Deliver & Accept (1-8) | 9 | 317520 | 100% | [11 empty] | 0 |  |  |  | 2016-08-25 | 100% | 317520 | 0 | 317520 | 0
10 | PH III: Deliver & Accept Cavities (9-12) | 10 | 160750 | 100% | [11 empty] | 0 |  |  |  | 2016-12-15 | 100% | 160750 | 0 | 160750 | 0
11 | PH III: Deliver & Accept Cavities (13-16) | 11 | 160750 | 100% | [11 empty] | 0 |  |  |  | 2017-01-03 | 100% | 160750 | 0 | 160750 | 0
12 | PH III: Deliver & Accept Cavities (17-20) | 12 | 160750 | 100% | [11 empty] | 0 |  |  |  | 2017-01-11 | 100% | 160750 | 0 | 160750 | 0
13 | PH III: Deliver & Accept Cavities (21-24) | 13 | 160750 |  | 160750 | [10 empty] | 0 |  |  |  | 2017-01-19 | 100% | 160750 | 0 | 160750 | 0
14 | PH III: Deliver & Accept Cavities (25-28) | 14 | 160750 |  |  | 160750 | [9 empty] | 0 |  |  |  | 2017-01-27 | 100% | 160750 | 0 | 160750 | 0
15 | PH III: Deliver & Accept Cavities (29-32) | 15 | 160750 |  |  | 160750 | [9 empty] | 0 |  |  |  | 2017-02-06 | 100% | 160750 | 0 | 160750 | 0
16 | PH III: Deliver & Accept Cavities (33-36) | 16 | 160750 |  |  | 160750 | [9 empty] | 0 |  |  |  | 2017-02-14 | 100% | 160750 | 0 | 160750 | 0
17 | PH III: Deliver & Accept Cavities (37-40) | 17 | 160750 |  |  | 160750 | [9 empty] | 0 |  |  |  | 2017-02-22 | 100% | 160750 | 0 | 160750 | 0
18 | PH III: Deliver & Accept Cavities (41-44) | 18 | 160750 |  |  | 160750 | [9 empty] | 0 |  |  |  | 2017-03-02 | 100% | 160750 | 0 | 160750 | 0
19 | PH III: Deliver & Accept Cavities (45-48) | 19 | 160750 | 100% |  |  |  | 160750 | [7 empty] | 0 |  |  |  | 2017-03-10 | 100% | 160750 | 0 | 160750 | 0
20 | PH III: Deliver & Accept Cavities (49-52) | 20 | 160750 | 100% |  |  |  | 160750 | [7 empty] | 0 |  |  |  | 2017-03-20 | 100% | 160750 | 0 | 160750 | 0
21 | MOD 002: DESY Equip Refurbishment | 21 | 90800 | 100% | [11 empty] | 0 |  |  |  | 2016-04-18 | 100% | 90800 | 0 | 90800 | 0
22 | MOD 002: DESY Equip Service & Support Costs | 22 | 49696 | 55.3% |  | 7554.66 | [7 empty] | 12375 | 7552.23 | 0 |  |  |  | 2017-06-19 | 55.3% | 27481.888 | 29766.34 | 19929.66 | 0
23 | MOD 003: Accel Shipment (1-16) Incentives (Max of $323,136) | 23 | 315800.81 | 100% | [11 empty] | 8.81 |  |  |  | 2016-10-10 | 100% | 315800.81 | 8.81 | 315792 | 0 | Remaining $7,344 to be de-obligated.
24 | MOD 004: Incentives for Accelerated Production Deliveries | 24 | 246240 | 99.59% | 23000 | 101080 |  | 18160 | 6000 | 15000 | 11000 | 18000 | 8000 | 12000 | 10000 | 23015.04 |  |  |  | 2017-07-17 | 99.6% | 245255.04 | 23000 | 223240 | 0 | Cavities 17-20.
25 | MOD 005: DESY Equipment Lease ($9,200/ month) | 25 | 147200 | 100% | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 9200 | 18224.28 | 27600 |  |  |  | 2017-07-17 | 100% | 147200 | 27600 | 119600 | 0 | 6.25% for October
26 | PH III: Deliver & Accept Cavities (53-56) | 26 | 160750 | [5 empty] | 160750 | [6 empty] | 0 |  |  |  | 2017-03-28 | 100% | 160750 | 0 | 160750 | 0
27 | PH III: Deliver & Accept Cavities (57-60) | 27 | 160750 |  |  |  |  | 80375 |  | 80375 | [5 empty] | 0 |  |  |  | 2017-04-05 | 100% | 160750 | 0 | 160750 | 0
28 | PH III: Deliver & Accept Cavities (61-64) | 28 | 160750 |  |  |  |  | 40187.5 | 120562.5 | [6 empty] | 0 |  |  |  | 2017-04-13 | 100% | 160750 | 0 | 160750 | 0
29 | PH III: Deliver & Accept Cavities (65-68) | 29 | 160750 | [6 empty] | 160750 | [5 empty] | 0 |  |  |  | 2017-04-21 | 100% | 160750 | 0 | 160750 | 0
30 | PH III: Deliver & Accept Cavities (69-72) | 30 | 160750 | [6 empty] | 160750 | [5 empty] | 0 |  |  |  | 2017-05-01 | 100% | 160750 | 0 | 160750 | 0
31 | PH III: Deliver & Accept Cavities (73-76) | 31 | 160750 | [6 empty] | 40187.5 | 120562.5 |  |  |  |  | 0 |  |  |  | 2017-05-09 | 100% | 160750 | 0 | 160750 | 0
32 | PH III: Deliver & Accept Cavities (77-80) | 32 | 160750 | [7 empty] | 160750 |  |  |  |  | 0 |  |  |  | 2017-05-17 | 100% | 160750 | 0 | 160750 | 0
33 | PH III: Deliver & Accept Cavities (81-84) | 33 | 160750 | [7 empty] | 160750 |  |  |  |  | 0 |  |  |  | 2017-05-25 | 100% | 160750 | 0 | 160750 | 0
34 | PH III: Deliver & Accept Cavities (85-88) | 34 | 160750 | [8 empty] | 160750 |  |  |  | 0 |  |  |  | 2017-06-02 | 100% | 160750 | 0 | 160750 | 0
35 | PH III: Deliver & Accept Cavities (89-92) | 35 | 160750 | [8 empty] | 160750 |  |  |  | 0 |  |  |  | 2017-06-12 | 100% | 160750 | 0 | 160750 | 0
36 | PH III: Deliver & Accept Cavities (93-96) | 36 | 160750 | [8 empty] | 160750 |  |  |  | 0 |  |  |  | 2017-06-20 | 100% | 160750 | 0 | 160750 | 0
37 | PH III: Deliver & Accept Cavities (97-100) | 37 | 160750 | [8 empty] | 160750 |  |  |  | 0 |  |  |  | 2017-06-28 | 100% | 160750 | 0 | 160750 | 0
38 | PH III: Deliver & Accept Cavities (101-104) | 38 | 160750 | [8 empty] | 80375 | 80375 |  |  | 0 |  |  |  | 2017-07-06 | 100% | 160750 | 0 | 160750 | 0
39 | PH III: Deliver & Accept Cavities (105-108) | 39 | 160750 | [9 empty] | 160750 |  |  | 0 |  |  |  | 2017-07-14 | 100% | 160750 | 0 | 160750 | 0
40 | PH III: Deliver & Accept Cavities (109-112) | 40 | 160750 | [9 empty] | 80375 | 80375 |  | 0 |  |  |  | 2017-07-24 | 100% | 160750 | 80375 | 80375 | 0
41 | PH III: Deliver & Accept Cavities (113-116) | 41 | 160750 | [10 empty] | 160750 |  | 0 |  |  |  | 2017-08-01 | 100% | 160750 | 160750 | 0 | 0
42 | PH III: Deliver & Accept Cavities (117-120) | 42 | 160750 | [10 empty] | 160750 |  | 0 |  |  |  | 2017-08-09 | 100% | 160750 | 160750 | 0 | 0
43 | PH III: Deliver & Accept Cavities (121-124) | 43 | 160750 | [10 empty] | 80375 | 80375 | 0 |  |  |  | 2017-08-17 | 100% | 160750 | 160750 | 0 | 0
44 | PH III: Deliver & Accept Cavities (125-128) | 44 | 160750 | [11 empty] | 160750 | 0 |  |  |  | 2017-08-25 | 100% | 160750 | 160750 | 0 | 0
45 | PH III: Deliver & Accept Cavities (129-133) | 45 | 160750 | [11 empty] | 120562.5 | 40187.5 |  |  |  | 2017-09-19 | 100% | 160750 | 160750 | 0 | 0
46 | MOD 007: LCLS-II R&D Cavities (4) | 46 | 38000 | 100% | [11 empty] | 0 |  |  |  | 2016-09-01 | 100% | 38000 | 0 | 38000 | 0
47 | MOD 008: CTM Spare Parts | 47 | 71500 | 100% | [11 empty] | 0 |  |  |  | 2016-09-30 | 100% | 71500 | 0 | 71500 | 0
48 | MOD 009: Recipe Modification (21-133) ($4283.18/cavity) | 48 | 484000 | 99.12% | 17132.76 | 102796.56 |  | 68530.88 | 29982.26 | 47114.98 | 47114.98 | 42831.52 | 34265.44 | 51398.16 | 38548.62 | 24.8 |  |  |  | 2017-09-09 | 99.12% | 479740.8 | 98513.8 | 385486.2 | 0
49 | MOD 010: Niobium Caps $490.00/ea (Cavs 17-133) | 49 | 57800 | 98.54% |  | 13720 | 112.56 | 7904.32 | 3430 | 5390 | 5390 | 6683.12 | 3920 | 5880 | 4410 | 116.12 |  |  |  | 2017-09-09 | 98.54% | 56956.12 | 11627.44 | 46172.56 | 0
50 | MOD 010: Ningxia Material Sorting | 50 | 21335 |  |  |  | 21335 | [12 empty] | 2017-09-09 | 100% | 21335 | 0 | 21335 | 0
51 | MOD 011: Optional Cavities 1-8 | 51 | 499817.6 | [16 empty] | 2018-01-31 | 0% | 0 | 499817.6 | 0 | 0
52 | MOD 012: DESY Testing 4X RF Tests | 52 | 129500 | [6 empty] | 64750 |  | 64750 | [7 empty] | 2017-06-02 | 100% | 129500 | 0 | 129500 | 0
53 | MOD 012: Add DESY Testing Costs (Not to Exceed) | 53 | 58240 | [10 empty] | 15630 | [5 empty] | 2017-09-19 | 26.84% | 15630 | 42610 | 15630 | 0
54 | MOD013-32+3: Material Supply, 1st lot | 54 | 658681 | [8 empty] | 658681 | [7 empty] | 2017-06-27 | 100% | 658681 | 658681 | 0 | 0
55 | MOD013-32+3: Material Supply, 2nd lot | 55 | 658681 | [11 empty] | 658681 |  |  |  |  | 2017-07-18 | 100% | 658681 | 658681 | 0 | 0
56 | MOD013-32+3: DESY QA of 1st material lot | 56 | 69750 | [11 empty] | 69750 |  |  |  |  | 2017-07-25 | 100% | 69750 | 69750 | 0 | 0
57 | MOD013-32+3: DESY Q of 2nd material lot | 57 | 69750 | [11 empty] | 69750 |  |  |  |  | 2017-08-15 | 100% | 69750 | 69750 | 0 | 0
58 | MOD013-32+3: Deliver & Accept 4 Cavities | 58 | 299200 | [16 empty] | 2018-03-28 | 0% | 0 | 299200 | 0 | 0
59 | MOD013-32+3: Deliver & Accept 4 Cavities | 59 | 299200 | [16 empty] | 2018-04-04 | 0% | 0 | 299200 | 0 | 0
60 | MOD013-32+3: Deliver & Accept 4 Cavities | 60 | 299200 | [16 empty] | 2018-04-11 | 0% | 0 | 299200 | 0 | 0
61 | MOD013-32+3: Deliver & Accept 4 Cavities | 61 | 299200 | [16 empty] | 2018-04-18 | 0% | 0 | 299200 | 0 | 0
62 | MOD013-32+3: Deliver & Accept 4 Cavities | 62 | 299200 | [16 empty] | 2018-04-25 | 0% | 0 | 299200 | 0 | 0
63 | MOD013-32+3: Deliver & Accept 4 Cavities | 63 | 299200 | [16 empty] | 2018-05-02 | 0% | 0 | 299200 | 0 | 0
64 | MOD013-32+3: Deliver & Accept 4 Cavities | 64 | 299200 | [16 empty] | 2018-05-09 | 0% | 0 | 299200 | 0 | 0
65 | MOD013-32+3: Deliver & Accept 4 Cavities | 65 | 299200 | [16 empty] | 2018-05-16 | 0% | 0 | 299200 | 0 | 0
66 | MOD013-32+3: Deliver & Accept 2 Single Cell Cavities | 66 | 23400 | [16 empty] | 2018-05-16 | 0% | 0 | 23400 | 0 | 0
67 | MOD013-32+3: Lease/Maintenance DESY Equipment | 67 | 93000 | [13 empty] | 9300 | 18600 | 9200 | 2019-03-26 | 39.89% | 37100 | 93000 | 0 | 0
68 | MOD013-Add Mat'l: Material Supply, 1st lot | 68 | 1299466.75 | [13 empty] | 1299466.75 |  |  | 2017-11-07 | 100% | 1299466.75 | 1299466.75 | 0 | 0
69 | MOD013-Add Mat'l: DESY QA of 1st material lot | 69 | 135725 | [13 empty] | 135725 |  |  | 2018-01-02 | 100% | 135725 | 135725 | 0 | 0
70 | MOD013-Add Mat'l: Material Supply, 2nd lot | 70 | 1299466.75 | [16 empty] | 2018-02-27 | 0% | 0 | 1299466.75 | 0 | 0
71 | MOD013-Add Mat'l: DESY QA of 2nd material lot | 71 | 135725 | [16 empty] | 2018-04-24 | 0% | 0 | 135725 | 0 | 0
72 | MOD013-Add Mat'l: Material Supply, 3rd lot | 72 | 1299466.75 | [16 empty] | 2018-06-19 | 0% | 0 | 1299466.75 | 0 | 0
73 | MOD013-Add Mat'l: DESY QA of 3rd material lot | 73 | 135725 | [16 empty] | 2018-08-14 | 0% | 0 | 135725 | 0 | 0
74 | MOD013-Add Mat'l: Material Supply, 4th lot | 74 | 1299466.75 | [16 empty] | 2018-10-09 | 0% | 0 | 1299466.75 | 0 | 0
75 | MOD013-Add Mat'l: DESY QA of 4th material lot | 75 | 135725 | [16 empty] | 2018-12-04 | 0% | 0 | 135725 | 0 | 0
76 | MOD013-Add Mat'l: Storage of material for up to 6 months | 76 | 4500 | [16 empty] | 2019-06-11 | 0% | 0 | 4500 | 0 | 0
77 | MOD013-Add Mat'l: Package and air shipment of material | 77 | 52300 | [16 empty] | 2018-12-04 | 0% | 0 | 52300 | 0 | 0
78 | MOD013-Add Mat'l: Deliver & Accept 1-Cell Cavites (Lot 1) | 78 | 19400 | [16 empty] | 2018-04-24 | 0% | 0 | 19400 | 0 | 0
79 | MOD013-Add Mat'l: Deliver & Accept 1-Cell Cavites (Lot 2) | 79 | 19400 | [16 empty] | 2018-08-14 | 0% | 0 | 19400 | 0 | 0
80 | MOD013-Add Mat'l: Deliver & Accept 1-Cell Cavites (Lot 3) | 80 | 19400 | [16 empty] | 2018-12-04 | 0% | 0 | 19400 | 0 | 0
81 | MOD013-Add Mat'l: Deliver & Accept 1-Cell Cavites (Lot 4) | 81 | 19400 | [16 empty] | 2019-03-26 | 0% | 0 | 19400 | 0 | 0
82 | MOD014: Supply & QC of 320 TD Sheets | 82 | 492989 | [6 empty] | 428480 | 64509 | [8 empty] | 2017-09-09 | 100% | 492989 | 64509 | 428480 | 0
83 | MOD015: Acceptance of Optional Cavities (9-16) | 83 | 499816 | [13 empty] | 499816 |  |  | 2017-01-05 | 100% | 499816 | 499816 | 0 | 0
84 | MOD015: Incentive- Accelerated Delivery $5K/ cavities (9-16) | 84 | 40000 | [16 empty] | 2018-01-31 | 0% | 0 | 40000 | 0 | 0
85 | MOD016: Transport Excess Zanon Cavity Materials to RI | 85 | 6150 | [8 empty] | 6150 | [7 empty] | 2017-05-30 | 100% | 6150 | 0 | 6150 | 0
86 | MOD016: Delivery & Accept TD Cavities (Zanon Material 1-4 of 18) | 86 | 299200 | [14 empty] | 299200 |  | 2018-01-15 | 100% | 299200 | 299200 | 0 | 0
87 | MOD016: Delivery & Accept 4 TD Cavities (Zanon Material 5-8 of 18) | 87 | 299200 | [14 empty] | 299200 |  | 2018-01-22 | 100% | 299200 | 299200 | 0 | 0
88 | MOD016: Delivery & Accept 4 TD Cavities (Zanon Material 9-12 of 18) | 88 | 299200 | [14 empty] | 299200 |  | 2018-01-29 | 100% | 299200 | 299200 | 0 | 0
89 | MOD016: Delivery & Accept 4 TD Cavities (Zanon Material 13-16 of 18) | 89 | 299200 | [14 empty] | 149600 |  | 2018-02-05 | 50% | 149600 | 299200 | 0 | -149600
90 | MOD016: Delivery & Accept 2 TD Cavities (Zanon Material 17-18 of 18) | 90 | 149600 | [16 empty] | 2018-02-12 | 0% | 0 | 149600 | 0 | -149600
91 | MOD019: Delivery & Accept Optional 3 | 91 | 224400 | [16 empty] | 2018-02-05 | 0% | 0 | 224400 | 0 | -224400
92 | MOD020: Heat Treatment of Lot B | 92 | 13800 | [16 empty] | 2018-02-05 | 0% | 0 | 13800 | 0 | -13800
93 | MOD020: Bellow Tank Replacement | 93 | 24600 | [16 empty] | 2018-02-05 | 0% | 0 | 24600 | 0 | -24600

## Invoices
Invoice # | Date | Milestone/ Line | Invoice Amount | Line | Approval Date | Notes
3456.01 | 4222700% | Proof of equipment order furnace uprade | 157470 | 1 | 2015-09-11
3456.02 | 4232000% | Proof of completed furnace uprade | 157470 | 2 | 2015-12-12
3456.03 | 4251500% | PH II: FAs Mech Pre-fab (Deep Draw) | 423360 | 6 | 2016-06-22
3456.04 | 4251500% | PH III: Mech Pre-Fab Cavities (9-72) | 1607500 | 7 | 2016-06-22
3456.05 | 4260100% | PH II: Mfg Drawings Accepted by JLab | 317520 | 5 | 2016-09-16
3456.06 | 4263300% | PH III: Mech Pre-Fab Cavities (73-133) | 1446750 | 8 | 2016-10-18
3991.01 | 4283100% | MOD014: Supply & QC of 320 TD Sheets | 428480 | 82 | 2017-08-22
51222 | 4241700% | Acceptance of Ni doping process - Cav 1 (of 2) | 104980 | 3 | 2016-03-16
51222 | 4241700% | Acceptance of Ni doping process - Cav 2 (of 2) | 104980 | 4 | 2016-03-16
51315 | 4251500% | MOD 002: DESY Equip Refurbishment | 90800 | 21 | 2016-06-22
51419 | 4261100% | MOD 003: Accel Shipment (1-16) Incentives (Max of $323,136) | 80784 | 23 | 2016-09-26
51419 | 4261100% | PH II: First Articles Deliver & Accept (1-8) | 158760 | 9 | 2016-09-26
51428 | 4261200% | MOD 008: CTM Spare Parts | 71500 | 47 | 2016-09-27
51448 | 4263600% | MOD 003: Accel Shipment (1-16) Incentives (Max of $323,136) | 73440 | 23 | 2016-10-30
51448 | 4263600% | PH II: First Articles Deliver & Accept (1-8) | 158760 | 9 | 2016-10-30
51450 | 4263900% | MOD 003: Accel Shipment (1-16) Incentives (Max of $323,136) | 161568 | 23 | 2016-10-30
51450 | 4263900% | PH III: Deliver & Accept Cavities (9-12) | 160750 | 10 | 2016-10-30
51450 | 4263900% | PH III: Deliver & Accept Cavities (13-16) | 160750 | 11 | 2016-10-30
51451 | 4263900% | MOD 005: DESY Equipment Lease ($9,200/ month) | 36800 | 25 | 2016-10-30
51452 | 4263900% | MOD 007: LCLS-II R&D Cavities (4) | 38000 | 46 | 2016-10-30
51511 | 4269800% | MOD 002: DESY Equip Service & Support Costs | 7554.66 | 22 | 2017-01-18
51533 | 4270400% | PH III: Deliver & Accept Cavities (17-20) | 160750 | 12 | 2016-12-02
51533 | 4270400% | MOD 004: Incentives for Accelerated Production Deliveries | 23000 | 24 | 2016-12-02
51554 | 4272300% | MOD 005: DESY Equipment Lease ($9,200/ month) | 27600 | 25 | 2017-01-18
51589 | 4272700% | MOD 004: Incentives for Accelerated Production Deliveries | 101080 | 24 | 2017-02-15
51589 | 4272700% | PH III: Deliver & Accept Cavities (21-24) | 160750 | 13 | 2017-02-15
51589 | 4272700% | PH III: Deliver & Accept Cavities (25-28) | 160750 | 14 | 2017-02-15
51589 | 4272700% | PH III: Deliver & Accept Cavities (29-32) | 160750 | 15 | 2017-02-15
51589 | 4272700% | PH III: Deliver & Accept Cavities (33-36) | 160750 | 16 | 2017-02-15
51589 | 4272700% | PH III: Deliver & Accept Cavities (37-40) | 160750 | 17 | 2017-02-15
51589 | 4272700% | PH III: Deliver & Accept Cavities (41-44) | 160750 | 18 | 2017-02-15
51589 | 4272700% | MOD 009: Recipe Modification (21-133) ($4283.18/cavity) | 102796.32 | 48 | 2017-02-15
51595 | 4273500% | MOD 010: Ningxia Material Sorting | 21335 | 50 | 2017-01-18
51595 | 4273500% | MOD 010: Niobium Caps $490.00/ea (Cavs 17-133) | 11856.48 | 49 | 2017-01-18
51599 | 4275500% | MOD 004: Incentives for Accelerated Production Deliveries | 23000 | 24 | 2017-02-15
51600 | 4275800% | MOD 010: Niobium Caps $490.00/ea (Cavs 17-133) | 1976.08 | 49 | 2017-02-17
51640 | 4285200% | PH III: Deliver & Accept Cavities (45-48) | 160750 | 19 | 2017-04-28
51640 | 4285200% | PH III: Deliver & Accept Cavities (49-52) | 160750 | 20 | 2017-04-28
51640 | 4285200% | MOD 004: Incentives for Accelerated Production Deliveries | 18160 | 24 | 2017-04-28
51640 | 4285200% | MOD 009: Recipe Modification (21-133) ($4283.18/cavity) | 34265.44 | 48 | 2017-04-28
51640 | 4285200% | MOD 010: Niobium Caps $490.00/ea (Cavs 17-133) | 3920 | 49 | 2017-04-28
51679 | 4282300% | MOD 005: DESY Equipment Lease ($9,200/ month) | 27600 | 25 | 2017-05-16
51680 | 4282300% | PH III: Deliver & Accept Cavities (53-56) | 160750 | 26 | 2017-05-16
51680 | 4282300% | PH III: Deliver & Accept Cavities (57-60) | 80375 | 27 | 2017-05-16
51680 | 4282300% | MOD 004: Incentives for Accelerated Production Deliveries | 6000 | 24 | 2017-05-16
51680 | 4282300% | MOD 009: Recipe Modification (21-133) ($4283.18/cavity) | 25699.08 | 48 | 2017-05-16
51680 | 4282300% | MOD 010: Niobium Caps $490.00/ea (Cavs 17-133) | 2940 | 49 | 2017-05-16
51718 | 4285200% | PH III: Deliver & Accept Cavities (57-60) | 80375 | 27 | 2017-05-16
51718 | 4285200% | PH III: Deliver & Accept Cavities (61-64) | 160750 | 28 | 2017-05-16
51718 | 4285200% | PH III: Deliver & Accept Cavities (65-68) | 160750 | 29 | 2017-05-16
51718 | 4285200% | PH III: Deliver & Accept Cavities (69-72) | 160750 | 30 | 2017-05-16
51718 | 4285200% | PH III: Deliver & Accept Cavities (73-76) | 40187.5 | 31 | 2017-05-16
51718 | 4285200% | MOD 004: Incentives for Accelerated Production Deliveries | 15000 | 24 | 2017-05-16
51718 | 4285200% | MOD 009: Recipe Modification (21-133) ($4283.18/cavity) | 64247.7 | 48 | 2017-05-16
51718 | 4285200% | MOD 010: Niobium Caps $490.00/ea (Cavs 17-133) | 7350 | 49 | 2017-05-16
51744 | 2017-06-13 | MOD016: Transport Excess Zanon Cavity Materials to RI | 6150 | 85 | 2017-08-22
51754 | 4288400% | MOD 004: Incentives for Accelerated Production Deliveries | 11000 | 24 | 2017-07-14
51754 | 4288400% | PH III: Deliver & Accept Cavities (73-76) | 120562.5 | 31 | 2017-07-14
51754 | 4288400% | PH III: Deliver & Accept Cavities (77-80) | 160750 | 32 | 2017-07-14
51754 | 4288400% | PH III: Deliver & Accept Cavities (81-84) | 160750 | 33 | 2017-07-14
51754 | 4288400% | MOD 009: Recipe Modification (21-133) ($4283.18/cavity) | 47114.98 | 48 | 2017-07-14
51754 | 4288400% | MOD 010: Niobium Caps $490.00/ea (Cavs 17-133) | 5390 | 49 | 2017-07-14
51780 | 2017-06-26 | MOD 005: DESY Equipment Lease ($9,200/ month) | 27600 | 25 | 2017-08-22
51781 | 4291200% | MOD 002: DESY Equip Service & Support Costs | 2475 | 22 | 2017-08-22 | Sept 16' (1st) Hazemema Service
51781 | 4291200% | MOD 002: DESY Equip Service & Support Costs | 2475 | 22 | 2017-08-22 | May 17' (2nd) Hazemema Service
51781 | 4291200% | MOD 002: DESY Equip Service & Support Costs | 7425 | 22 | 2017-08-22 | May 17' (1st) CTM Service
51799 | 4291500% | MOD 012: DESY Testing 4X RF Tests | 129500 | 52 | 2017-08-22
51799 | 4291500% | MOD 012: Add DESY Testing Costs (Not to Exceed) | 15630 | 53 | 2017-08-22 | 3 additional HPRs
51808 | 4291600% | PH III: Deliver & Accept Cavities (85-88) | 160750 | 34 | 2017-08-22
51808 | 4291600% | PH III: Deliver & Accept Cavities (89-92) | 160750 | 35 | 2017-08-22
51808 | 4291600% | PH III: Deliver & Accept Cavities (93-96) | 160750 | 36 | 2017-08-22
51808 | 4291600% | PH III: Deliver & Accept Cavities (97-100) | 160750 | 37 | 2017-08-22
51808 | 4291600% | PH III: Deliver & Accept Cavities (101-104) | 80375 | 38 | 2017-08-22
51808 | 4291600% | MOD 004: Incentives for Accelerated Production Deliveries | 18000 | 24 | 2017-08-22
51808 | 4291600% | MOD 009: Recipe Modification (21-133) ($4283.18/cavity) | 77097.24 | 48 | 2017-08-22
51808 | 4291600% | MOD 010: Niobium Caps $490.00/ea (Cavs 17-133) | 8820 | 49 | 2017-08-22
51842 | 4294400% | PH III: Deliver & Accept Cavities (101-104) | 80375 | 38 | 2017-08-22
51842 | 4294400% | PH III: Deliver & Accept Cavities (105-108) | 160750 | 39 | 2017-08-22
51842 | 4294400% | PH III: Deliver & Accept Cavities (109-112) | 80375 | 40 | 2017-08-22
51842 | 4294400% | MOD 004: Incentives for Accelerated Production Deliveries | 8000 | 24 | 2017-08-22
51842 | 4294400% | MOD 009: Recipe Modification (21-133) ($4283.18/cavity) | 34265.44 | 48 | 2017-08-22
51842 | 4294400% | MOD 010: Niobium Caps $490.00/ea (Cavs 17-133) | 3920 | 49 | 2017-08-22

## Sheet1
Amount | PO Line
101080 | 24
160750 | 13
160750 | 14
160750 | 15
160750 | 16
160750 | 17
160750 | 18
102796.32 | 48

## Cavity Status
RI CAVITY DELIVERY/ ACCEPTANCE
Unit # | Serial # | Description | Incentivized Ship Date | Actual Ship Date | Ship# | Wks +/- Incentive Date | FA Incentive Avail | FA Incentive | Prod Incentive Avail | Incentive Earned | Receipt Date | Recipe Modification (Mod 9) | Caps (Mod 10) | Delivery & Acceptance | Total | Accept Date
1 | CAV001 | First Articles | 2017-07-01 | 2016-07-01 | 1 | 0 | 20196 | 20196 |  |  | 2016-06-07 |  |  | 40187.5 | 40187.5 | 2016-08-05
2 | CAV002 | First Articles | 2016-07-01 | 2016-07-01 | 1 | 0 | 20196 | 20196 |  |  | 2016-06-07 |  |  | 40187.5 | 40187.5 | 2016-08-05
3 | CAV004 | First Articles | 2016-07-01 | 2016-07-01 | 1 | 0 | 20196 | 20196 |  |  | 2016-06-07 |  |  | 40187.5 | 40187.5 | 2016-08-05
4 | CAV005 | First Articles | 2016-07-01 | 2016-07-01 | 1 | 0 | 20196 | 20196 |  |  | 2016-06-07 |  |  | 40187.5 | 40187.5 | 2016-08-05
5 | CAV003 | First Articles | 2016-07-01 | 2016-07-01 | 2 | 0 | 20196 | 20196 |  |  | 2016-06-07 |  |  | 40187.5 | 40187.5 | 2016-08-05
6 | CAV006 | First Articles | 2016-07-01 | 2016-07-01 | 2 | 0 | 20196 | 20196 |  |  | 2016-06-07 |  |  | 40187.5 | 40187.5 | 2016-08-05
7 | CAV007 | First Articles | 2016-07-01 | 2016-07-01 | 2 | 0 | 20196 | 20196 |  |  | 2016-06-07 |  |  | 40187.5 | 40187.5 | 2016-08-05
8 | CAV008 | First Articles | 2016-07-01 | 2016-07-01 | 2 | 0 | 20196 | 20196 |  |  | 2016-06-07 |  |  | 40187.5 | 40187.5 | 2016-08-05
9 | CAV009 | First Articles | 2016-08-01 | 2016-08-01 | 3 | 0 | 20196 | 20196 |  |  | 2016-08-07 |  |  | 40187.5 | 40187.5 | 2016-08-05
10 | CAV010 | First Articles | 2016-08-01 | 2016-08-01 | 3 | 0 | 20196 | 20196 |  |  | 2016-08-07 |  |  | 40187.5 | 40187.5 | 2016-08-05
11 | CAV012 | First Articles | 2016-08-01 | 2016-08-01 | 3 | 0 | 20196 | 20196 |  |  | 2016-08-07 |  |  | 40187.5 | 40187.5 | 2016-08-05
12 | CAV014 | First Articles | 2016-08-01 | 2016-08-01 | 3 | 0 | 20196 | 20196 |  |  | 2016-08-07 |  |  | 40187.5 | 40187.5 | 2016-08-05
13 | CAV011 | First Articles | 2016-08-01 | 2016-08-01 | 4 | 0 | 20196 | 20196 |  |  | 2016-08-07 |  |  | 40187.5 | 40187.5 | 2016-08-05
14 | CAV013 | First Articles | 2016-08-01 | 2016-08-01 | 4 | 0 | 20196 | 20196 |  |  | 2016-08-07 |  |  | 40187.5 | 40187.5 | 2016-08-05
15 | CAV015 | First Articles | 2016-08-01 | 2016-08-01 | 4 | 0 | 20196 | 20196 |  |  | 2016-08-07 |  |  | 40187.5 | 40187.5 | 2016-08-05
16 | CAV016 | First Articles | 2016-08-01 | 2016-08-01 | 4 | 0 | 20196 | 20196 |  |  | 2016-08-07 |  |  | 40187.5 | 40187.5 | 2016-08-05
17 | CAV017 | Production | 2016-11-02 | 2016-10-07 | 5 | -3.7143 |  |  | 5750 | 5750 | 2016-10-26 |  | 490 | 40187.5 | 46427.5 | 2016-12-01
18 | CAV018 | Production | 2016-11-02 | 2016-10-07 | 5 | -3.7143 |  |  | 5750 | 5750 | 2016-10-26 |  | 490 | 40187.5 | 46427.5 | 2016-11-01
19 | CAV019 | Production | 2016-11-02 | 2016-10-19 | 6 | -2 |  |  | 5750 | 5750 | 2016-10-26 |  | 490 | 40187.5 | 46427.5 | 2016-11-01
20 | CAV020 | Production | 2016-11-02 | 2016-10-19 | 6 | -2 |  |  | 5750 | 5750 | 2016-10-26 |  | 490 | 40187.5 | 46427.5 | 2016-11-01
21 | CAV021 | Production | 2016-11-02 | 2016-11-02 | 7 | 0 |  |  | 5750 | 5750 | 2016-11-11 | 4283.18 | 490 | 40187.5 | 50710.68 | 2016-11-01
22 | CAV023 | Production | 2016-11-02 | 2016-11-02 | 7 | 0 |  |  | 5750 | 5750 | 2016-11-11 | 4283.18 | 490 | 40187.5 | 50710.68 | 2016-11-01
23 | CAV024 | Production | 2016-11-02 | 2016-11-02 | 7 | 0 |  |  | 5750 | 5750 | 2016-11-11 | 4283.18 | 490 | 40187.5 | 50710.68 | 2016-11-01
24 | CAV028 | Production | 2016-11-02 | 2016-11-02 | 7 | 0 |  |  | 5750 | 5750 | 2016-11-11 | 4283.18 | 490 | 40187.5 | 50710.68 | 2016-11-01
25 | CAV026 | Production | 2016-11-02 | 2016-11-14 | 8 | 1.7143 |  |  | 5750 | 5750 | 2016-11-21 | 4283.18 | 490 | 40187.5 | 50710.68 | 2016-12-01
26 | CAV027 | Production | 2016-11-02 | 2016-11-14 | 8 | 1.7143 |  |  | 5750 | 5750 | 2016-11-21 | 4283.18 | 490 | 40187.5 | 50710.68 | 2016-12-01
27 | CAV029 | Production | 2016-11-02 | 2016-11-14 | 8 | 1.7143 |  |  | 5750 | 5750 | 2016-11-21 | 4283.18 | 490 | 40187.5 | 50710.68 | 2016-12-01
28 | CAV032 | Production | 2016-11-02 | 2016-11-14 | 8 | 1.7143 |  |  | 5750 | 5750 | 2016-11-21 | 4283.18 | 490 | 40187.5 | 50710.68 | 2016-12-01
29 | CAV022 | Production | 2016-11-30 | 2016-11-16 | 9 | -2 |  |  | 5750 | 5750 | 2016-11-28 | 4283.18 | 490 | 40187.5 | 50710.68 | 2016-12-01
30 | CAV031 | Production | 2016-11-30 | 2016-11-16 | 9 | -2 |  |  | 5750 | 5750 | 2016-11-28 | 4283.18 | 490 | 40187.5 | 50710.68 | 2016-12-01
31 | CAV033 | Production | 2016-11-30 | 2016-11-16 | 9 | -2 |  |  | 5750 | 5750 | 2016-11-28 | 4283.18 | 490 | 40187.5 | 50710.68 | 2016-12-01
32 | CAV035 | Production | 2016-11-30 | 2016-11-16 | 9 | -2 |  |  | 5750 | 5750 | 2016-11-28 | 4283.18 | 490 | 40187.5 | 50710.68 | 2016-12-01
33 | CAV025 | Production | 2016-11-30 | 2016-11-24 | 10 | -0.85714 |  |  | 5750 | 5750 | 2016-12-01 | 4283.18 | 490 | 40187.5 | 50710.68 | 2016-12-01
34 | CAV030 | Production | 2016-11-30 | 2016-11-24 | 10 | -0.85714 |  |  | 5750 | 5750 | 2016-12-01 | 4283.18 | 490 | 40187.5 | 50710.68 | 2016-12-01
35 | CAV034 | Production | 2016-11-30 | 2016-11-24 | 10 | -0.85714 |  |  | 5750 | 5750 | 2016-12-01 | 4283.18 | 490 | 40187.5 | 50710.68 | 2016-12-01
36 | CAV036 | Production | 2016-11-30 | 2016-11-24 | 10 | -0.85714 |  |  | 5750 | 5750 | 2016-12-01 | 4283.18 | 490 | 40187.5 | 50710.68 | 2016-12-01
37 | CAV037 | Production | 2016-11-30 | 2016-11-28 | 11 | -0.28571 |  |  | 5750 | 5750 | 2016-12-05 | 4283.18 | 490 | 40187.5 | 50710.68 | 2016-12-01
38 | CAV038 | Production | 2016-11-30 | 2016-11-28 | 11 | -0.28571 |  |  | 5750 | 5750 | 2016-12-05 | 4283.18 | 490 | 40187.5 | 50710.68 | 2016-12-01
39 | CAV045 | Production | 2016-11-30 | 2016-11-28 | 11 | -0.28571 |  |  | 5750 | 5750 | 2016-12-05 | 4283.18 | 490 | 40187.5 | 50710.68 | 2016-12-01
40 | CAV049 | Production | 2016-11-30 | 2016-11-28 | 11 | -0.28571 |  |  | 5750 | 5750 | 2016-12-05 | 4283.18 | 490 | 40187.5 | 50710.68 | 2016-12-01
41 | CAV039 | Production | 2016-12-28 | 2016-11-30 | 12 | -4 |  |  | 2270 | 2270 | 2016-12-07 | 4283.18 | 490 | 40187.5 | 47230.68 | 2016-12-01
42 | CAV040 | Production | 2016-12-28 | 2016-11-30 | 12 | -4 |  |  | 2270 | 2270 | 2016-12-07 | 4283.18 | 490 | 40187.5 | 47230.68 | 2016-12-01
43 | CAV041 | Production | 2016-12-28 | 2016-11-30 | 12 | -4 |  |  | 2270 | 2270 | 2016-12-07 | 4283.18 | 490 | 40187.5 | 47230.68 | 2016-12-01
44 | CAV042 | Production | 2016-12-28 | 2016-11-30 | 12 | -4 |  |  | 2270 | 2270 | 2016-12-07 | 4283.18 | 490 | 40187.5 | 47230.68 | 2016-12-01
45 | CAV043 | Production | 2016-12-28 | 2016-12-16 | 13 | -1.7143 |  |  | 2270 | 2270 | 2017-01-11 | 4283.18 | 490 | 40187.5 | 47230.68 | 2017-02-22
46 | CAV044 | Production | 2016-12-28 | 2016-12-16 | 13 | -1.7143 |  |  | 2270 | 2270 | 2017-01-11 | 4283.18 | 490 | 40187.5 | 47230.68 | 2017-02-22
47 | CAV047 | Production | 2016-12-28 | 2016-12-16 | 13 | -1.7143 |  |  | 2270 | 2270 | 2017-01-11 | 4283.18 | 490 | 40187.5 | 47230.68 | 2017-02-22
48 | CAV048 | Production | 2016-12-28 | 2016-12-16 | 13 | -1.7143 |  |  | 2270 | 2270 | 2017-01-11 | 4283.18 | 490 | 40187.5 | 47230.68 | 2017-02-22
49 | CAV046 | Production | 2016-12-28 | 2017-01-11 | 14 | 2 |  |  | 2270 | 2270 | 2017-01-19 | 4283.18 | 490 | 40187.5 | 47230.68 | 2017-02-22
50 | CAV050 | Production | 2016-12-28 | 2017-01-11 | 14 | 2 |  |  | 2270 | 2270 | 2017-01-19 | 4283.18 | 490 | 40187.5 | 47230.68 | 2017-02-22
51 | CAV051 | Production | 2016-12-28 | 2017-01-11 | 14 | 2 |  |  | 2270 | 2270 | 2017-01-19 | 4283.18 | 490 | 40187.5 | 47230.68 | 2017-02-22
52 | CAV052 | Production | 2016-12-28 | 2017-01-11 | 14 | 2 |  |  | 2270 | 2270 | 2017-01-19 | 4283.18 | 490 | 40187.5 | 47230.68 | 2017-02-22
53 | CAV054 | Production | 2017-01-25 | 2017-02-16 | 15 | 3.1429 |  |  | 1000 | 1000 | 2017-02-17 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-03-20
54 | CAV055 | Production | 2017-01-25 | 2017-02-16 | 15 | 3.1429 |  |  | 1000 | 1000 | 2017-02-17 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-03-20
55 | CAV064 | Production | 2017-01-25 | 2017-02-27 | 16 | 4.7143 |  |  | 1000 | 1000 | 2017-02-27 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-03-20
56 | CAV066 | Production | 2017-01-25 | 2017-02-27 | 16 | 4.7143 |  |  | 1000 | 1000 | 2017-02-27 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-03-20
57 | CAV067 | Production | 2017-01-25 | 2017-02-27 | 16 | 4.7143 |  |  | 1000 | 1000 | 2017-02-27 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-03-20
58 | CAV068 | Production | 2017-01-25 | 2017-02-27 | 16 | 4.7143 |  |  | 1000 | 1000 | 2017-02-27 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-03-20
59 | CAV065 | Production | 2017-01-25 | 2017-03-09 | 17 | 6.1429 |  |  | 1000 | 1000 | 2017-02-15 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-04-21
60 | CAV069 | Production | 2017-01-25 | 2017-03-09 | 17 | 6.1429 |  |  | 1000 | 1000 | 2017-02-15 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-04-21
61 | CAV071 | Production | 2017-01-25 | 2017-03-09 | 17 | 6.1429 |  |  | 1000 | 1000 | 2017-02-15 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-04-21
62 | CAV070 | Production | 2017-01-25 | 2017-03-22 | 18 | 8 |  |  | 1000 | 1000 | 2017-04-04 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-04-21
63 | CAV072 | Production | 2017-01-25 | 2017-03-22 | 18 | 8 |  |  | 1000 | 1000 | 2017-04-04 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-04-21
64 | CAV073 | Production | 2017-01-25 | 2017-03-22 | 18 | 8 |  |  | 1000 | 1000 | 2017-04-04 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-04-21
65 | CAV075 | Production | 2017-02-22 | 2017-03-22 | 18 | 4 |  |  | 1000 | 1000 | 2017-04-04 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-04-21
66 | CAV074 | Production | 2017-02-22 | 2017-03-24 | 19 | 4.2857 |  |  | 1000 | 1000 | 2017-04-07 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-04-21
67 | CAV076 | Production | 2017-02-22 | 2017-03-24 | 19 | 4.2857 |  |  | 1000 | 1000 | 2017-04-07 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-04-21
68 | CAV077 | Production | 2017-02-22 | 2017-03-24 | 19 | 4.2857 |  |  | 1000 | 1000 | 2017-04-07 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-04-21
69 | CAV078 | Production | 2017-02-22 | 2017-03-24 | 19 | 4.2857 |  |  | 1000 | 1000 | 2017-04-07 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-04-21
70 | CAV079 | Production | 2017-02-22 | 2017-03-31 | 20 | 5.2857 |  |  | 1000 | 1000 | 2017-04-13 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-04-21
71 | CAV080 | Production | 2017-02-22 | 2017-03-31 | 20 | 5.2857 |  |  | 1000 | 1000 | 2017-04-13 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-04-21
72 | CAV082 | Production | 2017-02-22 | 2017-03-31 | 20 | 5.2857 |  |  | 1000 | 1000 | 2017-04-13 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-04-21
73 | CAV083 | Production | 2017-02-22 | 2017-03-31 | 20 | 5.2857 |  |  | 1000 | 1000 | 2017-04-13 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-04-21
74 | CAV081 | Production | 2017-02-22 | 2017-04-18 | 21 | 7.8571 |  |  | 1000 | 1000 | 2017-05-25 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-05-23
75 | CAV085 | Production | 2017-02-22 | 2017-04-18 | 21 | 7.8571 |  |  | 1000 | 1000 | 2017-05-25 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-05-23
76 | CAV086 | Production | 2017-02-22 | 2017-04-18 | 21 | 7.8571 |  |  | 1000 | 1000 | 2017-05-25 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-05-23
77 | CAV057 | Production | 2017-03-22 | 2017-04-28 | 22 | 5.2857 |  |  | 1000 | 1000 | 2017-05-05 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-05-23
78 | CAV061 | Production | 2017-03-22 | 2017-04-28 | 22 | 5.2857 |  |  | 1000 | 1000 | 2017-05-05 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-05-23
79 | CAV062 | Production | 2017-03-22 | 2017-04-28 | 22 | 5.2857 |  |  | 1000 | 1000 | 2017-05-05 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-05-23
80 | CAV063 | Production | 2017-03-22 | 2017-04-28 | 22 | 5.2857 |  |  | 1000 | 1000 | 2017-05-05 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-05-23
81 | CAV053 | Production | 2017-03-22 | 2017-05-10 | 23 | 7 |  |  | 1000 | 1000 | 2017-05-17 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-05-23
82 | CAV056 | Production | 2017-03-22 | 2017-05-10 | 23 | 7 |  |  | 1000 | 1000 | 2017-05-17 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-05-23
83 | CAV059 | Production | 2017-03-22 | 2017-05-10 | 23 | 7 |  |  | 1000 | 1000 | 2017-05-17 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-05-23
84 | CAV060 | Production | 2017-03-22 | 2017-05-10 | 23 | 7 |  |  | 1000 | 1000 | 2017-05-17 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-05-23
85 | CAV058 | Production | 2017-03-22 | 2017-05-15 | 24 | 7.7143 |  |  | 1000 | 1000 | 2017-05-22 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-06-30
86 | CAV091 | Production | 2017-03-22 | 2017-05-15 | 24 | 7.7143 |  |  | 1000 | 1000 | 2017-05-22 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-06-30
87 | CAV093 | Production | 2017-03-22 | 2017-05-15 | 24 | 7.7143 |  |  | 1000 | 1000 | 2017-05-22 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-06-30
88 | CAV098 | Production | 2017-03-22 | 2017-05-15 | 24 | 7.7143 |  |  | 1000 | 1000 | 2017-05-22 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-06-30
89 | CAV084 | Production | 2017-04-19 | 2017-05-22 | 25 | 4.7143 |  |  | 1000 | 1000 | 2017-05-30 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-06-30
90 | CAV092 | Production | 2017-04-19 | 2017-05-22 | 25 | 4.7143 |  |  | 1000 | 1000 | 2017-05-30 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-06-30
91 | CAV094 | Production | 2017-04-19 | 2017-05-22 | 25 | 4.7143 |  |  | 1000 | 1000 | 2017-05-30 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-06-30
92 | CAV104 | Production | 2017-05-17 | 2017-05-22 | 25 | 0.71429 |  |  | 1000 | 1000 | 2017-05-30 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-06-30
93 | CAV103 | Production | 2017-05-17 | 2017-06-02 | 26 | 2.2857 |  |  | 1000 | 1000 | 2017-06-09 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-06-30
94 | CAV108 | Production | 2017-05-17 | 2017-06-02 | 26 | 2.2857 |  |  | 1000 | 1000 | 2017-06-09 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-06-30
95 | CAV110 | Production | 2017-05-17 | 2017-06-02 | 26 | 2.2857 |  |  | 1000 | 1000 | 2017-06-09 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-06-30
96 | CAV111 | Production | 2017-05-17 | 2017-06-02 | 26 | 2.2857 |  |  | 1000 | 1000 | 2017-06-09 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-06-30
97 | CAV087 | Production | 2017-04-19 | 2017-06-09 | 27 | 7.2857 |  |  | 1000 | 1000 | 2017-06-15 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-06-30
98 | CAV088 | Production | 2017-04-19 | 2017-06-09 | 27 | 7.2857 |  |  | 1000 | 1000 | 2017-06-15 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-06-30
99 | CAV089 | Production | 2017-04-19 | 2017-06-09 | 27 | 7.2857 |  |  | 1000 | 1000 | 2017-06-15 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-06-30
100 | CAV090 | Production | 2017-04-19 | 2017-06-09 | 27 | 7.2857 |  |  | 1000 | 1000 | 2017-06-15 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-06-30
101 | CAV109 | Production | 2017-05-17 | 2017-06-09 | 27 | 3.2857 |  |  | 1000 | 1000 | 2017-06-15 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-06-30
102 | CAV112 | Production | 2017-05-17 | 2017-06-09 | 27 | 3.2857 |  |  | 1000 | 1000 | 2017-06-15 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-06-30
103 | CAV097 | Production | 2017-04-19 | 2017-06-22 | 28 | 9.1429 |  |  | 1000 | 1000 | 2017-06-30 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-07-27
104 | CAV113 | Production | 2017-06-14 | 2017-06-22 | 28 | 1.1429 |  |  | 1000 | 1000 | 2017-06-30 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-07-27
105 | CAV114 | Production | 2017-06-14 | 2017-06-22 | 28 | 1.1429 |  |  | 1000 | 1000 | 2017-06-30 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-07-27
106 | CAV117 | Production | 2017-06-14 | 2017-06-22 | 28 | 1.1429 |  |  | 1000 | 1000 | 2017-06-30 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-07-27
107 | CAV099 | Production | 2017-04-19 | 2017-06-28 | 29 | 10 |  |  | 1000 | 1000 | 2017-07-10 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-07-27
108 | CAV101 | Production | 2017-05-17 | 2017-06-28 | 29 | 6 |  |  | 1000 | 1000 | 2017-07-10 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-07-27
109 | CAV102 | Production | 2017-05-17 | 2017-06-28 | 29 | 6 |  |  | 1000 | 1000 | 2017-07-10 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-07-27
110 | CAV118 | Production | 2017-06-14 | 2017-06-28 | 29 | 2 |  |  | 1000 | 1000 | 2017-07-10 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-07-27
111 | CAV100 | Production | 2017-04-19 | 2017-07-06 | 30 | 11.1429 |  |  | 1000 | 1000 | 2017-07-11 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-08-31
112 | CAV119 | Production | 2017-06-14 | 2017-07-06 | 30 | 3.1429 |  |  | 1000 | 1000 | 2017-07-11 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-08-31
113 | CAV120 | Production | 2017-06-14 | 2017-07-06 | 30 | 3.1429 |  |  | 1000 | 1000 | 2017-07-11 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-08-31
114 | CAV121 | Production | 2017-06-14 | 2017-07-06 | 30 | 3.1429 |  |  | 1000 | 1000 | 2017-07-11 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-08-31
115 | CAV116 | Production | 2017-06-14 | 2017-07-12 | 31 | 4 |  |  | 1000 | 1000 | 2017-08-01 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-08-31
116 | CAV122 | Production | 2017-06-14 | 2017-07-12 | 31 | 4 |  |  | 1000 | 1000 | 2017-08-01 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-08-31
117 | CAV123 | Production | 2017-06-14 | 2017-07-12 | 31 | 4 |  |  | 1000 | 1000 | 2017-08-01 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-08-31
118 | CAV124 | Production | 2017-06-14 | 2017-07-12 | 31 | 4 |  |  | 1000 | 1000 | 2017-08-01 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-08-31
119 | CAV105 | Production | 2017-05-17 | 2017-07-21 | 32 | 9.2857 |  |  | 1000 | 1000 | 2017-08-04 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-08-31
120 | CAV107 | Production | 2017-05-17 | 2017-07-21 | 32 | 9.2857 |  |  | 1000 | 1000 | 2017-08-04 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-08-31
121 | CAV126 | Production | 2017-07-12 | 2017-07-21 | 32 | 1.2857 |  |  | 1000 | 1000 | 2017-08-04 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-08-31
122 | CAV127 | Production | 2017-07-12 | 2017-07-21 | 32 | 1.2857 |  |  | 1000 | 1000 | 2017-08-04 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-08-31
123 | CAV095 | Production | 2017-04-19 |  |  | 0 |  |  | 1000 | 1000 | 2017-08-30 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-09-01
124 | CAV096 | Production | 2017-04-19 |  |  | 0 |  |  | 1000 | 1000 | 2017-08-30 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-09-01
125 | CAV106 | Production | 2017-05-17 |  |  | 0 |  |  | 1000 | 1000 | 2017-08-30 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-09-01
126 | CAV125 | Production | 2017-07-12 |  |  | 0 |  |  | 1000 | 1000 | 2017-08-30 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-09-01
127 | CAV128 | Production | 2017-07-12 |  |  | 0 |  |  | 1000 | 1000 | 2017-08-30 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-09-01
128 | CAV129 | Production | 2017-07-12 |  |  | 0 |  |  | 1000 | 1000 | 2017-08-30 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-09-01
129 | CAV130 | Production | 2017-07-12 |  |  | 0 |  |  | 1000 | 1000 | 2017-08-30 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-09-01
130 | CAV131 | Production | 2017-07-12 |  |  | 0 |  |  | 1000 | 1000 | 2017-08-30 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-09-01
131 | CAV132 | Production | 2017-07-12 |  |  | 0 |  |  | 1000 | 1000 | 2017-08-30 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-09-01
132 | CAV133 | Production | 2017-07-12 |  |  | 0 |  |  | 1000 | 1000 | 2017-08-30 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-09-01
| CAV115 | Production | 2017-06-14 |  |  | 0 |  |  | 1000 |  |  |  |  | 40187.5 | 40187.5
| CAV134 | Options (1-16) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV135 | Options (1-16) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV136 | Options (1-16) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV137 | Options (1-16) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV138 | Options (1-16) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV139 | Options (1-16) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV140 | Options (1-16) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV141 | Options (1-16) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV142 | Options (1-16) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV143 | Options (1-16) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV144 | Options (1-16) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV145 | Options (1-16) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV146 | Options (1-16) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5 |  | 149
| CAV147 | Options (1-16) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5 |  | 18
| CAV148 | Options (1-16) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5 |  | 3
| CAV149 | Options (1-16) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5 |  | 32
| CAV150 | Excess Cavs (TD) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV150 | 32+3 (MOD13) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV151 | Excess Cavs (TD) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV151 | 32+3 (MOD13) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV152 | Excess Cavs (TD) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV152 | 32+3 (MOD13) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV153 | Excess Cavs (TD) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV153 | 32+3 (MOD13) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV154 | Excess Cavs (TD) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV154 | 32+3 (MOD13) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV155 | Excess Cavs (TD) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV155 | 32+3 (MOD13) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV156 | Excess Cavs (TD) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV156 | 32+3 (MOD13) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV157 | Excess Cavs (TD) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV157 | 32+3 (MOD13) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV158 | Excess Cavs (TD) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV158 | 32+3 (MOD13) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV159 | Excess Cavs (TD) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV159 | 32+3 (MOD13) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV160 | Excess Cavs (TD) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV160 | 32+3 (MOD13) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV161 | Excess Cavs (TD) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV161 | 32+3 (MOD13) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV162 | Excess Cavs (TD) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV162 | 32+3 (MOD13) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV163 | Excess Cavs (TD) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV163 | 32+3 (MOD13) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV164 | Excess Cavs (TD) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV164 | 32+3 (MOD13) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV165 | Excess Cavs (TD) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV165 | 32+3 (MOD13) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV166 | Excess Cavs (TD) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV166 | 32+3 (MOD13) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV167 | Excess Cavs (TD) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV167 | 32+3 (MOD13) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV168 | Excess Cavs (NX) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV168 | 32+3 (MOD13) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV169 | Excess Cavs (NX) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV169 | 32+3 (MOD13) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV170 | Excess Cavs (NX) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV170 | 32+3 (MOD13) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV171 | 32+3 (MOD13) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV172 | 32+3 (MOD13) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV173 | 32+3 (MOD13) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV174 | 32+3 (MOD13) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV175 | 32+3 (MOD13) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV176 | 32+3 (MOD13) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV177 | 32+3 (MOD13) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV178 | 32+3 (MOD13) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV179 | 32+3 (MOD13) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV180 | 32+3 (MOD13) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV181 | 32+3 (MOD13) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV182 | 32+3 (MOD13) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV183 | 32+3 (MOD13) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV184 | 32+3 (MOD13) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV185 | 32+3 (MOD13) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV186 | 32+3 (MOD13) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV187 | 32+3 (MOD13) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV188 | 32+3 (MOD13) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV189 | 32+3 (MOD13) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV190 | 32+3 (MOD13) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV191 | 32+3 (MOD13) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV192 | 32+3 (MOD13) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV193 | 32+3 (MOD13) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV194 | 32+3 (MOD13) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV195 | 32+3 (MOD13) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV196 | 32+3 (MOD13) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV197 | 32+3 (MOD13) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV198 | 32+3 (MOD13) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV199 | 32+3 (MOD13) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV200 | 32+3 (MOD13) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV201 | 32+3 (MOD13) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
| CAV202 | 32+3 (MOD13) |  |  |  | 0 | [7 empty] | 40187.5 | 40187.5
[6 empty] | 0 | [7 empty] | 40187.5 | 40187.5
132 | 223 | [5 empty] | 323136 |  | 246240 | 245240 |  | 479716.16 | 56840 | 9002000 | 9783796.16
99.59%

## Accept
RI Cavity Acceptance
Unit # | Serial # | Actual Ship Date | Incentive Earned | Receipt Date | Recipe Mod (Mod 9) | Caps (Mod 10) | Delivery & Acceptance | Total | Accept Date
1 | CAV001 |  | 0 | 2016-06-07 | 0 | 0 | 40187.5 | 40187.5 | 2016-08-05
2 | CAV002 |  | 0 | 2016-06-07 | 0 | 0 | 40187.5 | 40187.5 | 2016-08-05
3 | CAV004 | 2016-07-01 | 0 | 2016-06-07 | 0 | 0 | 40187.5 | 40187.5 | 2016-08-05
4 | CAV005 | 2016-07-01 | 0 | 2016-06-07 | 0 | 0 | 40187.5 | 40187.5 | 2016-08-05
5 | CAV003 | 2016-07-01 | 0 | 2016-06-07 | 0 | 0 | 40187.5 | 40187.5 | 2016-08-05
6 | CAV006 | 2016-07-01 | 0 | 2016-06-07 | 0 | 0 | 40187.5 | 40187.5 | 2016-08-05
7 | CAV007 | 2016-07-01 | 0 | 2016-06-07 | 0 | 0 | 40187.5 | 40187.5 | 2016-08-05
8 | CAV008 | 2016-07-01 | 0 | 2016-06-07 | 0 | 0 | 40187.5 | 40187.5 | 2016-08-05
9 | CAV009 | 2016-08-01 | 0 | 2016-08-07 | 0 | 0 | 40187.5 | 40187.5 | 2016-08-05
10 | CAV010 | 2016-08-01 | 0 | 2016-08-07 | 0 | 0 | 40187.5 | 40187.5 | 2016-08-05
11 | CAV012 | 2016-08-01 | 0 | 2016-08-07 | 0 | 0 | 40187.5 | 40187.5 | 2016-08-05
12 | CAV014 | 2016-08-01 | 0 | 2016-08-07 | 0 | 0 | 40187.5 | 40187.5 | 2016-08-05
13 | CAV011 | 2016-08-01 | 0 | 2016-08-07 | 0 | 0 | 40187.5 | 40187.5 | 2016-08-05
14 | CAV013 | 2016-08-01 | 0 | 2016-08-07 | 0 | 0 | 40187.5 | 40187.5 | 2016-08-05
15 | CAV015 | 2016-08-01 | 0 | 2016-08-07 | 0 | 0 | 40187.5 | 40187.5 | 2016-08-05
16 | CAV016 | 2016-08-01 | 0 | 2016-08-07 | 0 | 0 | 40187.5 | 40187.5 | 2016-08-05
17 | CAV017 | 2016-10-07 | 5750 | 2016-10-26 | 0 | 490 | 40187.5 | 46427.5 | 2016-12-01
18 | CAV018 | 2016-10-07 | 5750 | 2016-10-26 | 0 | 490 | 40187.5 | 46427.5 | 2016-11-01
19 | CAV019 | 2016-10-19 | 5750 | 2016-10-26 | 0 | 490 | 40187.5 | 46427.5 | 2016-11-01
20 | CAV020 | 2016-10-19 | 5750 | 2016-10-26 | 0 | 490 | 40187.5 | 46427.5 | 2016-11-01
21 | CAV021 | 2016-11-02 | 5750 | 2016-11-11 | 4283.18 | 490 | 40187.5 | 50710.68 | 2016-11-01
22 | CAV023 | 2016-11-02 | 5750 | 2016-11-11 | 4283.18 | 490 | 40187.5 | 50710.68 | 2016-11-01
23 | CAV024 | 2016-11-02 | 5750 | 2016-11-11 | 4283.18 | 490 | 40187.5 | 50710.68 | 2016-11-01
24 | CAV028 | 2016-11-02 | 5750 | 2016-11-11 | 4283.18 | 490 | 40187.5 | 50710.68 | 2016-11-01
25 | CAV026 | 2016-11-14 | 5750 | 2016-11-21 | 4283.18 | 490 | 40187.5 | 50710.68 | 2016-12-01
26 | CAV027 | 2016-11-14 | 5750 | 2016-11-21 | 4283.18 | 490 | 40187.5 | 50710.68 | 2016-12-01
27 | CAV029 | 2016-11-14 | 5750 | 2016-11-21 | 4283.18 | 490 | 40187.5 | 50710.68 | 2016-12-01
28 | CAV032 | 2016-11-14 | 5750 | 2016-11-21 | 4283.18 | 490 | 40187.5 | 50710.68 | 2016-12-01
29 | CAV022 | 2016-11-16 | 5750 | 2016-11-28 | 4283.18 | 490 | 40187.5 | 50710.68 | 2016-12-01
30 | CAV031 | 2016-11-16 | 5750 | 2016-11-28 | 4283.18 | 490 | 40187.5 | 50710.68 | 2016-12-01
31 | CAV033 | 2016-11-16 | 5750 | 2016-11-28 | 4283.18 | 490 | 40187.5 | 50710.68 | 2016-12-01
32 | CAV035 | 2016-11-16 | 5750 | 2016-11-28 | 4283.18 | 490 | 40187.5 | 50710.68 | 2016-12-01
33 | CAV025 | 2016-11-24 | 5750 | 2016-12-01 | 4283.18 | 490 | 40187.5 | 50710.68 | 2016-12-01
34 | CAV030 | 2016-11-24 | 5750 | 2016-12-01 | 4283.18 | 490 | 40187.5 | 50710.68 | 2016-12-01
35 | CAV034 | 2016-11-24 | 5750 | 2016-12-01 | 4283.18 | 490 | 40187.5 | 50710.68 | 2016-12-01
36 | CAV036 | 2016-11-24 | 5750 | 2016-12-01 | 4283.18 | 490 | 40187.5 | 50710.68 | 2016-12-01
37 | CAV037 | 2016-11-28 | 5750 | 2016-12-05 | 4283.18 | 490 | 40187.5 | 50710.68 | 2016-12-01
38 | CAV038 | 2016-11-28 | 5750 | 2016-12-05 | 4283.18 | 490 | 40187.5 | 50710.68 | 2016-12-01
39 | CAV045 | 2016-11-28 | 5750 | 2016-12-05 | 4283.18 | 490 | 40187.5 | 50710.68 | 2016-12-01
40 | CAV049 | 2016-11-28 | 5750 | 2016-12-05 | 4283.18 | 490 | 40187.5 | 50710.68 | 2016-12-01
41 | CAV039 | 2016-11-30 | 2270 | 2016-12-07 | 4283.18 | 490 | 40187.5 | 47230.68 | 2016-12-01
42 | CAV040 | 2016-11-30 | 2270 | 2016-12-07 | 4283.18 | 490 | 40187.5 | 47230.68 | 2016-12-01
43 | CAV041 | 2016-11-30 | 2270 | 2016-12-07 | 4283.18 | 490 | 40187.5 | 47230.68 | 2016-12-01
44 | CAV042 | 2016-11-30 | 2270 | 2016-12-07 | 4283.18 | 490 | 40187.5 | 47230.68 | 2016-12-01
45 | CAV043 | 2016-12-16 | 2270 | 2017-01-11 | 4283.18 | 490 | 40187.5 | 47230.68 | 2017-02-22
46 | CAV044 | 2016-12-16 | 2270 | 2017-01-11 | 4283.18 | 490 | 40187.5 | 47230.68 | 2017-02-22
47 | CAV047 | 2016-12-16 | 2270 | 2017-01-11 | 4283.18 | 490 | 40187.5 | 47230.68 | 2017-02-22
48 | CAV048 | 2016-12-16 | 2270 | 2017-01-11 | 4283.18 | 490 | 40187.5 | 47230.68 | 2017-02-22
49 | CAV046 | 2017-01-11 | 2270 | 2017-01-19 | 4283.18 | 490 | 40187.5 | 47230.68 | 2017-02-22
50 | CAV050 | 2017-01-11 | 2270 | 2017-01-19 | 4283.18 | 490 | 40187.5 | 47230.68 | 2017-02-22
51 | CAV051 | 2017-01-11 | 2270 | 2017-01-19 | 4283.18 | 490 | 40187.5 | 47230.68 | 2017-02-22
52 | CAV052 | 2017-01-11 | 2270 | 2017-01-19 | 4283.18 | 490 | 40187.5 | 47230.68 | 2017-02-22
53 | CAV054 | 2017-02-16 | 1000 | 2017-02-17 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-03-20
54 | CAV055 | 2017-02-16 | 1000 | 2017-02-17 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-03-20
55 | CAV064 | 2017-02-27 | 1000 | 2017-02-27 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-03-20
56 | CAV066 | 2017-02-27 | 1000 | 2017-02-27 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-03-20
57 | CAV067 | 2017-02-27 | 1000 | 2017-02-27 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-03-20
58 | CAV068 | 2017-02-27 | 1000 | 2017-02-27 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-03-20
59 | CAV065 | 2017-03-09 | 1000 | 2017-02-15 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-04-21
60 | CAV069 | 2017-03-09 | 1000 | 2017-02-15 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-04-21
61 | CAV071 | 2017-03-09 | 1000 | 2017-02-15 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-04-21
62 | CAV070 | 2017-03-22 | 1000 | 2017-04-04 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-04-21
63 | CAV072 | 2017-03-22 | 1000 | 2017-04-04 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-04-21
64 | CAV073 | 2017-03-22 | 1000 | 2017-04-04 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-04-21
65 | CAV075 | 2017-03-22 | 1000 | 2017-04-04 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-04-21
66 | CAV074 | 2017-03-24 | 1000 | 2017-04-07 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-04-21
67 | CAV076 | 2017-03-24 | 1000 | 2017-04-07 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-04-21
68 | CAV077 | 2017-03-24 | 1000 | 2017-04-07 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-04-21
69 | CAV078 | 2017-03-24 | 1000 | 2017-04-07 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-04-21
70 | CAV079 | 2017-03-31 | 1000 | 2017-04-13 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-04-21
71 | CAV080 | 2017-03-31 | 1000 | 2017-04-13 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-04-21
72 | CAV082 | 2017-03-31 | 1000 | 2017-04-13 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-04-21
73 | CAV083 | 2017-03-31 | 1000 | 2017-04-13 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-04-21
74 | CAV081 | 2017-04-18 | 1000 | 2017-05-25 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-05-23
75 | CAV085 | 2017-04-18 | 1000 | 2017-05-25 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-05-23
76 | CAV086 | 2017-04-18 | 1000 | 2017-05-25 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-05-23
77 | CAV057 | 2017-04-28 | 1000 | 2017-05-05 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-05-23
78 | CAV061 | 2017-04-28 | 1000 | 2017-05-05 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-05-23
79 | CAV062 | 2017-04-28 | 1000 | 2017-05-05 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-05-23
80 | CAV063 | 2017-04-28 | 1000 | 2017-05-05 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-05-23
81 | CAV053 | 2017-05-10 | 1000 | 2017-05-17 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-05-23
82 | CAV056 | 2017-05-10 | 1000 | 2017-05-17 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-05-23
83 | CAV059 | 2017-05-10 | 1000 | 2017-05-17 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-05-23
84 | CAV060 | 2017-05-10 | 1000 | 2017-05-17 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-05-23
85 | CAV058 | 2017-06-07 | 1000 | 2017-07-11 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-06-30
86 | CAV091 | 2017-05-15 | 1000 | 2017-05-22 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-06-30
87 | CAV093 | 2017-05-15 | 1000 | 2017-05-22 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-06-30
88 | CAV098 |  | 1000 | 2017-05-22 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-06-30
89 | CAV084 | 2017-05-22 | 1000 | 2017-05-30 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-06-30
90 | CAV092 | 2017-05-22 | 1000 | 2017-05-30 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-06-30
91 | CAV094 | 2017-06-22 | 1000 | 2017-05-30 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-06-30
92 | CAV104 | 2017-05-22 | 1000 | 2017-05-30 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-06-30
93 | CAV103 | 2017-06-07 | 1000 | 2017-06-09 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-06-30
94 | CAV108 | 2017-06-02 | 1000 | 2017-06-09 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-06-30
95 | CAV110 | 2017-06-07 | 1000 | 2017-07-11 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-06-30
96 | CAV111 | 2017-06-28 | 1000 | 2017-07-10 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-06-30
97 | CAV087 | 2017-07-12 | 1000 | 2017-06-15 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-06-30
98 | CAV088 | 2017-06-28 | 1000 | 2017-07-10 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-06-30
99 | CAV089 | 2017-06-07 | 1000 | 2017-07-11 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-06-30
100 | CAV090 | 2017-05-29 | 1000 | 2017-06-15 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-06-30
101 | CAV109 | 2017-06-09 | 1000 | 2017-06-15 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-06-30
102 | CAV112 | 2017-06-09 | 1000 | 2017-06-15 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-06-30
103 | CAV097 | 2017-06-22 | 1000 | 2017-06-30 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-07-27
104 | CAV113 | 2017-06-22 | 1000 | 2017-06-30 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-07-27
105 | CAV114 | 2017-06-22 | 1000 | 2017-06-30 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-07-27
106 | CAV117 | 2017-06-22 | 1000 | 2017-06-30 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-07-27
107 | CAV099 | 2017-06-28 | 1000 | 2017-07-10 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-07-27
108 | CAV101 | 2017-06-28 | 1000 | 2017-07-10 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-07-27
109 | CAV102 | 2017-06-28 | 1000 | 2017-07-10 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-07-27
110 | CAV118 | 2017-06-22 | 1000 | 2017-07-10 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-07-27
111 | CAV100 | 2017-07-06 | 1000 | 2017-07-11 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-08-31
112 | CAV119 |  | 1000 | 2017-07-11 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-08-31
113 | CAV120 | 2017-06-28 | 1000 | 2017-07-11 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-08-31
114 | CAV121 | 2017-05-29 | 1000 | 2017-07-11 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-08-31
115 | CAV116 | 2017-05-29 | 1000 | 2017-08-01 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-08-31
116 | CAV122 | 2017-07-12 | 1000 | 2017-08-01 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-08-31
117 | CAV123 | 2017-07-12 | 1000 | 2017-08-01 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-08-31
118 | CAV124 | 2017-06-28 | 1000 | 2017-08-01 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-08-31
119 | CAV105 | 2017-07-21 | 1000 | 2017-08-04 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-08-31
120 | CAV107 | 2017-07-12 | 1000 | 2017-08-04 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-08-31
121 | CAV126 | 2017-07-21 | 1000 | 2017-08-04 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-08-31
122 | CAV127 | 2017-07-21 | 1000 | 2017-08-04 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-08-31
123 | CAV095 | 2017-07-21 | 1000 | 2017-08-30 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-09-01
124 | CAV096 |  | 1000 | 2017-08-30 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-09-01
125 | CAV106 |  | 1000 | 2017-08-30 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-09-01
126 | CAV125 |  | 1000 | 2017-08-30 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-09-01
127 | CAV128 |  | 1000 | 2017-08-30 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-09-01
128 | CAV129 |  | 1000 | 2017-08-30 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-09-01
129 | CAV130 |  | 1000 | 2017-08-30 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-09-01
130 | CAV131 |  | 1000 | 2017-08-30 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-09-01
131 | CAV132 |  | 1000 | 2017-08-30 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-09-01
132 | CAV133 |  | 1000 | 2017-08-30 | 4283.18 | 490 | 40187.5 | 45960.68 | 2017-09-01
| CAV115 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV134 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV135 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV136 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV137 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV138 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV139 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV140 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV141 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV142 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV143 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV144 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV145 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV146 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV147 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV148 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV149 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV150 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV150 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV151 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV151 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV152 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV152 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV153 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV153 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV154 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV154 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV155 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV155 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV156 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV156 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV157 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV157 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV158 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV158 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV159 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV159 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV160 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV160 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV161 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV161 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV162 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV162 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV163 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV163 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV164 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV164 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV165 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV165 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV166 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV166 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV167 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV167 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV168 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV168 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV169 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV169 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV170 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV170 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV171 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV172 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV173 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV174 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV175 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV176 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV177 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV178 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV179 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV180 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV181 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV182 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV183 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV184 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV185 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV186 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV187 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV188 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV189 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV190 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV191 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV192 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV193 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV194 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV195 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV196 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV197 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV198 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV199 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV200 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV201 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| CAV202 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
| 0 |  | 0 |  | 0 | 0 | 40187.5 | 40187.5
Total | 224 |  | 245240 |  | 479716.16 | 56840 | 9002000 | 9783796.16
Formulas:
Receipt Date = IF(CavityStatus[[#This Row],[Receipt Date]]<>0,CavityStatus[[#This Row],[Receipt Date]],"")
Accept Date = IF(CavityStatus[[#This Row],[Accept Date]]<>0,CavityStatus[[#This Row],[Accept Date]],"")
Actual Ship Date = IF(CavityStatus[[#This Row],[Actual Ship Date]]<>0,CavityStatus[[#This Row],[Actual Ship Date]],"")

## Incentivized Schedule
Cavity | Incentive Date | Incentive
1 | 4255200% | 20196
2 | 4255200% | 20196
3 | 4255200% | 20196
4 | 4255200% | 20196
5 | 4255200% | 20196
6 | 4255200% | 20196
7 | 4255200% | 20196
8 | 4255200% | 20196
9 | 4258300% | 20196
10 | 4258300% | 20196
11 | 4258300% | 20196
12 | 4258300% | 20196
13 | 4258300% | 20196
14 | 4258300% | 20196
15 | 4258300% | 20196
16 | 4258300% | 20196
17 | 4267600% | 5750
18 | 4267600% | 5750
19 | 4267600% | 5750
20 | 4267600% | 5750
21 | 4267600% | 5750
22 | 4267600% | 5750
23 | 4267600% | 5750
24 | 4267600% | 5750
25 | 4267600% | 5750
26 | 4267600% | 5750
27 | 4267600% | 5750
28 | 4267600% | 5750
29 | 4270400% | 5750
30 | 4270400% | 5750
31 | 4270400% | 5750
32 | 4270400% | 5750
33 | 4270400% | 5750
34 | 4270400% | 5750
35 | 4270400% | 5750
36 | 4270400% | 5750
37 | 4270400% | 5750
38 | 4270400% | 5750
39 | 4270400% | 5750
40 | 4270400% | 5750
41 | 4273200% | 2270
42 | 4273200% | 2270
43 | 4273200% | 2270
44 | 4273200% | 2270
45 | 4273200% | 2270
46 | 4273200% | 2270
47 | 4273200% | 2270
48 | 4273200% | 2270
49 | 4273200% | 2270
50 | 4273200% | 2270
51 | 4273200% | 2270
52 | 4273200% | 2270
53 | 4276000% | 1000
54 | 4276000% | 1000
55 | 4276000% | 1000
56 | 4276000% | 1000
57 | 4276000% | 1000
58 | 4276000% | 1000
59 | 4276000% | 1000
60 | 4276000% | 1000
61 | 4276000% | 1000
62 | 4276000% | 1000
63 | 4276000% | 1000
64 | 4276000% | 1000
65 | 4278800% | 1000
66 | 4278800% | 1000
67 | 4278800% | 1000
68 | 4278800% | 1000
69 | 4278800% | 1000
70 | 4278800% | 1000
71 | 4278800% | 1000
72 | 4278800% | 1000
73 | 4278800% | 1000
74 | 4278800% | 1000
75 | 4278800% | 1000
76 | 4278800% | 1000
77 | 4281600% | 1000
78 | 4281600% | 1000
79 | 4281600% | 1000
80 | 4281600% | 1000
81 | 4281600% | 1000
82 | 4281600% | 1000
83 | 4281600% | 1000
84 | 4281600% | 1000
85 | 4281600% | 1000
86 | 4281600% | 1000
87 | 4281600% | 1000
88 | 4281600% | 1000
89 | 4284400% | 1000
90 | 4284400% | 1000
91 | 4284400% | 1000
92 | 4284400% | 1000
93 | 4284400% | 1000
94 | 4284400% | 1000
95 | 4284400% | 1000
96 | 4284400% | 1000
97 | 4284400% | 1000
98 | 4284400% | 1000
99 | 4284400% | 1000
100 | 4284400% | 1000
101 | 4287200% | 1000
102 | 4287200% | 1000
103 | 4287200% | 1000
104 | 4287200% | 1000
105 | 4287200% | 1000
106 | 4287200% | 1000
107 | 4287200% | 1000
108 | 4287200% | 1000
109 | 4287200% | 1000
110 | 4287200% | 1000
111 | 4287200% | 1000
112 | 4287200% | 1000
113 | 4290000% | 1000
114 | 4290000% | 1000
115 | 4290000% | 1000
116 | 4290000% | 1000
117 | 4290000% | 1000
118 | 4290000% | 1000
119 | 4290000% | 1000
120 | 4290000% | 1000
121 | 4290000% | 1000
122 | 4290000% | 1000
123 | 4290000% | 1000
124 | 4290000% | 1000
125 | 4292800% | 1000
126 | 4292800% | 1000
127 | 4292800% | 1000
128 | 4292800% | 1000
129 | 4292800% | 1000
130 | 4292800% | 1000
131 | 4292800% | 1000
132 | 4292800% | 1000
133 | 4292800% | 1000
Total |  | 569376

## List
| Description | PO# | RI |  | EZ |  | Ship Date | Ship Loc | Material | Status | % Complete | 2016-11-01 | CavityMilestone
% Complete | Proof of equipment order furnace uprade | 1 | 1-4 | JLab 02 | 1-4 | FNAL 03 | 2018-01-29 | JLab | TD | Pre-Fab | 0% | 2016-12-01 | 40187.5
100% | Proof of completed furnace uprade | 2 | 5-8 | FNAL 02 | 5-8 | FNAL 03 | 2018-01-30 | FNAL | NX | HP1 | 2.5% | 2017-01-01
95% | Acceptance of Ni doping process - Cav 1 (of 2) | 3 | 9-12 | FNAL 02 | 9-12 | FNAL 05 | 2018-01-31 |  |  | HP2 | 5% | 2017-02-01
90% | Acceptance of Ni doping process - Cav 2 (of 2) | 4 | 13-16 | JLab 02 | 13-16 | FNAL 05 | 2018-02-01 |  |  | HP3 | 7.5% | 2017-03-01
85% | PH II: Mfg Drawings Accepted by JLab | 5 | 17-20 | FNAL 04 | 17-20 | JLab 04 | 2018-02-02 |  |  | Shipped | 10% | 2017-04-01
80% | PH II: FAs Mech Pre-fab (Deep Draw) | 6 | 21-24 | FNAL 04 | 21-24 | JLab 04 | 2018-02-05 |  |  | Received | 12.5% | 2017-05-01
75% | PH III: Mech Pre-Fab Cavities (9-72) | 7 | 25-28 | JLab 03 | 25-28 | JLab 06 | 2018-02-06 |  |  | Accepted | 15% | 2017-06-01
70% | PH III: Mech Pre-Fab Cavities (73-133) | 8 | 29-32 | JLab 03 | 29-32 | JLab 06 | 2018-02-07 |  |  | Complete | 17.5% | 2017-07-01
65% | PH II: First Articles Deliver & Accept (1-8) | 9 | 33-36 | JLab 05 | 33-36 | FNAL 06 | 2018-02-08 |  |  |  | 20% | 2017-08-01
60% | PH III: Deliver & Accept Cavities (9-12) | 10 | 37-40 | JLab 05 | 37-40 | FNAL 06 | 2018-02-09 |  |  |  | 22.5% | 2017-09-01
55% | PH III: Deliver & Accept Cavities (13-16) | 11 | 41-44 | JLab 07 | 41-44 | FNAL 07 | 2018-02-12 |  |  |  | 25% | 2017-10-01
50% | PH III: Deliver & Accept Cavities (17-20) | 12 | 45-48 | JLab 07 | 45-48 | FNAL 07 | 2018-02-13 |  |  |  | 27.5% | 2017-11-01
45% | PH III: Deliver & Accept Cavities (21-24) | 13 | 49-52 | FNAL 08 | 49-52 | FNAL 09 | 2018-02-14 |  |  |  | 30% | 2017-12-01
40% | PH III: Deliver & Accept Cavities (25-28) | 14 | 53-56 | FNAL 08 | 53-56 | FNAL 09 | 2018-02-15 |  |  |  | 32.5% | 2018-01-01
35% | PH III: Deliver & Accept Cavities (29-32) | 15 | 57-60 | FNAL 11 | 57-60 | FNAL 10 | 2018-02-16 |  |  |  | 35% | 2018-02-01
30% | PH III: Deliver & Accept Cavities (33-36) | 16 | 61-64 | FNAL 11 | 61-64 | FNAL 10 | 2018-02-19 |  |  |  | 37.5% | 2018-03-01
25% | PH III: Deliver & Accept Cavities (37-40) | 17 | 65-68 | JLab 09 | 65-68 | JLab 08 | 2018-02-20 |  |  |  | 40% | 2018-04-01
20% | PH III: Deliver & Accept Cavities (41-44) | 18 | 69-72 | JLab 09 | 69-72 | JLab 08 | 2018-02-21 |  |  |  | 42.5% | 2018-05-01
15% | PH III: Deliver & Accept Cavities (45-48) | 19 | 73-76 | JLab 11 | 73-76 | JLab 10 | 2018-02-22 |  |  |  | 45% | 2018-06-01
10% | PH III: Deliver & Accept Cavities (49-52) | 20 | 77-80 | JLab 11 | 77-80 | Jlab 10 | 2018-02-23 |  |  |  | 47.5% | 2018-07-01
5% | MOD 002: DESY Equip Refurbishment | 21 | 81-84 | JLab 14 | 81-84 | JLab 12 | 2018-02-26 |  |  |  | 50% | 2018-08-01
-3.192e-14% | MOD 002: DESY Equip Service & Support Costs | 22 | 85-88 | JLab 14 | 85-88 | JLab 12 |  |  |  |  | 52.5% | 2018-09-01
| MOD 003: Accel Shipment (1-16) Incentives (Max of $323,136) | 23 | 89-92 | JLab 15 | 89-92 | JLab 13 |  |  |  |  | 55%
| MOD 004: Incentives for Accelerated Production Deliveries | 24 | 93-96 | JLab 15 | 93-96 | JLab 13 |  |  |  |  | 57.5%
| MOD 005: DESY Equipment Lease ($9,200/ month) | 25 | 97-100 | FNAL 13 | 97-100 | FNAL 12 |  |  |  |  | 60%
| PH III: Deliver & Accept Cavities (53-56) | 26 | 101-104 | FNAL 13 | 101-104 | FNAL 12 |  |  |  |  | 62.5%
| PH III: Deliver & Accept Cavities (57-60) | 27 | 105-108 | FNAL 14 | 105-108 | JLab 16 |  |  |  |  | 65%
| PH III: Deliver & Accept Cavities (61-64) | 28 | 109-112 | FNAL 14 | 109-112 | JLab 16 |  |  |  |  | 67.5%
| PH III: Deliver & Accept Cavities (65-68) | 29 | 113-116 | FNAL 16 | 113-116 | JLab 17 |  |  |  |  | 70%
| PH III: Deliver & Accept Cavities (69-72) | 30 | 117-120 | FNAL 16 | 117-120 | JLab 17 |  |  |  |  | 72.5%
| PH III: Deliver & Accept Cavities (73-76) | 31 | 121-124 | FNAL 17 | 121-124 | FNAL 15 |  |  |  |  | 75%
| PH III: Deliver & Accept Cavities (77-80) | 32 | 125-128 | FNAL 17 | 125-128 | FNAL 15 |  |  |  |  | 77.5%
| PH III: Deliver & Accept Cavities (81-84) | 33 | 129-130 | Jlab 18 | 129-133 | Jlab 18 |  |  |  |  | 80%
| PH III: Deliver & Accept Cavities (85-88) | 34 | 131-133 | Jlab 18 | [6 empty] | 82.5%
| PH III: Deliver & Accept Cavities (89-92) | 35 | [8 empty] | 85%
| PH III: Deliver & Accept Cavities (93-96) | 36 | [8 empty] | 87.5%
| PH III: Deliver & Accept Cavities (97-100) | 37 | [8 empty] | 90%
| PH III: Deliver & Accept Cavities (101-104) | 38 | [8 empty] | 92.5%
| PH III: Deliver & Accept Cavities (105-108) | 39 | [8 empty] | 95%
| PH III: Deliver & Accept Cavities (109-112) | 40 | [8 empty] | 97.5%
| PH III: Deliver & Accept Cavities (113-116) | 41 | [8 empty] | 100%
| PH III: Deliver & Accept Cavities (117-120) | 42
| PH III: Deliver & Accept Cavities (121-124) | 43
| PH III: Deliver & Accept Cavities (125-128) | 44
| PH III: Deliver & Accept Cavities (129-133) | 45
| MOD 007: LCLS-II R&D Cavities (4) | 46
| MOD 008: CTM Spare Parts | #REF!
| MOD 009: Recipe Modification (21-133) ($4283.18/cavity) | #REF!
| MOD 010: Niobium Caps $490.00/ea (Cavs 17-133) | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
#REF!
Formulas:
Ship Date = WORKDAY([Ship Date, row above],1)