## Form
JSA / Jefferson Lab - DOE
PO Percent Complete Form
Appendix A
Vendor Name | RI Research Instruments | [5 empty] | PO with Peg Points? (Yes or No)
PO Number | 15-C0587 |  |  | Buyer | Laney | Complete through | 2018-02-28
(Date)
PO Line # | Percent Complete | Completed Peg Point (X) |  | Summary of Work (only if less than 100%)
1 | 100% |  |  | Proof of equipment order furnace uprade
2 | 100% |  |  | Proof of completed furnace uprade
3 | 100% |  |  | Acceptance of Ni doping process - Cav 1 (of 2)
4 | 100% |  |  | Acceptance of Ni doping process - Cav 2 (of 2)
5 | 100% |  |  | PH II: Mfg Drawings Accepted by JLab
6 | 100% |  |  | PH II: FAs Mech Pre-fab (Deep Draw)
7 | 100% |  |  | PH III: Mech Pre-Fab Cavities (9-72)
8 | 100% |  |  | PH III: Mech Pre-Fab Cavities (73-133)
9 | 100% |  |  | PH II: First Articles Deliver & Accept (1-8)
10 | 100% |  |  | PH III: Deliver & Accept Cavities (9-12)
11 | 100% |  |  | PH III: Deliver & Accept Cavities (13-16)
12 | 100% |  |  | PH III: Deliver & Accept Cavities (17-20)
13 | 100% |  |  | PH III: Deliver & Accept Cavities (21-24)
14 | 100% |  |  | PH III: Deliver & Accept Cavities (25-28)
15 | 100% |  |  | PH III: Deliver & Accept Cavities (29-32)
16 | 100% |  |  | PH III: Deliver & Accept Cavities (33-36)
17 | 100% |  |  | PH III: Deliver & Accept Cavities (37-40)
18 | 100% |  |  | PH III: Deliver & Accept Cavities (41-44)
19 | 100% |  |  | PH III: Deliver & Accept Cavities (45-48)
20 | 100% |  |  | PH III: Deliver & Accept Cavities (49-52)
21 | 100% |  |  | MOD 002: DESY Equip Refurbishment
22 | 55.3% |  |  | MOD 002: DESY Equip Service & Support Costs
23 | 100% |  |  | MOD 003: Accel Shipment (1-16) Incentives (Max of $323,136)
24 | 99.6% |  |  | MOD 004: Incentives for Accelerated Production Deliveries
25 | 100% |  |  | MOD 005: DESY Equipment Lease ($9,200/ month)
26 | 100% |  |  | PH III: Deliver & Accept Cavities (53-56)
27 | 100% |  |  | PH III: Deliver & Accept Cavities (57-60)
28 | 100% |  |  | PH III: Deliver & Accept Cavities (61-64)
29 | 100% |  |  | PH III: Deliver & Accept Cavities (65-68)
30 | 100% |  |  | PH III: Deliver & Accept Cavities (69-72)
31 | 100% |  |  | PH III: Deliver & Accept Cavities (73-76)
32 | 100% |  |  | PH III: Deliver & Accept Cavities (77-80)
33 | 100% |  |  | PH III: Deliver & Accept Cavities (81-84)
34 | 100% |  |  | PH III: Deliver & Accept Cavities (85-88)
35 | 100% |  |  | PH III: Deliver & Accept Cavities (89-92)
36 | 100% |  |  | PH III: Deliver & Accept Cavities (93-96)
37 | 100% |  |  | PH III: Deliver & Accept Cavities (97-100)
38 | 100% |  |  | PH III: Deliver & Accept Cavities (101-104)
39 | 100% |  |  | PH III: Deliver & Accept Cavities (105-108)
40 | 100% |  |  | PH III: Deliver & Accept Cavities (109-112)
41 | 100% |  |  | PH III: Deliver & Accept Cavities (113-116)
42 | 100% |  |  | PH III: Deliver & Accept Cavities (117-120)
43 | 100% |  |  | PH III: Deliver & Accept Cavities (121-124)
44 | 100% |  |  | PH III: Deliver & Accept Cavities (125-128)
45 | 100% |  |  | PH III: Deliver & Accept Cavities (129-133)
46 | 100% |  |  | MOD 007: LCLS-II R&D Cavities (4)
47 | 100% |  |  | MOD 008: CTM Spare Parts
48 | 100% |  |  | MOD 009: Recipe Modification (21-133) ($4283.18/cavity)
49 | 99.4% |  |  | MOD 010: Niobium Caps $490.00/ea (Cavs 17-133)
50 | 100% |  |  | MOD 010: Ningxia Material Sorting
51 | 100% |  |  | MOD 011: Optional Cavities 1-8
52 | 100% |  |  | MOD 012: DESY Testing 4X RF Tests
53 | 26.84% |  |  | MOD 012: Add DESY Testing Costs (Not to Exceed)
54 | 100% |  |  | MOD013-32+3: Material Supply, 1st lot
55 | 100% |  |  | MOD013-32+3: Material Supply, 2nd lot
56 | 100% |  |  | MOD013-32+3: DESY QA of 1st material lot
57 | 100% |  |  | MOD013-32+3: DESY Q of 2nd material lot
58 | 0% |  |  | MOD013-32+3: Deliver & Accept 4 Cavities
59 | 0% |  |  | MOD013-32+3: Deliver & Accept 4 Cavities
60 | 0% |  |  | MOD013-32+3: Deliver & Accept 4 Cavities
61 | 0% |  |  | MOD013-32+3: Deliver & Accept 4 Cavities
62 | 0% |  |  | MOD013-32+3: Deliver & Accept 4 Cavities
63 | 0% |  |  | MOD013-32+3: Deliver & Accept 4 Cavities
64 | 0% |  |  | MOD013-32+3: Deliver & Accept 4 Cavities
65 | 0% |  |  | MOD013-32+3: Deliver & Accept 4 Cavities
66 | 0% |  |  | MOD013-32+3: Deliver & Accept 2 Single Cell Cavities
67 | 49.78% |  |  | MOD013-32+3: Lease/Maintenance DESY Equipment
68 | 100% |  |  | MOD013-Add Mat'l: Material Supply, 1st lot
69 | 100% |  |  | MOD013-Add Mat'l: DESY QA of 1st material lot
70 | 100% |  |  | MOD013-Add Mat'l: Material Supply, 2nd lot
71 | 0% |  |  | MOD013-Add Mat'l: DESY QA of 2nd material lot
72 | 0% |  |  | MOD013-Add Mat'l: Material Supply, 3rd lot
73 | 0% |  |  | MOD013-Add Mat'l: DESY QA of 3rd material lot
74 | 0% |  |  | MOD013-Add Mat'l: Material Supply, 4th lot
75 | 0% |  |  | MOD013-Add Mat'l: DESY QA of 4th material lot
76 | 0% |  |  | MOD013-Add Mat'l: Storage of material for up to 6 months
77 | 0% |  |  | MOD013-Add Mat'l: Package and air shipment of material
78 | 100% |  |  | MOD013-Add Mat'l: Deliver & Accept 1-Cell Cavites (Lot 1)
79 | 50% |  |  | MOD013-Add Mat'l: Deliver & Accept 1-Cell Cavites (Lot 2)
80 | 0% |  |  | MOD013-Add Mat'l: Deliver & Accept 1-Cell Cavites (Lot 3)
81 | 0% |  |  | MOD013-Add Mat'l: Deliver & Accept 1-Cell Cavites (Lot 4)
82 | 100% |  |  | MOD014: Supply & QC of 320 TD Sheets
83 | 100% |  |  | MOD015: Acceptance of Optional Cavities (9-16)
84 | 100% |  |  | MOD015: Incentive- Accelerated Delivery $5K/ cavities (9-16)
85 | 100% |  |  | MOD016: Transport Excess Zanon Cavity Materials to RI
86 | 100% |  |  | MOD016: Delivery & Accept TD Cavities (Zanon Material 1-4 of 18)
87 | 100% |  |  | MOD016: Delivery & Accept 4 TD Cavities (Zanon Material 5-8 of 18)
88 | 100% |  |  | MOD016: Delivery & Accept 4 TD Cavities (Zanon Material 9-12 of 18)
89 | 100% |  |  | MOD016: Delivery & Accept 4 TD Cavities (Zanon Material 13-16 of 18)
90 | 100% |  |  | MOD016: Delivery & Accept 2 TD Cavities (Zanon Material 17-18 of 18)
91 | 0% |  |  | MOD019: Delivery & Accept Optional 3
92 | 0% |  |  | MOD020: Heat Treatment of Lot B
93 | 0% |  |  | MOD020: Bellow Tank Replacement
94 | 0% |  |  | MOD021: Lease/Maintenance of DESY
95 | 0%
96 | 0%
97 | 0%
98 | 0%
99 | 0%
100 | 0%
101 | 0%
102 | 0%
103 | 0%
104 | 0%
105 | 0%
106 | 0%
Vendor Technical Representative Contacted:
|  |  | Name |  |  |  |  | Date
Jlab Control Account Manager (CAM): |  |  |  |  | Eden Evans for Ed Daly |  |  | 2018-02-28
[6 empty] | Name |  | Date
Below for use by Accounting/Shipping & Receiving Only
Accounting or Shipping & Receiving Entered By:
Date
Data Entry Verified By:
Date

## Process
JSA / Jefferson Lab - DOE
PO Accrual Form
Procedure
A Subcontract Purchase Order (PO) is a service type PO with loosely defined scheduled deliverables and/or variable amounts. A Peg Point PO has specified scheduled deliverable dates to be completed for a specified amount. Note Quantities Received if items did not come through Shipping & Receiving (e.g. items shipped to another vendor).
Complete this form by the 2nd work day after month end if an invoice has been not been approved by the SOTR or CAM for work completed through the end of the month. NOTE: This form can still be completed by the 2nd work day of the month to ensure the accrual is processed.
SOTR or CAM contacts a vendor technical representative for an evaluation of the percent of work completed (or quantity received by vendor). This can be done either verbally or via email.
OR
SOTR or CAM has an objective way to measure the perecent of work complete (e.g. Standardize monthly payment, using schedule of values to determine value of work complete)
Required information - Vendor Name, indicate if PO is a Peg Point type PO or not, PO #, Buyer, Complete through date (usually the end of the month), PO Line #, Percent complete (or quantity received by vendor), a short Summary of Work performed provided by the Vendor Technical Representative that supports the percent complete if less than 100%, the name of the Vendor Technical Representative contacted, and the CAM name.
The SOTR or CAM will submit a PO Accrual Form by the 2nd working day following the end of the month affected for work that has been completed. This allows time for Accounting to process an accrual for the month end closing. Reminder if PO is for Peg Points, the peg point must be fully complete before claiming it.
Submit the completed form with all the information via email to evpo@jlab.org. The file name of the spreadsheet attached to the email should always include the PO# and the letters 'S&R' if it is a Peg Point type PO or if items were received by did not go through JLab's Shipping and Receiving Department. File name examples: Peg Point Type PO 08-C5413 S&R, Subcontract Type PO 08-A2659. This email will forward the form automatically to personnel in Procurement, Shipping & Receiving, CFO, and PMO.
If the PO is a Subcontract type PO, the SOTR or CAM will still be required to sign all invoices received at JLab from the vendor up since this was an estimate. An approved invoice by the SOTR or CAM can also be used as basis for the percent of work complete.
If the PO is a Peg Point type PO or material has been received, Shipping & Receiving will use this form to enter the information into the Costpoint Financial System. No additional invoice approvals will be required since the SOTR or CAM already indicated the work was complete. An approved invoice by the SOTR or CAM can also be used as basis for the percent of work complete without having to complete this form.
If a previous percent complete was submitted and subsequently determined to be in error, adjust the percent complete to correct the error. Add an explanatory note to support the adjustment.

## Accting USE Data Entry Form
JSA / Jefferson Lab - DOE
Data Entry Update Subcontract PO Percent Complete
Appendix B
Vendor Name | RI Research Instruments | [5 empty] | Percent complete thru |  |  | 2018-02-28
(Date)
PO Number | 15-C0587 | [6 empty] | OR
Invoice Number
PO Line # | Percent Complete |  | PO Line Total | = | Completed Work Amt | Completed Work Amt | - | Eligible for Voucher Amt | - | Prev Vouchered Amount | = | Completed Work Retention Amt | Current Month Accrual
1 | 100% | X | 157470 | = | 157470 | 157470 | - | 0 | - | 157470 | = | 0
2 | 100% | X | 157470 | = | 157470 | 157470 | - | 0 | - | 157470 | = | 0
3 | 100% | X | 104980 | = | 104980 | 104980 | - | 0 | - | 104980 | = | 0
4 | 100% | X | 104980 | = | 104980 | 104980 | - | 0 | - | 104980 | = | 0
5 | 100% | X | 317520 | = | 317520 | 317520 | - | 0 | - | 317520 | = | 0
6 | 100% | X | 423360 | = | 423360 | 423360 | - | 0 | - | 423360 | = | 0
7 | 100% | X | 1607500 | = | 1607500 | 1607500 | - | 0 | - | 1607500 | = | 0
8 | 100% | X | 1446750 | = | 1446750 | 1446750 | - | 0 | - | 1446750 | = | 0
9 | 100% | X | 317520 | = | 317520 | 317520 | - | 0 | - | 317520 | = | 0
10 | 100% | X | 160750 | = | 160750 | 160750 | - | 0 | - | 160750 | = | 0
11 | 100% | X | 160750 | = | 160750 | 160750 | - | 0 | - | 160750 | = | 0
12 | 100% | X | 160750 | = | 160750 | 160750 | - | 0 | - | 160750 | = | 0
13 | 100% | X | 160750 | = | 160750 | 160750 | - | 0 | - | 160750 | = | 0
14 | 100% | X | 160750 | = | 160750 | 160750 | - | 0 | - | 160750 | = | 0
15 | 100% | X | 160750 | = | 160750 | 160750 | - | 0 | - | 160750 | = | 0
16 | 100% | X | 160750 | = | 160750 | 160750 | - | 0 | - | 160750 | = | 0
17 | 100% | X | 160750 | = | 160750 | 160750 | - | 0 | - | 160750 | = | 0
18 | 100% | X | 160750 | = | 160750 | 160750 | - | 0 | - | 160750 | = | 0
19 | 100% | X | 160750 | = | 160750 | 160750 | - | 0 | - | 160750 | = | 0
20 | 100% | X | 160750 | = | 160750 | 160750 | - | 0 | - | 160750 | = | 0
21 | 100% | X | 90800 | = | 90800 | 90800 | - | 0 | - | 90800 | = | 0
22 | 55.3% | X | 49696 | = | 27481.89 | 27481.89 | - | 22214.11 | - | 27481.89 | = | -22214.11
23 | 100% | X | 315800.81 | = | 315800.81 | 315800.81 | - | 0 | - | 315800.81 | = | 0
24 | 99.6% | X | 246240 | = | 245255.04 | 245255.04 | - | 984.96 | - | 245255.04 | = | -984.96
25 | 100% | X | 147200 | = | 147200 | 147200 | - | 0 | - | 147200 | = | 0
26 | 100% | X | 160750 | = | 160750 | 160750 | - | 0 | - | 160750 | = | 0
27 | 100% | X | 160750 | = | 160750 | 160750 | - | 0 | - | 160750 | = | 0
28 | 100% | X | 160750 | = | 160750 | 160750 | - | 0 | - | 160750 | = | 0
29 | 100% | X | 160750 | = | 160750 | 160750 | - | 0 | - | 160750 | = | 0
30 | 100% | X | 160750 | = | 160750 | 160750 | - | 0 | - | 160750 | = | 0
31 | 100% | X | 160750 | = | 160750 | 160750 | - | 0 | - | 160750 | = | 0
32 | 100% | X | 160750 | = | 160750 | 160750 | - | 0 | - | 160750 | = | 0
33 | 100% | X | 160750 | = | 160750 | 160750 | - | 0 | - | 160750 | = | 0
34 | 100% | X | 160750 | = | 160750 | 160750 | - | 0 | - | 160750 | = | 0
35 | 100% | X | 160750 | = | 160750 | 160750 | - | 0 | - | 160750 | = | 0
36 | 100% | X | 160750 | = | 160750 | 160750 | - | 0 | - | 160750 | = | 0
37 | 100% | X | 160750 | = | 160750 | 160750 | - | 0 | - | 160750 | = | 0
38 | 100% | X | 160750 | = | 160750 | 160750 | - | 0 | - | 160750 | = | 0
39 | 100% | X | 160750 | = | 160750 | 160750 | - | 0 | - | 160750 | = | 0
40 | 100% | X | 160750 | = | 160750 | 160750 | - | 0 | - | 160750 | = | 0
41 | 100% | X | 160750 | = | 160750 | 160750 | - | 0 | - | 160750 | = | 0
42 | 100% | X | 160750 | = | 160750 | 160750 | - | 0 | - | 160750 | = | 0
43 | 100% | X | 160750 | = | 160750 | 160750 | - | 0 | - | 160750 | = | 0
44 | 100% | X | 160750 | = | 160750 | 160750 | - | 0 | - | 160750 | = | 0
45 | 100% | X | 160750 | = | 160750 | 160750 | - | 0 | - | 160750 | = | 0
46 | 100% | X | 38000 | = | 38000 | 38000 | - | 0 | - | 38000 | = | 0
47 | 100% | X | 71500 | = | 71500 | 71500 | - | 0 | - | 71500 | = | 0
48 | 100% | X | 484000 | = | 484000 | 484000 | - | 0 | - | 484000 | = | 0
49 | 99.4% | X | 57800 | = | 57453.2 | 57453.2 | - | 346.8 | - | 57453.2 | = | -346.8
50 | 100% | X | 21335 | = | 21335 | 21335 | - | 0 | - | 21335 | = | 0
51 | 100% | X | 499817.6 | = | 499817.6 | 499817.6 | - | 0 | - | 499817.6 | = | 0
52 | 100% | X | 129500 | = | 129500 | 129500 | - | 0 | - | 129500 | = | 0
53 | 26.84% | X | 58240 | = | 15631.62 | 15631.62 | - | 42608.38 | - | 15631.62 | = | -42608.38
54 | 100% | X | 658681 | = | 658681 | 658681 | - | 0 | - | 658681 | = | 0
55 | 100% | X | 658681 | = | 658681 | 658681 | - | 0 | - | 658681 | = | 0
56 | 100% | X | 69750 | = | 69750 | 69750 | - | 0 | - | 69750 | = | 0
57 | 100% | X | 69750 | = | 69750 | 69750 | - | 0 | - | 69750 | = | 0
58 | 0% | X | 299200 | = | 0 | 0 | - | 299200 | - | 0 | = | -299200
59 | 0% | X | 299200 | = | 0 | 0 | - | 299200 | - | 0 | = | -299200
60 | 0% | X | 299200 | = | 0 | 0 | - | 299200 | - | 0 | = | -299200
61 | 0% | X | 299200 | = | 0 | 0 | - | 299200 | - | 0 | = | -299200
62 | 0% | X | 299200 | = | 0 | 0 | - | 299200 | - | 0 | = | -299200
63 | 0% | X | 299200 | = | 0 | 0 | - | 299200 | - | 0 | = | -299200
64 | 0% | X | 299200 | = | 0 | 0 | - | 299200 | - | 0 | = | -299200
65 | 0% | X | 299200 | = | 0 | 0 | - | 299200 | - | 0 | = | -299200
66 | 0% | X | 23400 | = | 0 | 0 | - | 23400 | - | 0 | = | -23400
67 | 49.78% | X | 93000 | = | 46300 | 46300 | - | 46700 | - | 37100 | = | -37500 | 9200
68 | 100% | X | 1299466.75 | = | 1299466.75 | 1299466.75 | - | 0 | - | 1299466.75 | = | 0
69 | 100% | X | 135725 | = | 135725 | 135725 | - | 0 | - | 135725 | = | 0
70 | 100% | X | 1299466.75 | = | 1299466.75 | 1299466.75 | - | 0 | - | 0 | = | 1299466.75 | 1299466.75
71 | 0% | X | 135725 | = | 0 | 0 | - | 135725 | - | 0 | = | -135725
72 | 0% | X | 1299466.75 | = | 0 | 0 | - | 1299466.75 | - | 0 | = | -1299466.75
73 | 0% | X | 135725 | = | 0 | 0 | - | 135725 | - | 0 | = | -135725
74 | 0% | X | 1299466.75 | = | 0 | 0 | - | 1299466.75 | - | 0 | = | -1299466.75
75 | 0% | X | 135725 | = | 0 | 0 | - | 135725 | - | 0 | = | -135725
76 | 0% | X | 4500 | = | 0 | 0 | - | 4500 | - | 0 | = | -4500
77 | 0% | X | 52300 | = | 0 | 0 | - | 52300 | - | 0 | = | -52300
78 | 100% | X | 19400 | = | 19400 | 19400 | - | 0 | - | 0 | = | 19400 | 19400
79 | 50% | X | 19400 | = | 9700 | 9700 | - | 9700 | - | 0 | = | 0 | 9700
80 | 0% | X | 19400 | = | 0 | 0 | - | 19400 | - | 0 | = | -19400
81 | 0% | X | 19400 | = | 0 | 0 | - | 19400 | - | 0 | = | -19400
82 | 100% | X | 492989 | = | 492989 | 492989 | - | 0 | - | 492989 | = | 0
83 | 100% | X | 499816 | = | 499816 | 499816 | - | 0 | - | 499816 | = | 0
84 | 100% | X | 40000 | = | 40000 | 40000 | - | 0 | - | 40000 | = | 0
85 | 100% | X | 6150 | = | 6150 | 6150 | - | 0 | - | 6150 | = | 0
86 | 100% | X | 299200 | = | 299200 | 299200 | - | 0 | - | 299200 | = | 0
87 | 100% | X | 299200 | = | 299200 | 299200 | - | 0 | - | 299200 | = | 0
88 | 100% | X | 299200 | = | 299200 | 299200 | - | 0 | - | 299200 | = | 0
89 | 100% | X | 299200 | = | 299200 | 299200 | - | 0 | - | 149600 | = | 149600 | 149600
90 | 100% | X | 149600 | = | 149600 | 149600 | - | 0 | - | 149600 | = | 0
91 | 0% | X | 224400 | = | 0 | 0 | - | 224400 | - | 0 | = | -224400
92 | 0% | X | 13800 | = | 0 | 0 | - | 13800 | - | 0 | = | -13800
93 | 0% | X | 24600 | = | 0 | 0 | - | 24600 | - | 0 | = | -24600
94 | 0% | X | 93000 | = | 0 | 0 | - | 93000 | - | 0 | = | -93000
Procurement Entered By: ________________________________________________________________
Date
Procurement Data Entry Verified By: _______________________________________________________
Date