## Form
JSA / Jefferson Lab - DOE
PO Percent Complete Form
Appendix A
Vendor Name | Etorre Zanon | [5 empty] | PO with Peg Points? (Yes or No)
PO Number | 15-C0753 |  |  | Buyer | Laney | Complete through | 2019-01-31
(Date)
PO Line # | Percent Complete | Completed Peg Point (X) |  | Summary of Work (only if less than 100%)
1 | 100% |  |  | Proof of Complete Furnace Upgrade
2 | 100% |  |  | JLab Acceptance of nitrogen doping process - Cavity 1 (of 2)
3 | 100% |  |  | JLab Acceptance of nitrogen doping process - Cavity 2 (of 2)
4 | 100% |  |  | Manufacturing Drawings released and accepted by JLab
5 | 100% |  |  | First Article Cavities Mechanical Pre-fab
6 | 100% |  |  | First Articles (1-8) Delivered and Accepted by JLab
7 | 100% |  |  | Production Cavities (9-72) Mechanical Pre-Fabrication
8 | 100% |  |  | Production Cavities (73-133) Mechanical Pre-Fabrication
9 | 100% |  |  | Delivery & Acceptance of Cavities (9-12)
10 | 100% |  |  | Delivery & Acceptance of Cavities (13-16)
11 | 100% |  |  | Delivery & Acceptance of Cavities (17-20)
12 | 100% |  |  | Delivery & Acceptance of Cavities (21-24)
13 | 100% |  |  | Delivery & Acceptance of Cavities (25-28)
14 | 100% |  |  | Delivery & Acceptance of Cavities (29-32)
15 | 100% |  |  | Delivery & Acceptance of Cavities (33-36)
16 | 100% |  |  | Delivery & Acceptance of Cavities (37-40)
17 | 100% |  |  | Delivery & Acceptance of Cavities (41-44)
18 | 100% |  |  | Delivery & Acceptance of Cavities (45-48)
19 | 100% |  |  | Delivery & Acceptance of Cavities (49-52)
20 | 100% |  |  | Delivery & Acceptance of Cavities (53-56)
21 | 100% |  |  | Delivery & Acceptance of Cavities (57-60)
22 | 100% |  |  | Delivery & Acceptance of Cavities (61-64)
23 | 84.48% |  |  | MOD 002: Support of DESY EQUIPMENT ($7,621/mo)
24 | 56.34% |  |  | MOD 003: First Article Incentives
25 | 100% |  |  | MOD 004: Right Angle Valves
26 | 100% |  |  | MOD 005: CTM Spare Parts
27 | 100% |  |  | Delivery & Acceptance of Cavities (65-68)
28 | 100% |  |  | Delivery & Acceptance of Cavities (69-72)
29 | 100% |  |  | MOD 006: Recipe Modification (Cavities 9-16)
30 | 100% |  |  | MOD 007: Recipe Mod (Cavs 17-133) $3547.1/ea
31 | 100% |  |  | MOD 008: Right Angle Valves
32 | 100% |  |  | MOD 009 Shipping and Customs
33 | 100% |  |  | MOD 009 Shipping and Customs
34 | 100% |  |  | MOD 011 BCP Rework
35 | 100% |  |  | Delivery & Acceptance of Cavities (73-76)
36 | 100% |  |  | Delivery & Acceptance of Cavities (77-80)
37 | 100% |  |  | Delivery & Acceptance of Cavities (81-84)
38 | 100% |  |  | Delivery & Acceptance of Cavities (85-88)
39 | 100% |  |  | Delivery & Acceptance of Cavities (89-92)
40 | 100% |  |  | Delivery & Acceptance of Cavities (93-96)
41 | 100% |  |  | Delivery & Acceptance of Cavities (97-100)
42 | 100% |  |  | Delivery & Acceptance of Cavities (101-104)
43 | 100% |  |  | Delivery & Acceptance of Cavities (105-108)
44 | 100% |  |  | Delivery & Acceptance of Cavities (109-112)
45 | 100% |  |  | Delivery & Acceptance of Cavities (113-116)
46 | 100% |  |  | Delivery & Acceptance of Cavities (117-120)
47 | 100% |  |  | Delivery & Acceptance of Cavities (121-124)
48 | 100% |  |  | Delivery & Acceptance of Cavities (125-128)
49 | 100% |  |  | Delivery & Acceptance of Cavities (129-133)
50 | 100% |  |  | Performance Incentives
51 | 100% |  |  | MOD 015: Misc Changes and Lease Funding - Mfg Changes
52 | 100% |  |  | MOD 015: Misc Changes and Lease Funding - DESY Lease
53 | 100% |  |  | MOD 015: Misc Changes and Lease Funding - CRN-EZ-001
54 | 100% |  |  | MOD 015: Misc Changes and Lease Funding - CRN-EZ-011
55 | 100% |  |  | MOD 015: Misc Changes and Lease Funding - CRN-EZ-015
56 | 100% |  |  | MOD 015: Misc Changes and Lease Funding - CRN-EZ-014
57 | 100% |  |  | MOD 016: 4 Cavities - Delivery and Acceptance of 134 - 137
58 | 100% |  |  | MOD 016: 4 Cavities - Delivery and Acceptance of 138 - 141
59 | 0% |  |  | MOD 016: 4 Cavities - Delivery and Acceptance of 142 - 145
60 | 0% |  |  | MOD 016: 4 Cavities - Delivery and Acceptance of 146 - 149
61 | 0% |  |  | MOD 016: 4 Cavities - Delivery and Acceptance of 150 - 153
62 | 0% |  |  | MOD 016: 4 Cavities - Delivery and Acceptance of 154 - 157
63 | 0% |  |  | MOD 016: 4 Cavities - Delivery and Acceptance of 158 - 161
64 | 0% |  |  | MOD 016: 4 Cavities - Delivery and Acceptance of 162 - 165
65 | 100% |  |  | MOD 016: Tooling and Hardware Set-Up for Single Cell Processing
66 | 100% |  |  | MOD 016: Single Cell Manufacture and Processing (7 each)
67 | 100% |  |  | MOD 016: Delivery of Single Cell Cavities (7 each)
68 | 100% |  |  | MOD 017: Realign Line Items In The Award
69 | 0% |  |  | MOD 018: Cavity 249
70 | 0% |  |  | MOD 018: Cavity 229
71 | 100% |  |  | MOD 018: Cavity 244
72 | 0% |  |  | MOD 018: Cavity 238
73 | 0% |  |  | MOD 019: Radial Tuning Cavity 226
74 | 100% |  |  | MOD 020: Exchange Rate Adjustments
Vendor Technical Representative Contacted:
|  |  | Name |  |  |  |  | Date
Jlab Control Account Manager (CAM): |  |  |  |  | Eden Evans for Ed Daly |  |  | 2019-01-31
[6 empty] | Name |  | Date
Below for use by Accounting/Shipping & Receiving Only
Accounting or Shipping & Receiving Entered By:
Date
Data Entry Verified By:
Date

## Process
JSA / Jefferson Lab - DOE
PO Accrual Form
Procedure
A Subcontract Purchase Order (PO) is a service type PO with loosely defined scheduled deliverables and/or variable amounts. A Peg Point PO has specified scheduled deliverable dates to be completed for a specified amount. Note Quantities Received if items did not come through Shipping & Receiving (e.g. items shipped to another vendor).
Complete this form by the 2nd work day after month end if an invoice has been not been approved by the SOTR or CAM for work completed through the end of the month. NOTE: This form can still be completed by the 2nd work day of the month to ensure the accrual is processed.
SOTR or CAM contacts a vendor technical representative for an evaluation of the percent of work completed (or quantity received by vendor). This can be done either verbally or via email.
OR
SOTR or CAM has an objective way to measure the perecent of work complete (e.g. Standardize monthly payment, using schedule of values to determine value of work complete)
Required information - Vendor Name, indicate if PO is a Peg Point type PO or not, PO #, Buyer, Complete through date (usually the end of the month), PO Line #, Percent complete (or quantity received by vendor), a short Summary of Work performed provided by the Vendor Technical Representative that supports the percent complete if less than 100%, the name of the Vendor Technical Representative contacted, and the CAM name.
The SOTR or CAM will submit a PO Accrual Form by the 2nd working day following the end of the month affected for work that has been completed. This allows time for Accounting to process an accrual for the month end closing. Reminder if PO is for Peg Points, the peg point must be fully complete before claiming it.
Submit the completed form with all the information via email to evpo@jlab.org. The file name of the spreadsheet attached to the email should always include the PO# and the letters 'S&R' if it is a Peg Point type PO or if items were received by did not go through JLab's Shipping and Receiving Department. File name examples: Peg Point Type PO 08-C5413 S&R, Subcontract Type PO 08-A2659. This email will forward the form automatically to personnel in Procurement, Shipping & Receiving, CFO, and PMO.
If the PO is a Subcontract type PO, the SOTR or CAM will still be required to sign all invoices received at JLab from the vendor up since this was an estimate. An approved invoice by the SOTR or CAM can also be used as basis for the percent of work complete.
If the PO is a Peg Point type PO or material has been received, Shipping & Receiving will use this form to enter the information into the Costpoint Financial System. No additional invoice approvals will be required since the SOTR or CAM already indicated the work was complete. An approved invoice by the SOTR or CAM can also be used as basis for the percent of work complete without having to complete this form.
If a previous percent complete was submitted and subsequently determined to be in error, adjust the percent complete to correct the error. Add an explanatory note to support the adjustment.

## Accting USE Data Entry Form
JSA / Jefferson Lab - DOE
Data Entry Update Subcontract PO Percent Complete
Appendix B
Vendor Name | Etorre Zanon | [5 empty] | Percent complete thru |  |  | 2019-01-31
(Date)
PO Number | 15-C0753 | [6 empty] | OR
Invoice Number
PO Line # | Percent Complete |  | PO Line Total | = | Completed Work Amt | Completed Work Amt | - | Eligible for Voucher Amt | - | Prev Vouchered Amount | = | Completed Work Retention Amt | Current Month Accrual
1 | 100% | X | 27286.996 | = | 27287 | 27287 | - | -0.004 | - | 27287 | = | 0.004
2 | 100% | X | 54573.992 | = | 54573.992 | 54573.992 | - | 0 | - | 54573.992 | = | 0
3 | 100% | X | 54573.992 | = | 54573.992 | 54573.992 | - | 0 | - | 54573.992 | = | 0
4 | 100% | X | 114938.04 | = | 114938.04 | 114938.04 | - | 0 | - | 114938.04 | = | 0
5 | 100% | X | 229876.08 | = | 229876.08 | 229876.08 | - | 0 | - | 229876.08 | = | 0
6 | 100% | X | 229876.08 | = | 229876.08 | 229876.08 | - | 0 | - | 229876.08 | = | 0
7 | 100% | X | 777203.75 | = | 777203.75 | 777203.75 | - | 0 | - | 777203.75 | = | 0
8 | 100% | X | 2176170.5 | = | 2176170.5 | 2176170.5 | - | 0 | - | 2176170.5 | = | 0
9 | 100% | X | 233161.13 | = | 233161.13 | 233161.13 | - | 0 | - | 233161.13 | = | 0
10 | 100% | X | 233161.13 | = | 233161.13 | 233161.13 | - | 0 | - | 233161.13 | = | 0
11 | 100% | X | 233161.13 | = | 233161.13 | 233161.13 | - | 0 | - | 233161.13 | = | 0
12 | 100% | X | 233161.13 | = | 233161.13 | 233161.13 | - | 0 | - | 233161.13 | = | 0
13 | 100% | X | 233161.13 | = | 233161.13 | 233161.13 | - | 0 | - | 233161.13 | = | 0
14 | 100% | X | 233161.13 | = | 233161.13 | 233161.13 | - | 0 | - | 233161.13 | = | 0
15 | 100% | X | 233161.13 | = | 233161.13 | 233161.13 | - | 0 | - | 233161.13 | = | 0
16 | 100% | X | 233161.13 | = | 233161.13 | 233161.13 | - | 0 | - | 233161.13 | = | 0
17 | 100% | X | 233161.13 | = | 233161.13 | 233161.13 | - | 0 | - | 233161.13 | = | 0
18 | 100% | X | 233161.13 | = | 233161.13 | 233161.13 | - | 0 | - | 233161.13 | = | 0
19 | 100% | X | 155440.75 | = | 155440.75 | 155440.75 | - | 0 | - | 155440.75 | = | 0
20 | 100% | X | 155440.75 | = | 155440.75 | 155440.75 | - | 0 | - | 155440.75 | = | 0
21 | 100% | X | 155440.75 | = | 155440.75 | 155440.75 | - | 0 | - | 155440.75 | = | 0
22 | 100% | X | 155440.75 | = | 155440.75 | 155440.75 | - | 0 | - | 155440.75 | = | 0
23 | 84.48% | X | 262347.64 | = | 221644.2 | 221644.2 | - | 40703.44 | - | 214023.2 | = | -33082.44 | 7621
24 | 56.34% | X | 300000 | = | 169020 | 169020 | - | 130980 | - | 169020 | = | -130980
25 | 100% | X | 2545 | = | 2545 | 2545 | - | 0 | - | 2545 | = | 0
26 | 100% | X | 59400 | = | 59400 | 59400 | - | 0 | - | 59400 | = | 0
27 | 100% | X | 155440.75 | = | 155440.75 | 155440.75 | - | 0 | - | 155440.75 | = | 0
28 | 100% | X | 155440.75 | = | 155440.75 | 155440.75 | - | 0 | - | 155440.75 | = | 0
29 | 100% | X | 25000 | = | 25000 | 25000 | - | 0 | - | 25000 | = | 0
30 | 100% | X | 415000 | = | 415000 | 415000 | - | 0 | - | 415000 | = | 0
31 | 100% | X | 11830 | = | 11830 | 11830 | - | 0 | - | 11830 | = | 0
32 | 100% | X | 2000 | = | 2000 | 2000 | - | 0 | - | 2000 | = | 0
33 | 100% | X | 4132.13 | = | 4132.13 | 4132.13 | - | 0 | - | 4132.13 | = | 0
34 | 100% | X | 15840 | = | 15840 | 15840 | - | 0 | - | 15840 | = | 0
35 | 100% | X | 155440.75 | = | 155440.75 | 155440.75 | - | 0 | - | 155440.75 | = | 0
36 | 100% | X | 155440.75 | = | 155440.75 | 155440.75 | - | 0 | - | 155440.75 | = | 0
37 | 100% | X | 155440.75 | = | 155440.75 | 155440.75 | - | 0 | - | 155440.75 | = | 0
38 | 100% | X | 155440.75 | = | 155440.75 | 155440.75 | - | 0 | - | 155440.75 | = | 0
39 | 100% | X | 155440.75 | = | 155440.75 | 155440.75 | - | 0 | - | 155440.75 | = | 0
40 | 100% | X | 77720.375 | = | 77720.375 | 77720.375 | - | 0 | - | 77720.375 | = | 0
41 | 100% | X | 77720.375 | = | 77720.375 | 77720.375 | - | 0 | - | 77720.375 | = | 0
42 | 100% | X | 77720.375 | = | 77720.375 | 77720.375 | - | 0 | - | 77720.375 | = | 0
43 | 100% | X | 14387.05 | = | 14387.05 | 14387.05 | - | 0 | - | 14387.05 | = | 0
44 | 100% | X | 14387.05 | = | 14387.05 | 14387.05 | - | 0 | - | 14387.05 | = | 0
45 | 100% | X | 14387.05 | = | 14387.05 | 14387.05 | - | 0 | - | 14387.05 | = | 0
46 | 100% | X | 77720.375 | = | 77720.375 | 77720.375 | - | 0 | - | 77720.375 | = | 0
47 | 100% | X | 77720.375 | = | 77720.375 | 77720.375 | - | 0 | - | 77720.375 | = | 0
48 | 100% | X | 77720.375 | = | 77720.38 | 77720.38 | - | -0.005 | - | 77720.38 | = | 0.005
49 | 100% | X | 77720.375 | = | 77720.38 | 77720.38 | - | -0.005 | - | 77720.38 | = | 0.005
50 | 100% | X | 190000 | = | 190000 | 190000 | - | 0 | - | 190000 | = | 0
51 | 100% | X | 90410 | = | 90410 | 90410 | - | 0 | - | 90410 | = | 0
52 | 100% | X | 74590 | = | 74590 | 74590 | - | 0 | - | 74590 | = | 0
53 | 100% | X | 28600 | = | 28600 | 28600 | - | 0 | - | 28600 | = | 0
54 | 100% | X | 2400 | = | 2400 | 2400 | - | 0 | - | 2400 | = | 0
55 | 100% | X | 15080 | = | 15080 | 15080 | - | 0 | - | 15080 | = | 0
56 | 100% | X | 10190 | = | 10190 | 10190 | - | 0 | - | 10190 | = | 0
57 | 100% | X | 206635 | = | 206635 | 206635 | - | 0 | - | 206635 | = | 0
58 | 100% | X | 206635 | = | 206635 | 206635 | - | 0 | - | 206635 | = | 0
59 | 0% | X | 206635 | = | 0 | 0 | - | 206635 | - | 0 | = | -206635
60 | 0% | X | 206635 | = | 0 | 0 | - | 206635 | - | 0 | = | -206635
61 | 0% | X | 206635 | = | 0 | 0 | - | 206635 | - | 0 | = | -206635
62 | 0% | X | 206635 | = | 0 | 0 | - | 206635 | - | 0 | = | -206635
63 | 0% | X | 206635 | = | 0 | 0 | - | 206635 | - | 0 | = | -206635
64 | 0% | X | 206635 | = | 0 | 0 | - | 206635 | - | 0 | = | -206635
65 | 100% | X | 7450 | = | 7450 | 7450 | - | 0 | - | 7450 | = | 0
66 | 100% | X | 74900 | = | 74900 | 74900 | - | 0 | - | 74900 | = | 0
67 | 100% | X | 2800 | = | 2800 | 2800 | - | 0 | - | 2800 | = | 0
68 | 100% |  | 291720 |  | 291720 | 291720 |  | 0 |  | 291720 |  | 0
69 | 0% |  | 17489 |  | 0 | 0 |  | 17489 |  | 0 |  | -17489
70 | 0% |  | 15265 |  | 0 | 0 |  | 15265 |  | 0 |  | -15265
71 | 100% |  | 7889 |  | 7889 | 7889 |  | 0 |  | 7889 |  | 0
72 | 0% |  | 14391 |  | 0 | 0 |  | 14391 |  | 0 |  | -14391
73 | 0% |  | 3897 |  | 0 | 0 |  | 3897 |  | 0 |  | -3897
74 | 100% |  | 173608.08 |  | 173608.08 | 173608.08 |  | 0 |  | 173608.08 |  | 0
Procurement Entered By: ________________________________________________________________
Date
Procurement Data Entry Verified By: _______________________________________________________
Date