## Form
JSA / Jefferson Lab - DOE
PO Percent Complete Form
Appendix A
Vendor Name | Air Liquide Advanced Technologies, US Inc. (ALATUS) | [5 empty] | PO with Peg Points? (Yes or No) | No
PO Number | 15-C1196 |  |  | Buyer | Peshehonoff | Complete through | 2019-05-31
(Date)
PO Line # | Percent Complete | Completed Peg Point (X) |  | Summary of Work (only if less than 100%)
1 | 100% |  |  | Completion of Kick Off Meeting (KOM)
2 | 100% |  |  | Preliminary Design Review (PDR)
3 | 100% |  |  | MOD 002: Issue order for Long Lead Items, add engineering*
4 | 100% |  |  | MOD 003: Complete final design review (FDR)
5 | 100% |  |  | MOD 004: Delivery of main material to start CB manufacturing at factory
6 | 100% |  |  | MOD 004: CB1 UCB Fabrication
7 | 100% |  |  | MOD 005: Customs & Duties for Line 5
8 | 100% |  |  | MOD 005: UL Stamp for ELE Boxes
9 | 100% |  |  | MOD 007: Bayonet Relocation
10 | 100% |  |  | MOD 007: Stair Arrangement Relocation
11 | 100% |  |  | MOD 008: Cold Box 1 Anchor Design Change
12 | 100% |  |  | MOD 008: Cold Box 2 Anchor Design Change
13 | 100% |  |  | MOD 009: Factory acceptance of completed turbines - CP1
14 | 100% |  |  | MOD 010: Process Mode Calculations
15 | 100% |  |  | MOD 010: GN2 Vent/ LN2 Drain, Process Mode Calcs
16 | 100% |  |  | MOD 009: Factory acceptance of completed turbines - CP2
17 | 100% |  |  | Mod 004: CB1 LCB Fabrication
18 | 100% |  |  | Mod 011: C1 UCB AWS Lines 23,25,26,28
19 | 100% |  |  | Mod 011: C1 UCB Delivery to SLAC
20 | 100% |  |  | Mod 011: C1 LCB AWS Line 27
21 | 100% |  |  | Mod 011: C1 LCB Delivery to SLAC
22 | 74.4% |  |  | Mod 011: C1 CB Assembled @ SLAC
23 | 100% |  |  | Mod 011: C2 UCB Fab & AWS Line 24
24 | 98% |  |  | Mod 011: C2 LCB Fabrication
25 | 100% |  |  | Mod 12: Shipping C2 UCB Loads 1,2,3 & 6
26 | 100% |  |  | Mod 12: Shipping C2 LCB Loads 4 & 5
27 | 50% |  |  | Mod 13: C2 CB Assembled @ SLAC
28 | 100% |  |  | Mod 13: C2 CB Assembled at SLAC adds UCB Post Lifting
29 | 100% |  |  | Mod 13: C1 CB Assembled at SLAC adds UCB Post Lifting
30 | 100% |  |  | Mod 13: LCB Lift Analysis
31 | 0% |  |  | Mod 14: Modify Relief valves as per ARA030C
N/A | #DIV/0! |  |  | Commissioning, Training, & Acceptance - CB1
32 | 0% |  |  | Delivery of operating and maintenance manuals
N/A | #DIV/0! |  |  | Commissioning, Training, & Acceptance - CB2
0%
0%
Vendor Technical Representative Contacted: |  |  |  |  | David Clark |  |  | 4361600%
|  |  | Name |  |  |  |  | Date
Jlab Control Account Manager (CAM): |  |  |  |  | John Hogan |  |  | 2019-05-31
[6 empty] | Name |  | Date
Below for use by Accounting/Shipping & Receiving Only
Accounting or Shipping & Receiving Entered By:
Date
Data Entry Verified By:
Date

## Process
JSA / Jefferson Lab - DOE
PO Percent Complete Form
Procedure
A Subcontract Purchase Order (PO) is a service type PO with loosely defined scheduled deliverables and variable amounts. A Peg Point PO has specified scheduled deliverable dates for a specified amount.
This form is to be used if NO invoice has been approved by the SOTR or CAM for work completed.
SOTR or CAM contacts a vendor technical representative for an evaluation of the percent of work completed. This can be done either verbally or via email.
Required information - Vendor Name, indicate if PO is a Peg Point type PO or not, PO #, Buyer, Complete through date (usually the end of the month), PO Line #, Percent complete, a short Summary of Work performed provided by the Vendor Technical Representative that supports the percent complete if less than 100%, the name of the Vendor Technical Representative contacted, and the CAM name.
The SOTR or CAM will submit a PO Percent Complete form by the 2nd working day following the end of the month affected for work that has been completed. This allows time for Accounting to process an accrual for the month end closing. Reminder if PO is for Peg Points, the peg point must be fully complete before claiming it.
Submit the completed form with all the information via email to evpo@jlab.org. The file name of the spreadsheet attached to the email should always include the PO# and the letters 'S&R' if it is a Peg Point type PO. File name examples: Peg Point Type PO 08-C5413 S&R, Subcontract Type PO 08-A2659. This email will forward the form automatically to personnel in Procurement, Shipping & Receiving, CFO, and PMI.
If the PO is a Subcontract type PO, the SOTR or CAM will still be required to sign all invoices received at JLab from the vendor up since this was an estimate. An approved invoice by the SOTR or CAM can also be used as basis for the percent of work complete.
If the PO is a Peg Point type PO, Shipping & Receiving will use this form to enter that Peg Point into the Costpoint Financial System. No additional invoice approvals will be required since the SOTR or CAM already indicated the work was complete. An approved invoice by the SOTR or CAM can also be used as basis for the percent of work complete without having to complete this form.
If a previous percent complete was submitted and subsequently determined to be in error, adjust the percent complete to correct the error. Add an explanatory note to support the adjustment.

## Accting USE Data Entry Form
557592
Vendor Name |  | Air Liquide Advanced Technologies, US Inc. (ALATUS) | [20 empty] | 4361600%
[23 empty] | (Date) |  |  | 67028.4
PO Number |  | 15-C1196 | [19 empty] | OR |  |  |  | -64539.66
Buyer |  | Peshehonoff
Milestone # | PO Line # | Description | Est Date | Beg % Complete | Nov-16 | Dec-16 | Jan-17 | Feb-17 | Mar-17 | Apr-17 | May-17 | Jun-17 | Jul-17 | Aug-17 | Sep-17 | Oct-17 | Nov-17 | Dec-17 | % Complete | PO Line Total | Work Complete | Eligible for Voucher Amt | Total Paid | Completed Work Retention Amt | Work Remaining | Remaining Unfunded (or % complete) | Column1 | Column2 | Column3 | Column4 | Column5
1 | 1 | Completion of Kick Off Meeting (KOM) | 2015-10-08 | 100% | [14 empty] | 100% | 502100 | 502100 | 0 | 502100 | 0 | 0
2 | 2 | Preliminary Design Review (PDR) | 2016-03-10 | 100% | [14 empty] | 100% | 502100 | 502100 | 0 | 502100 | 0 | 0
3 | 3 | MOD 002: Issue order for Long Lead Items, add engineering* | 2016-04-08 | 82.25% |  |  | 936680 | [11 empty] | 100% | 5277520 | 5277520 | 0 | 5277520 | 0 | 0
4 | 4 | MOD 003: Complete final design review (FDR) | 2016-07-11 | 90.11% | [7 empty] | 184143.956 | [6 empty] | 100% | 1861900 | 1861900 | 0 | 1861900 | 0 | 0
5 | 5 | MOD 004: Delivery of main material to start CB manufacturing at factory | 2016-11-11 | 0% |  |  | 910806.018 | 1515207.982 | [10 empty] | 100% | 2426014 | 2426014 | 0 | 2426014 | 0 | 0
7 | 6 | MOD 004: CB1 UCB Fabrication | 2018-01-25 | 0% | [14 empty] | 100% | 741988 | 741988 | 0 | 741988 | 0 | 0 | 100%
5 | 7 | MOD 005: Customs & Duties for Line 5 | 2019-02-11 | 0% | [11 empty] | 40816 |  |  | 100% | 40816 | 40816 | 0 | 40816 | 0 | 0 | 100%
5 | 8 | MOD 005: UL Stamp for ELE Boxes | 2019-02-11 | 0% | [11 empty] | 5544 |  |  | 100% | 5544 | 5544 | 0 | 5544 | 0 | 0 | 100%
7 | 9 | MOD 007: Bayonet Relocation | 2019-02-11 | [15 empty] | 100% | 8572 | 8572 | 0 | 8572 |  | 0 | 100%
7 | 10 | MOD 007: Stair Arrangement Relocation | 2019-02-11 | [15 empty] | 100% | 11962 | 11962 | 0 | 11962 |  | 0 | 100%
7 | 11 | MOD 008: Cold Box 1 Anchor Design Change | 2019-02-11 | [15 empty] | 100% | 57670 | 57670 | 0 | 57670 |  | 0 | 100%
7 | 12 | MOD 008: Cold Box 2 Anchor Design Change | 2019-02-11 | [15 empty] | 100% | 57670 | 57670 | 0 | 57670 |  | 0 | 100%
6 | 13 | MOD 009: Factory acceptance of completed turbines - CP1 | 2017-08-25 | 0% | [8 empty] | 465475 | [5 empty] | 100% | 465475 | 465475 | 0 | 465475 | 0 | 0 | 100%
7 | 14 | MOD 010: Process Mode Calculations | 2019-02-11 | [15 empty] | 100% | 33433 | 33433 | 0 | 33433 | 0 | 0 | 100%
7 | 15 | MOD 010: GN2 Vent/ LN2 Drain, Process Mode Calcs | 2019-02-11 | 0% | [14 empty] | 100% | 14935 | 14935 | 0 | 14935 | 0 | 0 | 100%
12 | 16 | MOD 009: Factory acceptance of completed turbines - CP2 | 2018-03-15 | [15 empty] | 100% | 465475 | 465475 | 0 | 465475 | 0 | 0 | 100%
9 | 17 | Mod 004: CB1 LCB Fabrication | 2018-04-23 | 0% | [14 empty] | 100% | 741988 | 741988 | 0 | 741988 | 0 | 0 | 100%
7 | 18 | Mod 011: C1 UCB AWS Lines 23,25,26,28 | 2018-01-25 | 0% | [14 empty] | 100% | 122403 | 122403 | 0 | 122403 | 0 | 0 | 100%
8 | 19 | Mod 011: C1 UCB Delivery to SLAC | 2018-02-15 | 0% | [14 empty] | 100% | 232737 | 232737 | 0 | 232737 | 0 | 0 | 100%
9 | 20 | Mod 011: C1 LCB AWS Line 27 | 2018-04-23 | 0% | [14 empty] | 100% | 975 | 975 | 0 | 975 | 0 | 0 | 100%
10 | 21 | Mod 011: C1 LCB Delivery to SLAC | 2018-05-07 | 0% | [14 empty] | 100% | 232738 | 232738 | 0 | 232738 | 0 | 0 | 100% |  | just this line | Total of C1 Assembly work (line 22 + 29) | % C1 Assembly Complete | Vouchered %
11 | 22 | Mod 011: C1 CB Assembled @ SLAC | 2019-04-30 | [15 empty] | 74.4% | 465475 | 346324.89 | 0.01 | 346324.88 | 0 | 119150.11 | 74.4% | 256011.25 | 74.4% | 496459 | 76% | 76%
13 | 23 | Mod 011: C2 UCB Fab & AWS Line 24 | 2018-04-26 | [15 empty] | 100% | 863174 | 863174 | 0 | 863174 | 0 | 0 | 100%
15 | 24 | Mod 011: C2 LCB Fabrication | 2018-09-11 | [15 empty] | 98% | 744760 | 729864.2 | 0 | 729864.2 | 0 | 14895.8 | 98% | 729864.8 | 0.6
14 | 25 | Mod 12: Shipping C2 UCB Loads 1,2,3 & 6 | 2018-09-16 | [15 empty] | 100% | 232737 | 232737 | 0 | 232737 | 0 | 0
16 | 26 | Mod 12: Shipping C2 LCB Loads 4 & 5 | 2019-03-13 | [15 empty] | 100% | 232738 | 232738 | 232738 | 0 | 0 | 0 | 100% |  |  | Total of C2 Assembly work (line 27 + 28) | % C2 Assembly Complete | Vouchered %
17 | 27 | Mod 13: C2 CB Assembled @ SLAC | 2019-10-14 | [15 empty] | 50% | 465475 | 232737.5 | 45279.5 | 187458 | 0 | 232737.5 | 50% | 232737.5 |  | 496459 | 53.12% | 44%
17 | 28 | Mod 13: C2 CB Assembled at SLAC adds UCB Post Lifting | 2019-10-14 | [15 empty] | 100% | 30984 | 30984 | 0 | 30984 | 0 | 0 | 100%
11 | 29 | Mod 13: C1 CB Assembled at SLAC adds UCB Post Lifting | 2019-04-30 | [15 empty] | 100% | 30984 | 30984 | 0 | 30984 | 0 | 0 | 100%
21 | 30 | Mod 13: LCB Lift Analysis | 2018-10-30 | [15 empty] | 100% | 7318 | 7318 | 0 | 7318 | 0 | 0 | 100%
22 | 31 | Mod 14: Modify Relief valves as per ARA030C | 2019-10-14 | [15 empty] | 0% | 7737 |  | 0 |  | 0 | 7737 | 0%
18 | N/A | Commissioning, Training, & Acceptance - CB1 | 2019-11-12 | 0% | [14 empty] | #DIV/0! |  | #DIV/0! | #DIV/0! | 0 | #DIV/0! |  | 930950.4 | Requires funding
19 | 32 | Delivery of operating and maintenance manuals | 2020-01-17 | 0% | [14 empty] | 0% | 485320 |  | 0 | 0 | 0 |  | 0%
20 | N/A | Commissioning, Training, & Acceptance - CB2 | 2020-01-30 | 0% | [14 empty] | #DIV/0! |  | #DIV/0! | #DIV/0! | 0 | #DIV/0! |  | 930950.4 | Requires funding
[20 empty] | 17370717 | #DIV/0! | #DIV/0! | 16232859.08 |  | 374520.41 | 2236421.21
0
[26 empty] | 19232617.8 | Total Contract Value
Procurement Entered By: ________________________________________________________________ | [22 empty] | 4361600% |  |  | 17370717 | Total Funded Value
[23 empty] | Date |  |  | 16232859.08 | Total Paid
[26 empty] | 2999758.72 | Remaining on Contract Value
Procurement Data Entry Verified By: _______________________________________________________ | [25 empty] | 84.4% | Percent Paid on Contract | 93.45%
Date
Note on A16: Ted Peshehonoff: Half with Milestone 7 and half with Milestone 8.
Note on U17: Ted Peshehonoff: Orginal amount wad $278,066. Mod 11 deobligated 237,250 to make line total 40,816.

## Invoices
[21 empty] | -1.0379 | 1.1021
[18 empty] | base rate | + / - |  | minus | plus | Note:
[16 empty] | 1EU = Xdollars | Award | 1.07 | 3% | 0.0321 | 1.0379 | 1.1021 | Equitable adjustment based on difference greater than the 3%
[16 empty] | Base is 1EU to $1.07 | US$ go down from 1.07 it is good for us
[6 empty] | From Matt K | [9 empty] | Currency Exchange rate | rates outside $1.1639 - $1.0961 need equitable adjustment
Invoice # | Invoice Date | Description | Invoice Amount | Approved Amount | Approval Date | Actaul Pay Date | PO line | Column6 | Column5 | Column4 | Column3 | Column2 | Column1 | Exchange rate applicable | [5 empty] | Positive = they pay us
63449614 | 4235600% | Completion of Kick Off Meeting (KOM) | 502100 | 502100 | Jarrod | 4233200% | 1 | [6 empty] | Turbo expanders and Heat exchangers |  |  | Based on invoice date | Adjustment |  | Negative = we pay them
64678952 | 4249600% | Mod 002: Issue order for Long Lead Items, add engineering* | 4340840 | 4340840 | Jarrod | 4252100% | 3 | [6 empty] | 3093819.94 |  | 1.1134 | Get actuals from ALATUS | -0.0113 |  | -32673.0517
64737390 | 4250800% | Preliminary Design Review (PDR) | 502100 | 502100 | Jarrod | 4253500% | 2 | [8 empty] | 1.1211 | Get actuals from ALATUS | -0.019 |  | 0
65699321 | 4264400% | MOD 003: Complete final design review (FDR) | 1677756 | 1677756 | 4266900% | 4267500% | 4 | [8 empty] | 1.1042 | Get actuals from ALATUS | -0.0021 |  | 0
66002927 | 4270900% | Mod 002: Issue order for Long Lead Items, add engineering* | 936680 | 936680 | 4276200% | 4276900% | 3 | [8 empty] | 1.0791 | Get actuals from ALATUS | 0 |  | 0
66210090 | 4276100% | MOD 003: Complete final design review (FDR) | 184144 | 184144 | 4291600% | 4292700% | 4 | [8 empty] | 1.1429 | Get actuals from ALATUS | -0.0408 |  | 0
66311061 | 4277400% | MOD 004: Delivery of main material to start CB manufacturing at factory | 2426014 | 2426014 | 4279500% | 4280100% | 5 | [6 empty] | 1778254.94 |  | 1.058 | Get actuals from ALATUS | 0 |  | 0
67491271 | 4303200% | MOD 009: Factory acceptance of completed turbines - CP1 | 465475 | 465475 | 4303400% | 4306000% | 13 | [6 empty] | 465475 |  | 1.174 | Get actuals from ALATUS | -0.0719 |  | -31278.1799
67495210 | 4303300% | MOD 005: Customs & Duties for Line 5 | 40816 | 40816 | 4303800% | 4306000% | 7 | [8 empty] | 1.174 | Get actuals from ALATUS | -0.0719 |  | 0
67495210 | 4303400% | MOD 005: UL Stamp for ELE Boxes | 5544 | 5544 | 4303800% | 4306000% | 8 | [8 empty] | 1.174 | Get actuals from ALATUS | -0.0719 |  | 0
67849414 | 4311500% | Multiple Lines paid or drawn down for Fab and mods | 1607077 | 1607077 | 4311700% | 4314000% | 6,9,10,11,12,14,15,17,20,23,24 | [6 empty] | 384614.99 |  | 1.2227 | Get actuals from ALATUS | -0.1206 |  | -43350.0634
68073557 | 4316100% | Multiple Lines paid or drawn down for Fab of all vessels | 662550 | 662550 | 4316500% | 4318700% | 6,16,17,18,23,24 | [6 empty] | 465475 |  | 1.2351 | Get actuals from ALATUS | -0.133 |  | -57858.1075
68374783 | 4323500% | Multiple Lines paid or drawn down for Fab on all vessels | 801626 | 801626 | 4324200% | 4326300% | 17,18,19 (piad in full),23,24 | [8 empty] | 1.1793 | Get actuals from ALATUS | -0.0772 |  | 0
68519890 | 4327000% | Multiple Lines paid or drawn down for Fab on all vessels | 169892 | 169892 | 4328600% | 4329800% | 17, 18, 23, 24 | [8 empty] | 1.1678 | Get actuals from ALATUS | -0.0657 |  | 0
68654441 | 4330100% | Multiple Lines paid or drawn down for Fab of vessels | 59563 | 59563 | 4330600% | 4332700% | 17, 24 | [8 empty] | 1.133 | Get actuals from ALATUS | -0.0309 |  | 0
68800436 | 4333900% | Multiple Lines paid or drawn down for Fab of vessels | 90883 | 90883 | 4334100% | 4335700% | 18,23,24 | [8 empty] | 1.1659 | Get actuals from ALATUS | -0.0638 |  | 0
68948421 | 4337400% | Multiple Lines paid or drawn down for Fab of vessels & delivery of C2 UCB | 475274 | 475274 | 4338100% | 4339900% | 17,23,24,25 | [8 empty] | 1.1388 | Get actuals from ALATUS | -0.0367 |  | 0
69052377 | 4339600% | Multiple Lines paid or drawn down for Fab of vessels | 92887 | 92887 | 4339700% | 4342400% | 17,23,24 | [8 empty] | 1.1391 | Get actuals from ALATUS | -0.037 |  | 0
69203729 | 4343100% | Multiple Lines paid or drawn down for Fab of vessels | 30827 | 30827 | 4343800% | 4345500% | 17,23,24,30 | [8 empty] | 1.1402 | Get actuals from ALATUS | -0.0381 |  | 0
69430498 | 4348300% | Multiple Lines paid or drawn down for Fab of vessels & delivery of C1 LCB | 557592 | 557592 | 4348900% |  | 17, 21, 22, 23, 24, 27 | [8 empty] | 0 | Get actuals from ALATUS | 0 |  | 0
69544687 | 4350900% | Mulitple Lines drawn down for C2 LCB Fab and on-site work | 243267 | 243267 | 4351000% |  | 22,24,27 | [9 empty] | Get actuals from ALATUS | 0 |  | 0
69686902 | 4354400% | C2 LCB fab draw down and C1 on-site reassmebly drawdown | 91848.49 | 91848.49 | 4355000% |  | 22, 24
69811138 | 4357100% | C2 LCB fab draw down and C1 on-site reassmebly drawdown | 131568.07 | 131568.07 | 4357200% |  | 22,24
69942324 | 4357000% | C2 LCB fab draw down and C1 on-site reassmebly drawdown | 136535.52 | 136535.52 | 4360600% |  | 22,24
[17 empty] | Get actuals from ALATUS | 0 |  | 0
Total |  |  |  | 16232859.08 | [9 empty] | 6187639.87 | [5 empty] | -165159.4024
|  |  |  | Total Invoiced to date | [15 empty] | Positive = they pay us
|  | ` |  |  |  |  | Turbines and HX Material Order Order | [6 empty] | 3093819.94 | Exchange Rate topic |  |  |  |  | Negative = we pay them
[7 empty] | Delivery of HX | [6 empty] | 1778254.94 | Exchange Rate topic
[7 empty] | Turbines Fabrication Complete | [6 empty] | 384614.99 | Exchange Rate topic
[7 empty] | Turbines FAT Test | [6 empty] | 930950 | Exchange Rate topic
[14 empty] | 6187639.87 | Exchange Rate topic
[7 empty] | Cost of turbines and HX from Proforma invoice normalized to US dollars @ base exchange rate | [6 empty] | 6187639.87 | Exchange Rate topic
[7 empty] | Cost of HX from Proforma invoice normalized to US dollars @ base exchange rate | [6 empty] | 3556509.87 | Exchange Rate topic
[7 empty] | Cost of turbines from Proforma invoice normalized to US dollars @ base exchange rate | [6 empty] | 2631130 | Exchange Rate topic
0
Note on V7: Theodore Peshehonoff: Basis of rates come from: https://www.xe.com/currencytables/
Note on V10: Theodore Peshehonoff: https://www.x-rates.com/historical/?from=EUR&amount=1&date=2018-03-28
Note on O42: Theodore Peshehonoff: This total value was derived from the proforma invoices ALATUS provided.

## Mods
C | Mod# | New Award Sched Line | Cost Point PO Line Item | Description | Unit | Unit Amount | Total
| 1 | N/A |  | Administrative Mod | 0 | 0 | 0
| 2 | 5 |  | CP2 Fabrication | 1 | 7719000 | 7719000
| 2 | 6 |  | CP2 Seismic Option 2 | 1 | 90000 | 90000
| 2 | 7 |  | CP2 Delivery | 1 | 228000 | 228000
| 2 | 8 |  | Dual Core HX-1 Design | 2 | 270000 | 540000
| 2 | 9 |  | Delay Costs for HX-1 Design | 4 | 16050 | 64200
| 3 | N/A | 5 | Funding Modification | 0 | 0 | 0
| 4 | N/A | 6 | Funding Modification | 0 | 0 | 0
2017-01-24 | 5 | 11 | 7 | Customs & Duties Heat Exchangers Shipment - CP1 | 1 | 114453 | 114453
2017-01-24 | 5 | 11 | 7 | Customs & Duties Turbine Casing Shipment - CP1 | 1 | 19420 | 19420
2017-01-24 | 5 | 11 | 7 | Customs & Duties Turbine Cartridges and Spare Parts Shipment - CP1 | 1 | 19846 | 19846
2017-01-24 | 5 | 11 | 7 | Customs & Duties Heat Exchangers Shipment - CP2 | 1 | 91648 | 91648
2017-01-24 | 5 | 11 | 7 | Customs & Duties Turbine Casing Shipment - CP2 | 1 | 17218 | 17218
2017-01-24 | 5 | 11 | 7 | Customs & Duties Turbine Cartridges and Spare Parts Shipment - CP2 | 1 | 15481 | 15481
2017-01-24 | 5 | 10 | 8 | Additional cost for UL Stamp on Electrical Enclosures | 1 | 5544 | 5544
| 6 | N/A |  | no cost mod to change clause JSA 217 |  |  | 0
| 7 | 12 | 9 | Bayonet Relocation |  |  | 0
| 7 |  | 10 | Stair Arrangement Relocation |  |  | 0
| 8 |  | 11 | Cold Box 1 Anchor Design |  |  | 0
| 8 |  | 12 | Cold Box 2 Anchor Design |  |  | 0
0
0
0
Total | [6 empty] | 8924810

## Change Request
Change Requests
CRN# | Description | Date Issued | Issued By | Review Date | Approved? | Resulting Mod | Notes
CRNAL_001
CRNAL_002
CRNAL_003
CRNAL_004
CRNAL_005
CRNAL_006 | Anchor Design Change | 4277500% | ALATUS
CRNAL_007
CRNAL_008
CRNAL_009

## Milestone
# | Milestone/ Witness Point Description | Est. Finish | Status |  | Comments
1 | ♦ Completion of Kick Off Meeting | 2015-10-08 | Complete | 100%
2 | ♦ Preliminary Design Review (PDR) | 2016-03-10 | Complete | 100%
3 | ♦ Order LLPs (Heat Exchangers, Cryovalves, Cold Box Shell) | 2016-04-08 | Complete | 100% | 11/1/16 - All LLPs orderd. Jlab approval is pending FDR (Seismic Design Report) acceptance.
4 | ♦ Final Design Review (FDR) | 2016-07-11 | In Progress | 90% | 3/23 - Awaiting Final Hopper Report. AL expects by the end of next week. 2/24/17 - Revised Hopper Report expected on March 6th. 2/9/17 - Conference call with all parties scheduled for Monday morning. 1/26/17 - Approval pending resolution of FDR/ Seismic Report comments. 1/13/17 - All Seismic Report comments submitted to AL for response.
5 | ♦ Main Material Delivery (to PHPK) | 2016-11-11 | Complete | 100% | 2/23/17 - Main materials delivered. Manufacturing has begun.
6 | ♦ Cold Box 1 Manufacturing | 2017-08-11 | Started | 10% | 2/1/17 - AL internal manufacturing readiness review conducted at PHPK.
| WP1 - Pressure/ Leak Test Heat Exchangers - Shipment 1 | 2016-12-02 | Complete | 100%
| WP2 - Testing of Cryogenic Control Valves | 2017-04-13 | Complete | 100% | 4/20 - Vishy witnessed inspection last week at PHPK. 3/21 - Ongoing inspections to be witnessed during HX Leak Check witness point (WP9) April 10-14.
| WP3 - Pressure/ Leak Test Heat Exchangers - Shipments 2&3 | 2017-03-08 | Complete | 100%
| WP4 - VCB & HCB Electrical/Control Cabinets Completed - CB1 | 2017-03-17 | Complete | 100%
| WP5 - VCB Install HXs, Pres Vessels, & Absorbers, Internal Frame - CB1 | 2017-06-12 | Behind | 100% | Completed in laet Sept/early Oct 2017. Initial ;eak test before closing shell was held on 11 Oct at PHPK
| WP6 - VCB Final Pumping Down & Leak Check - CB1 | 2017-07-28 | Behind | 0%
| WP7 - HCB Install HXs, Pres Vessels, & Absorbers, Internal Frame - CB2 | 2017-05-27 | Behind | 0%
| WP8 - HCB Final Pumping Down & Leak Check - CB2 | 2017-08-20 | Behind | 0%
| WP9 - Pressure/ Leak Test Heat Exchangers - Shipment 4 | 2017-04-28 | Complete | 100% | 4/14 - Vishy witnessed final HX shipment inspection at PHPK.
7 | ♦ Factory acceptance of completed turbines | 2017-08-25 | Behind | 50% | Dana and Ted witnessed in France on 19,20 July 2017. Test reports provided on 10/12/2017.
8 | ♦ Cold Box 1 Received at SLAC | 2017-09-11 | On Schedule | 0%
9 | ♦ Cold Box 1 Assembled at SLAC | 2017-12-11 | On Schedule | 0%
10 | ♦ Cold Box 2 Manufacturing Complete | 2018-02-12 | On Schedule | 0%
11 | ♦ Cold Box 2 Received at SLAC | 2018-03-12 | On Schedule | 0%
12 | ♦ Cold Box 2 Assembled at SLAC | 2018-06-11 | On Schedule | 0%
13 | ♦ Commissioning, Train, & Accept (CB1) | 2018-10-11 | On Schedule | 0%
14 | ♦ Deliver Ops & Main Manuals | 2019-01-11 | On Schedule | 0%
15 | ♦ Commissioning, Train, & Accept (CB2) | 2019-02-11 | On Schedule | 0%
Note: | ♦ Subcontract Milestone. Milestone finish dates shown are subcontract required.

## Calendar
Meetings
Date | Time | Description | Status | Cancelled for? | Column1
4269000% | 8:00 | Director's Review |  | N/A
4265600% | 10:00 | ALATUS/ PHPK Weekly Update
4266300% | 10:00 | ALATUS/ PHPK Weekly Update
4267000% | 10:00 | ALATUS/ PHPK Weekly Update
4267700% | 10:00 | ALATUS/ PHPK Weekly Update | Canceled
4268400% | 10:00 | ALATUS/ PHPK Weekly Update
4269100% | 10:00 | ALATUS/ PHPK Weekly Update
4269800% | 10:00 | ALATUS/ PHPK Weekly Update
4270500% | 10:00 | ALATUS/ PHPK Weekly Update | Canceled |  | I apologize for the late notice, but the weekly PHPK meeting has been canceled so PHPK can focus on completing the Hopper report and seismic reporting package for Monday.
4271200% | 10:00 | ALATUS/ PHPK Weekly Update
4271900% | 10:00 | ALATUS/ PHPK Weekly Update | Moved
4272600% | 10:00 | ALATUS/ PHPK Weekly Update
4273300% | 10:00 | ALATUS/ PHPK Weekly Update
4274000% | 10:00 | ALATUS/ PHPK Weekly Update | Moved
4274700% | 10:00 | ALATUS/ PHPK Weekly Update
4275400% | 10:00 | ALATUS/ PHPK Weekly Update
4276100% | 10:00 | ALATUS/ PHPK Weekly Update
4276800% | 10:00 | ALATUS/ PHPK Weekly Update
4277500% | 10:00 | ALATUS/ PHPK Weekly Update
4278200% | 10:00 | ALATUS/ PHPK Weekly Update
4278900% | 10:00 | ALATUS/ PHPK Weekly Update | Moved
4279600% | 10:00 | ALATUS/ PHPK Weekly Update
4280300% | 10:00 | ALATUS/ PHPK Weekly Update | Canceled |  | The PHPK weekly meeting has been canceled. PHPK is focused on completing critical activities and has suggested we meet early next week instead.
4281000% | 10:00 | ALATUS/ PHPK Weekly Update
4281700% | 10:00 | ALATUS/ PHPK Weekly Update
4282400% | 10:00 | ALATUS/ PHPK Weekly Update
4283100% | 10:00 | ALATUS/ PHPK Weekly Update
4283800% | 10:00 | ALATUS/ PHPK Weekly Update
4284500% | 10:00 | ALATUS/ PHPK Weekly Update
4285200% | 10:00 | ALATUS/ PHPK Weekly Update
4285900% | 10:00 | ALATUS/ PHPK Weekly Update
4286600% | 10:00 | ALATUS/ PHPK Weekly Update | Moved
4287300% | 10:00 | ALATUS/ PHPK Weekly Update
4288000% | 10:00 | ALATUS/ PHPK Weekly Update
4288700% | 10:00 | ALATUS/ PHPK Weekly Update | Canceled |  | Today's PHPK weekly tracker meeting has been canceled.
4289400% | 10:00 | ALATUS/ PHPK Weekly Update
4290100% | 10:00 | ALATUS/ PHPK Weekly Update
4290800% | 10:00 | ALATUS/ PHPK Weekly Update | Moved
4291500% | 10:00 | ALATUS/ PHPK Weekly Update | Canceled |  | Today's weekly PHPK tracker meeting has been canceled.
4292200% | 10:00 | ALATUS/ PHPK Weekly Update | Moved
4292900% | 10:00 | ALATUS/ PHPK Weekly Update
4293600% | 10:00 | ALATUS/ PHPK Weekly Update | Canceled |  | Today's PHPK Tracker meeting has been canceled.
4294300% | 10:00 | ALATUS/ PHPK Weekly Update | Canceled |  | Today's PHPK Tracker meeting has been canceled.
4295000% | 10:00 | ALATUS/ PHPK Weekly Update
4295700% | 10:00 | ALATUS/ PHPK Weekly Update | Canceled |  | Today's PHPK meeting has been canceled as they have customers in the office. I'm working to reschedule the meeting.
4296400% | 10:00 | ALATUS/ PHPK Weekly Update
4297100% | 10:00 | ALATUS/ PHPK Weekly Update
4297800% | 10:00 | ALATUS/ PHPK Weekly Update | Canceled
4298500% | 10:00 | ALATUS/ PHPK Weekly Update | Canceled |  | I apologize, I did not send out the cancellation notice prior to the meeting. Chris and Brad are focused on their schedule meeting this morning and I am in the process of rescheduling the tracker meeting.
Total |  | 49 | 16 |  | 8

## List
% Complete | Date
100% | 2019-05-24
95% | 2019-05-27
90% | 2019-05-28
85% | 2019-05-29
80% | 2019-05-30
75% | 2019-05-31
70% | 2019-06-03
65% | 2019-06-04
60% | 2019-06-05
55% | 2019-06-06
50% | 2019-06-07
45% | 2019-06-10
40% | 2019-06-11
35% | 2019-06-12
30% | 2019-06-13
25% | 2019-06-14
20% | 2019-06-17
15% | 2019-06-18
10% | 2019-06-19
5% | 2019-06-20
-3.192e-14% | 2019-06-21