## FY20
Subcontract PO Status Update |  |  |  | Updated: | 2020-06-30
PO NUMBER | PO STATUS | VENDOR NAME | PO Value (in $K) | PO Accrued (in $K) | PO Vouchered (in $K) | Balance (Val-Accr) (in $K) | Bal (Val-Vouch) (in $K) | BUYER | END USER | POC1 | POC2 | POC1 Email | POC2 Email | NOTES | VENDOR NAME
15-C1196 | Open | AIR LIQUIDE ADVANCED TECH | 18503.5828 | 17240.6481 | 17240.6101 | 1262.9346 | 1262.9726 | THEODORE PESHEHONOFF | ARENIUS/MBEVINS | PESHEHONOFF, THEODORE | ARENIUS, DANA M | tvp@jlab.org | arenius@jlab.org |  | AIR LIQUIDE 15-C1196
18-C0415 | Open | AIR LIQUIDE ADVANCED TECH | 2512.855 | 2362.726 | 2362.726 | 150.129 | 150.129 | THEODORE PESHEHONOFF | NORTON | PESHEHONOFF, THEODORE | NORTON, ROBERT O | tvp@jlab.org | norton@jlab.org | Ted - No accrual until provided Milestone expected Nov 2018
20-C0007 | Open | ANDERSON & DAHLEN INC | 1259.3 | 503.72 | 503.72 | 755.58 | 755.58 | THEODORE PESHEHONOFF | MARCHLIK | PESHEHONOFF, THEODORE | WILSON, KATHERINE M | tvp@jlab.org | kwilson@jlab.org
20-C0248 | Open | BENNU GROUP INC | 430.818 | 202.488 | 202.488 | 228.33 | 228.33 | THOMAS HURATIAK | M MARCHLIK | MARCHLIK, MATTHEW J | WILSON, KATHERINE M | marchlik@jlab.org | kwilson@jlab.org
20-C0733 | Open | CARR ELECTRICAL TECHNOLOG | 431.623 | 51.7948 | 10.958 | 379.8282 | 420.665 | CAROLYN STEPNEY | J WILLOUGHBY | WILLOUGHBY, JASON | FRIES, RUSSELL W | jasonw@jlab.org | rfries@jlab.org
20-C0820 | Open | CARR ELECTRICAL TECHNOLOG | 281.815 | 8.9335 | 8.927 | 272.8815 | 272.888 | CAROLYN STEPNEY | E WINSLOW | WINSLOW, EDWARD B | FRIES, RUSSELL W | winslow@jlab.org | rfries@jlab.org
19-D0681 | Open | CENTRE NATIONALE DE | 28.8 | 14.4 | 14.4 | 14.4 | 14.4 | GIUSEPPINA TENBUSCH | TANYA STEWART | STEWART, TANYA-GAYE N | PARKINSON, SHARON K | fraites@jlab.org | spark@jlab.org | Yes
15C1526400 | Open | CHRISTOPHER NEWPORT UNIV. | 152.894 | 152.894 | 152.8743 | 0 | 0.01972 | MICHELE KHASIDIS | TANYA STEWART | STEWART, TANYA-GAYE N |  | fraites@jlab.org |  | Nothing until August
17-C1149 | Open | COLLEGE OF WILLIAM & MARY | 438.7782 | 372.2801 | 336.6532 | 66.4981 | 102.125 | DENISE LEARY-STITH | TANYA STEWART | STEWART, TANYA-GAYE N | PARKINSON, SHARON K | fraites@jlab.org | spark@jlab.org | Yes | COLLEGE OF WILLIAM & MARY 17-C1149
18-C0507 | Open | COLLEGE OF WILLIAM & MARY | 797.6264 | 671.3953 | 640.6524 | 126.231 | 156.9739 | DENISE LEARY-STITH | TANYA STEWART | STEWART, TANYA-GAYE N | PARKINSON, SHARON K | fraites@jlab.org | spark@jlab.org | Yes
18-C0548 | Open | DANFYSIK A/S | 492.842 | 485.6169 | 485.6145 | 7.2251 | 7.2275 | THOMAS HURATIAK | JAMES COLEMAN | PHILIP, SARIN | COLEMAN, JAMES L | philip@jlab.org | colemanj@jlab.org | Nothing Due until 4/20/18 1st Inv expected in June 2018 Milestone $172K materials expected 10/15/18
19-C0747 | Open | DANFYSIK A/S | 445.9 | 298.97 | 298.97 | 146.93 | 146.93 | THOMAS HURATIAK | S LASSITER | LASSITER, STEVEN R | HURATIAK, THOMAS | lassiter@jlab.org | huratiak@jlab.org
19-D0461 | Open | DAVIDSON COLLEGE | 43.3598 | 23.3964 | 21.8738 | 19.9634 | 21.486 | GIUSEPPINA TENBUSCH | TANYA STEWART | STEWART, TANYA-GAYE N | TENBUSCH, GIUSEPPINA | fraites@jlab.org | jessie@jlab.org | Yes
18-C0268 | Open | DUKE UNIVERSITY | 192.2692 | 174.5188 | 174.5188 | 17.7505 | 17.7505 | GIUSEPPINA TENBUSCH | TANYA STEWART | STEWART, TANYA-GAYE N | PARKINSON, SHARON K | fraites@jlab.org | spark@jlab.org | Yes
19-C0777 | Open | D&D MECHANICAL INC | 345.1408 | 291.5204 | 259.8063 | 53.6204 | 85.3345 | CAROLYN STEPNEY | J WILLOUGHBY | WILLOUGHBY, JASON | FRIES, RUSSELL W | jasonw@jlab.org | rfries@jlab.org
19-D0253 | Open | FLORIDA STATE UNIVERSITY | 71.6716 | 56.0816 | 52.9067 | 15.5901 | 18.7649 | GIUSEPPINA TENBUSCH | TANYA STEWART | STEWART, TANYA-GAYE N | PARKINSON, SHARON K | fraites@jlab.org | spark@jlab.org | Yes
20-C0031 | Open | GEORGE WASHINGTON UNIV | 73.4682 | 36.2018 | 36.2012 | 37.2664 | 37.267 | MICHELE KHASIDIS | T STEWART | STEWART, TANYA-GAYE N |  | fraites@jlab.org |  | Yes | GEORGE WASHINGTON UNIV 14C0252400
17-C1197 | Open | HAMPTON UNIVERSITY | 183.5834 | 159.8334 | 159.8334 | 23.75 | 23.75 | GIUSEPPINA TENBUSCH | TANYA STEWART | STEWART, TANYA-GAYE N | PARKINSON, SHARON K | fraites@jlab.org | spark@jlab.org | Yes | HAMPTON UNIVERSITY 17-C1197
18-C1361 | Open | HAMPTON UNIVERSITY | 332.9872 | 297.7697 | 289.55 | 35.2175 | 43.4372 | GIUSEPPINA TENBUSCH | TANYA STEWART | [5 empty] | HAMPTON UNIVERSITY 17-C1197
19-C0904 | Open | HOMELAND CONTRACTING CORP | 1460.471 | 1052.7576 | 1052.6409 | 407.7134 | 407.8301 | CAROLYN STEPNEY | T RENZO | FRIES, RUSSELL W | DOLBECK, JOEL | rfries@jlab.org | dolbeck@jlab.org | Russell Fries is SOTR.
20-C0029 | Open | JOSEPH OAT CORPORATION | 1844.463 | 1237.2878 | 1237.2878 | 607.1752 | 607.1752 | THOMAS HURATIAK | K WILSON/MIKED | WILSON, KATHERINE M | DICKEY, MICHAEL D | kwilson@jlab.org | mdickey@jlab.org
20-C0009 | Open | KELLER TECHNOLOGY CORP. | 271.91 | 158.16 | 158.16 | 113.75 | 113.75 | THEODORE PESHEHONOFF | N HUQUE | PESHEHONOFF, THEODORE | WILSON, KATHERINE M | tvp@jlab.org | kwilson@jlab.org
20-D0103 | Open | MASSACHUSETTS INST OF TEC | 30 | 9.999 | 5 | 20.001 | 25 | MICHELE KHASIDIS | T STEWART | STEWART, TANYA-GAYE N |  | fraites@jlab.org |  | Yes
20-C0439 | Open | MEYER TOOL & MFG INC | 335.82 | 117.537 | 117.537 | 218.283 | 218.283 | DEANN MADDOX | M MARCHLIK | MARCHLIK, MATTHEW J |  | marchlik@jlab.org
20-C0499 | Open | MEYER TOOL & MFG INC | 1149.47 | 474.705 | 474.705 | 674.765 | 674.765 | MELISSA TORRES | G CHENG | TORRES, MELISSA C | CHENG, GUANGFENG | torres@jlab.org | cheng@jlab.org
19-D0382 | Open | MICHIGAN STATE UNIVERSITY | 82.8631 | 45.4151 | 38.8068 | 37.448 | 44.0564 | MICHELE KHASIDIS | TANYA STEWART | STEWART, TANYA-GAYE N |  | fraites@jlab.org |  | Yes
20-D0554 | Open | MISSISSIPPI STATE UNIVER. | 34.631 | 24.2417 | 20.7786 | 10.3893 | 13.8524 | MICHELE KHASIDIS | T STEWART | STEWART, TANYA-GAYE N |  | fraites@jlab.org |  | Yes
19-C1456 | Open | NORFOLK STATE UNIVERSITY | 55.2221 | 55.2221 | 7.3629 | 0 | 47.8591 | MICHELE KHASIDIS | T STEWART | STEWART, TANYA-GAYE N |  | fraites@jlab.org |  | Nothing until August
17-C1093 | Open | OLD DOMINION UNIV. RESEAR | 2363.5924 | 2208.2055 | 1991.0678 | 155.3869 | 372.5246 | GIUSEPPINA TENBUSCH | TANYA STEWART | STEWART, TANYA-GAYE N | PARKINSON, SHARON K | fraites@jlab.org | spark@jlab.org | Yes | ODU 17-C1093
17-C1150 | Open | OLD DOMINION UNIV. RESEAR | 1012.8526 | 881.2458 | 771.077 | 131.6068 | 241.7756 | GIUSEPPINA TENBUSCH | TANYA STEWART | STEWART, TANYA-GAYE N |  | fraites@jlab.org |  | Yes | ODU 17-C1150
15C1391400 | Open | PENNSYLVANIA STATE UNIV. | 49.2186 | 46.7186 | 46.7186 | 2.5 | 2.5 | DENISE LEARY-STITH | TANYA STEWART | STEWART, TANYA-GAYE N | PARKINSON, SHARON K | fraites@jlab.org | spark@jlab.org | Contract Ended. This should be closed
20-C0726 | Open | RI RESEARCH INSTRUMENTS | 280.2 | 56.04 | 56.04 | 224.16 | 224.16 | MELISSA TORRES | G CIVOVATI | TORRES, MELISSA C | CIOVATI, GIANLUIGI | torres@jlab.org | gciovati@jlab.org
20-C0011 | Open | SCIAKY INC | 1588.647 | 714.891 | 714.891 | 873.756 | 873.756 | THEODORE PESHEHONOFF | PHILIP DENNY | PESHEHONOFF, THEODORE | DENNY, PHILIP J | tvp@jlab.org | denny@jlab.org
20-C0825 | Open | SHANGHAI SICCAS HIGH TECH | 484 | 0 | 0 | 484 | 484 | MELISSA TORRES | A SOMOV | TORRES, MELISSA C | SOMOV, ALEXANDER | torres@jlab.org | somov@jlab.org
20-C0004 | Open | SUMITOMO CORP OF AMERICAS | 368.872 | 0 | 0 | 368.872 | 368.872 | MELISSA TORRES | G CHENG | TORRES, MELISSA C | CHENG, GUANGFENG | torres@jlab.org | cheng@jlab.org |  | CATHOLIC UNIVERSITY 17-C1148
20-C0375 | Open | TECHNIFAB PRODUCTS INC | 328.972 | 68.1075 | 68.1075 | 260.8645 | 260.8645 | MELISSA TORRES | N LAVERDURE | TORRES, MELISSA C | LAVERDURE, NATHANIEL A | torres@jlab.org | nal@jlab.org
17-C1148 | Open | THE CATHOLIC UNIVERSITY | 286.8417 | 263.7077 | 263.7077 | 23.134 | 23.134 | MICHELE KHASIDIS | TANYA STEWART | STEWART, TANYA-GAYE N |  | fraites@jlab.org |  | yes | CATHOLIC UNIVERSITY 17-C1148
18-P1387 | Open | THE CATHOLIC UNIVERSITY | 56.216 | 48.68 | 48.68 | 7.536 | 7.536 | MICHELE KHASIDIS | TANYA STEWART | STEWART, TANYA-GAYE N |  | fraites@jlab.org |  | yes
20-D0376 | Open | THE CATHOLIC UNIVERSITY | 24.75 | 12.375 | 9.625 | 12.375 | 15.125 | MICHELE KHASIDIS | T STEWART | STEWART, TANYA-GAYE N |  | fraites@jlab.org |  | yes
18-C1373 | Open | TRUSTEES OF INDIANA UNIVE | 292.4698 | 278.9123 | 249.9405 | 13.5575 | 42.5293 | GIUSEPPINA TENBUSCH | TANYA STEWART | STEWART, TANYA-GAYE N | PARKINSON, SHARON K | fraites@jlab.org | spark@jlab.org | Nothing until August | CATHOLIC UNIVERSITY 17-C1148
19-D1431 | Open | TRUSTEES OF INDIANA UNIVE | 57 | 38 | 38 | 19 | 19 | GIUSEPPINA TENBUSCH | T STEWART | STEWART, TANYA-GAYE N | PARKINSON, SHARON K | fraites@jlab.org | spark@jlab.org | Yes | CATHOLIC UNIVERSITY 17-C1148
20-C0568 | Open | UNIVERSITY OF CALIFORNIA | 44.9973 | 21.505 | 0 | 23.4923 | 44.9973 | MICHELE KHASIDIS | T STEWART | STEWART, TANYA-GAYE N |  | fraites@jlab.org |  | Yes
19-D1166 | Open | UNIVERSITY OF CONNECTICUT | 46.8066 | 32.324 | 32.324 | 14.4826 | 14.4826 | MICHELE KHASIDIS | TANYA STEWART | STEWART, TANYA-GAYE N |  | fraites@jlab.org |  | Yes
20-D0982 | Open | UNIVERSITY OF VIRGINIA | 45 | 0 | 0 | 45 | 45 | MICHELE KHASIDIS | TANYA STEWART | STEWART, TANYA-GAYE N |  | fraites@jlab.org |  | Yes
19-D0351 | Open | WESSINGTON CRYOGENICS LTD | 150.622 | 150.622 | 113.1949 | 0 | 37.4271 | MELISSA TORRES | C KAUFMANN | TORRES, MELISSA C | LAVERDURE, NATHANIEL A | torres@jlab.org | nal@jlab.org
Open Count
45 | 45