## Sheet1
Subcontract PO Status Update |  |  |  | Updated: | 2020-07-31
PO NUMBER | PO STATUS | VENDOR NAME | PO Value (in $K) | PO Accrued (in $K) | PO Vouchered (in $K) | Balance (Val-Accr) (in $K) | Bal (Val-Vouch) (in $K) | BUYER | END USER | POC1 | POC2 | POC1 Email | POC2 Email | NOTES
15-C1196 | Open | AIR LIQUIDE ADVANCED TECH | 18607.6228 | 17240.6481 | 17240.6101 | 1366.9747 | 1367.0126 | THEODORE PESHEHONOFF | ARENIUS/MBEVINS | PESHEHONOFF, THEODORE | ARENIUS, DANA M | tvp@jlab.org | arenius@jlab.org
18-C0415 | Open | AIR LIQUIDE ADVANCED TECH | 2512.855 | 2362.726 | 2362.726 | 150.129 | 150.129 | THEODORE PESHEHONOFF | NORTON | PESHEHONOFF, THEODORE | NORTON, ROBERT O | tvp@jlab.org | norton@jlab.org | Ted - No accrual until provided Milestone expected Nov 2018
20-C0007 | Open | ANDERSON & DAHLEN INC | 1259.3 | 503.72 | 503.72 | 755.58 | 755.58 | THEODORE PESHEHONOFF | MARCHLIK | PESHEHONOFF, THEODORE | WILSON, KATHERINE M | tvp@jlab.org | kwilson@jlab.org
20-C0733 | Open | CARR ELECTRICAL TECHNOLOG | 431.623 | 52.6148 | 52.605 | 379.0082 | 379.018 | CAROLYN STEPNEY | J WILLOUGHBY | WILLOUGHBY, JASON | FRIES, RUSSELL W | jasonw@jlab.org | rfries@jlab.org
20-C0820 | Open | CARR ELECTRICAL TECHNOLOG | 281.815 | 34.466 | 34.459 | 247.349 | 247.356 | CAROLYN STEPNEY | E WINSLOW | WINSLOW, EDWARD B | FRIES, RUSSELL W | winslow@jlab.org | rfries@jlab.org
19-D0681 | Open | CENTRE NATIONALE DE | 28.8 | 14.4 | 14.4 | 14.4 | 14.4 | GIUSEPPINA TENBUSCH | TANYA STEWART | STEWART, TANYA-GAYE N | PARKINSON, SHARON K | fraites@jlab.org | spark@jlab.org
17-C1149 | Open | COLLEGE OF WILLIAM & MARY | 438.7782 | 386.5282 | 336.6532 | 52.25 | 102.125 | DENISE LEARY-STITH | TANYA STEWART | STEWART, TANYA-GAYE N | PARKINSON, SHARON K | fraites@jlab.org | spark@jlab.org
18-C0507 | Open | COLLEGE OF WILLIAM & MARY | 814.3555 | 753.9001 | 640.6524 | 60.4555 | 173.7031 | DENISE LEARY-STITH | TANYA STEWART | STEWART, TANYA-GAYE N | PARKINSON, SHARON K | fraites@jlab.org | spark@jlab.org
20-C0336 | Open | CPI INTERNATIONAL INC | 5562.455 | 0 | 0 | 5562.455 | 5562.455 | THEODORE PESHEHONOFF | HUQUE | PESHEHONOFF, THEODORE | HUQUE, NAEEM A | tvp@jlab.org | huque@jlab.org
18-C0548 | Open | DANFYSIK A/S | 492.842 | 485.6169 | 485.6145 | 7.2251 | 7.2275 | THOMAS HURATIAK | JAMES COLEMAN | PHILIP, SARIN | COLEMAN, JAMES L | philip@jlab.org | colemanj@jlab.org | Nothing Due until 4/20/18 1st Inv expected in June 2018 Milestone $172K materials expected 10/15/18
19-C0747 | Open | DANFYSIK A/S | 445.9 | 298.97 | 298.97 | 146.93 | 146.93 | THOMAS HURATIAK | S LASSITER | LASSITER, STEVEN R | HURATIAK, THOMAS | lassiter@jlab.org | huratiak@jlab.org
19-D0461 | Open | DAVIDSON COLLEGE | 43.3598 | 30.6928 | 21.8738 | 12.667 | 21.486 | GIUSEPPINA TENBUSCH | TANYA STEWART | STEWART, TANYA-GAYE N | TENBUSCH, GIUSEPPINA | fraites@jlab.org | jessie@jlab.org
18-C0268 | Open | DUKE UNIVERSITY | 192.2692 | 192.2692 | 187.9293 | 0 | 4.3399 | GIUSEPPINA TENBUSCH | TANYA STEWART | STEWART, TANYA-GAYE N | PARKINSON, SHARON K | fraites@jlab.org | spark@jlab.org
19-C0777 | Open | D&D MECHANICAL INC | 345.1408 | 291.5204 | 259.8063 | 53.6204 | 85.3345 | CAROLYN STEPNEY | J WILLOUGHBY | WILLOUGHBY, JASON | FRIES, RUSSELL W | jasonw@jlab.org | rfries@jlab.org
19-D0253 | Open | FLORIDA STATE UNIVERSITY | 71.6716 | 59.9791 | 59.2564 | 11.6926 | 12.4152 | GIUSEPPINA TENBUSCH | TANYA STEWART | STEWART, TANYA-GAYE N | PARKINSON, SHARON K | fraites@jlab.org | spark@jlab.org
20-C0031 | Open | GEORGE WASHINGTON UNIV | 73.4682 | 47.8581 | 47.6328 | 25.6101 | 25.8354 | MICHELE KHASIDIS | T STEWART | STEWART, TANYA-GAYE N |  | fraites@jlab.org
17-C1197 | Open | HAMPTON UNIVERSITY | 183.5834 | 161.0209 | 159.8334 | 22.5625 | 23.75 | GIUSEPPINA TENBUSCH | TANYA STEWART | STEWART, TANYA-GAYE N | PARKINSON, SHARON K | fraites@jlab.org | spark@jlab.org
18-C1361 | Open | HAMPTON UNIVERSITY | 332.9872 | 309.204 | 289.55 | 23.7833 | 43.4372 | GIUSEPPINA TENBUSCH | TANYA STEWART | STEWART, TANYA-GAYE N | PARKINSON, SHARON K | fraites@jlab.org | spark@jlab.org
19-C0904 | Open | HOMELAND CONTRACTING CORP | 1460.471 | 1052.7576 | 1052.6409 | 407.7134 | 407.8301 | CAROLYN STEPNEY | T RENZO | FRIES, RUSSELL W | DOLBECK, JOEL | rfries@jlab.org | dolbeck@jlab.org | Russell Fries is SOTR.
20-C0029 | Open | JOSEPH OAT CORPORATION | 1844.463 | 1326.3652 | 1326.3652 | 518.0978 | 518.0978 | THOMAS HURATIAK | K WILSON/MIKED | WILSON, KATHERINE M | DICKEY, MICHAEL D | kwilson@jlab.org | mdickey@jlab.org
20-D0103 | Open | MASSACHUSETTS INST OF TEC | 30 | 9.999 | 5 | 20.001 | 25 | MICHELE KHASIDIS | T STEWART | STEWART, TANYA-GAYE N |  | fraites@jlab.org
20-C0439 | Open | MEYER TOOL & MFG INC | 335.82 | 167.91 | 167.91 | 167.91 | 167.91 | DEANN MADDOX | M MARCHLIK | MARCHLIK, MATTHEW J |  | marchlik@jlab.org
20-C0499 | Open | MEYER TOOL & MFG INC | 1149.47 | 551.18 | 551.18 | 598.29 | 598.29 | MELISSA TORRES | G CHENG | TORRES, MELISSA C | CHENG, GUANGFENG | torres@jlab.org | cheng@jlab.org
19-D0382 | Open | MICHIGAN STATE UNIVERSITY | 82.8631 | 48.6959 | 38.8068 | 34.1672 | 44.0564 | MICHELE KHASIDIS | TANYA STEWART | STEWART, TANYA-GAYE N |  | fraites@jlab.org
20-D0554 | Open | MISSISSIPPI STATE UNIVER. | 34.631 | 24.2417 | 20.7786 | 10.3893 | 13.8524 | MICHELE KHASIDIS | T STEWART | STEWART, TANYA-GAYE N |  | fraites@jlab.org
19-C1456 | Open | NORFOLK STATE UNIVERSITY | 66.2665 | 55.2221 | 7.3629 | 11.0444 | 58.9035 | MICHELE KHASIDIS | T STEWART | STEWART, TANYA-GAYE N |  | fraites@jlab.org
17-C1093 | Open | OLD DOMINION UNIV. RESEAR | 2363.5924 | 2208.2055 | 2137.1317 | 155.3869 | 226.4607 | GIUSEPPINA TENBUSCH | TANYA STEWART | STEWART, TANYA-GAYE N | PARKINSON, SHARON K | fraites@jlab.org | spark@jlab.org
20-D0972 | Open | OLD DOMINION UNIV. RESEAR | 94.3784 | 0 | 0 | 94.3784 | 94.3784 | GIUSEPPINA TENBUSCH | TANYA STEWART | STEWART, TANYA-GAYE N | PARKINSON, SHARON K | fraites@jlab.org | spark@jlab.org
17-C1150 | Open | OLD DOMINION UNIV. RESEAR | 1012.8526 | 894.2978 | 837.5499 | 118.5548 | 175.3027 | GIUSEPPINA TENBUSCH | TANYA STEWART | STEWART, TANYA-GAYE N |  | fraites@jlab.org
15C1391400 | Open | PENNSYLVANIA STATE UNIV. | 49.2186 | 46.7186 | 46.7186 | 2.5 | 2.5 | DENISE LEARY-STITH | TANYA STEWART | STEWART, TANYA-GAYE N | PARKINSON, SHARON K | fraites@jlab.org | spark@jlab.org
20-C0726 | Open | RI RESEARCH INSTRUMENTS | 280.2 | 56.04 | 56.04 | 224.16 | 224.16 | MELISSA TORRES | G CIVOVATI | TORRES, MELISSA C | CIOVATI, GIANLUIGI | torres@jlab.org | gciovati@jlab.org
20-C0011 | Open | SCIAKY INC | 1588.647 | 714.891 | 714.891 | 873.756 | 873.756 | THEODORE PESHEHONOFF | PHILIP DENNY | PESHEHONOFF, THEODORE | DENNY, PHILIP J | tvp@jlab.org | denny@jlab.org
20-C0825 | Open | SHANGHAI SICCAS HIGH TECH | 484 | 0 | 0 | 484 | 484 | MELISSA TORRES | A SOMOV | TORRES, MELISSA C | SOMOV, ALEXANDER | torres@jlab.org | somov@jlab.org
20-C0004 | Open | SUMITOMO CORP OF AMERICAS | 368.872 | 0 | 0 | 368.872 | 368.872 | MELISSA TORRES | G CHENG | TORRES, MELISSA C | CHENG, GUANGFENG | torres@jlab.org | cheng@jlab.org
20-C0375 | Open | TECHNIFAB PRODUCTS INC | 328.972 | 173.227 | 173.224 | 155.745 | 155.748 | MELISSA TORRES | N LAVERDURE | TORRES, MELISSA C | LAVERDURE, NATHANIEL A | torres@jlab.org | nal@jlab.org
17-C1148 | Open | THE CATHOLIC UNIVERSITY | 286.8417 | 278.9646 | 278.9646 | 7.8772 | 7.8772 | MICHELE KHASIDIS | TANYA STEWART | STEWART, TANYA-GAYE N |  | fraites@jlab.org
18-P1387 | Open | THE CATHOLIC UNIVERSITY | 56.216 | 50.564 | 50.564 | 5.652 | 5.652 | MICHELE KHASIDIS | TANYA STEWART | STEWART, TANYA-GAYE N |  | fraites@jlab.org
20-D0376 | Open | THE CATHOLIC UNIVERSITY | 24.75 | 15.1272 | 15.125 | 9.6228 | 9.625 | MICHELE KHASIDIS | T STEWART | STEWART, TANYA-GAYE N |  | fraites@jlab.org
18-C1373 | Open | TRUSTEES OF INDIANA UNIVE | 292.4698 | 282.395 | 249.9405 | 10.0747 | 42.5293 | GIUSEPPINA TENBUSCH | TANYA STEWART | STEWART, TANYA-GAYE N | PARKINSON, SHARON K | fraites@jlab.org | spark@jlab.org
19-D1431 | Open | TRUSTEES OF INDIANA UNIVE | 57 | 42.75 | 42.75 | 14.25 | 14.25 | GIUSEPPINA TENBUSCH | T STEWART | STEWART, TANYA-GAYE N | PARKINSON, SHARON K | fraites@jlab.org | spark@jlab.org
20-C0568 | Open | UNIVERSITY OF CALIFORNIA | 44.9973 | 28.6733 | 0 | 16.324 | 44.9973 | MICHELE KHASIDIS | T STEWART | STEWART, TANYA-GAYE N |  | fraites@jlab.org
19-D1166 | Open | UNIVERSITY OF CONNECTICUT | 46.8066 | 36.4362 | 36.4362 | 10.3704 | 10.3704 | MICHELE KHASIDIS | TANYA STEWART | STEWART, TANYA-GAYE N |  | fraites@jlab.org
20-D1030 | Open | UNIV OF MASSACHUSETTS | 48.0912 | 0 | 0 | 48.0912 | 48.0912 | MICHELE KHASIDIS | TANYA STEWART | STEWART, TANYA-GAYE N |  | fraites@jlab.org
20-D0982 | Open | UNIVERSITY OF VIRGINIA | 40.512 | 2.7112 | 0 | 37.8008 | 40.512 | MICHELE KHASIDIS | TANYA STEWART | STEWART, TANYA-GAYE N |  | fraites@jlab.org
19-D0351 | Open | WESSINGTON CRYOGENICS LTD | 150.622 | 150.622 | 148.5459 | 0 | 2.0761 | MELISSA TORRES | C KAUFMANN | TORRES, MELISSA C | LAVERDURE, NATHANIEL A | torres@jlab.org | nal@jlab.org
Open Count
45 | 45