## Form
JSA / Jefferson Lab - DOE
PO Accrual Form
Appendix A
Vendor Name | CPI | [9 empty] | PO with Peg Points? (Yes or No) | No
PO Number | 20-C0336 | LCLS-II HE FPC Subcontract | [5 empty] | Buyer | Peshehonoff | Complete through | 2021-05-31
|  | Only one column should have data | [7 empty] | Date | 2021-05-31
PO Line # | Description | Percent Complete | OR | Quantity Received | OR | Completed Peg Point (X) |  | Summary of Work (if less than 100%)
1 | Completion of Kickoff Meeting / Long-lead Material Order | 100%
2 | Review and Approval of Manufacturing Drawings | 100%
3 | Receipt of long-lead material | 100%
4 | Production Readiness Review (PRR) | 100%
5 | First Article Completion and Pre-Shipment Review (PSR) | 100%
6 | First Article Acceptance (Lots 1-5) (10 units) | 0%
7 | Lots 6-9 (8 units) | 0%
8 | Lots 10-17 (16 units) | 0%
9 | Lots 18-25 (16 units) | 0%
10 | Lots 26-33 (16 units) | 0%
11 | Lots 34-41 (16 units) | 0%
12 | Lots 42-49 (16 units) | 0%
13 | Lots 50-57 (16 units) | 0%
14 | Lots 58-65 (16 units) | 0%
15 | Lots 66-73 (16 units) | 0%
16 | Lots 74-81 (16 units) | 0%
17 | Lot 82 + 1 unit (3 Units) | 0%
18 | Mod001/002 Changes Post Drawing Review | 100%
Vendor Technical Representative Contacted: | [8 empty] | Steve Einarson |  |  | 2021-05-31
[7 empty] | Name |  |  |  |  | Date
Jlab Control Account Manager (CAM): | [8 empty] | Katherine Wilson |  |  | 2021-05-31
[10 empty] | Name |  | Date
Below for use by Accounting/Shipping & Receiving Only
Accounting or Shipping & Receiving Entered By:
Date
Data Entry Verified By:
Date

## Process
JSA / Jefferson Lab - DOE
PO Accrual Form
Procedure
A Subcontract Purchase Order (PO) is a service type PO with loosely defined scheduled deliverables and/or variable amounts. A Peg Point PO has specified scheduled deliverable dates to be completed for a specified amount. Note Quantities Received if items did not come through Shipping & Receiving (e.g. items shipped to another vendor).
Complete this form by the 2nd work day after month end if an invoice has been not been approved by the SOTR or CAM for work completed through the end of the month. NOTE: This form can still be completed by the 2nd work day of the month to ensure the accrual is processed.
SOTR or CAM contacts a vendor technical representative for an evaluation of the percent of work completed (or quantity received by vendor). This can be done either verbally or via email.
OR
SOTR or CAM has an objective way to measure the perecent of work complete (e.g. Standardize monthly payment, using schedule of values to determine value of work complete)
Required information - Vendor Name, indicate if PO is a Peg Point type PO or not, PO #, Buyer, Complete through date (usually the end of the month), PO Line #, Percent complete (or quantity received by vendor), a short Summary of Work performed provided by the Vendor Technical Representative that supports the percent complete if less than 100%, the name of the Vendor Technical Representative contacted, and the CAM name.
The SOTR or CAM will submit a PO Accrual Form by the 2nd working day following the end of the month affected for work that has been completed. This allows time for Accounting to process an accrual for the month end closing. Reminder if PO is for Peg Points, the peg point must be fully complete before claiming it.
Submit the completed form with all the information via email to evpo@jlab.org. The file name of the spreadsheet attached to the email should always include the PO# and the letters 'S&R' if it is a Peg Point type PO or if items were received by did not go through JLab's Shipping and Receiving Department. File name examples: Peg Point Type PO 08-C5413 S&R, Subcontract Type PO 08-A2659. This email will forward the form automatically to personnel in Procurement, Shipping & Receiving, CFO, and PMO.
If the PO is a Subcontract type PO, the SOTR or CAM will still be required to sign all invoices received at JLab from the vendor up since this was an estimate. An approved invoice by the SOTR or CAM can also be used as basis for the percent of work complete.
If the PO is a Peg Point type PO or material has been received, Shipping & Receiving will use this form to enter the information into the Costpoint Financial System. No additional invoice approvals will be required since the SOTR or CAM already indicated the work was complete. An approved invoice by the SOTR or CAM can also be used as basis for the percent of work complete without having to complete this form.
If a previous percent complete was submitted and subsequently determined to be in error, adjust the percent complete to correct the error. Add an explanatory note to support the adjustment.

## Accting USE Data Entry Form
JSA / Jefferson Lab - DOE
Data Entry Update Subcontract PO Percent Complete
Appendix B
| Vendor Name |  | CPI | [5 empty] | Percent complete thru |  |  | 2021-05-31
(Date)
| PO Number |  | 20-C0336 | [6 empty] | OR
Invoice Number
PO Line # | Description | Expected Due Date | Percent Complete |  | PO Line Total | = | Completed Work Amt | Completed Work Amt | - | Eligible for Voucher Amt | - | Invoice Approved Amount | = | Completed Work Retention Amt | Invoice # | Date Approved
1 | Completion of Kickoff Meeting / Long-lead Material Order | 2020-07-10 | 100% | X | 553506.5 | = | 553506.5 | 553506.5 | - | 553506.5 | - | 553506.5 | = | 0 | 29804 | 2020-09-15
2 | Review and Approval of Manufacturing Drawings | 2020-07-31 | 100% | X | 276753.25 | = | 276753.25 | 276753.25 | - | 276753.25 | - | 276753.25 | = | 0 | 29805 | 2020-09-14
3 | Receipt of long-lead material | 2020-12-11 | 100% | X | 553506.5 | = | 553506.5 | 553506.5 | - | 553506.5 | - | 553506.5 | = | 0 | 30361 | 2021-01-06
4 | Production Readiness Review (PRR) | 2020-12-16 | 100% | X | 276753.25 | = | 276753.25 | 276753.25 | - | 276753.25 | - | 276753.25 | = | 0 | 30329 | 2021-01-05
5 | First Article Completion and Pre-Shipment Review (PSR) | 2021-05-07 | 100% | X | 553506.5 | = | 553506.5 | 553506.5 | - | 553506.5 | - |  | = | 553506.5
6 | First Article Acceptance (Lots 1-5) (10 units) | 2021-06-11 |  | X | 553506.5 | = | 0 | 0 | - | 0 | - |  | = | 0
7 | Lots 6-9 (8 units) | 2021-07-12 |  | X | 135000 | = | 0 | 0 | - | 0 | - |  | = | 0
8 | Lots 10-17 (16 units) | 2021-08-11 |  | X | 270000 | = | 0 | 0 | - | 0 | - |  | = | 0
9 | Lots 18-25 (16 units) | 2021-09-10 |  | X | 270000 | = | 0 | 0 | - | 0 | - |  | = | 0
10 | Lots 26-33 (16 units) | 2021-10-10 |  | X | 270000 | = | 0 | 0 | - | 0 | - |  | = | 0
11 | Lots 34-41 (16 units) | 2021-11-09 |  | X | 270000 | = | 0 | 0 | - | 0 | - |  | = | 0
12 | Lots 42-49 (16 units) | 2021-12-09 |  | X | 270000 | = | 0 | 0 | - | 0 | - |  | = | 0
13 | Lots 50-57 (16 units) | 2022-01-08 |  | X | 270000 | = | 0 | 0 | - | 0 | - |  | = | 0
14 | Lots 58-65 (16 units) | 2022-02-07 |  | X | 270000 | = | 0 | 0 | - | 0 | - |  | = | 0
15 | Lots 66-73 (16 units) | 2022-03-09 |  | X | 270000 | = | 0 | 0 | - | 0 | - |  | = | 0
16 | Lots 74-81 (16 units) | 2022-04-08 |  | X | 270000 | = | 0 | 0 | - | 0 | - |  | = | 0
17 | Lot 82 + 1 unit (3 Units) | 2022-05-08 |  | X | 229922.5 | = | 0 | 0 | - | 0 | - |  | = | 0
18 | Mod001/002 Changes Post Drawing Review | 2022-11-20 | 100% | X | 125496.75 | = | 125496.75 | 125496.75 | - | 125496.75 | - |  | = | 125496.75 | 30189 | 2020-12-01
|  |  | Total Value |  | 5687951.75 |  |  |  |  | Total Paid |  | 1660519.5
Procurement Entered By: ________________________________________________________________ |  |  |  |  | Ted Peshehonoff
Date
Procurement Data Entry Verified By: _______________________________________________________
Date