## Form
JSA / Jefferson Lab - DOE
PO Accrual Form
Appendix A
Vendor Name | MIT | [8 empty] | PO with Peg Points? (Yes or No) | No
PO Number | 24-D0863 | [5 empty] | Buyer | Giuseppina Tenbusch | Complete through | 2024-08-28
| Only one column should have data | [8 empty] | (Date)
PO Line # | Percent Complete | OR | Quantity Received | OR | Completed Peg Point (X) |  | Summary of Work (only if less than 100%)
1 | 31% | [5 empty] | Periphery implementation: Add report lint stage int the implementation flow and analysis of lint errors Dummy sbb_buf, sbb_lec and sbb_rec cells replaced by the golden schmatics in the sbb OA: added model for all leaf cells, adapt scritp for netlist parsign, adapt new config view for the schematics testbench on sos, regenerate .lib files, netlist, models and models with annotated timing. Did investigation on isolation cells and proposed architetural solution to the fact that these cells do not protect against undefiend states going from periphery when is powered off to the sbb tile block. Adapt sbb tile block for this change. Adapt connections on RSU level for the architectural change of sbb_tile. Driving the rest of specifiation for final sbb_tile design including removing isolation cells from the configuration bits to not introduce TMR senstivity and final specification for the retiming part of the sbb_tile. Did shematics for all sub-block of sbb_tile and the top level shematic. Further finalized prepapration of sbb_tile for integraiton inside the periphery, including: - generate abstract - adapted cell configuration for netlist extraction - add models for all leaf cells; change extracted model for sbb_tile_S2D_PreDriver_TX manually due to back-to-back inverters - generate .lib files; adapt template for the final sbb_tile; sanity check of timing arcs - adapt netlist parsing script for sbb_tile - generate models - adapting uvm tests for the final sbb_tile Did studies and trials for liberate characterization until convering on the liberate AMS configuraton that gives all wanted timing arcs. Periphery implementation: Adapting the LAVDD power strips that were out of pitch with relation to the pixel matrix, fixing the power grid. Adding power pin on periphery for new conf bit. Investigation on the implemetnaiton flowkit issue, where timing reports differ significantly from design_finishing and export. Found a source of the mismathc to be in commos steps provided by Cadence and triggered further investigation on this. Updated documentation for the final sbb_tile. Integration of the sbb_tile inside the periphery: 1) Adapt periphery: - Adapt pinout connections of the wrapper for sbb_tile - adapt power intent file - adapt .sdc constraints 2) Solved setup timing violations. Did a big analysis to find the best way to skew-balance the clock trees, this includes: - doing clock skew balancing for 160 MHz clock separately from the main clock - found several issues and currently working on the solution (clock used for fifo inside periphery not reported as clock tree, clock implicitely created on the pins of differential data output, liberate AMS givess only falling arc for output data). Fix hold violations in the priphery; Implemented design custom steps to set nets between sbb_tile and periphery IOs as ""don't touch"" during synthesis and routing and manually routed all these nets and changing positions of needed IOs to enable vertical alignment. Solved a few issues found in verification regarding the models automatically extracted from the netlist which includes adding models manully,adapting netlist tb and regenerating .rtl and annotated models. Regenerate also all models and netlists after OA porting to 7M2L1F metal stuck as some schematics as some schematics were adopted only on the new OA. Did a case study of what is causing 3ns capture edge for timing analysis for setialier->sbb_tile data path. Found source of the problem and imporoved setup for running Liberate AMS characterization such that this problem does not occur. Cleanup async reser in tile serialzier and perifperhy following the decision to use only sync reset and solving JG superlint failures. Extensive analoysis of CCopt clock specifications and solving implictly declared clock on wrong pins.
2 | 0% | [5 empty] | ER2 sensors not delivered yet
Vendor Technical Representative Contacted: | [7 empty] | Jelena Lalic |  |  | 2024-08-21
[6 empty] | Name |  |  |  |  | Date
Jlab Control Account Manager (CAM): | [7 empty] | Brian Eng |  |  | 2024-08-22
[9 empty] | Name |  | Date
Below for use by Accounting/Shipping & Receiving Only
Accounting or Shipping & Receiving Entered By:
Date
Data Entry Verified By:
Date

## Process
JSA / Jefferson Lab - DOE
PO Accrual Form
Procedure
A Subcontract Purchase Order (PO) is a service type PO with loosely defined scheduled deliverables and/or variable amounts. A Peg Point PO has specified scheduled deliverable dates to be completed for a specified amount. Note Quantities Received if items did not come through Shipping & Receiving (e.g. items shipped to another vendor).
Complete this form by the 2nd work day after month end if an invoice has been not been approved by the SOTR or CAM for work completed through the end of the month. NOTE: This form can still be completed by the 2nd work day of the month to ensure the accrual is processed.
SOTR or CAM contacts a vendor technical representative for an evaluation of the percent of work completed (or quantity received by vendor). This can be done either verbally or via email.
OR
SOTR or CAM has an objective way to measure the perecent of work complete (e.g. Standardize monthly payment, using schedule of values to determine value of work complete)
Required information - Vendor Name, indicate if PO is a Peg Point type PO or not, PO #, Buyer, Complete through date (usually the end of the month), PO Line #, Percent complete (or quantity received by vendor), a short Summary of Work performed provided by the Vendor Technical Representative that supports the percent complete if less than 100%, the name of the Vendor Technical Representative contacted, and the CAM name.
The SOTR or CAM will submit a PO Accrual Form by the 2nd working day following the end of the month affected for work that has been completed. This allows time for Accounting to process an accrual for the month end closing. Reminder if PO is for Peg Points, the peg point must be fully complete before claiming it.
Submit the completed form with all the information via email to evpo@jlab.org. The file name of the spreadsheet attached to the email should always include the PO# and the letters 'S&R' if it is a Peg Point type PO or if items were received by did not go through JLab's Shipping and Receiving Department. File name examples: Peg Point Type PO 08-C5413 S&R, Subcontract Type PO 08-A2659. This email will forward the form automatically to personnel in Procurement, Shipping & Receiving, CFO, and PMO.
If the PO is a Subcontract type PO, the SOTR or CAM will still be required to sign all invoices received at JLab from the vendor up since this was an estimate. An approved invoice by the SOTR or CAM can also be used as basis for the percent of work complete.
If the PO is a Peg Point type PO or material has been received, Shipping & Receiving will use this form to enter the information into the Costpoint Financial System. No additional invoice approvals will be required since the SOTR or CAM already indicated the work was complete. An approved invoice by the SOTR or CAM can also be used as basis for the percent of work complete without having to complete this form.
If a previous percent complete was submitted and subsequently determined to be in error, adjust the percent complete to correct the error. Add an explanatory note to support the adjustment.