## ME Status Report
Open Count | Subcontract PO Status Update |  |  |  |  | Updated: | 2024-12-05
8 |  | NO | PO STATUS | VENDOR NAME | PO Value (in $K) | PO ACCRed (in $K) | PO Vouchered (in $K) | Balance (Val-Accr) (in $K) | Bal (Val-Vouch) (in $K) | BUYER | END USER | POC1 | POC2 | BUYER EMAIL | POC1 Email | POC2 Email | SUPERVISOR EMAIL
|  | 24-C0186 | OPEN | CORNELL UNIVERSITY | 760.106 | 34.0112 | 0 | 726.0947 | 760.106 | MICHELE KHASIDIS | #VALUE! | VALENTE-FELICIANO, ANNE-M |  | michele@jlab.org | valente@jlab.org |  | geng@jlab.org
|  | 24-D0258 | OPEN | GENERAL ATOMICS | 169 | 82 | 82 | 87 | 87 | MELISSA TORRES | #VALUE! | WANG, HAIPENG | SPATA, MICHAEL F | torres@jlab.org | haipeng@jlab.org | spata@jlab.org | geng@jlab.org
|  | 25-C0162 | OPEN | LINDE GMBH | 158.767 | 0 | 0 | 158.767 | 158.767 | CEDRIC JACKSON |  |  |  | cedric@jlab.org | cedric@jlab.org
|  | 23-D1216 | OPEN | OLD DOMINION UNIV. RESEAR | 238.5765 | 204.7117 | 204.7096 | 33.8648 | 33.8669 | BRITTANY DENNIS | #VALUE! | HUQUE, NAEEM A | WILSON, KATHERINE M | tolbert@jlab.org | huque@jlab.org | kwilson@jlab.org | conway@jlab.org
|  | 24-C0335 | OPEN | QUANTUM DESIGN INC | 749.24 | 674.316 | 674.316 | 74.924 | 74.924 | THOMAS HURATIAK | #VALUE! | VALENTE-FELICIANO, ANNE-M | HURATIAK, THOMAS | huratiak@jlab.org | valente@jlab.org | huratiak@jlab.org | geng@jlab.org
|  | 23-D1614 | OPEN | SIEMENS PRODUCT LIFECYCLE | 194.46 | 0 | 0 | 194.46 | 194.46 | BRITTANY DENNIS | #VALUE! | COATES, TODD Q |  | tolbert@jlab.org | tcoates@jlab.org |  | kelvin@jlab.org
|  | 24-C1673 | OPEN | STELLANT SYSTEMS INC | 284.612 | 14.2306 | 0 | 270.3814 | 284.612 | THOMAS HURATIAK |  | BAUMGARTNER, WILLIAM | SHIN, YOUNG-MIN | huratiak@jlab.org | wbaum@jlab.org | shin@jlab.org | shin@jlab.org
|  | 25-D0310 | OPEN | ULTRAMET | 100 | 0 | 0 | 100 | 100 | SETH FRISBY | #VALUE! | VALENTE-FELICIANO, ANNE-M |  | frisby@jlab.org | valente@jlab.org |  | geng@jlab.org

## Email Notifications
** add the following to cc group: Eden Evans (eaevans@jlab.org); Tony Risk (antonior@jlab.org)
1st Request - sent 10/18/2024 |  |  |  |  | 2nd Request - |  |  |  |  | 3rd and FINAL Request -
- send to POC 1 and POC 2 |  |  |  |  | - send to POC 1, POC 2, Supervisor's,& Buyers |  |  |  |  | - send to POC 1, POC 2, Supervisor's, Buyers, J. Huff, & G. Frayne
| To: |  | Cc: |  |  | To: |  | Cc: |  |  | To: |  | Cc:
|  | cedric@jlab.org |  | antonior@jlab.org |  |  | cedric@jlab.org |  | antonior@jlab.org |  |  | cedric@jlab.org
|  | conway@jlab.org |  | dolbeck@jlab.org |  |  | conway@jlab.org |  | cclark@jlab.org |  |  | haipeng@jlab.org |  | antonior@jlab.org
|  | csmith@jlab.org |  | eaevans@jlab.org |  |  | cutler@jlab.org |  | ckim@jlab.org |  |  | huque@jlab.org |  | conway@jlab.org
|  | cutler@jlab.org |  | ghoshal@jlab.org |  |  | delisas@jlab.org |  | csmith@jlab.org |  |  | tcoates@jlab.org |  | eaevans@jlab.org
|  | delisas@jlab.org |  | huratiak@jlab.org |  |  | ent@jlab.org |  | dolbeck@jlab.org |  |  | valente@jlab.org |  | frisby@jlab.org
|  | dion@jlab.org |  | jessie@jlab.org |  |  | gciovati@jlab.org |  | drew@jlab.org |  |  | wbaum@jlab.org |  | geng@jlab.org
|  | ent@jlab.org |  | kdehmelt@jlab.org |  |  | gen@jlab.org |  | eaevans@jlab.org |  |  |  |  | huratiak@jlab.org
|  | fraites@jlab.org |  | kwilson@jlab.org |  |  | gopinath@jlab.org |  | frisby@jlab.org |  |  |  |  | jhuff@jlab.org
|  | gciovati@jlab.org |  | marla@jlab.org |  |  | haipeng@jlab.org |  | geng@jlab.org |  |  |  |  | kelvin@jlab.org
|  | gen@jlab.org |  | may@jlab.org |  |  | huque@jlab.org |  | ghoshal@jlab.org |  |  |  |  | kwilson@jlab.org
|  | ghoshal@jlab.org |  | renuka@jlab.org |  |  | jfast@jlab.org |  | hammack@jlab.org |  |  |  |  | lucento@jlab.org
|  | gopinath@jlab.org |  | shin@jlab.org |  |  | ncarter@jlab.org |  | hope@jlab.org |  |  |  |  | michele@jlab.org
|  | haipeng@jlab.org |  | spata@jlab.org |  |  | nigg@jlab.org |  | huratiak@jlab.org |  |  |  |  | shin@jlab.org
|  | hannesv@jlab.org |  | tolbert@jlab.org |  |  | renzo@jlab.org |  | jessie@jlab.org |  |  |  |  | spata@jlab.org
|  | hovater@jlab.org |  | xgomez@jlab.org |  |  | rfries@jlab.org |  | jhuff@jlab.org |  |  |  |  | tolbert@jlab.org
|  | huque@jlab.org |  | yeg@jlab.org |  |  | tcoates@jlab.org |  | jonesc@jlab.org |  |  |  |  | torres@jlab.org
|  | jfast@jlab.org |  |  |  |  | valente@jlab.org |  | kdehmelt@jlab.org
|  | kashy@jlab.org |  |  |  |  | wbaum@jlab.org |  | kelvin@jlab.org
|  | marchlik@jlab.org |  |  |  |  | zorn@jlab.org |  | keppel@jlab.org
|  | maynardb@jlab.org | [6 empty] | kimberly@jlab.org
|  | meekins@jlab.org | [6 empty] | kwilson@jlab.org
|  | metzger@jlab.org | [6 empty] | marla@jlab.org
|  | ncarter@jlab.org | [6 empty] | may@jlab.org
|  | nigg@jlab.org | [6 empty] | michele@jlab.org
|  | okumar@jlab.org |  | mccallum@jlab.org |  |  |  |  | renuka@jlab.org
|  | patricka@jlab.org |  | brakhas@jlab.org |  |  |  |  | scales@jlab.org
|  | qsun@jlab.org |  | cadams@jlab.org |  |  |  |  | scottb@jlab.org
|  | renzo@jlab.org |  | hundley@jlab.org |  |  |  |  | shin@jlab.org |  |  |  |  | mccallum@jlab.org
|  | rfries@jlab.org | [6 empty] | spata@jlab.org |  |  |  |  | brakhas@jlab.org
|  | scottb@jlab.org | [6 empty] | stepney@jlab.org |  |  |  |  | cadams@jlab.org
|  | sthomas@jlab.org | [6 empty] | swill@jlab.org |  |  |  |  | hundley@jlab.org
|  | tcoates@jlab.org | [6 empty] | tolbert@jlab.org
|  | valente@jlab.org | [6 empty] | torres@jlab.org
|  | wang@jlab.org | [6 empty] | yeg@jlab.org
wbaum@jlab.org
|  | zorn@jlab.org | [6 empty] | mccallum@jlab.org
brakhas@jlab.org
cadams@jlab.org
hundley@jlab.org