## ME Status Report
Open Count | Subcontract PO Status Update |  |  |  |  | Updated: | 2024-12-05
37 |  | NO | PO STATUS | VENDOR NAME | PO Value (in $K) | PO ACCRed (in $K) | PO Vouchered (in $K) | Balance (Val-Accr) (in $K) | Bal (Val-Vouch) (in $K) | BUYER | END USER | POC1 | POC2 | BUYER EMAIL | POC1 Email | POC2 Email | SUPERVISOR EMAIL
|  | 24-C0013 | OPEN | A+ CONCRETE INC | 335.7 | 30.0075 | 0 | 305.6925 | 335.7 | GIUSEPPINA TENBUSCH | #VALUE! | SHIFLETT, JAMIE |  | jessie@jlab.org | shiflett@jlab.org |  | lassiter@jlab.org
|  | 25C0030001 | OPEN | AKIMA SUPPORT OPERATIONS | 160 | 109.6 | 0 | 50.4 | 160 | MELISSA TORRES |  | CARTER, NATALIE | MAY, ROBERT T | torres@jlab.org | ncarter@jlab.org | may@jlab.org | jhuff@jlab.org
|  | 24-C0164 | OPEN | ANDERSON & DAHLEN INC | 1215.8 | 851.06 | 851.06 | 364.74 | 364.74 | GIUSEPPINA TENBUSCH | #VALUE! | GOPINATH, SANDESH |  | jessie@jlab.org | gopinath@jlab.org |  | ghoshal@jlab.org
|  | 25-D0510 | OPEN | ANZELC WELDING AND FABRIC | 122.3781 | 0 | 0 | 122.3781 | 122.3781 | EBONY BEAVER | #VALUE! | WINES, ROBIN R | GAL, CIPRIAN | beaver@jlab.org | wines@jlab.org | ciprian@jlab.org | jones@jlab.org
|  | 24-C0715 | OPEN | BFPE INTERNATIONAL INC | 754.984 | 731.234 | 663.812 | 23.75 | 91.172 | MICHELE KHASIDIS | #VALUE! | FRIES, RUSSELL W | DOLBECK, JOEL | michele@jlab.org | rfries@jlab.org | dolbeck@jlab.org | dolbeck@jlab.org
|  | 22C0005001 | OPEN | BURNS & MCDONNELL ENG | 453.6486 | 448.6486 | 416.5717 | 5 | 37.0768 | DENISE LEARY-STITH | #VALUE! | RENZO, THOMAS C | DOLBECK, JOEL | greene@jlab.org | renzo@jlab.org | dolbeck@jlab.org | hammack@jlab.org
|  | 22C005004 | OPEN | BURNS & MCDONNELL ENG | 205.3168 | 192.5604 | 171.4876 | 12.7564 | 33.8292 | MELISSA TORRES | #VALUE! | RENZO, THOMAS C | SMITH, CORRY E | torres@jlab.org | renzo@jlab.org | csmith@jlab.org | hammack@jlab.org
|  | 22-C1473 | OPEN | COLONIAL WEBB CONTRACTORS | 925.702 | 905.7026 | 905.702 | 19.9994 | 20 | CAROLYN STEPNEY | #VALUE! | FRIES, RUSSELL W | DOLBECK, JOEL | stepney@jlab.org | rfries@jlab.org | dolbeck@jlab.org | dolbeck@jlab.org
|  | 25-D0033 | OPEN | COLONIAL WEBB CONTRACTORS | 200.87 | 110.4785 | 40.81 | 90.3915 | 160.06 | HOPE POWELL |  | CUTLER, ADAM |  | hope@jlab.org | cutler@jlab.org |  | jonesc@jlab.org
|  | 24-C0186 | OPEN | CORNELL UNIVERSITY | 760.106 | 68.0225 | 0 | 692.0835 | 760.106 | MICHELE KHASIDIS | #VALUE! | VALENTE-FELICIANO, ANNE-M |  | michele@jlab.org | valente@jlab.org |  | geng@jlab.org
|  | 24-C1207 | OPEN | FRANKLIN MACHINE SHOP INC | 284 | 282.16 | 100 | 1.84 | 184 | DEANN MADDOX | #VALUE! | MARCHLIK, MATTHEW J | HUQUE, NAEEM A | maddox@jlab.org | marchlik@jlab.org | huque@jlab.org | josephm@jlab.org
|  | 24-C1394 | OPEN | G C ZARNAS & CO INC NE | 326.8025 | 0 | 0 | 326.8025 | 326.8025 | SHARON WILLIAMS | #VALUE! | BROWN, MAYNARD |  | swill@jlab.org | maynardb@jlab.org |  | hammack@jlab.org
|  | 24-C0221 | OPEN | GENERAL ATOMICS | 110 | 64 | 64 | 46 | 46 | MICHELE KHASIDIS | #VALUE! | CIOVATI, GIANLUIGI |  | michele@jlab.org | gciovati@jlab.org |  | geng@jlab.org
|  | 24-C0397 | OPEN | GENERAL ATOMICS | 350 | 261.25 | 0 | 88.75 | 350 | MICHELE KHASIDIS | #VALUE! | CIOVATI, GIANLUIGI |  | michele@jlab.org | gciovati@jlab.org |  | geng@jlab.org
|  | 25-C0005 | OPEN | IMEC VZW INTERUNIVERSITAI | 799.8628 | 0 | 0 | 799.8628 | 799.8628 | BRITTANY DENNIS |  |  |  | tolbert@jlab.org | tolbert@jlab.org |  | torres@jlab.org
|  | 25-C0006 | OPEN | IMEC USA NANOELECTRONICS | 799.575 | 0 | 0 | 799.575 | 799.575 | BRITTANY DENNIS |  |  |  | tolbert@jlab.org | tolbert@jlab.org |  | torres@jlab.org
|  | 24-C0184 | OPEN | KAMATICS CORPORATION | 230.3485 | 43.1185 | 43.1085 | 187.23 | 187.24 | CONNOR CLARK | #VALUE! | DION, MICHAEL | DION, MICHAEL | cclark@jlab.org | dion@jlab.org | dion@jlab.org | drew@jlab.org
|  | 24-C0460 | OPEN | LANCASTER UNIVERSITY | 464.2527 | 105.3285 | 66.6086 | 358.9241 | 397.6441 | MELISSA TORRES | #VALUE! | CONWAY, ZACHARY | WILSON, KATHERINE M | torres@jlab.org | conway@jlab.org | kwilson@jlab.org | jfast@jlab.org
|  | 25-C0162 | OPEN | LINDE GMBH | 158.767 | 0.86429 | 0 | 157.9027 | 158.767 | CEDRIC JACKSON |  | WEAKS, MATTHEW |  | cedric@jlab.org | weaksmc@jlab.org |  | buttles@jlab.org
|  | 25-C0301 | OPEN | MASSACHUSETTS INST OF TEC | 362.862 | 0 | 0 | 362.862 | 362.862 | CHARLIE KIM | #VALUE! | TARAFDAR, SOURAV |  | ckim@jlab.org | stara@jlab.org |  | ent@jlab.org
|  | 24-D0863 | OPEN | MASSACHUSETTS INST OF TEC | 189.8 | 74.4319 | 74.4303 | 115.3681 | 115.3698 | GIUSEPPINA TENBUSCH | #VALUE! | ENT, ROLF | YEGNESWARAN, AMRIT S | jessie@jlab.org | ent@jlab.org | yeg@jlab.org | keppel@jlab.org
|  | 25-C0684 | OPEN | MISSISSIPPI STATE UNIVER. | 12.1078 | 0 | 0 | 12.1078 | 12.1078 | BRITTANY DENNIS | #VALUE! |  |  | tolbert@jlab.org | tolbert@jlab.org |  | torres@jlab.org
|  | 25-C0509 | OPEN | NANSEMOND PRE-CAST | 277.51 | 0 | 0 | 277.51 | 277.51 | CEDRIC JACKSON | #VALUE! |  |  | cedric@jlab.org | cedric@jlab.org |  | laney@jlab.org
|  | 23-D1216 | OPEN | OLD DOMINION UNIV. RESEAR | 238.5765 | 230.1106 | 230.1097 | 8.4659 | 8.4667 | BRITTANY DENNIS | #VALUE! | HUQUE, NAEEM A | WILSON, KATHERINE M | tolbert@jlab.org | huque@jlab.org | kwilson@jlab.org | conway@jlab.org
|  | 22-C0008 | OPEN | RI RESEARCH INSTRUMENTS | 1646.69 | 1369.3081 | 1369.0948 | 277.3819 | 277.5952 | GIUSEPPINA TENBUSCH | G CIOVATI | CIOVATI, GIANLUIGI | TENBUSCH, GIUSEPPINA | jessie@jlab.org | gciovati@jlab.org | jessie@jlab.org | geng@jlab.org
|  | 23-D1488 | OPEN | SENSEICS CORPORATION | 96 | 82.2858 | 41.1429 | 13.7142 | 54.8571 | CONNOR CLARK | #VALUE! | GASKELL, DAVID J |  | cclark@jlab.org | gaskelld@jlab.org |  | kimberly@jlab.org
|  | 23-D1614 | OPEN | SIEMENS PRODUCT LIFECYCLE | 194.46 | 0 | 0 | 194.46 | 194.46 | BRITTANY DENNIS | #VALUE! | COATES, TODD Q |  | tolbert@jlab.org | tcoates@jlab.org |  | kelvin@jlab.org
|  | 21C0935005 | OPEN | SMITHGROUP INC | 2405.7616 | 747.6373 | 745.108 | 1658.1243 | 1660.6536 | SHARON WILLIAMS |  | RENZO, THOMAS C | BENTIVEGNA, SCOTT M | swill@jlab.org | renzo@jlab.org | scottb@jlab.org | hammack@jlab.org
|  | 23-C1068 | OPEN | STELLANT SYSTEMS INC | 363.655 | 352.3088 | 352.3088 | 11.3462 | 11.3462 | THOMAS HURATIAK | #VALUE! | BAUMGARTNER, WILLIAM | SHIN, YOUNG-MIN | huratiak@jlab.org | wbaum@jlab.org | shin@jlab.org | shin@jlab.org
|  | 23-C1384 | OPEN | STELLANT SYSTEMS INC | 836.472 | 751.1519 | 731.913 | 85.3201 | 104.559 | THOMAS HURATIAK | #VALUE! | BAUMGARTNER, WILLIAM | SHIN, YOUNG-MIN | huratiak@jlab.org | wbaum@jlab.org | shin@jlab.org | shin@jlab.org
|  | 24-C1673 | OPEN | STELLANT SYSTEMS INC | 284.612 | 42.6918 | 0 | 241.9202 | 284.612 | THOMAS HURATIAK |  | BAUMGARTNER, WILLIAM | SHIN, YOUNG-MIN | huratiak@jlab.org | wbaum@jlab.org | shin@jlab.org | shin@jlab.org
|  | 24-D0516 | OPEN | STICHTING SUPERACT | 159.6 | 44.4 | 22 | 115.2 | 137.6 | MELISSA TORRES | #VALUE! | GOPINATH, SANDESH | RAJPUT-GHOSHAL, RENUKA | torres@jlab.org | gopinath@jlab.org | renuka@jlab.org | ghoshal@jlab.org
|  | 25-C0200 | OPEN | THE RESEARCH FOUNDATION | 800 | 200 | 173.9131 | 600 | 626.0869 | MICHELE KHASIDIS | #VALUE! | VALENTE-FELICIANO, ANNE-M |  | michele@jlab.org | valente@jlab.org |  | geng@jlab.org
|  | 24-C0904 | OPEN | TST TACTICAL DEFENSE | 1675.5362 | 1324.75 | 930.3924 | 350.7862 | 745.1438 | CAROLYN STEPNEY | #VALUE! | FRIES, RUSSELL W | DOLBECK, JOEL | stepney@jlab.org | rfries@jlab.org | dolbeck@jlab.org | dolbeck@jlab.org
|  | 25-D0310 | OPEN | ULTRAMET | 100 | 2.6 | 0 | 97.4 | 100 | SETH FRISBY | #VALUE! | VALENTE-FELICIANO, ANNE-M |  | frisby@jlab.org | valente@jlab.org |  | geng@jlab.org
|  | 25-C0530 | OPEN | VBG CONTRACTING INC | 203.58 | 0 | 0 | 203.58 | 203.58 | EBONY BEAVER | #VALUE! | WINES, ROBIN R | GAL, CIPRIAN | beaver@jlab.org | wines@jlab.org | ciprian@jlab.org | jones@jlab.org
|  | 24-C1073 | OPEN | WARWICK PLUMBING&HEATING | 1706.587 | 1484.126 | 1344.599 | 222.461 | 361.988 | CAROLYN STEPNEY | #VALUE! | NIGG, JAMES | FRIES, RUSSELL W | stepney@jlab.org | nigg@jlab.org | rfries@jlab.org | rfries@jlab.org

## Email Notifications
** add the following to cc group: Eden Evans (eaevans@jlab.org); Tony Risk (antonior@jlab.org)
1st Request - sent 10/18/2024 |  |  |  |  | 2nd Request - |  |  |  |  | 3rd and FINAL Request -
- send to POC 1 and POC 2 |  |  |  |  | - send to POC 1, POC 2, Supervisor's,& Buyers |  |  |  |  | - send to POC 1, POC 2, Supervisor's, Buyers, J. Huff, & G. Frayne
| To: |  | Cc: |  |  | To: |  | Cc: |  |  | To: |  | Cc:
|  | alther@jlab.org |  | antonior@jlab.org |  |  | antonior@jlab.org |  | beaver@jlab.org
|  | cedric@jlab.org |  | ciprian@jlab.org |  |  | cedric@jlab.org |  | buttles@jlab.org
|  | ciprian@jlab.org |  | csmith@jlab.org |  |  | ciprian@jlab.org |  | cclark@jlab.org
|  | conway@jlab.org |  | dolbeck@jlab.org |  |  | conway@jlab.org |  | ckim@jlab.org
|  | csmith@jlab.org |  | eaevans@jlab.org |  |  | csmith@jlab.org |  | drew@jlab.org
|  | cutler@jlab.org |  | hammack@jlab.org |  |  | cutler@jlab.org |  | frisby@jlab.org
|  | dion@jlab.org |  | huratiak@jlab.org |  |  | dion@jlab.org |  | geng@jlab.org
|  | duane@jlab.org |  | jessie@jlab.org |  |  | dolbeck@jlab.org |  | ghoshal@jlab.org
|  | ent@jlab.org |  | kdehmelt@jlab.org |  |  | eaevans@jlab.org |  | greene@jlab.org
|  | fraites@jlab.org |  | kwilson@jlab.org |  |  | ent@jlab.org |  | hammack@jlab.org
|  | gaskelld@jlab.org |  | lhansen@jlab.org |  |  | gaskelld@jlab.org |  | hope@jlab.org
|  | gciovati@jlab.org |  | may@jlab.org |  |  | gciovati@jlab.org |  | huratiak@jlab.org
|  | gen@jlab.org |  | renuka@jlab.org |  |  | gopinath@jlab.org |  | jessie@jlab.org
|  | ghoshal@jlab.org |  | shin@jlab.org |  |  | huque@jlab.org |  | jfast@jlab.org
|  | gopinath@jlab.org |  | spata@jlab.org |  |  | jessie@jlab.org |  | jhuff@jlab.org
|  | haipeng@jlab.org |  | wseay@jlab.org |  |  | kwilson@jlab.org |  | jones@jlab.org
|  | hannesv@jlab.org |  | xgomez@jlab.org |  |  | marchlik@jlab.org |  | jonesc@jlab.org
|  | hovater@jlab.org |  | yeg@jlab.org |  |  | may@jlab.org |  | josephm@jlab.org
|  | huque@jlab.org |  |  |  |  | maynardb@jlab.org |  | kelvin@jlab.org
|  | kashy@jlab.org |  |  |  |  | ncarter@jlab.org |  | keppel@jlab.org
|  | marchlik@jlab.org |  |  |  |  | nigg@jlab.org |  | kimberly@jlab.org
|  | maynardb@jlab.org |  |  |  |  | renuka@jlab.org |  | laney@jlab.org
|  | ncarter@jlab.org |  |  |  |  | renzo@jlab.org |  | lassiter@jlab.org
|  | nigg@jlab.org |  |  |  |  | rfries@jlab.org |  | maddox@jlab.org
|  | okumar@jlab.org |  |  |  |  | scottb@jlab.org |  | michele@jlab.org
|  | patricka@jlab.org |  |  |  |  | shiflett@jlab.org |  | stepney@jlab.org
|  | renzo@jlab.org |  | mccallum@jlab.org |  |  | shin@jlab.org |  | swill@jlab.org
|  | rfries@jlab.org |  | brakhas@jlab.org |  |  | stara@jlab.org |  | torres@jlab.org |  |  |  |  | mccallum@jlab.org
|  | scottb@jlab.org |  | cadams@jlab.org |  |  | tcoates@jlab.org | [6 empty] | brakhas@jlab.org
|  | shiflett@jlab.org |  | hundley@jlab.org |  |  | tolbert@jlab.org | [6 empty] | cadams@jlab.org
|  | stara@jlab.org |  |  |  |  | valente@jlab.org |  | mccallum@jlab.org |  |  |  |  | hundley@jlab.org
|  | sthomas@jlab.org |  |  |  |  | wbaum@jlab.org |  | brakhas@jlab.org
|  | tcoates@jlab.org |  |  |  |  | weaksmc@jlab.org |  | cadams@jlab.org
|  | tolbert@jlab.org |  |  |  |  | wines@jlab.org |  | hundley@jlab.org
|  | valente@jlab.org |  |  |  |  | yeg@jlab.org
wang@jlab.org
wbaum@jlab.org
weaksmc@jlab.org
wines@jlab.org
zorn@jlab.org
mccallum@jlab.org
brakhas@jlab.org
cadams@jlab.org
hundley@jlab.org