## Form
JSA / Jefferson Lab - DOE
PO Accrual Form
Appendix A
Vendor Name | Everson Tesla Inc | [8 empty] | PO with Peg Points? (Yes or No) | No
PO Number |  | 21-C1495-0 |  |  |  |  | Buyer | DeAnn Maddox | Complete through | 2025-07-29
| Only one column should have data | [8 empty] | (Date)
PO Line # | Percent Complete | OR | Quantity Received | OR | Completed Peg Point (X) |  | Summary of Work (only if less than 100%)
1 | 100% | [5 empty] | Winding blocks and potting molds received
2 | 100% | [5 empty] | Prototype coils received and accepted by Jlab
3 | 100% | [5 empty] | Mold and g10 mods for Prototype coil SC3 completed
4 | 100% | [5 empty] | Pot SC1 and SC2 separately of SC3 completed
5 | 100% | [5 empty] | Fabricate and delivery all production coils.
6 | 100% | [5 empty] | Six of the 6 extra coils have been wound (SC1)
7 | 100% | [5 empty] | The 3 smaller molds have had their tapper removed, SC4 coil is in process
8 | 100% | [5 empty] | This is a mod that should be coming soon and will be to wind an 8th SC4 coil but not pot it.
9 | 100% | [5 empty] | This mod pays for re-machining of g10 parts due to drawing change, parts already received can be reworked
10 | 100% | [5 empty] | MOD 008 Reduction of subcontrract price by 1200$
11 | 100% | [5 empty] | MOD 008: NON-RECURRING TOOLING, 1 WINDING BLOCK, 2 POTTING MOLDS - MEET WITH JLAB BEFORE WORK BEGINS
12 | 100% | [5 empty] | MOD 008: US TOROID COILS 7 EACH - UNIT PRICE $13,235 - TOTAL PRICE $92,645.00
13 | 100% | [5 empty] | MOD 008: US TOROID COILS SPARE COIL WINDING ONLY - QUANTITY 1 EACH - UNIT PRICE $3,635.00 - TOTAL PRICE $3,635.00
14 | 100% | [5 empty] | Expedited Tooling Fee,$3580 Mod 9
Vendor Technical Representative Contacted: | [8 empty] | Sandesh Gopinath |  | 7/33/2025
[6 empty] | Name |  |  |  |  | Date
Jlab Control Account Manager (CAM): | [8 empty] | Mike Dion
[9 empty] | Name |  | Date
Below for use by Accounting/Shipping & Receiving Only
Accounting or Shipping & Receiving Entered By:
Date
Data Entry Verified By:
Date

## With steps
| LT CAP | GT CAP | TOTAL | CUM TOTAL | PO | Description | Progress Steps | winding | material receipt | prep potting | potting, testing, shipping
1 | 34300 |  | 34300 | 34300 | line #5 | SC1, SC2, SC3 Toroid Coils Set 1 |  | 10290 | 6860 | 3430 | 13720
2 | 34300 |  | 34300 | 68600 | line #5 | SC1, SC2, SC3 Toroid Coils Set 2 |  | 10290 | 6860 | 3430 | 13720 | Set coming out of molds today 1/23/24
3 | 34300 |  | 34300 | 102900 | line #5 | SC1, SC2, SC3 Toroid Coils Set 3 |  | 10290 | 6860 | 3430 | 13720
4 | 34300 |  | 34300 | 137200 | line #5 | SC1, SC2, SC3 Toroid Coils Set 4 |  | 10290 | 6860 | 3430 | 13720
5 | 34300 |  | 34300 | 171500 | line #5 | SC1, SC2, SC3 Toroid Coils Set 5 |  | 10290 | 6860 | 3430 | 13720
6 | 34300 |  | 34300 | 205800 | line #5 | SC1, SC2, SC3 Toroid Coils Set 6 |  | 10290 | 6860 | 3430 | 13720
7 | 34300 |  | 34300 | 240100 | line #5 | SC1, SC2, SC3 Toroid Coils Set 7 |  | 10290 | 6860 | 3430 | 13720
8 | 34300 |  | 34300 | 274400 | line #5 | SC4 Production Number 1 | 0.5 | 10290 | 6860 | 3430 | 13720
9 | 13055 | 21245 | 34300 | 308700 | line #5 | SC4 Production Number 2 |  | 10290 | 6860 | 3430 | 13720
10 |  | 34300 | 34300 | 343000 | line #5 | SC4 Production Number 3 |  | 10290 | 6860 | 3430 | 13720 | Coil complete (tested not shpped)1/23/24
11 |  | 34300 | 34300 | 377300 | line #5 | SC4 Production Number 4 |  | 10290 | 6860 | 3430 | 13720 | Coil in the mold and filling this week
12 |  | 34300 | 34300 | 411600 | line #5 | SC4 Production Number 5 |  | 10290 | 6860 | 3430 | 13720
13 |  | 34300 | 34300 | 445900 | line #5 | SC4 Production Number 6 |  | 10290 | 6860 | 3430 | 13720
14 |  | 34300 | 34300 | 480200 | line #5 | SC4 Production Number 7 |  | 10290 | 6860 | 3430 | 13720
[7 empty] | Total Line 5 | 144060 | 96040 | 48020 | 192080 | 480200
[8 empty] | 30% | 20% | 10% | 40% | 100%
15 | 7400 |  | 6200 |  | line #6 | spare windings of SC1, 2, 3 | [6 empty] | 100%
16 | 5145 |  | 5145 |  | line #7 | modify molds | [6 empty] | 100% Sep
17 |  |  | 10010 |  | line #8 | Spare winding of SC4 coil
18 |  |  | 966.8 |  | line #9 | Modify g10 to latest rev for SC2 &3
| 300000 | 192745 | 502521.8 |  |  |  |  | 144060 | 96040 | 48020 | 164640
March 27,24
Line 5 direct dollar value |  |  | 502521.8 |  |  | These were finished and claimed by 10/27
Reported Accrual for Line 5 |  |  | 100% |  |  | These are predicted to be finished by 11/30 |  |  |  |  | 94.54%
Proposed ACWP for line 5 based on accrual |  |  | 502521.8 |  |  | Finished by 01/29/24
Finished by 5/28/24 delivered by 5/29/24
Proposed BCWP |  |  | 502521.8
actual progress |  |  | 100%
CV |  |  | 0 | 1

## Process
JSA / Jefferson Lab - DOE
PO Accrual Form
Procedure
A Subcontract Purchase Order (PO) is a service type PO with loosely defined scheduled deliverables and/or variable amounts. A Peg Point PO has specified scheduled deliverable dates to be completed for a specified amount. Note Quantities Received if items did not come through Shipping & Receiving (e.g. items shipped to another vendor).
Complete this form by the 2nd work day after month end if an invoice has been not been approved by the SOTR or CAM for work completed through the end of the month. NOTE: This form can still be completed by the 2nd work day of the month to ensure the accrual is processed.
SOTR or CAM contacts a vendor technical representative for an evaluation of the percent of work completed (or quantity received by vendor). This can be done either verbally or via email.
OR
SOTR or CAM has an objective way to measure the perecent of work complete (e.g. Standardize monthly payment, using schedule of values to determine value of work complete)
Required information - Vendor Name, indicate if PO is a Peg Point type PO or not, PO #, Buyer, Complete through date (usually the end of the month), PO Line #, Percent complete (or quantity received by vendor), a short Summary of Work performed provided by the Vendor Technical Representative that supports the percent complete if less than 100%, the name of the Vendor Technical Representative contacted, and the CAM name.
The SOTR or CAM will submit a PO Accrual Form by the 2nd working day following the end of the month affected for work that has been completed. This allows time for Accounting to process an accrual for the month end closing. Reminder if PO is for Peg Points, the peg point must be fully complete before claiming it.
Submit the completed form with all the information via email to evpo@jlab.org. The file name of the spreadsheet attached to the email should always include the PO# and the letters 'S&R' if it is a Peg Point type PO or if items were received by did not go through JLab's Shipping and Receiving Department. File name examples: Peg Point Type PO 08-C5413 S&R, Subcontract Type PO 08-A2659. This email will forward the form automatically to personnel in Procurement, Shipping & Receiving, CFO, and PMO.
If the PO is a Subcontract type PO, the SOTR or CAM will still be required to sign all invoices received at JLab from the vendor up since this was an estimate. An approved invoice by the SOTR or CAM can also be used as basis for the percent of work complete.
If the PO is a Peg Point type PO or material has been received, Shipping & Receiving will use this form to enter the information into the Costpoint Financial System. No additional invoice approvals will be required since the SOTR or CAM already indicated the work was complete. An approved invoice by the SOTR or CAM can also be used as basis for the percent of work complete without having to complete this form.
If a previous percent complete was submitted and subsequently determined to be in error, adjust the percent complete to correct the error. Add an explanatory note to support the adjustment.