## ME Status Report
Open Count | Subcontract PO Status Update |  |  |  |  | Updated: | 2025-10-16
75 |  | NO | PO STATUS | VENDOR NAME | PO Value (in $K) | PO ACCRed (in $K) | PO Vouchered (in $K) | Balance (Val-Accr) (in $K) | Bal (Val-Vouch) (in $K) | BUYER | END USER | POC1 | POC2 | BUYER EMAIL | POC1 Email | POC2 Email | SUPERVISOR EMAIL
|  | 24-C1425 | OPEN | ALLFIRST LLC | 4033.0241 | 3810.8133 | 3810.6806 | 222.2108 | 222.3435 | SHARON WILLIAMS | #VALUE! | ALTHER, TODD | FRIES, RUSSELL W | swill@jlab.org | alther@jlab.org | rfries@jlab.org | dolbeck@jlab.org
|  | 24-C0164 | OPEN | ANDERSON & DAHLEN INC | 1389.79 | 1189.1855 | 1094.22 | 200.6045 | 295.57 | GIUSEPPINA TENBUSCH | #VALUE! | GOPINATH, SANDESH |  | jessie@jlab.org | gopinath@jlab.org |  | ghoshal@jlab.org
|  | 22C0005001 | OPEN | BURNS & MCDONNELL ENG | 453.6486 | 448.6486 | 416.5717 | 5 | 37.0768 | DENISE LEARY-STITH | #VALUE! | RENZO, THOMAS C | DOLBECK, JOEL | greene@jlab.org | renzo@jlab.org | dolbeck@jlab.org | bdhill@jlab.org
|  | 22C005004 | OPEN | BURNS & MCDONNELL ENG | 205.3168 | 191.4888 | 191.4876 | 13.828 | 13.8292 | MELISSA TORRES | #VALUE! | RENZO, THOMAS C | SMITH, CORRY E | torres@jlab.org | renzo@jlab.org | csmith@jlab.org | bdhill@jlab.org
|  | 24-C1709 | OPEN | CARNEGIE MELLON UNIVER. | 238.2896 | 117.8336 | 78.5558 | 120.456 | 159.7339 | BRITTANY DENNIS | #VALUE! | STEWART, TANYA-GAYE N |  | tolbert@jlab.org | fraites@jlab.org |  | brandons@jlab.org
|  | 25-C1418 | OPEN | CEA-SACLAY | 300 | 24 | 0 | 276 | 300 | CEDRIC JACKSON | #VALUE! | BARBOSA, FERNANDO J |  | cedric@jlab.org | barbosa@jlab.org |  | cuevas@jlab.org
|  | 25-C1113 | OPEN | CEM LTD. | 595 | 360.0345 | 360 | 234.9655 | 235 | DEANN MADDOX | #VALUE! | CUEVAS, CHRIS | DONG, HAI T | maddox@jlab.org | cuevas@jlab.org | hdong@jlab.org | keppel@jlab.org
|  | 24-D1748 | OPEN | CHRISTOPHER NEWPORT UNIV. | 44.1194 | 40.4428 | 40.4428 | 3.6766 | 3.6766 | MICHELE KHASIDIS | #VALUE! | STEWART, TANYA-GAYE N |  | michele@jlab.org | fraites@jlab.org |  | brandons@jlab.org
|  | 21-C0006 | OPEN | CHRISTOPHER NEWPORT UNIV. | 1127.6234 | 1085.4561 | 1085.4561 | 42.1672 | 42.1672 | MICHELE KHASIDIS | TANYA STEWART | STEWART, TANYA-GAYE N |  | michele@jlab.org | fraites@jlab.org |  | brandons@jlab.org
|  | 24-D1733 | OPEN | CHRISTOPHER NEWPORT UNIV. | 220.519 | 209.4724 | 209.4724 | 11.0466 | 11.0466 | MICHELE KHASIDIS | #VALUE! | STEWART, TANYA-GAYE N |  | michele@jlab.org | fraites@jlab.org |  | brandons@jlab.org
|  | 24C0558001 | OPEN | CLARK NEXSEN INC | 2833.0176 | 1439.2755 | 1439.2206 | 1393.7421 | 1393.797 | MELISSA TORRES | #VALUE! | SMITH, CORRY E | HILL, BRIAN | torres@jlab.org | csmith@jlab.org | bdhill@jlab.org | bdhill@jlab.org
|  | 24C0558003 | OPEN | CLARK NEXSEN INC | 750 | 0 | 0 | 750 | 750 | MELISSA TORRES | #VALUE! |  |  | torres@jlab.org | torres@jlab.org |  | chilee@jlab.org
|  | 23-C0739 | OPEN | COLLEGE OF WILLIAM & MARY | 896.6829 | 850.4252 | 836.1463 | 46.2577 | 60.5365 | MELISSA TORRES | #VALUE! | STEWART, TANYA-GAYE N |  | torres@jlab.org | fraites@jlab.org |  | brandons@jlab.org
|  | 24-C0830 | OPEN | COLLEGE OF WILLIAM & MARY | 289.79 | 196.3469 | 163.1199 | 93.4431 | 126.6702 | MELISSA TORRES | #VALUE! | STEWART, TANYA-GAYE N |  | torres@jlab.org | fraites@jlab.org |  | brandons@jlab.org
|  | 23-C0331 | OPEN | COLLEGE OF WILLIAM & MARY | 592.406 | 553.906 | 553.906 | 38.5 | 38.5 | MELISSA TORRES | #VALUE! | STEWART, TANYA-GAYE N |  | torres@jlab.org | fraites@jlab.org |  | brandons@jlab.org
|  | 22-C1473 | OPEN | COLONIAL WEBB CONTRACTORS | 943.8537 | 935.1545 | 933.8537 | 8.6992 | 10 | CAROLYN STEPNEY | #VALUE! | FRIES, RUSSELL W | DOLBECK, JOEL | stepney@jlab.org | rfries@jlab.org | dolbeck@jlab.org | dolbeck@jlab.org
|  | 24-C0186 | OPEN | CORNELL UNIVERSITY | 760.106 | 509.977 | 509.977 | 250.129 | 250.129 | MICHELE KHASIDIS | #VALUE! | VALENTE-FELICIANO, ANNE-M |  | michele@jlab.org | valente@jlab.org |  | geng@jlab.org
|  | 25-C1924 | OPEN | CORNES TECHNOLOGIES USA | 511.43 | 0 | 0 | 511.43 | 511.43 | CEDRIC JACKSON | #VALUE! | WISSMANN, MARK J |  | cedric@jlab.org | wissmann@jlab.org |  | garza@jlab.org
|  | 25-C1619 | OPEN | CT HX LLC | 324.741 | 205.009 | 205 | 119.732 | 119.741 | CAROLYN STEPNEY | #VALUE! |  |  | stepney@jlab.org | stepney@jlab.org |  | torres@jlab.org
|  | 25-D1681 | OPEN | DANFYSIK A/S | 159.1 | 47.73 | 47.73 | 111.37 | 111.37 | CHARLIE KIM | #VALUE! | KUMAR, ONISH | ROY, MAXWELL P | ckim@jlab.org | okumar@jlab.org | maxwellr@jlab.org | hovater@jlab.org
|  | 22-C0525 | OPEN | DUKE UNIVERSITY | 362.1538 | 354.9992 | 354.9979 | 7.1546 | 7.1559 | BRITTANY DENNIS | #VALUE! | STEWART, TANYA-GAYE N |  | tolbert@jlab.org | fraites@jlab.org |  | brandons@jlab.org
|  | 25-D1331 | OPEN | EAGLE ALLOYS CORP | 183.9632 | 11.1612 | 11.1612 | 172.802 | 172.802 | GIUSEPPINA TENBUSCH | #VALUE! |  |  | jessie@jlab.org | jessie@jlab.org |  | laney@jlab.org
|  | 24-C1558 | OPEN | EUCLID TECHLABS LLC | 335.4 | 243.3 | 166.7 | 92.1 | 168.7 | CONNOR CLARK | #VALUE! | WANG, SHAOHENG | RIMMER, ROBERT A | cclark@jlab.org | wang@jlab.org | rarimmer@jlab.org | geng@jlab.org
|  | 21-C1495 | OPEN | EVERSON TESLA INC | 825.4218 | 826.6218 | 826.6218 | -1.2 | -1.2 | DEANN MADDOX | D KASHY/55E | GOPINATH, SANDESH | KASHY, DAVID H | maddox@jlab.org | gopinath@jlab.org | kashy@jlab.org | ghoshal@jlab.org
|  | 24-C0310 | OPEN | FLORIDA INTERNATIONAL UNV | 583.412 | 334.9477 | 291.101 | 248.4644 | 292.311 | BRITTANY DENNIS | #VALUE! | VENNEKATE, HANNES | DENNIS, BRITTANY L | tolbert@jlab.org | hannesv@jlab.org | tolbert@jlab.org | gciovati@jlab.org
|  | 25-D1449 | OPEN | FLORIDA STATE UNIVERSITY | 9.1125 | 6.075 | 3.0375 | 3.0375 | 6.075 | BRITTANY DENNIS | #VALUE! | STEWART, TANYA-GAYE N |  | tolbert@jlab.org | fraites@jlab.org |  | brandons@jlab.org
|  | 24-C0221 | OPEN | GENERAL ATOMICS | 110 | 64 | 64 | 46 | 46 | MICHELE KHASIDIS | #VALUE! | CIOVATI, GIANLUIGI |  | michele@jlab.org | gciovati@jlab.org |  | geng@jlab.org
|  | 24-C0397 | OPEN | GENERAL ATOMICS | 350 | 261.25 | 0 | 88.75 | 350 | MICHELE KHASIDIS | #VALUE! | CIOVATI, GIANLUIGI |  | michele@jlab.org | gciovati@jlab.org |  | geng@jlab.org
|  | 22-C0202 | OPEN | GEORGIA STATE UNIVERSITY | 383.011 | 379.6465 | 379.6465 | 3.3645 | 3.3645 | BRITTANY DENNIS | #VALUE! | STEWART, TANYA-GAYE N |  | tolbert@jlab.org | fraites@jlab.org |  | brandons@jlab.org
|  | 22C1262002 | OPEN | HILL-BAKER JOINT VENTURE | 296.0066 | 121.2051 | 102.5805 | 174.8015 | 193.4262 | SHARON WILLIAMS | #VALUE! | BENTIVEGNA, SCOTT M |  | swill@jlab.org |  |  | bdhill@jlab.org
|  | 25-C0005 | OPEN | IMEC VZW INTERUNIVERSITAI | 1679.1995 | 420 | 400 | 1259.1995 | 1279.1995 | BRITTANY DENNIS | #VALUE! | VALENTE-FELICIANO, ANNE-M |  | tolbert@jlab.org | valente@jlab.org |  | geng@jlab.org
|  | 25-C0006 | OPEN | IMEC USA NANOELECTRONICS | 1679.373 | 506.3975 | 266.525 | 1172.9755 | 1412.848 | BRITTANY DENNIS | #VALUE! | VALENTE-FELICIANO, ANNE-M |  | tolbert@jlab.org | valente@jlab.org |  | geng@jlab.org
|  | 25-C0871 | OPEN | INFN ISTITUTO NAZIONALE | 470 | 156.6667 | 156.6667 | 313.3333 | 313.3333 | CONNOR CLARK | #VALUE! | ENT, ROLF | FRAGAPANE, CHRISTINE A | cclark@jlab.org | ent@jlab.org | chummel@jlab.org | keppel@jlab.org
|  | 25-D0774 | OPEN | INNOSYS INC | 104.2044 | 63.9431 | 0 | 40.2613 | 104.2044 | EBONY BEAVER-FOWLKES | #VALUE! | WANG, SHAOHENG | RIMMER, ROBERT A | beaver@jlab.org | wang@jlab.org | rarimmer@jlab.org | geng@jlab.org
|  | 24-C0460 | OPEN | LANCASTER UNIVERSITY | 464.2527 | 115.3194 | 66.6086 | 348.9333 | 397.6441 | MELISSA TORRES | #VALUE! | CONWAY, ZACHARY | WILSON, KATHERINE M | torres@jlab.org | conway@jlab.org | kwilson@jlab.org | kwilson@jlab.org
|  | 25-C0162 | OPEN | LINDE GMBH | 158.767 | 151.9099 | 151.9099 | 6.8571 | 6.8571 | CEDRIC JACKSON | #VALUE! | WEAKS, MATTHEW |  | cedric@jlab.org | weaksmc@jlab.org |  | buttles@jlab.org
|  | 22-D0013 | OPEN | LONGENECKER & ASSOCIATES | 35.3243 | 24.1224 | 24.121 | 11.2019 | 11.2033 | MELISSA TORRES | M SOLAROLI | SMITH, CORRY E | HILL, BRIAN | torres@jlab.org | csmith@jlab.org | bdhill@jlab.org | bdhill@jlab.org
|  | 25-C0300 | OPEN | LUVATA WATERBURY INC | 3547.8 | 0 | 0 | 3547.8 | 3547.8 | DEANN MADDOX | #VALUE! | RAJPUT-GHOSHAL, RENUKA | GOPINATH, SANDESH | maddox@jlab.org | renuka@jlab.org | gopinath@jlab.org | ent@jlab.org>
|  | 25C1295001 | OPEN | MANTA RAY CONSULTING INC | 249.9867 | 69.3463 | 66.8787 | 180.6404 | 183.1079 | MELISSA TORRES | #VALUE! | SMITH, STEPHEN J | MACE, KATHRYN | torres@jlab.org | sjsmith@jlab.org | kmace@jlab.org | jhuff@jlab.org
|  | 25-C0301 | OPEN | MASSACHUSETTS INST OF TEC | 362.862 | 136.5813 | 136.5517 | 226.2807 | 226.3103 | CHARLIE KIM | #VALUE! | TARAFDAR, SOURAV |  | ckim@jlab.org | stara@jlab.org |  | ent@jlab.org
|  | 24-D0863 | OPEN | MASSACHUSETTS INST OF TEC | 189.8 | 142.0542 | 142.043 | 47.7458 | 47.757 | GIUSEPPINA TENBUSCH | #VALUE! | ENT, ROLF | YEGNESWARAN, AMRIT S | jessie@jlab.org | ent@jlab.org | yeg@jlab.org | keppel@jlab.org
|  | 25-D0440 | OPEN | MASSACHUSETTS INST OF TEC | 54.4414 | 45.1047 | 45.1044 | 9.3367 | 9.337 | BRITTANY DENNIS | #VALUE! | STEWART, TANYA-GAYE N |  | tolbert@jlab.org | fraites@jlab.org |  | brandons@jlab.org
|  | 25-C0684 | OPEN | MISSISSIPPI STATE UNIVER. | 66.108 | 55.2251 | 0 | 10.8829 | 66.108 | BRITTANY DENNIS | #VALUE! | STEWART, TANYA-GAYE N |  | tolbert@jlab.org | fraites@jlab.org |  | brandons@jlab.org
|  | 25-D1718 | OPEN | NANSEMOND PRE-CAST | 215.5 | 0 | 0 | 215.5 | 215.5 | GIUSEPPINA TENBUSCH | #VALUE! |  |  | jessie@JLAB.ORG | jessie@JLAB.ORG |  | laney@jlab.org
|  | 22-C0405 | OPEN | OCEM ACQUISITION CORP | 1319.1272 | 1250.9081 | 1250.9047 | 68.2191 | 68.2225 | DEANN MADDOX | #VALUE! | GHOSHAL, PROBIR K | DION, MICHAEL | maddox@jlab.org | ghoshal@jlab.org | dion@jlab.org | keppel@jlab.org
|  | 23-C0344 | OPEN | OLD DOMINION UNIV. RESEAR | 1303.9546 | 1237.3435 | 1237.3435 | 66.6111 | 66.6111 | BRITTANY DENNIS | 12B | STEWART, TANYA-GAYE N | DENNIS, BRITTANY L | tolbert@jlab.org | fraites@jlab.org | tolbert@jlab.org | brandons@jlab.org
|  | 23-C0346 | OPEN | OLD DOMINION UNIV. RESEAR | 2320.0105 | 2207.1102 | 2189.3332 | 112.9003 | 130.6773 | BRITTANY DENNIS | #VALUE! | STEWART, TANYA-GAYE N | DENNIS, BRITTANY L | tolbert@jlab.org | fraites@jlab.org | tolbert@jlab.org | brandons@jlab.org
|  | 23-D1216 | OPEN | OLD DOMINION UNIV. RESEAR | 395.2347 | 386.7688 | 386.7679 | 8.4659 | 8.4667 | BRITTANY DENNIS | #VALUE! | HUQUE, NAEEM A | WILSON, KATHERINE M | tolbert@jlab.org | huque@jlab.org | kwilson@jlab.org | conway@jlab.org
|  | 25-D1463 | OPEN | PHYTRON INC | 97.7 | 19.8 | 19.8 | 77.9 | 77.9 | CHARLIE KIM | #VALUE! | GALWAY, DANIEL | MATALEVICH, JOSEPH R | ckim@jlab.org | galway@jlab.org | josephm@jlab.org | mbevins@jlab.org
|  | 25-C1503 | OPEN | PURDUE UNIVERSITY | 292.494 | 0 | 0 | 292.494 | 292.494 | BRITTANY DENNIS | A114 ZIHLMAN | ZIHLMANN, BENEDIKT J |  | tolbert@jlab.org | zihlmann@jlab.org |  | gen@jlab.org
|  | 22-C0008 | OPEN | RI RESEARCH INSTRUMENTS | 1646.69 | 1609.49 | 1557.89 | 37.2 | 88.8 | GIUSEPPINA TENBUSCH | G CIOVATI | CIOVATI, GIANLUIGI | TENBUSCH, GIUSEPPINA | jessie@jlab.org | gciovati@jlab.org | jessie@jlab.org | geng@jlab.org
|  | 23-D1488 | OPEN | SENSEICS CORPORATION | 96 | 82.2858 | 68.5715 | 13.7142 | 27.4285 | CONNOR CLARK | #VALUE! | GASKELL, DAVID J |  | cclark@jlab.org | gaskelld@jlab.org |  | jones@jlab.org
|  | 25-C1648 | OPEN | SENSEICS CORPORATION | 629 | 83.866 | 83.866 | 545.134 | 545.134 | CONNOR CLARK | #VALUE! | GASKELL, DAVID J | GASKELL, DAVID J | cclark@jlab.org | gaskelld@jlab.org | gaskelld@jlab.org | jones@jlab.org
|  | 23-D1614 | OPEN | SIEMENS INDUSTRY SOFTWARE | 209.04 | 16.9569 | 16.9506 | 192.0831 | 192.0894 | BRITTANY DENNIS | #VALUE! | COATES, TODD Q |  | tolbert@jlab.org | tcoates@jlab.org |  | kelvin@jlab.org
|  | 21C0935005 | OPEN | SMITHGROUP INC | 2405.7616 | 2008.3028 | 1664.3229 | 397.4588 | 741.4387 | SHARON WILLIAMS | #VALUE! | RENZO, THOMAS C | BENTIVEGNA, SCOTT M | swill@jlab.org | renzo@jlab.org |  | bdhill@jlab.org
|  | 25-C1969 | OPEN | STELLANT SYSTEMS INC | 496.2 | 0 | 0 | 496.2 | 496.2 | EBONY BEAVER-FOWLKES | #VALUE! | BAUMGARTNER, WILLIAM |  | beaver@jlab.org | wbaum@jlab.org |  | garza@jlab.org
|  | 24-D0516 | OPEN | STICHTING SUPERACT | 159.6 | 44.4 | 22 | 115.2 | 137.6 | MELISSA TORRES | #VALUE! | GOPINATH, SANDESH | RAJPUT-GHOSHAL, RENUKA | torres@jlab.org | gopinath@jlab.org | renuka@jlab.org | ghoshal@jlab.org
|  | 25-D1991 | OPEN | SW FUNK INDUSTRIAL | 65.587 | 6.5587 | 0 | 59.0283 | 65.587 | CAROLYN STEPNEY | #VALUE! |  |  | stepney@jlab.org | stepney@jlab.org |  | torres@jlab.org
|  | 24-D0253 | OPEN | SYRACUSE UNIVERSITY | 115.115 | 110.4644 | 73.255 | 4.6506 | 41.86 | BRITTANY DENNIS | #VALUE! | STEWART, TANYA-GAYE N |  | tolbert@jlab.org | fraites@jlab.org |  | brandons@jlab.org
|  | 23-C0161 | OPEN | THE CATHOLIC UNIVERSITY | 272.2585 | 265.5724 | 258.6949 | 6.6861 | 13.5636 | MICHELE KHASIDIS | #VALUE! | STEWART, TANYA-GAYE N |  | michele@jlab.org | fraites@jlab.org |  | brandons@jlab.org
|  | 24-D0462 | OPEN | THE CATHOLIC UNIVERSITY | 49.4293 | 46.8277 | 46.8277 | 2.6015 | 2.6015 | HOPE POWELL | #VALUE! | STEWART, TANYA-GAYE N |  | hope@jlab.org | fraites@jlab.org |  | brandons@jlab.org
|  | 21-C1176 | OPEN | THE RESEARCH FOUNDATION | 731.9636 | 625.7378 | 625.7343 | 106.2258 | 106.2292 | DEANN MADDOX | C ZORN | ZORN, CARL J | DEHMELT, KLAUS | maddox@jlab.org | zorn@jlab.org | kdehmelt@jlab.org | christy@jlab.org
|  | 25-C0200 | OPEN | THE RESEARCH FOUNDATION | 1600 | 836 | 796 | 764 | 804 | MICHELE KHASIDIS | #VALUE! | VALENTE-FELICIANO, ANNE-M |  | michele@jlab.org | valente@jlab.org |  | geng@jlab.org
|  | 24-C0313 | OPEN | TRUSTEES OF INDIANA UNIVE | 170.2203 | 163.9539 | 151.421 | 6.2664 | 18.7994 | BRITTANY DENNIS | #VALUE! | STEWART, TANYA-GAYE N |  | tolbert@jlab.org | fraites@jlab.org |  | brandons@jlab.org
|  | 25-C1974 | OPEN | TST ROOFING & GLAZING | 465.788 | 4.0541 | 4.052 | 461.7339 | 461.736 | SETH FRISBY | #VALUE! | NIGG, JAMES |  | frisby@jlab.org | nigg@jlab.org |  | dolbeck@jlab.org
|  | 25-D0310 | OPEN | ULTRAMET | 100 | 19.5 | 0 | 80.5 | 100 | SETH FRISBY | #VALUE! | VALENTE-FELICIANO, ANNE-M |  | frisby@jlab.org | valente@jlab.org |  | geng@jlab.org
|  | 24-C0387 | OPEN | UNIVERSITY OF TENNESSEE | 206.9937 | 167.1087 | 157.1598 | 39.885 | 49.834 | MICHELE KHASIDIS | #VALUE! | STEWART, TANYA-GAYE N |  | michele@jlab.org | fraites@jlab.org |  | brandons@jlab.org
|  | 24-C0532 | OPEN | UNIVERSITY OF VIRGINIA | 579.6917 | 479.1917 | 479.1726 | 100.5 | 100.519 | GIUSEPPINA TENBUSCH |  | STEPANYAN, STEPAN |  | jessie@jlab.org | stepanya@jlab.org |  | keppel@jlab.org
|  | 24-D0309 | OPEN | UNIVERSITY OF VIRGINIA | 248.613 | 216.3278 | 205.566 | 32.2852 | 43.047 | MICHELE KHASIDIS | #VALUE! | STEWART, TANYA-GAYE N |  | michele@jlab.org | fraites@jlab.org |  | brandons@jlab.org
|  | 25-D1948 | OPEN | UNIVERSITY OF VIRGINIA | 137.954 | 8.6221 | 0 | 129.3319 | 137.954 | BRITTANY DENNIS | #VALUE! | STEWART, TANYA-GAYE N |  | tolbert@jlab.org | fraites@jlab.org |  | brandons@jlab.org
|  | 20-C1456 | OPEN | VIRGINIA POLYTECHNIC INST | 390.2035 | 382.0413 | 371.0515 | 8.1621 | 19.1519 | MICHELE KHASIDIS | TANYA STEWART | STEWART, TANYA-GAYE N |  | michele@jlab.org | fraites@jlab.org |  | brandons@jlab.org
|  | 25-D1633 | OPEN | VISION MACHINE & FABRICAT | 117.138 | 28.5659 | 28.56 | 88.5721 | 88.578 | DEANN MADDOX | PETER OWEN | OWEN, PETER | GRABOWSKI, ADAM | maddox@jlab.org | powen@jlab.org | adamg@jlab.org | kdavis@jlab.org
|  | 25-D2070 | OPEN | V3 GATE LLC | 237.0232 | 0 | 0 | 237.0232 | 237.0232 | BRITTANY DENNIS | #VALUE! | PERRY, JESSICA A |  | tolbert@jlab.org | jperry@jlab.org |  | heffner@jlab.org
|  | 25-C1734 | OPEN | W M JORDAN COMPANY INC | 37149.591 | 0 | 0 | 37149.591 | 37149.591 | MELISSA TORRES | 28G |  |  | torres@jlab.org | torres@jlab.org |  | chilee@jlab.org
|  | 25-C0737 | OPEN | YIELD ENGINEERING SYSTEMS | 1487 | 446.1 | 446.1 | 1040.9 | 1040.9 | GIUSEPPINA TENBUSCH | #VALUE! | DENNY, PHILIP J |  | jessie@jlab.org | denny@jlab.org |  | conway@jlab.org

## Email Notifications
** add the following to cc group: Eden Evans (eaevans@jlab.org); Tony Risk (antonior@jlab.org)
1st Request - sent 10/17/2025 |  |  |  |  | 2nd Request - |  |  | 3rd and FINAL Request -
- send to POC 1 and POC 2 |  |  |  |  | - send to POC 1, POC 2, Supervisor's,& Buyers |  |  | - send to POC 1, POC 2, Supervisor's, Buyers, J. Huff, & G. Frayne
| To: |  | Cc: |  |  | To: | Cc: |  | To: | Cc:
|  | alther@jlab.org |  | adamg@jlab.org
|  | barbosa@jlab.org |  | antonior@jlab.org
|  | conway@jlab.org |  | bdhill@jlab.org
|  | csmith@jlab.org |  | chummel@jlab.org
|  | cuevas@jlab.org |  | dion@jlab.org
|  | denny@jlab.org |  | dolbeck@jlab.org
|  | ent@jlab.org |  | eaevans@jlab.org
|  | fraites@jlab.org |  | hdong@jlab.org
|  | galway@jlab.org |  | josephm@jlab.org
|  | gaskelld@jlab.org |  | kashy@jlab.org
|  | gciovati@jlab.org |  | kdehmelt@jlab.org
|  | ghoshal@jlab.org |  | kmace@jlab.org
|  | gopinath@jlab.org |  | kwilson@jlab.org
|  | hannesv@jlab.org |  | maxwellr@jlab.org
|  | huque@jlab.org |  | rarimmer@jlab.org
|  | jessie@jlab.org |  | renuka@jlab.org
|  | jperry@jlab.org |  | tolbert@jlab.org
|  | nigg@jlab.org |  | yeg@jlab.org
okumar@jlab.org
powen@jlab.org
renuka@jlab.org
renzo@jlab.org
rfries@jlab.org
sjsmith@jlab.org
|  | stara@jlab.org |  | mccallum@jlab.org
|  | stepanya@jlab.org |  | brakhas@jlab.org
|  | stepney@jlab.org |  | hundley@jlab.org
tcoates@jlab.org
torres@jlab.org
valente@jlab.org
wang@jlab.org
wbaum@jlab.org
weaksmc@jlab.org
wissmann@jlab.org
zihlmann@jlab.org
zorn@jlab.org