## 24-C1709C 11 14 2025
JSA / Jefferson Lab - DOE
Data Entry Update Subcontract PO Percent Complete
Appendix B
Vendor Name | CARNEGIE MELLON UNIVERSITY | [5 empty] | Percent complete thru |  |  | 2025-11-24
(Date)
PO Number | 24-C1709 | [6 empty] | OR
Status Update ID | 24-C1709C | [5 empty] | Invoice Number
T3334
PO Line # | Percent Complete |  | PO Line Total | = | Completed Work Amt | Completed Work Amt | - | Eligible for Voucher Amt | - | Prev Vouchered Amount | = | Completed Work Retention Amt
1 | 100% | X | 39277.88 | = | 39277.88 | 39277.88 | - | 0 |  | 39277.88 | = | 0
2 | 100% | X | 46151.51 | = | 46151.51 | 46151.51 | - | 0 |  | 39277.88 | = | 6873.63
3 | 100% | X | 29923 | = | 29923 | 29923 | - | 0 |  | 0 | = | 29923
4 | 40% | X | 62494.64 | = | 24997.86 | 24997.86 | - | 0 |  | 0 | = | 24997.86
|  |  | 177847.03 |  | 140350.25 | 140350.25 |  | 0 |  | 78555.76 |  | 61794.49
Finance Entered By: ________________________________________________________________
Date
Finance Data Entry Verified By: _______________________________________________________
Date
Line 2: DEOB ($2,581.25)
Line 3: Add $100.00
Line 4: DEOB ($57,961.36)