## 25-D1948A 11 14 2025
JSA / Jefferson Lab - DOE
Data Entry Update Subcontract PO Percent Complete
Appendix B
Vendor Name | UNIVERSITY OF VIRGINIA | [5 empty] | Percent complete thru |  |  | 2025-11-24
(Date)
PO Number | 25-D1948 | [6 empty] | OR
Status Update ID | 25-D1948A | [5 empty] | Invoice Number
T3334
PO Line # | Percent Complete |  | PO Line Total | = | Completed Work Amt | Completed Work Amt | - | Eligible for Voucher Amt | - | Prev Vouchered Amount | = | Completed Work Retention Amt
1 | 100% | X | 17244.25 | = | 17244.25 | 17244.25 | - | 0 |  | 0 | = | 17244.25
2 | 22.22% | X | 17244.25 | = | 3831.67 | 3831.67 | - | 0 |  | 0 | = | 3831.67
3 | 0% | X | 17244.25 | = | 0 | 0 | - | 0 |  | 0 | = | 0
4 | 0% | X | 17244.25 | = | 0 | 0 | - | 0 |  | 0 | = | 0
5 | 0% | X | 17244.25 | = | 0 | 0 | - | 0 |  | 0 | = | 0
6 | 0% | X | 17244.25 | = | 0 | 0 | - | 0 |  | 0 | = | 0
7 | 0% | X | 17244.25 | = | 0 | 0 | - | 0 |  | 0 | = | 0
8 | 0% | X | 17244.25 | = | 0 | 0 | - | 0 |  | 0 | = | 0
|  |  | 137954 |  | 21075.92 | 21075.92 |  | 0 |  | 0 |  | 21075.92
Finance Entered By: ________________________________________________________________
Date
Finance Data Entry Verified By: _______________________________________________________
Date