## 24-C0460C 11 14 2025
JSA / Jefferson Lab - DOE
Data Entry Update Subcontract PO Percent Complete
Appendix B
Vendor Name | LANCASTER UNIVERSITY | [5 empty] | Percent complete thru |  |  | 2025-11-24
(Date)
PO Number | 24-C0460 | [6 empty] | OR
Status Update ID | 24-C0460C | [5 empty] | Invoice Number
T3153
PO Line # | Percent Complete |  | PO Line Total | = | Completed Work Amt | Completed Work Amt | - | Eligible for Voucher Amt | - | Prev Vouchered Amount | = | Completed Work Retention Amt
1 | 100% | X | 33304.28 | = | 33304.28 | 33304.28 | - | 0 |  | 33304.28 | = | 0
2 | 100% | X | 34303.41 | = | 34303.41 | 34303.41 | - | 0 |  | 34303.41 | = | 0
3 | 16% | X | 35332.51 | = | 5653.2 | 5653.2 | - | 0 |  | 0 | = | 5653.2
4 | 0% | X | 17666.25 | = | 0 | 0 | - | 0 |  | 0 | = | 0
5 | 100% | X | 33304.28 | = | 33304.28 | 33304.28 | - | 0 |  | 33304.28 | = | 0
6 | 42% | X | 34303.41 | = | 14407.43 | 14407.43 | - | 0 |  | 0 | = | 14407.43
7 | 0% | X | 35332.51 | = | 0 | 0 | - | 0 |  | 0 | = | 0
8 | 0% | X | 17666.25 | = | 0 | 0 | - | 0 |  | 0 | = | 0
9 | 0% | X | 61590.23 | = | 0 | 0 | - | 0 |  | 0 | = | 0
10 | 0% | X | 63437.94 | = | 0 | 0 | - | 0 |  | 0 | = | 0
11 | 0% | X | 65341.07 | = | 0 | 0 | - | 0 |  | 0 | = | 0
12 | 0% | X | 32670.54 | = | 0 | 0 | - | 0 |  | 0 | = | 0
|  |  | 464252.68 |  | 120972.6 | 120972.6 |  | 0 |  | 100911.97 |  | 20060.63
Finance Entered By: ________________________________________________________________
Date
Finance Data Entry Verified By: _______________________________________________________
Date