## 25-C0301K 11 18 2025
JSA / Jefferson Lab - DOE
Data Entry Update Subcontract PO Percent Complete
Appendix B
Vendor Name | MASSACHUSETTS INST OF TEC | [5 empty] | Percent complete thru |  |  | 2025-11-24
(Date)
PO Number | 25-C0301 | [6 empty] | OR
Status Update ID | 25-C0301K | [5 empty] | Invoice Number
370932
PO Line # | Percent Complete |  | PO Line Total | = | Completed Work Amt | Completed Work Amt | - | Eligible for Voucher Amt | - | Prev Vouchered Amount | = | Completed Work Retention Amt
1 | 50% | X | 362862 | = | 181431 | 181431 | - | 0 |  | 165236.83 | = | 16194.17
|  |  | 362862 |  | 181431 | 181431 |  | 0 |  | 165236.83 |  | 16194.17
Finance Entered By: ________________________________________________________________
Date
Finance Data Entry Verified By: _______________________________________________________
Date