## 24-C1558E 11 18 2025
JSA / Jefferson Lab - DOE
Data Entry Update Subcontract PO Percent Complete
Appendix B
Vendor Name | EUCLID TECHLABS LLC | [5 empty] | Percent complete thru |  |  | 2025-11-24
(Date)
PO Number | 24-C1558 | [6 empty] | OR
Status Update ID | 24-C1558E | [5 empty] | Invoice Number
374019
PO Line # | Percent Complete |  | PO Line Total | = | Completed Work Amt | Completed Work Amt | - | Eligible for Voucher Amt | - | Prev Vouchered Amount | = | Completed Work Retention Amt
1 | 100% | X | 47900 | = | 47900 | 47900 | - | 0 |  | 47900 | = | 0
2 | 100% | X | 8400 | = | 8400 | 8400 | - | 0 |  | 8400 | = | 0
3 | 100% | X | 20400 | = | 20400 | 20400 | - | 0 |  | 20400 | = | 0
4 | 100% | X | 22300 | = | 22300 | 22300 | - | 0 |  | 0 | = | 22300
5 | 100% | X | 90000 | = | 90000 | 90000 | - | 0 |  | 90000 | = | 0
6 | 100% | X | 37400 | = | 37400 | 37400 | - | 0 |  | 0 | = | 37400
7 | 100% | X | 16000 | = | 16000 | 16000 | - | 0 |  | 0 | = | 16000
8 | 50% | X | 3000 | = | 1500 | 1500 | - | 0 |  | 0 | = | 1500
9 | 0% | X | 90000 | = | 0 | 0 | - | 0 |  | 0 | = | 0
|  |  | 335400 |  | 243900 | 243900 |  | 0 |  | 166700 |  | 77200
Finance Entered By: ________________________________________________________________
Date
Finance Data Entry Verified By: _______________________________________________________
Date